## Sheet3
Count of Id | Column Labels
| Basic |  |  |  |  | Basic Total | Detail | [5 empty] | Detail Total | Grand Total
Row Labels |  | A | AC | AFC | OB |  |  | A | AC | AFC | OB | -
Automation and Instrumentation |  | 10 | 27 | 12 | 8 | 57 | 2 | 73 | 171 | 82 | 79 |  | 407 | 464
Civil and Steel Structure | 2 | 17 | 104 | 198 | 10 | 331 | 70 | 90 | 423 | 1042 | 128 |  | 1753 | 2084
Electrical |  | 1 |  | 66 | 7 | 74 | 5 | 16 | 33 | 305 | 177 |  | 536 | 610
Mechanical | 6 | 66 | 107 | 190 | 80 | 449 | 9 | 75 | 125 | 149 | 1309 | 2 | 1669 | 2118
Piping & Utility | 1 | 2 | 32 | 23 | 33 | 91 | 4 | 11 | 77 | 77 | 178 | 3 | 350 | 441
Grand Total | 9 | 96 | 270 | 489 | 138 | 1002 | 90 | 265 | 829 | 1655 | 1871 | 5 | 4715 | 5717

## Sheet4
| Basic | [6 empty] | Detail | [7 empty] | Total
Description | No Comment | A | Approved with Comment | AFC | OB | Approved | Basic Total | No Comment | A | Approved with Comment | AFC | OB | Approved | Not Issued | Detail Total | No Comment | Approved with Comment | Approved | Not Issued | Grand Total
Automation and Instrumentation |  | 10 | 27 | 12 | 8 | 30 | 57 | 2 | 73 | 171 | 82 | 79 | 234 |  | 407
Civil and Steel Structure | 2 | 17 | 104 | 198 | 10 | 225 | 331 | 70 | 90 | 423 | 1042 | 128 | 1260 |  | 1753
Electrical |  | 1 |  | 66 | 7 | 74 | 74 | 5 | 16 | 33 | 305 | 177 | 498 |  | 536
Mechanical | 6 | 66 | 107 | 190 | 80 | 336 | 449 | 9 | 75 | 125 | 149 | 1309 | 1533 | 2 | 1669
Piping & Utility | 1 | 2 | 32 | 23 | 33 | 58 | 91 | 4 | 11 | 77 | 77 | 178 | 266 | 3 | 350
Grand Total | 9 | 96 | 270 | 489 | 138 | 723 | 1002 | 90 | 265 | 829 | 1655 | 1871 | 3791 | 5 | 4715 | 99 | 1099 | 4514 | 5 | 5717

## Sheet
Id | Doc/DWG.No | Description | Rev | RevDate | TraceRevs | Document Group | Phase | Area | Discipline | Company | Received Date | 2nd POI Status | 2nd Comment Status | Approved (AFC - A - OB) | Approved with Comment (AC) | No Comment | Not Issued
130932 | 1491TB05-0DTLV91-001-001 | Fume Treatment Plant Bucket Elavetor Assembly Operation And Maintenance Manual | 00 | 2017-08-02 09:39 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2017-08-02 09:39 | IFI | OB | 100%
133456 | F101TA05-0MRAC91-001-001 | Calculation Book For RO Substation Building HVAC | 01 | 2018-07-07 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment System | Mechanical | TAM | 2018-07-10 10:50 | IFC | A | 100%
131347 | F101TB13-0MMAA91-001-001 | WTP RO SUB-STATION Master Documents Registry | 00 | 2017-09-23 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment System | Mechanical | TAM | 2017-10-08 13:38 | IFA | AC |  | 95%
131303 | F101TC02-0MMSD91-001-001 | Basis Of Design For RO Substation Building (Civil & Steel Structure) | 00 | 2017-09-06 | Indeterminate | Miscellaneous(MISC) | Basic | Water Treatment System | Civil and Steel Structure | TAM | 2017-10-07 14:56 | IFA | AC |  | 95%
131617 | F101TC02-0MMSD91-002-001 | Calculation Book For WTP RO Substation Building (Civil&Structure) | 01 | 2017-11-04 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment System | Civil and Steel Structure | TAM | 2017-11-08 09:40 | IFC | A | 100%
131304 | F101TC06-0MMSD91-001-001 | WTP RO SUBSTATION ARCHITECTURAL DRAWINGS | 00 | 2017-09-06 | Indeterminate | Drawing | Basic | Water Treatment System | Civil and Steel Structure | TAM | 2017-10-07 14:56 | IFA | AC |  | 95%
131309 | F101TC06-0MMSD91-001-002 | WTP RO SUBSTATION GROUND & FIRST FLOOR PLAN | 00 | 2017-09-06 | Indeterminate | Drawing | Basic | Water Treatment System | Civil and Steel Structure | TAM | 2017-10-07 14:57 | IFA | AC |  | 95%
131305 | F101TC06-0MMSD91-001-003 | WTP RO SUBSTATION ROOF PLAN | 00 | 2017-09-06 | Indeterminate | Drawing | Basic | Water Treatment System | Civil and Steel Structure | TAM | 2017-10-07 14:57 | IFA | AC |  | 95%
131306 | F101TC06-0MMSD91-001-004 | WTP RO SUBSTATION SECTION "A-A" & ''B-B'' | 00 | 2017-09-06 | Indeterminate | Drawing | Basic | Water Treatment System | Civil and Steel Structure | TAM | 2017-10-07 14:57 | IFA | AC |  | 95%
131307 | F101TC06-0MMSD91-001-005 | WTP RO SUBSTATION VIEW | 00 | 2017-09-06 | Indeterminate | Drawing | Basic | Water Treatment System | Civil and Steel Structure | TAM | 2017-10-07 14:57 | IFA | AC |  | 95%
131308 | F101TC06-0MMSD91-001-006 | WTP RO SUBSTATION Detail | 00 | 2017-09-06 | Indeterminate | Drawing | Basic | Water Treatment System | Civil and Steel Structure | TAM | 2017-10-07 14:57 | IFA | AC |  | 95%
131612 | F101TC07-0MMSD91-001-001 | RO SUBSTATION ARCHITECTURAL DETAIL GROUND & FIRST FLOOR PLAN | 01 | 2017-10-31 | Indeterminate | Drawing | Detail | Water Treatment System | Civil and Steel Structure | TAM | 2017-11-08 09:35 | IFC | A | 100%
131613 | F101TC07-0MMSD91-001-002 | RO SUBSTATION ARCHITECTURAL DETAIL ROOF PLAN | 01 | 2017-10-31 | Indeterminate | Drawing | Detail | Water Treatment System | Civil and Steel Structure | TAM | 2017-11-08 09:35 | IFC | A | 100%
131614 | F101TC07-0MMSD91-001-003 | RO SUBSTATION ARCHITECTURAL DETAIL SECTION "A-A" & ''B-B'' | 01 | 2017-10-31 | Indeterminate | Drawing | Detail | Water Treatment System | Civil and Steel Structure | TAM | 2017-11-08 09:35 | IFC | A | 100%
131615 | F101TC07-0MMSD91-001-004 | RO SUBSTATION ARCHITECTURAL DETAIL VIEW | 01 | 2017-10-31 | Indeterminate | Drawing | Detail | Water Treatment System | Civil and Steel Structure | TAM | 2017-11-08 09:35 | IFC | A | 100%
131616 | F101TC07-0MMSD91-001-005 | RO SUBSTATION ARCHITECTURAL DETAIL DETAILS | 01 | 2017-10-31 | Indeterminate | Drawing | Detail | Water Treatment System | Civil and Steel Structure | TAM | 2017-11-08 09:35 | IFC | A | 100%
131624 | F101TC08-0MMSD91-001-001 | RO SUBSTATION CIVIL & CONCRETE STRUCTURE COLUMNS PLAN | 01 | 2017-11-04 | Indeterminate | Drawing | Detail | Water Treatment System | Civil and Steel Structure | TAM | 2017-11-08 09:42 | IFC | A | 100%
131625 | F101TC08-0MMSD91-001-002 | RO SUBSTATION CIVIL & CONCRETE STRUCTURE FOUNDATION PLAN & SECTION | 01 | 2017-11-04 | Indeterminate | Drawing | Detail | Water Treatment System | Civil and Steel Structure | TAM | 2017-11-08 09:42 | IFC | A | 100%
131626 | F101TC08-0MMSD91-001-003 | RO SUBSTATION CIVIL & CONCRETE STRUCTURE FOUNDATION PLAN & SECTION | 01 | 2017-11-04 | Indeterminate | Drawing | Detail | Water Treatment System | Civil and Steel Structure | TAM | 2017-11-08 09:42 | IFC | A | 100%
131627 | F101TC08-0MMSD91-001-004 | RO SUBSTATION CIVIL & CONCRETE STRUCTURE FOUNDATION PLAN & SECTION | 01 | 2017-11-04 | Indeterminate | Drawing | Detail | Water Treatment System | Civil and Steel Structure | TAM | 2017-11-08 09:42 | IFC | A | 100%
131628 | F101TC08-0MMSD91-001-005 | RO SUBSTATION CIVIL & CONCRETE STRUCTURE COLUMNS&RETAINING WALLS PLAN | 01 | 2017-11-04 | Indeterminate | Drawing | Detail | Water Treatment System | Civil and Steel Structure | TAM | 2017-11-08 09:42 | IFC | A | 100%
131629 | F101TC08-0MMSD91-001-006 | RO SUBSTATION CIVIL & CONCRETE STRUCTURE RETAINING WALLS DETAILS | 01 | 2017-11-04 | Indeterminate | Drawing | Detail | Water Treatment System | Civil and Steel Structure | TAM | 2017-11-08 09:42 | IFC | A | 100%
131618 | F101TC08-0MMSD91-001-007 | RO SUBSTATION CIVIL & CONCRETE STRUCTURE COLUMNS DETAILS | 01 | 2017-11-04 | Indeterminate | Drawing | Detail | Water Treatment System | Civil and Steel Structure | TAM | 2017-11-08 09:41 | IFC | A | 100%
131619 | F101TC08-0MMSD91-001-008 | RO SUBSTATION CIVIL & CONCRETE STRUCTURE FRAMING PLANS +1.00 & +5.70 | 01 | 2017-11-04 | Indeterminate | Drawing | Detail | Water Treatment System | Civil and Steel Structure | TAM | 2017-11-08 09:41 | IFC | A | 100%
131620 | F101TC08-0MMSD91-001-009 | RO SUBSTATION CIVIL & CONCRETE STRUCTURE BEAMS DETAILS | 01 | 2017-11-04 | Indeterminate | Drawing | Detail | Water Treatment System | Civil and Steel Structure | TAM | 2017-11-08 09:41 | IFC | A | 100%
131621 | F101TC08-0MMSD91-001-010 | RO SUBSTATION CIVIL & CONCRETE STRUCTURE BEAMS DETAILS | 01 | 2017-11-04 | Indeterminate | Drawing | Detail | Water Treatment System | Civil and Steel Structure | TAM | 2017-11-08 09:41 | IFC | A | 100%
131622 | F101TC08-0MMSD91-001-011 | RO SUBSTATION CIVIL & CONCRETE STRUCTURE FRAMING PLANS +1.00 & +5.70 | 01 | 2017-11-04 | Indeterminate | Drawing | Detail | Water Treatment System | Civil and Steel Structure | TAM | 2017-11-08 09:41 | IFC | A | 100%
131623 | F101TC08-0MMSD91-001-012 | RO SUBSTATION CIVIL & CONCRETE STRUCTURE FRAMING PLANS +1.00 & +5.70 | 01 | 2017-11-04 | Indeterminate | Drawing | Detail | Water Treatment System | Civil and Steel Structure | TAM | 2017-11-08 09:42 | IFC | A | 100%
131333 | F101TC08-0MMSD91-001-013 | RO SUBSTATION CIVIL & CONCRETE STRUCTURE TRANSFORMER & DESEL AREA DETAILS | 00 | 2017-09-17 | Indeterminate | Drawing | Detail | Water Treatment System | Civil and Steel Structure | TAM | 2017-10-08 09:35 | IFA | AC |  | 95%
131310 | F101TC09-0MMSD91-001-001 | WTP RO SUBSTATION LIST OF DRAWING | 00 | 2017-09-06 | Indeterminate | Drawing | Basic | Water Treatment System | Civil and Steel Structure | TAM | 2017-10-07 14:57 | IFA | AC |  | 95%
131311 | F101TC09-0MMSD91-001-002 | WTP RO SUBSTATION CIVIL & CONCRETE STRUCTURE COLUMNS PLAN | 00 | 2017-09-06 | Indeterminate | Drawing | Basic | Water Treatment System | Civil and Steel Structure | TAM | 2017-10-07 14:57 | IFA | AC |  | 95%
131312 | F101TC09-0MMSD91-001-003 | WTP RO SUBSTATION CIVIL & CONCRETE STRUCTURE FOUNDATION PLAN & SECTION | 00 | 2017-09-06 | Indeterminate | Drawing | Basic | Water Treatment System | Civil and Steel Structure | TAM | 2017-10-07 14:57 | IFA | AC |  | 95%
131313 | F101TC09-0MMSD91-001-004 | WTP RO SUBSTATION CIVIL & CONCRETE STRUCTURE FIRST & ROOF FRAMING PLAN | 00 | 2017-09-06 | Indeterminate | Drawing | Basic | Water Treatment System | Civil and Steel Structure | TAM | 2017-10-07 14:57 | IFA | AC |  | 95%
133159 | F101TE01-0MMSD91-001-001 | WTP RO- SUBSTATION LAYOUT | 01 | 2018-05-13 | Indeterminate | Drawing | Detail | Water Treatment System | Electrical | TAM | 2018-05-28 11:08 | IFC | A | 100%
133155 | F101TE05-0MMSD91-001-001 | RO SUBSTATION LIGHTING LAYOUT | 02 | 2018-05-13 | Indeterminate | Drawing | Detail | Water Treatment System | Electrical | TAM | 2018-05-28 11:03 | IFC | A | 100%
133156 | F101TE05-0MMSD91-002-001 | RO SUBSTATION SOCKET LAYOUT | 02 | 2018-05-13 | Indeterminate | Drawing | Detail | Water Treatment System | Electrical | TAM | 2018-05-28 11:03 | IFC | A | 100%
133357 | F101TE05-0MMSD91-003-001 | RO SUBSTATION LIGHTING AND SOCKET ELECTRCIAL PANEL LAYOUT | 03 | 2018-06-20 | Indeterminate | Drawing | Detail | Water Treatment System | Electrical | TAM | 2018-07-03 11:21 | IFC | A | 100%
133158 | F101TE07-0MMSD91-001-001 | RO SUBSTATION GROUNDING LAYOUT | 02 | 2018-05-13 | Indeterminate | Drawing | Detail | Water Treatment System | Electrical | TAM | 2018-05-28 11:03 | IFC | A | 100%
135201 | F101TE09-0MMSD91-001-001 | RO SUBSTATION FIRE ALARM LAYOUT | 01 | 2019-02-16 | Indeterminate | Drawing | Detail | Water Treatment System | Electrical | TAM | 2019-04-09 11:04 | IFC | AC |  | 95%
135202 | F101TE09-0MMSD91-002-001 | RO SUBSTATION TELEPHONE AND PC NETWORK LAYOUT | 03 | 2019-02-26 | Indeterminate | Drawing | Detail | Water Treatment System | Electrical | TAM | 2019-04-09 11:06 | IFC |  |  |  | 85%
132964 | F101TR09-0MMAM01-001-001 | RO SUBSTATION BUILDING SEWER& DRAINAGE PIPING PLAN FIRST FLOOR PLAN | 00 | 2018-02-12 | Indeterminate | Drawing | Detail | Water Treatment System | Mechanical | TAM | 2018-03-14 12:40 | IFA | AC |  | 95%
132965 | F101TR09-0MMAM01-002-001 | RO SUBSTATION BUILDING WATER PLUMBING PLAN FIRST FLOOR PLAN | 00 | 2018-02-12 | Indeterminate | Drawing | Detail | Water Treatment System | Mechanical | TAM | 2018-03-14 12:40 | IFA | AC |  | 95%
133162 | F101TR09-0MRAC91-001-001 | HVAC DUCTING & EQUIPMENT LAYOUT | 01 | 2018-05-16 | Indeterminate | Drawing | Detail | Water Treatment System | Mechanical | TAM | 2018-05-28 11:16 | IFC | AC |  | 95%
133163 | F101TR09-0MRAC91-001-002 | HVAC DUCTING & EQUIPMENT LAYOUT | 01 | 2018-05-16 | Indeterminate | Drawing | Detail | Water Treatment System | Mechanical | TAM | 2018-05-28 11:16 | IFC | AC |  | 95%
11784 | I491T101-0MEYC02-301-001 | Interlocking Logic Diagram | 00 | 2013-06-12 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
11785 | I491TA01-0AUEA91-001-001 | Eaf Automation Block Diagram | 00 | 2012-04-14 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Automation and Instrumentation | FUCHS |  | IFA | AC |  | 95%
11786 | I491TA01-0AULF91-001-001 | LF Automation Block Diagram | 00 | 2012-04-14 | Indeterminate | Drawing | Detail | Ladle Furnace | Automation and Instrumentation | FUCHS |  | IFA | AC |  | 95%
114780 | I491TA02-0ASAA91-001-001 | PFD FOR AIR SEPRATION PLANT | 01 | 2015-12-20 | Indeterminate | Drawing | Basic | Air Separation Plant | Mechanical | Fortune | 2015-12-27 09:59 | IFC | AFC | 100%
111830 | I491TA02-0CCAA91-001-001 | Media Schematic | 00 | 2013-10-29 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | INTECO | 2014-04-29 16:19 | IFA | AFC | 100%
112796 | I491TA02-0CCAA91-014-001 | Note and Symbols for pdf +P&ID | 00 | 2014-09-06 18:20 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Automation and Instrumentation | TAM | 2014-09-06 18:20 | IFA | A | 100%
112797 | I491TA02-0CCAS91-001-001 | CCM Oxygen Distribution pdf+P&ID | 00 | 2014-09-06 18:20 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Automation and Instrumentation | TAM | 2014-09-06 18:20 | IFA | A | 100%
11788 | I491TA02-0CCCW91-001-001 | CCM Machine Cooling | 00 | 2013-10-29 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Mechanical | TAM |  | IFA | AFC | 100%
112798 | I491TA02-0CCCW91-001-002 | CCM TERTIARY CLOSED CIRCUIT COOLING WATER DISTRIBUTION PFD+ P&ID | 00 | 2014-09-06 18:21 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Automation and Instrumentation | TAM | 2014-09-06 18:21 | IFA | A | 100%
112799 | I491TA02-0CCCW91-002-001 | CCM TERTIARY CLOSED CIRCUIT FIXED BENDING SECTOR COOLING WATER DISTRIBUTION PFD+ P&ID | 00 | 2014-09-06 18:21 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Automation and Instrumentation | TAM | 2014-09-06 18:21 | IFA | A | 100%
112800 | I491TA02-0CCCW91-003-001 | CCM TERTIARY CLOSED CIRCUIT W.S MACHINE STRANDS 1 3 OOLING WATER DISTRIBUTION PFD+ P&ID | 00 | 2014-09-06 18:21 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Automation and Instrumentation | TAM | 2014-09-06 18:21 | IFA | A | 100%
112801 | I491TA02-0CCCW91-004-001 | CCM TERTIARY CLOSED CIRCUIT W.S MACHINE STRANDS 4 6 COOLING WATER DISTRIBUTION PFD+ P&ID | 00 | 2014-09-06 18:21 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Automation and Instrumentation | TAM | 2014-09-06 18:21 | IFA | A | 100%
112802 | I491TA02-0CCCW91-005-001 | CCM TERTIARY CLOSED CIRCUIT INTERMEDIATE ROLLER TABLE COOLING WATER DISTRIBUTION PFD+ P&ID | 00 | 2014-09-06 18:21 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Automation and Instrumentation | TAM | 2014-09-06 18:21 | IFA | A | 100%
112803 | I491TA02-0CCCW91-006-001 | CCM TERTIARY CLOSED CIRCUIT INTERMEDIATE ROLLER TABLE COOLING WATER DISTRIBUTION PFD+ P&ID | 00 | 2014-09-06 18:21 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Automation and Instrumentation | TAM | 2014-09-06 18:21 | IFA | A | 100%
112804 | I491TA02-0CCCW91-007-001 | CCM TERTIARY CLOSED CIRCUIT CUTTING AREA COOLING WATER DISTRIBUTION PFD+ P&ID | 00 | 2014-09-06 18:21 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Automation and Instrumentation | TAM | 2014-09-06 18:21 | IFA | A | 100%
112805 | I491TA02-0CCCW91-008-001 | CCM TERTIARY CLOSED CIRCUIT DISCHARGE AREA COOLING WATER DISTRIBUTION PFD+ P&ID | 00 | 2014-09-06 18:21 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Automation and Instrumentation | TAM | 2014-09-06 18:21 | IFA | A | 100%
112806 | I491TA02-0CCCW91-010-001 | CCM TERTIARY OPEN CIRCUIT DISTRIBUTION PFD+ P&ID | 00 | 2014-09-06 18:21 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Automation and Instrumentation | TAM | 2014-09-06 18:21 | IFA | A | 100%
112807 | I491TA02-0CCCW91-011-001 | CCM SECONDARY SPARY CIRCUIT DISTRIBUTION PFD+ P&ID | 00 | 2014-09-06 18:21 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Automation and Instrumentation | TAM | 2014-09-06 18:21 | IFA | A | 100%
112808 | I491TA02-0CCCW91-012-001 | CCM TERTIARY OPEN CIRCUIT CUTTING AREA DISTRIBUTION PFD+ P&ID | 00 | 2014-09-06 18:21 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Automation and Instrumentation | TAM | 2014-09-06 18:21 | IFA | A | 100%
112809 | I491TA02-0CCCW91-013-001 | CCM TERTIARY OPEN CIRCUIT CUTTING AREA TRANSPORT ROLLER TABLE DISTRIBUTION PFD+ P&ID | 00 | 2014-09-06 18:21 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Automation and Instrumentation | TAM | 2014-09-06 18:21 | IFA | A | 100%
112810 | I491TA02-0CCCW91-014-001 | CCM TERTIARY OPEN CIRCUIT DISCHARGE ROLLER TABLE DISTRIBUTION PFD+ P&ID | 00 | 2014-09-06 18:21 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Automation and Instrumentation | TAM | 2014-09-06 18:21 | IFA | A | 100%
112811 | I491TA02-0CCCW91-015-001 | CCM SECONDARY CIRCUIT BOOSTER PUMPS DISTRIBUTION PFD+ P&ID | 00 | 2014-09-06 18:21 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Automation and Instrumentation | TAM | 2014-09-06 18:21 | IFA | A | 100%
11789 | I491TA02-0CCDF91-001-001 | Roller Table&Dummy Bar | 00 | 2013-10-29 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Mechanical | TAM |  | IFA | AFC | 100%
112812 | I491TA02-0CCGG91-002-001 | CCM ARGON DISTRIBUTION PFD+ P&ID | 00 | 2014-09-06 18:21 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Automation and Instrumentation | TAM | 2014-09-06 18:21 | IFA | A | 100%
11790 | I491TA02-0CCLB91-001-001 | Cm Central Lubrication System | 00 | 2013-10-29 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM |  | IFA | AFC | 100%
11791 | I491TA02-0CCMJ91-001-001 | CCM MOULD | 00 | 2013-10-29 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Mechanical | TAM |  | IFA | AFC | 100%
112813 | I491TA02-0CCMJ91-001-002 | CCM MOULD COOLING WATER DISTRIBUTION PFD+ P&ID | 00 | 2014-09-06 18:21 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Automation and Instrumentation | TAM | 2014-09-06 18:21 | IFA | A | 100%
11792 | I491TA02-0CCMS91-001-001 | Ccm Spray Cooling | 00 | 2013-10-29 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Mechanical | TAM |  | IFA | AFC | 100%
11793 | I491TA02-0CCPW91-001-001 | Roller Table1,Deburring,Liftable Roller | 00 | 2013-10-29 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Mechanical | TAM |  | IFA | AFC | 100%
11794 | I491TA02-0CCPW91-002-001 | Roller Table2,Billet Lifter | 00 | 2013-10-29 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Mechanical | TAM |  | IFA | AFC | 100%
11795 | I491TA02-0CCSX91-001-001 | Withdrawal&Straightening Unit 1+2 | 00 | 2013-10-29 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Mechanical | TAM |  | IFA | AFC | 100%
11848 | I491TA02-0CPAA91-001-001 | Process Flow Diagram (Pfd) | 00 | 2013-02-20 | Indeterminate | Miscellaneous(MISC) | Basic | Compressed Air Production Plant | Piping & Utility | HAVAYAR |  | IFA | AC |  | 95%
11849 | I491TA02-0CPAA91-001-002 | Process Flow Diagram For Air Compressor Plant | 01 | 2013-05-25 | Indeterminate | Miscellaneous(MISC) | Basic | Compressed Air Production Plant | Piping & Utility | HAVAYAR |  | IFC | AFC | 100%
11814 | I491TA02-0CPAA91-001-003 | Plant And Instrument Package Process Flow Diagram | 01 | 2013-05-25 | Indeterminate | Drawing | Basic | Compressed Air Production Plant | Piping & Utility | HAVAYAR |  | IFC | AFC | 100%
130642 | I491TA02-0DTAA91-001-001 | Dedusting System Fournace 140 Ton EAF+LF&MH Flow Sheet-DEDUSTING PLANT | 02 | 2017-05-29 14:14 | Indeterminate | Miscellaneous(MISC) | Basic | Fume Treatment Equipment | Mechanical | HASCON | 2017-05-29 14:14 | IFC | AFC | 100%
11797 | I491TA02-0DTAA91-002-001 | Dedusting System Fournace 140 Ton Eaf+Lf&Mh Flow Sheet-Bag Filter For Dri | 00 | 2013-03-12 | Indeterminate | Miscellaneous(MISC) | Basic | Fume Treatment Equipment | Mechanical | HASCON |  | IFA | AFC | 100%
11798 | I491TA02-0DTAA91-003-001 | Dedusting System Furnace 140 Ton Eaf+Lf & Mh Cooled Duct - Flow Diagram | 04 | 2013-05-12 | Indeterminate | Drawing | Basic | Fume Treatment Equipment | Mechanical | HASCON |  | IFA | AC |  | 95%
113383 | I491TA02-0DTAA91-008-001 | DEDUSTING SYSTEM FURNACE 140ton EAF + LF & MH FLOW SHEET- SUCTION ASSEMBLY | 00 | 2015-02-21 14:54 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | TAM | 2015-02-21 14:54 | IFI | OB | 100%
112463 | I491TA02-0MDAA91-001-007 | Material Handling System Function Diagram | 08 | 2014-06-29 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | TAM | 2014-07-01 14:51 | IFC | AFC | 100%
11808 | I491TA02-0MKGN91-001-003 | Process Flow Diagram For Cooling System | 02 | 2012-06-12 | Indeterminate | Drawing | Basic | Water Treatment & Cooling System | Piping & Utility | TAM |  | IFC | AFC | 100%
11809 | I491TA02-0MMCT01-001-002 | Process Flow Diagram For Cooling System Ct01 (1-4) | 01 | 2013-06-09 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Piping & Utility | TAM |  | IFC | AFC | 100%
11812 | I491TA02-0MMCT02-001-002 | Process Flow Diagram For Cooling System Ct02 (2-4) | 01 | 2013-06-09 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Piping & Utility | TAM |  | IFC | AFC | 100%
135117 | I491TA03-0CCAA91-001-001 | Manual for CCM Lubrication Tables Collection | 00 | 2019-03-06 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2019-03-09 13:34 | IFI | OB | 100%
11815 | I491TA03-0DTAA91-001-001 | Dedusting System Fournace 140 Ton Eaf+Lf&Mh Cooled Duct-Flow Diagram | 03 | 2013-03-12 | Indeterminate | Miscellaneous(MISC) | Basic | Fume Treatment Equipment | Mechanical | HASCON |  | IFA | AFC | 100%
11816 | I491TA03-0LFAA91-001-001 | Utilities Ead/Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Basic | Ladle Furnace | Piping & Utility | TAM |  | IFI | OB | 100%
11817 | I491TA03-0LFAA91-002-001 | Water Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Basic | Ladle Furnace | Piping & Utility | TAM |  | IFI | OB | 100%
11818 | I491TA03-0LFAA91-003-001 | High Current System Water Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Basic | Ladle Furnace | Piping & Utility | TAM |  | IFI | OB | 100%
113332 | I491TA03-0MBAA91-001-001 | High Quality Cooling water Fluid Diagram of Media Distribution | 00 | 2015-02-09 | Indeterminate | Drawing | Basic | Media Distribution System | Mechanical | TAM | 2015-02-16 08:39 | IFI | AC |  | 95%
113333 | I491TA03-0MBAA91-002-001 | Normal Cooling water Fluid Diagram of Media Distribution | 00 | 2015-02-09 | Indeterminate | Drawing | Basic | Media Distribution System | Mechanical | TAM | 2015-02-16 08:39 | IFI | AC |  | 95%
113334 | I491TA03-0MBAA91-003-001 | Compressed Air Fluid Diagram of Media Distribution | 00 | 2015-02-09 | Indeterminate | Drawing | Basic | Media Distribution System | Mechanical | TAM | 2015-02-16 08:39 | IFI | AC |  | 95%
113335 | I491TA03-0MBAA91-004-001 | Instrument Air Fluid Diagram of Media Distribution | 00 | 2015-02-09 | Indeterminate | Drawing | Basic | Media Distribution System | Mechanical | TAM | 2015-02-16 08:39 | IFI | AC |  | 95%
113336 | I491TA03-0MBAA91-005-001 | Nitrogen Fluid Diagram of Media Distribution | 00 | 2015-02-09 | Indeterminate | Drawing | Basic | Media Distribution System | Mechanical | TAM | 2015-02-16 08:39 | IFI | AC |  | 95%
135485 | I491TA03-0MBAA91-006-001 | Oxygen Fluid Diagram of Media Distribution | 01 | 2019-07-06 | Indeterminate | Drawing | Basic | Media Distribution System | Mechanical | TAM | 2019-07-07 10:10 | IFI | OB | 100%
135486 | I491TA03-0MBAA91-007-001 | Argon Fluid Diagram of Media Distribution | 01 | 2019-07-06 | Indeterminate | Drawing | Basic | Media Distribution System | Mechanical | TAM | 2019-07-07 10:11 | IFI | OB | 100%
135487 | I491TA03-0MBAA91-008-001 | Natural Gas Fluid Diagram of Media Distribution | 01 | 2019-07-06 | Indeterminate | Drawing | Basic | Media Distribution System | Mechanical | TAM | 2019-07-07 10:11 | IFI | OB | 100%
113340 | I491TA03-0MBAA91-009-001 | Potable Fluid Diagram of Media Distribution | 00 | 2015-02-09 | Indeterminate | Drawing | Basic | Media Distribution System | Mechanical | TAM | 2015-02-16 08:39 | IFI | AC |  | 95%
11821 | I491TA05-0MDAA91-001-003 | Calculation Booklet For Basic Design Of Material Handling System | 02 | 2012-12-25 | Indeterminate | Miscellaneous(MISC) | Basic | Material Handling | Mechanical | TAM |  | IFC | AFC | 100%
11822 | I491TA05-0MELA01-755-001 | 400/33 Kv Substation Catalogur And Test Report For String Insulators | 00 | 2012-04-09 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
11824 | I491TA05-0MMCT01-001-002 | Process And Design Data Ct01 | 01 | 2013-03-10 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Piping & Utility | TAM |  | IFC | AFC | 100%
11826 | I491TA05-0MMCT02-001-002 | Process And Design Data Ct02 | 01 | 2013-03-10 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Piping & Utility | TAM |  | IFC | AFC | 100%
130704 | I491TA05-0MRAC91-002-001 | Calculation Book For EAF Building Hvac | 00 | 2017-06-19 | Indeterminate | Miscellaneous(MISC) | Detail | Air Conditioning and Ventilation | Mechanical | TAM | 2017-06-21 13:19 | IFA | AC |  | 95%
130705 | I491TA05-0MRAC91-003-001 | Calculation Book For LF Building Hvac | 00 | 2017-06-19 | Indeterminate | Miscellaneous(MISC) | Detail | Air Conditioning and Ventilation | Mechanical | TAM | 2017-06-21 13:19 | IFA | AC |  | 95%
132919 | I491TA05-0MRAC91-005-001 | Calculation Book For Air Separation Plant Substation Hvac | 01 | 2018-02-18 | Indeterminate | Miscellaneous(MISC) | Detail | Air Conditioning and Ventilation | Mechanical | TAM | 2018-02-19 09:11 | IFC | AC |  | 95%
130707 | I491TA05-0MRAC91-008-001 | Calculation Book For WorkShop Hvac | 00 | 2017-06-19 | Indeterminate | Miscellaneous(MISC) | Detail | Air Conditioning and Ventilation | Mechanical | TAM | 2017-06-21 13:20 | IFA | AC |  | 95%
133223 | I491TA05-0MRAC91-009-001 | Calculation Book For SMP Substation Building Hvac | 02 | 2018-05-30 | Indeterminate | Miscellaneous(MISC) | Detail | Air Conditioning and Ventilation | Mechanical | TAM | 2018-06-11 10:32 | IFC | AFC | 100%
132921 | I491TA05-0MRAC91-010-001 | Calculation Book For Wtp Substation Building Hvac | 00 | 2018-02-18 | Indeterminate | Miscellaneous(MISC) | Detail | Air Conditioning and Ventilation | Mechanical | TAM | 2018-02-19 09:15 | IFC | AC |  | 95%
132922 | I491TA05-0MRAC91-011-001 | Calculation Book For Fume Treatment Plant electrical substation Hvac | 01 | 2018-02-18 | Indeterminate | Miscellaneous(MISC) | Detail | Air Conditioning and Ventilation | Mechanical | TAM | 2018-02-19 09:16 | IFC | AC |  | 95%
133442 | I491TA05-0MRAC91-012-001 | Calculation Book For Meltshop Office Hvac | 01 | 2018-07-07 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop | Mechanical | TAM | 2018-07-10 09:20 | IFC | AC |  | 95%
133446 | I491TA05-0MRAC91-013-001 | Calculation Book For Ccm FNC Maintenance Room Hvac | 00 | 2018-07-07 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2018-07-10 09:29 | IFA | A | 100%
133449 | I491TA05-0MRAC91-014-001 | Calculation Book For Workshop Building 2nd Floor Hvac | 00 | 2018-07-07 | Indeterminate | Miscellaneous(MISC) | Detail | Air Conditioning and Ventilation | Mechanical | TAM | 2018-07-10 09:34 | IFA | A | 100%
133833 | I491TA05-0MRAC91-015-001 | Calculation Book For LF Transformer Room Hvac | 00 | 2018-07-21 09:42 | Indeterminate | Miscellaneous(MISC) | Detail | Air Conditioning and Ventilation | Mechanical | TAM | 2018-07-21 09:42 | IFA | AC |  | 95%
134327 | I491TA05-0MRAC91-016-001 | Calculation Book For ASP Electrical And Control Room Hvac | 01 | 2018-10-29 14:17 | Indeterminate | Miscellaneous(MISC) | Detail | Air Separation Plant | Mechanical | TAM | 2018-10-29 14:17 | IFC | AFC | 100%
114817 | I491TA06-0ASAA91-001-001 | Equipments List For Air Separation Plant | 00 | 2016-01-23 | Indeterminate | Miscellaneous(MISC) | Detail | Air Separation Plant | Piping & Utility | TAM | 2016-01-24 09:42 | IFA | A | 100%
113201 | I491TA06-0CCAA91-010-001 | CCM Equipment List GP08VB-HC11-E9000-EL121 | 00 | 2015-01-07 18:21 | Indeterminate | Miscellaneous(MISC) | Basic | Continuous Casting Machine (CCM) | Automation and Instrumentation | TAM | 2015-01-07 18:21 | IFA | AC |  | 95%
11828 | I491TA06-0CPAA91-001-002 | Process Description For Air Compressor Plant | 00 | 2013-03-03 | Indeterminate | Miscellaneous(MISC) | Detail | Compressed Air Production Plant | Piping & Utility | HAVAYAR |  | IFA | AC |  | 95%
11829 | I491TA06-0CPAA91-001-003 | Equipment List For Air Compressor Plant | 01 | 2013-05-25 | Indeterminate | Miscellaneous(MISC) | Detail | Compressed Air Production Plant | Piping & Utility | HAVAYAR |  | IFC | AFC | 100%
11830 | I491TA06-0MKGN91-001-001 | Water Cooling System Preliminary Process Equipment List | 00 | 2012-06-12 | Indeterminate | Miscellaneous(MISC) | Basic | Water Treatment & Cooling System | Mechanical | TAM |  | IFA | AC |  | 95%
11832 | I491TA06-0MMCT01-001-002 | Equipment List For Cooling System (Ct01) | 01 | 2013-03-11 | Indeterminate | Miscellaneous(MISC) | Basic | Water Treatment & Cooling System | Piping & Utility | TAM |  | IFC | AFC | 100%
11834 | I491TA06-0MMCT02-001-002 | Equipment List For Cooling System (Ct02) | 01 | 2013-03-11 | Indeterminate | Miscellaneous(MISC) | Basic | Water Treatment & Cooling System | Piping & Utility | TAM |  | IFC | AFC | 100%
11835 | I491TA99-0CPAA91-001-001 | Process Description For Air Compressor Plant | 01 | 2013-05-25 | Indeterminate | Miscellaneous(MISC) | Detail | Compressed Air Production Plant | Piping & Utility | HAVAYAR |  | IFC | AFC | 100%
113566 | I491TA99-0LFAA92-001-001 | LADLE FURNACE - STEEL PRODUCTION | 00 | 2015-05-06 | Indeterminate | Miscellaneous(MISC) | Basic | Ladle Furnace | Mechanical | FUCHS | 2015-05-27 16:06 | IFI | OB | 100%
11836 | I491TA99-0LFEJ01-001-001 | Piping Tarnsformer Wall Water Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Piping & Utility | FUCHS |  | IFI | OB | 100%
11837 | I491TA99-0LFEJ02-001-001 | Piping Tarnsformer Wall Water Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Piping & Utility | FUCHS |  | IFI | OB | 100%
11838 | I491TA99-0LFEJ03-001-001 | Piping Tarnsformer Wall Water Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Piping & Utility | FUCHS |  | IFI | OB | 100%
11839 | I491TA99-0LFEJ04-001-001 | Piping Tarnsformer Wall Water Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Piping & Utility | FUCHS |  | IFI | OB | 100%
11840 | I491TA99-0LFEJ05-001-001 | Piping Tarnsformer Wall Water Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Piping & Utility | FUCHS |  | IFI | OB | 100%
11841 | I491TA99-0LFEJ06-001-001 | Piping Tarnsformer Wall Water Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Piping & Utility | FUCHS |  | IFI | OB | 100%
11843 | I491TA99-0MKGN91-001-002 | Legend And General Notes For Water Cooling System | 01 | 2012-04-28 | Indeterminate | Drawing | Basic | Water Treatment & Cooling System | Piping & Utility | TAM |  | IFC | AC |  | 95%
114801 | I491TA99-0MMCT01-002-001 | Alarm & Trip list For Water Cooling System (CT01) | 00 | 2016-01-16 | Indeterminate | Miscellaneous(MISC) | Basic | Water Treatment & Cooling System | Piping & Utility | TAM | 2016-01-18 09:07 | IFA | AC |  | 95%
112723 | I491TA99-0MMCT01-003-001 | Control Philosophy for WATER COOLING SYSTEM | 02 | 2014-08-24 | Indeterminate | Miscellaneous(MISC) | Basic | Water Treatment & Cooling System | Automation and Instrumentation | TAM | 2014-09-01 13:50 | IFC | AFC | 100%
114802 | I491TA99-0MMCT02-002-001 | Alarm & Trip list For Water Cooling System (CT02) | 00 | 2016-01-16 | Indeterminate | Miscellaneous(MISC) | Basic | Water Treatment & Cooling System | Piping & Utility | TAM | 2016-01-18 09:08 | IFA | AC |  | 95%
130746 | I491TA99-0MMTK01-001-001 | Basis of Design For Elevated Tank of Emergency Condition | 02 | 2017-07-05 | Indeterminate | Miscellaneous(MISC) | Basic | Water Treatment & Cooling System | Piping & Utility | TAM | 2017-07-10 09:17 | IFC | AFC | 100%
11847 | I491TA99-0MXAA91-001-004 | Process And Plant Description | 03 | 2012-09-25 | Indeterminate | Miscellaneous(MISC) | Basic | General | Mechanical | TAM |  | IFC | AFC | 100%
130923 | I491TB02-0CCAA91-001-001 | ASSEMBLY SEQUENCES AND FIRST START--UP INSTRUCTIONS | 00 | 2017-07-30 16:46 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2017-07-30 16:46 | IFI | OB | 100%
135118 | I491TB02-0CCAA91-002-001 | Assembly Sequences and First Start-up Instructions for The Casting Area | 00 | 2019-03-06 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2019-03-09 13:34 | IFI | OB | 100%
135119 | I491TB02-0CCAA91-003-001 | Manual for CCM General Installation Rules | 00 | 2019-03-06 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2019-03-09 13:34 | IFI | OB | 100%
135120 | I491TB02-0CCDF91-001-001 | Assembly Sequences and First Start-up Instructions for The Dummy Bar and Dummy Bar Parking Device | 00 | 2019-03-06 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2019-03-09 13:34 | IFI | OB | 100%
135121 | I491TB02-0CCHY91-001-001 | Assembly Sequences and First Start-up Instructions for CCM Hydraulic Central Units for The Caster | 00 | 2019-03-06 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2019-03-09 13:34 | IFI | OB | 100%
135122 | I491TB02-0CCLB91-001-001 | Assembly Sequences and First Start-up Instructions for The CCM Mould Lubrication Central Unit | 00 | 2019-03-06 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2019-03-09 13:34 | IFI | OB | 100%
135123 | I491TB02-0CCLK91-001-001 | Assembly Sequences and First Start-up Instructions for the Ladle Turning Turret | 00 | 2019-03-06 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2019-03-09 13:34 | IFI | OB | 100%
135124 | I491TB02-0CCRL91-001-001 | Assembly Sequences and First Start-up Instructions for The CCM Evacuation Area | 00 | 2019-03-06 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2019-03-09 13:35 | IFI | OB | 100%
135125 | I491TB02-0CCSO91-001-001 | Assembly Sequences and First Start-up Instructions forThe Electromechanical Stopper Rod | 00 | 2019-03-06 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2019-03-09 13:35 | IFI | OB | 100%
135126 | I491TB02-0CCSX91-001-001 | Assembly Sequences and First Start-up Instructions for The Extracting-Straightening Machine | 00 | 2019-03-06 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2019-03-09 13:35 | IFI | OB | 100%
135127 | I491TB02-0CCTD91-001-001 | Assembly Sequences and First Start-up Instructions for The Fast Nozzle Changing | 00 | 2019-03-06 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2019-03-09 13:35 | IFI | OB | 100%
135128 | I491TB02-0CCTH91-001-001 | Assembly Sequences and First Start-up Instructions for The CCM Maintenance Area | 00 | 2019-03-06 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2019-03-09 13:35 | IFI | OB | 100%
113434 | I491TB02-0MDAA91-001-001 | Erection Operation & Maintenance manual For Belt Conveyors | 00 | 2015-03-15 | Indeterminate | Miscellaneous(MISC) | Detail | Material Handling | Mechanical | DATIS | 2015-03-17 09:52 | IFI | OB | 100%
11850 | I491TB02-0MEDC01-113-001 | 400/33 Kv Substation (110 Dc ) Installation Document | 01 | 2013-09-04 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
11851 | I491TB02-0MEHV01-759-001 | (Design,Supply And Installation Of Bardsir Steel Making Plant 400/33Kv Substation) Instalation Documents Chapter 6-1-4 | 00 | 2013-04-14 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
11852 | I491TB02-0MEHV02-769-001 | (Design,Supply And Installation Of Bardsir Steel Making Plant 400/33Kv Substation) Instalation Documents Chapter 6-1-3 | 00 | 2013-04-15 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFC | OB | 100%
11853 | I491TB02-0MEHV03-764-001 | (Design,Supply And Installation Of Bardsir Steel Making Plant 400/33Kv Substation) Instalation Documents Chapter 6-1-5 | 00 | 2013-04-15 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFC | OB | 100%
11854 | I491TB02-0MEHV05-779-001 | (Design,Supply And Installation Of Bardsir Steel Making Plant 400/33Kv Substation) Instalation Documents Chapter 6-1-1 & 6-1-2 | 00 | 2013-04-15 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFC | OB | 100%
11855 | I491TB02-0MESS01-001-001 | Support 4Ds Erection Drawing | 00 | 2012-03-18 | Indeterminate | Drawing | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
11856 | I491TB02-0MESS01-002-001 | Support 4Ds Erection Drawing | 00 | 2012-03-18 | Indeterminate | Drawing | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
11857 | I491TB02-0MESS01-003-001 | Support 4Ct12 Erection Drawing | 00 | 2012-03-18 | Indeterminate | Drawing | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
11858 | I491TB02-0MESS01-004-001 | Support 4Ct34 Erection Drawing | 00 | 2012-03-18 | Indeterminate | Drawing | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
11859 | I491TB02-0MESS01-005-001 | Support 4Ct34 Erection Drawing | 00 | 2012-03-18 | Indeterminate | Drawing | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
11860 | I491TB02-0MESS01-006-001 | Support 4Cvt3 Erection Drawing | 00 | 2012-03-18 | Indeterminate | Drawing | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
11861 | I491TB02-0MESS01-007-001 | Support 4La1 Erection Drawing | 00 | 2012-03-18 | Indeterminate | Drawing | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
11862 | I491TB02-0MESS01-008-001 | Support 4La2 Erection Drawing | 00 | 2012-03-18 | Indeterminate | Drawing | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
11863 | I491TB02-0MESS01-009-001 | Support 4Pi1 Erection Drawing | 00 | 2012-03-18 | Indeterminate | Drawing | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
11864 | I491TB02-0MESS01-010-001 | Support 4Pi2 Erection Drawing | 00 | 2012-03-18 | Indeterminate | Drawing | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
11865 | I491TB02-0MESS01-011-001 | Support 4Pi3 Erection Drawing | 00 | 2012-03-18 | Indeterminate | Drawing | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
11866 | I491TB02-0MESS01-012-001 | Support 4Pi4 Erection Drawing | 00 | 2012-03-18 | Indeterminate | Drawing | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
11867 | I491TB02-0MESS01-013-001 | Support 4Pi6 Erection Drawing | 00 | 2012-03-18 | Indeterminate | Drawing | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
11868 | I491TB02-0MESS01-014-001 | Support 4Nct Erection Drawing | 00 | 2012-03-18 | Indeterminate | Drawing | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
11869 | I491TB02-0MESS01-020-001 | Erection Drawing Of Anchor Bolt | 00 | 2012-03-18 | Indeterminate | Drawing | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
113130 | I491TB02-0MMCT01-001-001 | erection manual of fan of cooling tower CT01 | 00 | 2014-12-10 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Piping & Utility | FARABARD | 2014-12-15 09:14 | IFI | OB | 100%
113131 | I491TB02-0MMCT02-001-001 | erection manual of fan of cooling tower CT02 | 00 | 2014-12-10 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Piping & Utility | FARABARD | 2014-12-15 09:14 | IFI | OB | 100%
130924 | I491TB03-0CCAA91-001-001 | ALIGNMENT PROCEDURES FOR THE CONTINUOUS CASTING MACHINE | 00 | 2017-07-30 16:47 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2017-07-30 16:47 | IFI | OB | 100%
130312 | I491TB03-0CHEU01-001-001 | Teeming Crane Test instruction | 01 | 2017-02-15 11:39 | Indeterminate | Miscellaneous(MISC) | Detail | Crane and Hiosts | Mechanical | TAM | 2017-02-15 11:39 | IFI | OB | 100%
130330 | I491TB03-0CHEU02-001-001 | Scrap Chrging Crane Test instruction | 00 | 2017-02-27 14:55 | Indeterminate | Miscellaneous(MISC) | Detail | Crane and Hiosts | Mechanical | TAM | 2017-02-27 14:55 | IFI | OB | 100%
133127 | I491TB03-0CHEU03-001-001 | Empty Ladle Crane 15A0281 Test Instruction | 01 | 2018-05-08 | Indeterminate | Miscellaneous(MISC) | Detail | Crane and Hiosts | Mechanical | TAM | 2018-05-15 09:15 | IFI | OB | 100%
133128 | I491TB03-0CHEU04-001-001 | Tundish Handling Crane 15A0282 Test Instruction | 01 | 2018-05-08 | Indeterminate | Miscellaneous(MISC) | Detail | Crane and Hiosts | Mechanical | TAM | 2018-05-15 09:16 | IFI | OB | 100%
133129 | I491TB03-0CHEU05-001-001 | Billet Handling Crane 15A0284 Test Instruction | 01 | 2018-05-08 | Indeterminate | Miscellaneous(MISC) | Detail | Crane and Hiosts | Mechanical | TAM | 2018-05-15 09:16 | IFI | OB | 100%
133130 | I491TB03-0CHEU06-001-001 | Billet Handling Crane 15A0285 Test Instruction | 01 | 2018-05-08 | Indeterminate | Miscellaneous(MISC) | Detail | Crane and Hiosts | Mechanical | TAM | 2018-05-15 09:16 | IFI | OB | 100%
131122 | I491TB03-0MSAA91-001-001 | Test Procedure for Piping of Total Flooding Fire Fighting System | 00 | 2017-08-27 | Indeterminate | Miscellaneous(MISC) | Detail | Fire Fighting System | Mechanical | TAM | 2017-08-30 14:31 | IFA |  |  |  | 85%
129960 | I491TB03-0MXAA91-001-001 | Inspection Test plan For Electical Installation | 00 | 2016-12-13 09:08 | Indeterminate | Miscellaneous(MISC) | Basic | General | Automation and Instrumentation | TAM | 2016-12-13 09:08 | IFI | OB | 100%
135079 | I491TB05-0ASAA91-001-001 | Operational Manual For ASP Equipments | 00 | 2019-02-26 | Indeterminate | Miscellaneous(MISC) | Detail | Air Separation Plant | Civil and Steel Structure | Fortune | 2019-03-09 12:31 | IFI | OB | 100%
135070 | I491TB05-0ASCP01-001-001 | Operation & Maintenance Manual For ASP Main Air Comprsor (MAC) Samsung SM6000 Series Manual | 00 | 2019-03-05 15:16 | Indeterminate | Miscellaneous(MISC) | Detail | Air Separation Plant | Mechanical | Fortune | 2019-03-05 15:16 | IFI | OB | 100%
135069 | I491TB05-0ASCP01-002-001 | Operation & Maintenance Manual for ASP Main Air Compressor (MAC) Samsung SM Series Manual | 00 | 2019-03-05 15:16 | Indeterminate | Miscellaneous(MISC) | Detail | Air Separation Plant | Mechanical | Fortune | 2019-03-05 15:16 | IFI | OB | 100%
135068 | I491TB05-0ASCP01-003-001 | Manual for ASP Main Air Compressor (MAC) TECO 3 Phase Induction Motor Manual | 00 | 2019-03-05 15:16 | Indeterminate | Miscellaneous(MISC) | Detail | Air Separation Plant | Mechanical | Fortune | 2019-03-05 15:16 | IFI | OB | 100%
135074 | I491TB05-0ASCP02-001-001 | Operating Manual For IR Booster (BAC) Compressor | 00 | 2019-02-26 | Indeterminate | Miscellaneous(MISC) | Detail | Air Separation Plant | Mechanical | Fortune | 2019-03-05 15:37 | IFI | OB | 100%
135075 | I491TB05-0ASCP02-002-001 | Instruction Manual For IR Booster (BAC) Compressor Conttrol System | 00 | 2019-02-26 | Indeterminate | Miscellaneous(MISC) | Detail | Air Separation Plant | Mechanical | Fortune | 2019-03-05 15:37 | IFI | OB | 100%
135076 | I491TB05-0ASCP02-003-001 | Instruction Manual For IR Booster (BAC) Compressor TECO 3Phase Induction Motor | 00 | 2019-02-26 | Indeterminate | Miscellaneous(MISC) | Detail | Air Separation Plant | Mechanical | Fortune | 2019-03-05 15:37 | IFI | OB | 100%
130925 | I491TB05-0CCAA91-001-001 | OPERATING AND MAINTENANCE | 00 | 2017-07-30 16:47 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2017-07-30 16:47 | IFI | OB | 100%
135129 | I491TB05-0CCAA91-002-001 | Operating and Maintenance Instructions for The Casting Area | 00 | 2019-03-06 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2019-03-09 13:35 | IFI | OB | 100%
135227 | I491TB05-0CCCP91-001-001 | Instructions Manual for CCM Steam Exhaust Fans | 00 | 2019-04-14 16:01 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2019-04-14 16:01 | IFI | OB | 100%
135130 | I491TB05-0CCDF91-001-001 | Operating and Maintenance Instructions for The Dummy Bar and Dummy Bar Parking Device | 00 | 2019-03-06 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2019-03-09 13:36 | IFI | OB | 100%
134209 | I491TB05-0CCHB01-001-001 | Instruction Manual For Tundish Preheating Station | 00 | 2018-09-22 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | CEBA | 2018-09-30 11:36 | IFI | OB | 100%
134208 | I491TB05-0CCHB02-001-001 | Instruction Manual For Sen Preheating Stove | 00 | 2018-09-22 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | CEBA | 2018-09-30 11:36 | IFI | OB | 100%
134207 | I491TB05-0CCHB03-001-001 | Instruction Manual For Sen Preheating Station (Venturi Type) | 00 | 2018-09-22 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | CEBA | 2018-09-30 11:36 | IFI | OB | 100%
135131 | I491TB05-0CCHY91-001-001 | Operating and Maintenance Instructions for CCM Hydraulic Central Units for The Caster | 00 | 2019-03-06 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2019-03-09 13:36 | IFI | OB | 100%
135132 | I491TB05-0CCLB91-001-001 | Operating and Maintenance Instructions for The CCM Mould Lubrication Central Unit | 00 | 2019-03-06 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2019-03-09 13:36 | IFI | OB | 100%
135228 | I491TB05-0CCLB91-002-001 | Instructions Manual for CCM Grease Central Unit for the Caster | 00 | 2019-04-14 16:01 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2019-04-14 16:01 | IFI | OB | 100%
135133 | I491TB05-0CCLK91-001-001 | Operating and Maintenance Instructions for The Ladle Turning Turret | 00 | 2019-03-06 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2019-03-09 13:36 | IFI | OB | 100%
135229 | I491TB05-0CCLY91-001-001 | Instructions Manual for CCM Temperature Measurement System | 00 | 2019-04-14 16:01 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2019-04-14 16:01 | IFI | OB | 100%
135230 | I491TB05-0CCMM91-001-001 | Instructions Manual for CCM Marking System | 00 | 2019-04-14 16:01 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2019-04-14 16:01 | IFI | OB | 100%
135231 | I491TB05-0CCMS91-001-001 | Instructions Manual for CCM Spray Of Water | 00 | 2019-04-14 16:02 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2019-04-14 16:02 | IFI | OB | 100%
135232 | I491TB05-0CCRB91-001-001 | Instructions Manual for CCM Radioactive Mould Level Control System | 00 | 2019-04-14 16:02 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2019-04-14 16:02 | IFI | OB | 100%
135233 | I491TB05-0CCRJ91-001-001 | Instructions Manual for CCM Oxy Cutting System | 00 | 2019-04-14 16:02 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2019-04-14 16:02 | IFI | OB | 100%
135134 | I491TB05-0CCRL91-001-001 | Operating and Maintenance Instructions for The CCM Evacuation Area | 00 | 2019-03-06 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2019-03-09 13:36 | IFI | OB | 100%
135135 | I491TB05-0CCSO91-001-001 | Operating and Maintenance Instructions The Electromechanical Stopper Rod | 00 | 2019-03-06 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2019-03-09 13:36 | IFI | OB | 100%
135136 | I491TB05-0CCSX91-001-001 | Operating and Maintenance Instructions for The Extracting-Straightening Machine | 00 | 2019-03-06 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2019-03-09 13:36 | IFI | OB | 100%
134210 | I491TB05-0CCTD10-001-001 | Instruction Manual For Tundish Drying Station | 00 | 2018-09-22 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | CEBA | 2018-09-30 11:37 | IFI | OB | 100%
135137 | I491TB05-0CCTD91-001-001 | Operating and Maintenance Instructions for The Fast Nozzle Changing | 00 | 2019-03-06 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2019-03-09 13:37 | IFI | OB | 100%
135138 | I491TB05-0CCTH91-001-001 | Operating and Maintenance Instructions for The CCM Maintenance Area | 00 | 2019-03-06 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2019-03-09 13:37 | IFI | OB | 100%
134644 | I491TB05-0CCVI01-001-001 | Operation Manual For CCM Tundish Vibrator | 01 | 2018-12-12 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2018-12-17 10:00 | IFI | OB | 100%
135234 | I491TB05-0CCWE91-001-001 | Instructions Manual for CCM Ladle Weighing System | 00 | 2019-04-14 16:02 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2019-04-14 16:02 | IFI | OB | 100%
135235 | I491TB05-0CCWE91-002-001 | Instructions Manual for CCM Ladle Weighing System | 00 | 2019-04-14 16:02 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2019-04-14 16:02 | IFI | OB | 100%
133401 | I491TB05-0CHEU02-001-001 | SPS for Charging Crane | 00 | 2018-06-25 | Indeterminate | Miscellaneous(MISC) | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-07 11:38 | IFI | OB | 100%
133400 | I491TB05-0CHEU02-002-001 | Operating and Maintenance of Purchased Parts for Charging Crane | 00 | 2018-06-25 | Indeterminate | Miscellaneous(MISC) | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-07 11:38 | IFI | OB | 100%
133545 | I491TB05-0CHEU03-001-001 | SPS for Double girder crane 15A0281 | 00 | 2018-07-08 | Indeterminate | Miscellaneous(MISC) | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-11 14:56 | IFI | OB | 100%
133546 | I491TB05-0CHEU03-002-001 | Operating and Maintenance of Purchased Parts For Double girder crane 15A0281 | 00 | 2018-07-08 | Indeterminate | Miscellaneous(MISC) | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-11 14:56 | IFI | OB | 100%
133556 | I491TB05-0CHEU04-001-001 | SPS for Double girder crane 15A0282 | 00 | 2018-07-08 | Indeterminate | Miscellaneous(MISC) | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-11 14:57 | IFI | OB | 100%
133555 | I491TB05-0CHEU04-002-001 | Operating and Maintenance of Purchased Parts For Double girder crane 15A0282 | 00 | 2018-07-08 | Indeterminate | Miscellaneous(MISC) | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-11 14:57 | IFI | OB | 100%
133554 | I491TB05-0CHEU05-001-001 | SPS for Billet handling crane 15A0284 | 00 | 2018-07-08 | Indeterminate | Miscellaneous(MISC) | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-11 14:57 | IFI | OB | 100%
133553 | I491TB05-0CHEU05-002-001 | Operating and Maintenance of Purchased Parts For Billet handling crane 15A0284 | 00 | 2018-07-08 | Indeterminate | Miscellaneous(MISC) | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-11 14:57 | IFI | OB | 100%
133552 | I491TB05-0CHEU06-001-001 | SPS for Billet handling crane 15A0285 | 00 | 2018-07-08 | Indeterminate | Miscellaneous(MISC) | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-11 14:57 | IFI | OB | 100%
133551 | I491TB05-0CHEU06-002-001 | Operating and Maintenance of Purchased Parts For Billet handling crane 15A0285 | 00 | 2018-07-08 | Indeterminate | Miscellaneous(MISC) | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-11 14:57 | IFI | OB | 100%
133550 | I491TB05-0CHEU07-001-001 | SPS for Scrap Loading Crane 15A0287 | 00 | 2018-07-08 | Indeterminate | Miscellaneous(MISC) | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-11 14:57 | IFI | OB | 100%
133549 | I491TB05-0CHEU07-002-001 | Operating and Maintenance of Purchased Parts For Scrap Loading Crane 15A0287 | 00 | 2018-07-08 | Indeterminate | Miscellaneous(MISC) | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-11 14:57 | IFI | OB | 100%
133548 | I491TB05-0CHEU08-001-001 | SPS for Scrap Loading Crane 15A0288 | 00 | 2018-07-08 | Indeterminate | Miscellaneous(MISC) | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-11 14:57 | IFI | OB | 100%
133547 | I491TB05-0CHEU08-002-001 | Operating and Maintenance of Purchased Parts For Scrap Loading Crane 15A0288 | 00 | 2018-07-08 | Indeterminate | Miscellaneous(MISC) | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-11 14:57 | IFI | OB | 100%
11871 | I491TB05-0CPAA01-001-002 | Operating And Maintenance Manuals For Air Compressor Plant | 01 | 2013-05-25 | Indeterminate | Miscellaneous(MISC) | Detail | Compressed Air Production Plant | Piping & Utility | HAVAYAR |  | IFC | AFC | 100%
115215 | I491TB05-0DTAA91-002-001 | Manual Equipment For Fume Treatment Plant | 00 | 2016-05-07 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2016-05-14 08:57 | IFI | OB | 100%
133311 | I491TB05-0DTAA91-003-001 | Instaling, and Maintenance Instructions Manual for Fume Treatment Plant | 00 | 2018-06-19 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Equipment | Mechanical | TAM | 2018-06-26 10:18 | IFI | OB | 100%
135491 | I491TB05-0MCLW01-001-001 | Operation Manual for Sepahan Electric Forklift Machine SEM20-35 | 00 | 2019-07-06 | Indeterminate | Miscellaneous(MISC) | Detail | Mobile Equipment | Mechanical | TAM | 2019-07-07 10:25 | IFI | OB | 100%
11872 | I491TB05-0MMCT01-001-001 | Operating & Maintenance Manual For Cooling Tower System Ct01 | 00 | 2013-11-26 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Piping & Utility | FARABARD |  | IFA | AC |  | 95%
11873 | I491TB05-0MMCT02-001-001 | Operating & Maintenance Manual For Cooling Towe System Ct02 | 00 | 2013-11-26 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Piping & Utility | FARABARD |  | IFA | AC |  | 95%
134914 | I491TB05-0MMEG02-001-001 | Operator’s Manual For WTP Diesel Pump | 00 | 2018-12-25 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Mechanical | TAM | 2018-12-31 12:26 | IFI | OB | 100%
130666 | I491TB05-0MMXL01-001-001 | User Guide For XRF Portable Spectrometer | 00 | 2017-05-30 | Indeterminate | Miscellaneous(MISC) | Detail | Scrap Yard Equipment | Mechanical | TAM | 2017-05-31 10:39 | IFI | OB | 100%
134934 | I491TB05-0MXEG01-001-001 | Operation Manual For Diesel Generator | 00 | 2019-01-08 | Indeterminate | Miscellaneous(MISC) | Detail | General | Electrical | TAM | 2019-01-12 09:11 | IFI | OB | 100%
132894 | I491TB05-0MYRJ01-001-001 | Operation And Maintenance Manual For Lathe Machin Tn 50 BR | 00 | 2018-02-13 | Indeterminate | Miscellaneous(MISC) | Detail | Maintenance Workshop | Mechanical | TAM | 2018-02-17 09:58 | IFI | OB | 100%
134633 | I491TB05-0PXFD91-001-001 | Operation Manual For Melt Shop Debricking | 00 | 2018-12-12 | Indeterminate | Miscellaneous(MISC) | Detail | Mobile Equipment | Mechanical | TAM | 2018-12-17 09:21 | IFI | OB | 100%
114683 | I491TB05-0PXHB91-002-001 | Installation, operation and Maintenance Manual for Horizontal Preheater | 00 | 2015-11-23 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop Auxiliaries | Mechanical | TAM | 2015-11-24 10:58 | IFI | OB | 100%
135449 | I491TB05-0PXXL03-001-001 | Cattallogue For Laborattory Jaw-Crusher-BB-200 | 00 | 2019-06-12 15:20 | Indeterminate | Miscellaneous(MISC) | Detail | Laboratory | Mechanical | TAM | 2019-06-12 15:20 | IFI | OB | 100%
135450 | I491TB05-0PXXL06-001-001 | Catalogue For Muffle Furnace | 00 | 2019-06-12 15:20 | Indeterminate | Miscellaneous(MISC) | Detail | Laboratory | Mechanical | TAM | 2019-06-12 15:20 | IFI | OB | 100%
135451 | I491TB05-0PXXL07-001-001 | Catalogue For Hydraulic Table Pellet Press-PP-40 | 00 | 2019-06-12 15:20 | Indeterminate | Miscellaneous(MISC) | Detail | Laboratory | Mechanical | TAM | 2019-06-12 15:20 | IFI | OB | 100%
135452 | I491TB05-0PXXL09-001-001 | Catalogue For Vibratory Disc Mill RS- 200 | 00 | 2019-06-12 15:20 | Indeterminate | Miscellaneous(MISC) | Detail | Laboratory | Mechanical | TAM | 2019-06-12 15:20 | IFI | OB | 100%
135453 | I491TB05-0PXXL10-001-001 | Catalogue For Optical Emission Spectrometer(OES) | 00 | 2019-06-12 15:20 | Indeterminate | Miscellaneous(MISC) | Detail | Laboratory | Mechanical | TAM | 2019-06-12 15:20 | IFI | OB | 100%
114727 | I491TB05-0RXGA01-001-001 | Erection Operation and Maintenace Manual for Emergency Stirring Lance | 00 | 2015-12-05 15:17 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace Auxiliary | Mechanical | CEBA | 2015-12-05 15:17 | IFI | OB | 100%
114732 | I491TB05-0RXLY01-001-001 | Erection,Operation and Maintenance Manual for Temperature and Sampling Manipulator | 00 | 2015-11-28 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace Auxiliary | Mechanical | CEBA | 2015-12-07 10:34 | IFI | OB | 100%
114720 | I491TB05-0RXWH91-001-001 | Installation,Operation and Maintenance Manuall for Wire Feeder | 00 | 2015-11-28 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace Auxiliary | Mechanical | CEBA | 2015-12-01 11:20 | IFI | A | 100%
114740 | I491TB05-0SXCJ91-001-001 | Installation,Operation and Maintenance Manual for Carbon Injection system | 00 | 2015-12-06 | Indeterminate | Miscellaneous(MISC) | Detail | Eaf Auxiliaries | Mechanical | TAM | 2015-12-07 10:58 | IFI | OB | 100%
134283 | I491TB05-0SXGU01-001-001 | Operation Manual For EAF Anker jet gunning Machiine | 00 | 2018-10-13 | Indeterminate | Miscellaneous(MISC) | Detail | Eaf Auxiliaries | Mechanical | RHI AG | 2018-10-15 10:03 | IFI | OB | 100%
114706 | I491TB05-0SXHB91-003-001 | Installation,Operation and Maintenance Manual for Vertical Preheater | 00 | 2015-11-24 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop Auxiliaries | Mechanical | TAM | 2015-11-25 10:23 | IFI | OB | 100%
134401 | I491TB05-0SXIE01-001-001 | Operation Manual Electrode Nippling Device (ElectrodeTourque Station) | 00 | 2018-11-17 | Indeterminate | Miscellaneous(MISC) | Detail | Eaf Auxiliaries | Civil and Steel Structure | Piccardi | 2018-12-01 09:28 | IFI | OB | 100%
114676 | I491TB05-0SXLD91-001-001 | Installation,Operation and Maintenance Manual for Vertical Ladle Dryer | 00 | 2015-11-22 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop Auxiliaries | Mechanical | CEBA | 2015-11-23 11:24 | IFI | OB | 100%
133404 | I491TB06-0CHEU02-001-001 | Maintenance manuals of Mechanical Equipment for Charging Crane | 00 | 2018-06-25 | Indeterminate | Miscellaneous(MISC) | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-07 11:38 | IFI | OB | 100%
133403 | I491TB06-0CHEU02-002-001 | Maintenance manuals of Electrical Equipment for Charging Crane | 00 | 2018-06-25 | Indeterminate | Miscellaneous(MISC) | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-07 11:38 | IFI | OB | 100%
133568 | I491TB06-0CHEU03-001-001 | Maintenance Manuals of Mechanical Equipment for Double girder crane 15A0281 | 00 | 2018-07-08 | Indeterminate | Miscellaneous(MISC) | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-11 14:58 | IFI | OB | 100%
133567 | I491TB06-0CHEU03-002-001 | Maintenance Manuals of Electrical Equipment for Double girder crane15A0281 | 00 | 2018-07-08 | Indeterminate | Miscellaneous(MISC) | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-11 14:58 | IFI | OB | 100%
133566 | I491TB06-0CHEU04-001-001 | Maintenance Manuals of Mechanical Equipment for Double girder crane 15A0282 | 00 | 2018-07-08 | Indeterminate | Miscellaneous(MISC) | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-11 14:58 | IFI | OB | 100%
133565 | I491TB06-0CHEU04-002-001 | Maintenance Manuals of Electrical Equipment for Double girder crane15A0282 | 00 | 2018-07-08 | Indeterminate | Miscellaneous(MISC) | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-11 14:58 | IFI | OB | 100%
133564 | I491TB06-0CHEU05-001-001 | Maintenance Manuals of Mechanical Equipment for Billet handling crane 15A0284 | 00 | 2018-07-08 | Indeterminate | Miscellaneous(MISC) | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-11 14:58 | IFI | OB | 100%
133563 | I491TB06-0CHEU05-002-001 | Maintenance Manuals of Electrical Equipment for Billet handling crane 15A0284 | 00 | 2018-07-08 | Indeterminate | Miscellaneous(MISC) | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-11 14:58 | IFI | OB | 100%
133562 | I491TB06-0CHEU06-001-001 | Maintenance Manuals of Mechanical Equipment for Billet handling crane 15A0285 | 00 | 2018-07-08 | Indeterminate | Miscellaneous(MISC) | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-11 14:58 | IFI | OB | 100%
133561 | I491TB06-0CHEU06-002-001 | Maintenance Manuals of Electrical Equipment for Billet handling crane 15A0285 | 00 | 2018-07-08 | Indeterminate | Miscellaneous(MISC) | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-11 14:58 | IFI | OB | 100%
133560 | I491TB06-0CHEU07-001-001 | Maintenance Manuals of Mechanical Equipment for Scrap Loading Crane | 00 | 2018-07-08 | Indeterminate | Miscellaneous(MISC) | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-11 14:58 | IFI | OB | 100%
133559 | I491TB06-0CHEU07-002-001 | Maintenance Manuals of Electrical Equipment for Scrap Loading Crane 15A0287 | 00 | 2018-07-08 | Indeterminate | Miscellaneous(MISC) | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-11 14:58 | IFI | OB | 100%
133558 | I491TB06-0CHEU08-001-001 | Maintenance Manuals of Mechanical Equipment for Scrap Loading Crane | 00 | 2018-07-08 | Indeterminate | Miscellaneous(MISC) | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-11 14:58 | IFI | OB | 100%
133557 | I491TB06-0CHEU08-002-001 | Maintenance Manuals of Electrical Equipment for Scrap Loading Crane 15A0288 | 00 | 2018-07-08 | Indeterminate | Miscellaneous(MISC) | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-11 14:58 | IFI | OB | 100%
135496 | I491TB06-0LAXL06-001-001 | Maintenance Manual For Muffle Furnace | 00 | 2019-07-06 | Indeterminate | Miscellaneous(MISC) | Detail | Laboratory | Mechanical | TAM | 2019-07-07 10:31 | IFI | OB | 100%
130245 | I491TB06-0MMOS01-001-001 | Oil Slimmer Installation And Maintenance Instruction Water Cooling Plant Sedimentation System | 00 | 2017-01-16 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Mechanical | TAM | 2017-01-22 09:33 | IFI | OB | 100%
133416 | I491TB06-0SHEG01-001-001 | Operation and Maiinttenance Manual for Scrap Transfer Car Diesel Generator | 00 | 2018-07-02 | Indeterminate | Miscellaneous(MISC) | Detail | Scrap Yard Equipment | Mechanical | TAM | 2018-07-08 16:49 | IFI | OB | 100%
115772 | I491TB06-0SHXM91-001-001 | Scrap Preparation and Storage Equipment Manuals | 00 | 2016-06-21 14:37 | Indeterminate | Miscellaneous(MISC) | Detail | Scrap Yard Equipment | Mechanical | FUCHS | 2016-06-21 14:37 | IFI | OB | 100%
130622 | I491TB07-0ASAA91-001-001 | Spare part List for Air Separatin | 00 | 2017-05-15 | Indeterminate | Miscellaneous(MISC) | Detail | Air Separation Plant | Mechanical | Fortune | 2017-05-27 11:11 | IFI | OB | 100%
114097 | I491TB07-0AUAA91-001-001 | Spare Part List Automation | 00 | 2015-05-30 | Indeterminate | Miscellaneous(MISC) | Detail | Automation and Control System | Automation and Instrumentation | TAM | 2015-06-17 10:50 | IFA | A | 100%
130684 | I491TB07-0CCAA91-001-001 | Part List For Continuous Casting Machine | 00 | 2017-06-12 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2017-06-14 14:41 | IFI | OB | 100%
130623 | I491TB07-0CHEU01-001-001 | Spare Part List For teeming Crane | 00 | 2017-05-16 | Indeterminate | Miscellaneous(MISC) | Detail | Crane and Hiosts | Mechanical | TAM | 2017-05-27 11:33 | IFI | OB | 100%
130624 | I491TB07-0CHEU02-001-001 | Spare Part List for scrap charging crane | 00 | 2017-05-16 | Indeterminate | Miscellaneous(MISC) | Detail | Crane and Hiosts | Mechanical | TAM | 2017-05-27 11:33 | IFI | OB | 100%
133402 | I491TB07-0CHEU02-002-001 | Consumtion list first 2years for Charging Crane | 00 | 2018-06-25 | Indeterminate | Miscellaneous(MISC) | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-07 11:38 | IFI | OB | 100%
133406 | I491TB07-0CHEU02-003-001 | Consumtion list further 2years for Charging Crane | 00 | 2018-06-25 | Indeterminate | Miscellaneous(MISC) | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-07 11:38 | IFI | OB | 100%
133601 | I491TB07-0CHEU03-002-001 | Consummation list first 2years for Double girder crane 15A0281 | 00 | 2018-07-08 | Indeterminate | Miscellaneous(MISC) | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-11 16:12 | IFI | OB | 100%
133602 | I491TB07-0CHEU03-003-001 | Consummation list further 2years for Double girder crane 15A0281 | 00 | 2018-07-08 | Indeterminate | Miscellaneous(MISC) | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-11 16:12 | IFI | OB | 100%
133600 | I491TB07-0CHEU04-002-001 | Consummation list first 2years for Double girder crane 15A0282 | 00 | 2018-07-08 | Indeterminate | Miscellaneous(MISC) | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-11 16:12 | IFI | OB | 100%
133599 | I491TB07-0CHEU04-003-001 | Consummation list further 2years for Double girder crane 15A0282 | 00 | 2018-07-08 | Indeterminate | Miscellaneous(MISC) | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-11 16:12 | IFI | OB | 100%
133598 | I491TB07-0CHEU05-002-001 | Consummation list first 2years for Billet handling crane 15A0284 | 00 | 2018-07-08 | Indeterminate | Miscellaneous(MISC) | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-11 16:12 | IFI | OB | 100%
133597 | I491TB07-0CHEU05-003-001 | Consummation list further 2years for Billet handling crane 15A0284 | 00 | 2018-07-08 | Indeterminate | Miscellaneous(MISC) | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-11 16:12 | IFI | OB | 100%
133596 | I491TB07-0CHEU06-002-001 | Consummation list first 2years for Billet handling crane 15A0285 | 00 | 2018-07-08 | Indeterminate | Miscellaneous(MISC) | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-11 16:12 | IFI | OB | 100%
133595 | I491TB07-0CHEU06-003-001 | Consummation list further 2years for Billet handling crane 15A0285 | 00 | 2018-07-08 | Indeterminate | Miscellaneous(MISC) | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-11 16:12 | IFI | OB | 100%
133594 | I491TB07-0CHEU07-002-001 | Consummation list first 2years for Scrap Loading Crane 15A0287 | 00 | 2018-07-08 | Indeterminate | Miscellaneous(MISC) | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-11 16:12 | IFI | OB | 100%
133593 | I491TB07-0CHEU07-003-001 | Consummation list further 2years for Scrap Loading Crane 15A0287 | 00 | 2018-07-08 | Indeterminate | Miscellaneous(MISC) | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-11 16:12 | IFI | OB | 100%
133592 | I491TB07-0CHEU08-002-001 | Consummation list first 2years for Scrap Loading Crane 15A0288 | 00 | 2018-07-08 | Indeterminate | Miscellaneous(MISC) | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-11 16:12 | IFI | OB | 100%
133591 | I491TB07-0CHEU08-003-001 | Consummation list further 2years for Scrap Loading Crane 15A0288 | 00 | 2018-07-08 | Indeterminate | Miscellaneous(MISC) | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-11 16:12 | IFI | OB | 100%
130552 | I491TB07-0EAAA91-001-001 | Part List for EAF and EAF Auxiliary | 00 | 2017-05-07 | Indeterminate | Miscellaneous(MISC) | Detail | Electric Arc Furnace | Mechanical | FUCHS | 2017-05-09 13:24 | IFI | AC |  | 95%
115292 | I491TB07-0EAFG01-002-001 | EF.07.310.WLD-D-20.00.002.322C PANEL TYPE A BOM | 00 | 2016-05-10 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS | 2016-05-24 17:02 | IFI | OB | 100%
115293 | I491TB07-0EAFG01-003-001 | EF.07.320.WLD-D-20.00.002.323A PANEL TYPE B BOM | 00 | 2016-05-10 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS | 2016-05-24 17:02 | IFI | OB | 100%
115294 | I491TB07-0EAFG01-004-001 | EF.07.330.WLD-D-20.00.002.324B PANEL TYPE C BOM | 00 | 2016-05-10 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS | 2016-05-24 17:02 | IFI | OB | 100%
130553 | I491TB07-0LFAA91-001-001 | Part List for LF and LF Auxiliary | 00 | 2017-05-07 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Mechanical | FUCHS | 2017-05-09 13:30 | IFI | AC |  | 95%
135492 | I491TB07-0MCLW01-001-001 | Spare Part List for Sepahan Electric Forklift Machine SEM20-35 | 00 | 2019-07-06 | Indeterminate | Miscellaneous(MISC) | Detail | Mobile Equipment | Mechanical | TAM | 2019-07-07 10:25 | IFI | OB | 100%
130573 | I491TB07-0MMAA91-001-001 | Spare Part List for Water Cooling Plant | 00 | 2017-05-09 16:08 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Mechanical | FARABARD | 2017-05-09 16:08 | IFI | OB | 100%
134635 | I491TB07-0PXFD91-001-001 | Spare Part List For Melt Shop Debricking | 00 | 2018-12-12 | Indeterminate | Miscellaneous(MISC) | Detail | Mobile Equipment | Mechanical | TAM | 2018-12-17 09:24 | IFI | OB | 100%
130322 | I491TB08-0CCAA91-001-001 | Oil and Lubrication Tables Collection For CCM | 00 | 2017-02-15 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2017-02-16 12:45 | IFI | OB | 100%
115127 | I491TB09-0ASAA91-001-001 | Air Separation Plant Utilities Consumption | 00 | 2016-04-05 | Indeterminate | Miscellaneous(MISC) | Detail | Air Separation Plant | Piping & Utility | TAM | 2016-04-09 16:57 | IFI | OB | 100%
135139 | I491TB11-0CCAA91-001-001 | Manual for CCM General Lubrication Rules | 00 | 2019-03-06 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2019-03-09 13:37 | IFI | OB | 100%
135236 | I491TB11-0CCAA91-002-001 | Components Catalogues Collection for The Continuous Casting Machine | 00 | 2019-04-14 16:03 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2019-04-14 16:03 | IFI | OB | 100%
135237 | I491TB11-0CCHY91-001-001 | Catalogues for CCM Hydraulic and Oil Lubrication Central Units | 00 | 2019-04-14 16:03 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2019-04-14 16:03 | IFI | OB | 100%
113041 | I491TB11-0MCFD91-001-001 | Technical Specification For Crawler wrecking machine Holtman (Option1) | 00 | 2014-10-25 | Indeterminate | Miscellaneous(MISC) | Detail | Mobile Equipment | Mechanical | TAM | 2014-10-26 08:51 | IFA | AFC | 100%
113042 | I491TB11-0MCFD91-002-001 | Technical Specification For Wrecking Machine BROKK (Option2) | 00 | 2014-10-25 | Indeterminate | Miscellaneous(MISC) | Detail | Mobile Equipment | Mechanical | TAM | 2014-10-26 08:52 | IFA | AFC | 100%
115302 | I491TB13-0EAFG01-002-001 | EF.07.310.WLD-D-20.00.002.322C PANEL TYPE A.1 | 00 | 2016-05-10 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS | 2016-05-25 08:58 | IFI | OB | 100%
115303 | I491TB13-0EAFG01-003-001 | EF.07.320.WLD-D-20.00.002.323A PANEL TYPE B.1 | 00 | 2016-05-10 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS | 2016-05-25 08:59 | IFI | OB | 100%
115304 | I491TB13-0EAFG01-004-001 | EF.07.330.WLD-D-20.00.002.324B PANEL TYPE C.1 | 00 | 2016-05-10 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS | 2016-05-25 09:00 | IFI | OB | 100%
11874 | I491TB13-0LFAA91-001-001 | Lubrication System Piping Gantry Lf | 00 | 2012-03-12 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Mechanical | TAM |  | IFI | OB | 100%
11875 | I491TB13-0LFAA91-002-001 | Pneumatic Piping Roof Lf | 00 | 2012-03-12 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
11876 | I491TB13-0LFAA91-003-001 | Pneumatic Piping Roof Lf | 00 | 2012-03-12 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
11877 | I491TB13-0LFAA91-004-001 | Pneumatic Piping Roof Lf | 00 | 2012-03-12 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
11878 | I491TB13-0LFAA91-005-001 | Piping Electrode Arms Lf | 00 | 2012-03-12 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
11879 | I491TB13-0LFAA91-006-001 | Pneumatic Piping Roof Lf | 00 | 2012-03-12 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
11880 | I491TB13-0LFAA91-007-001 | Pneumatic Piping Roof Lf | 00 | 2012-03-12 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
11881 | I491TB13-0LFAA91-008-001 | Pneumatic Piping Roof Lf | 00 | 2012-03-12 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
11882 | I491TB13-0LFAA91-009-001 | Earthing Gantry Lf | 00 | 2012-03-12 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
11883 | I491TB13-0LFAA91-010-001 | Earthing Gantry Lf | 00 | 2012-03-12 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
11884 | I491TB13-0LFAA91-011-001 | Earthing Gantry Lf | 00 | 2012-03-12 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
11885 | I491TB13-0LFAA91-012-001 | Electrode Lifting Device Ladle Furnace | 00 | 2012-03-12 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
11886 | I491TB13-0LFAA91-013-001 | Lifting Cylinder Electrode Lifting Device Lf | 00 | 2012-03-12 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
11887 | I491TB13-0LFAA91-014-001 | Locking Device Electrode Lifting Device L | 00 | 2012-03-12 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
11888 | I491TB13-0LFAA91-015-001 | Electro Electrode Lifting Device Lf | 00 | 2012-03-12 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
11889 | I491TB13-0LFAA91-016-001 | Gantry Gantry Lf | 00 | 2012-03-12 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
11890 | I491TB13-0LFAA91-017-001 | Heat Protection Gantry Lf | 00 | 2012-03-12 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
11891 | I491TB13-0LFAA91-018-001 | Lubrication System Piping Gantry Lf | 00 | 2012-03-12 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
11892 | I491TB13-0LFAA91-019-001 | Lubrication System Piping Gantry Lf | 00 | 2012-03-12 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
11893 | I491TB13-0LFAA91-020-001 | Gantry Ladle Furnace | 00 | 2012-03-12 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
11894 | I491TB13-0LFAA91-021-001 | Heat Protection Gantry Lf | 00 | 2012-03-12 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
11895 | I491TB13-0LFAA91-022-001 | Lubrication System Piping Gantry Lf | 00 | 2012-03-12 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
11896 | I491TB13-0LFAA91-023-001 | Lubrication System Piping Gantry Lf | 00 | 2012-03-12 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
11897 | I491TB13-0LFAA91-024-001 | Roof Lifting Device Ladle Furnace | 00 | 2012-03-12 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
11898 | I491TB13-0LFAA91-025-001 | Lifting & Support Structure Roof Lifting Device Lf | 00 | 2012-03-12 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
11899 | I491TB13-0LFAA91-026-001 | Lifting Cylinder Roof Lifting Device Lf | 00 | 2012-03-12 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
11900 | I491TB13-0LFAA91-027-001 | Locking Device Roof Lifting Device Lf | 00 | 2012-03-12 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
11901 | I491TB13-0LFAA91-028-001 | Piping Roof Lifting Device Lf | 00 | 2012-03-12 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
11902 | I491TB13-0LFAA91-029-001 | Piping Roof Lifting Device Lf | 00 | 2012-03-12 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
11903 | I491TB13-0LFAA91-030-001 | Electro Electrode Lifting Device Lf | 00 | 2012-03-12 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
11904 | I491TB13-0LFAA91-031-001 | Piping Electrode Arms Lf | 00 | 2012-03-12 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Mechanical | TAM |  | IFI | OB | 100%
11905 | I491TB13-0LFAA91-032-001 | Pneumatic Piping Roof Lf | 00 | 2012-03-12 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
11906 | I491TB13-0LFAA91-033-001 | Pneumatic Piping Roof Lf | 00 | 2012-03-12 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
11907 | I491TB13-0LFAA91-034-001 | Pneumatic Piping Roof Lf | 00 | 2012-03-12 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
11908 | I491TB13-0LFAA91-036-001 | Ladle Furnace Steel Production | 00 | 2012-03-12 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
11909 | I491TB13-0LFAA91-037-001 | High Current System Ladle Furnace | 00 | 2012-03-12 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
11910 | I491TB13-0LFAA91-038-001 | Hc-Cabel Fixing Elektrode Arm Side Flexibles Hcs Lf | 00 | 2012-03-12 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
11911 | I491TB13-0LFAA91-039-001 | Roof Ladle Furnace | 00 | 2012-03-12 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
11912 | I491TB13-0LFAA91-040-001 | Steel Structure Roof Lf | 00 | 2012-03-12 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
11913 | I491TB13-0LFAA91-041-001 | Steel Structure Roof Lf | 00 | 2012-03-12 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
11914 | I491TB13-0LFAA91-042-001 | Holder Steel Structure Roof Lf | 00 | 2012-03-12 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
11915 | I491TB13-0LFAA91-043-001 | Holder Steel Structure Roof Lf | 00 | 2012-03-12 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
11916 | I491TB13-0LFAA91-044-001 | Holder Steel Structure Roof Lf | 00 | 2012-03-12 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
11917 | I491TB13-0LFAA91-045-001 | Holder Steel Structure Roof Lf | 00 | 2012-03-12 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
11918 | I491TB13-0LFAA91-046-001 | Holder Steel Structure Roof Lf | 00 | 2012-03-12 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
11919 | I491TB13-0LFAA91-047-001 | Opening For Wire Feeding Roof Lf | 00 | 2012-03-12 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
11920 | I491TB13-0LFAA91-048-001 | Exhaust Roof Lf | 00 | 2012-03-12 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
11921 | I491TB13-0LFAA91-049-001 | Exhaust Hood Accessories Exhaust Roof Lf | 00 | 2012-03-12 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
11922 | I491TB13-0LFAA91-050-001 | Center Piece Exhaust Roof Lf | 00 | 2012-03-12 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
11923 | I491TB13-0LFAA91-051-001 | Working Door System Roof Lf | 00 | 2012-03-12 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
11924 | I491TB13-0LFAA91-052-001 | Working Door System Roof Lf | 00 | 2012-03-12 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
11925 | I491TB13-0LFAA91-053-001 | Door Roof Working Door Lf | 00 | 2012-03-12 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
11926 | I491TB13-0LFAA91-054-001 | Bracket Roof Working Door Lf | 00 | 2012-03-12 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
11927 | I491TB13-0LFAA91-055-001 | Water Piping Roof Lf | 00 | 2012-03-12 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
133408 | I491TB99-0CHEU02-001-001 | Equipment list for Charging Crane | 00 | 2018-06-25 | Indeterminate | Miscellaneous(MISC) | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-07 11:39 | IFI | OB | 100%
133407 | I491TB99-0CHEU02-001-002 | Maintenance list for Charging Crane | 00 | 2018-06-25 | Indeterminate | Miscellaneous(MISC) | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-07 11:39 | IFI | OB | 100%
133612 | I491TB99-0CHEU03-001-001 | Maintenance list For Double girder crane 15A0281 | 00 | 2018-07-08 | Indeterminate | Miscellaneous(MISC) | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-11 16:13 | IFI | OB | 100%
133611 | I491TB99-0CHEU03-001-002 | Equipment list for Double girder crane 15A0281 | 00 | 2018-07-08 | Indeterminate | Miscellaneous(MISC) | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-11 16:13 | IFI | OB | 100%
133610 | I491TB99-0CHEU04-001-001 | Maintenance list For Double girder crane 15A0282 | 00 | 2018-07-08 | Indeterminate | Miscellaneous(MISC) | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-11 16:13 | IFI | OB | 100%
133609 | I491TB99-0CHEU04-001-002 | Equipment list for Double girder crane 15A0282 | 00 | 2018-07-08 | Indeterminate | Miscellaneous(MISC) | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-11 16:13 | IFI | OB | 100%
133608 | I491TB99-0CHEU05-001-001 | Maintenance list For Billet handling crane 15A0284 | 00 | 2018-07-08 | Indeterminate | Miscellaneous(MISC) | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-11 16:13 | IFI | OB | 100%
133607 | I491TB99-0CHEU05-001-002 | Equipment list for Billet handling crane 15A0284 | 00 | 2018-07-08 | Indeterminate | Miscellaneous(MISC) | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-11 16:13 | IFI | OB | 100%
133606 | I491TB99-0CHEU06-001-001 | Maintenance list For Billet handling crane 15A0285 | 00 | 2018-07-08 | Indeterminate | Miscellaneous(MISC) | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-11 16:13 | IFI | OB | 100%
133605 | I491TB99-0CHEU06-001-002 | Equipment list for Billet handling crane 15A0285 | 00 | 2018-07-08 | Indeterminate | Miscellaneous(MISC) | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-11 16:13 | IFI | OB | 100%
133604 | I491TB99-0CHEU07-001-001 | Maintenance list For Scrap Loading Crane 15A0287 | 00 | 2018-07-08 | Indeterminate | Miscellaneous(MISC) | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-11 16:13 | IFI | OB | 100%
133603 | I491TB99-0CHEU07-001-002 | Equipment list for Scrap Loading Crane 15A0287 | 00 | 2018-07-08 | Indeterminate | Miscellaneous(MISC) | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-11 16:13 | IFI | OB | 100%
133636 | I491TB99-0CHEU08-001-001 | Maintenance list For Scrap Loading Crane 15A0288 1-2 | 00 | 2018-07-08 | Indeterminate | Miscellaneous(MISC) | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-12 11:11 | IFI | OB | 100%
133635 | I491TB99-0CHEU08-001-002 | Equipment list for Scrap Loading Crane 15A0288 | 00 | 2018-07-08 | Indeterminate | Miscellaneous(MISC) | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-12 11:11 | IFI | OB | 100%
130250 | I491TB99-0LFAA92-001-001 | LADLE FURNACE OPERATION AND MAINTENANCE MANUAL | 01 | 2017-01-17 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Mechanical | TAM | 2017-01-24 15:03 | IFI | OB | 100%
11931 | I491TB99-999AA91-001-003 | Equipment List | 03 | 2012-12-24 | Indeterminate | Miscellaneous(MISC) | Detail | General | Mechanical | TAM |  | IFC | AFC | 100%
130343 | I491TC01-0ASAM91-001-001 | Basis of Design for Compressor Room of AIR SEPARATION PLANT (Civil and Steel Structure) | 02 | 2017-02-27 | Indeterminate | Miscellaneous(MISC) | Basic | Air Separation Plant Main Building | Civil and Steel Structure | TAM | 2017-02-28 10:30 | IFC | AFC | 100%
112368 | I491TC01-0ASAM91-002-001 | BASIS OF DESIGN FOR ASP-CAP SUBSTATION BUILDING (CIVIL & STRUCTURES) | 01 | 2014-06-08 | Indeterminate | Miscellaneous(MISC) | Basic | Air Separation Plant Electrical substation Building | Civil and Steel Structure | TAM | 2014-06-09 16:50 | IFC | AFC | 100%
11933 | I491TC01-0CPAM91-001-001 | Cap Compressor Room Basis Of Design Compressor | 00 | 2013-10-28 | Indeterminate | Miscellaneous(MISC) | Basic | Compressed Air Production Plant | Civil and Steel Structure | TAM |  | IFA | A | 100%
112378 | I491TC01-0DTAM91-001-001 | BASIS OF DESIGN for FTP-MHS SUBSTATION BUILDING (CIVIL& STRUCTURES) | 01 | 2014-06-09 17:29 | Indeterminate | Miscellaneous(MISC) | Basic | Fume Treatment Plant Electrical Substation Building | Civil and Steel Structure | TAM | 2014-06-09 17:29 | IFC | AFC | 100%
11935 | I491TC01-0DTSB91-001-002 | F. T. P. Basis Of Design Civil & Steel Structure | 01 | 2013-02-11 | Indeterminate | Miscellaneous(MISC) | Basic | Fume Treatment Equipment | Civil and Steel Structure | HASCON |  | IFC | AFC | 100%
115639 | I491TC01-0EAAA91-001-003 | MELTSHOP BASIS OF DESIGN (CIVIL & STEEL STRUCTURE) | 03 | 2016-05-31 11:11 | Indeterminate | Miscellaneous(MISC) | Basic | Melt Shop Main Building | Civil and Steel Structure | TAM | 2016-05-31 11:11 | IFC | AFC | 100%
113496 | I491TC01-0EAFM91-001-001 | Basis Of Design For Eaf Foundation & Related Transfer Car | 01 | 2015-04-21 | Indeterminate | Miscellaneous(MISC) | Basic | Eaf Auxiliaries | Civil and Steel Structure | INTECO | 2015-04-22 10:49 | IFC | AFC | 100%
11941 | I491TC01-0LFLE91-001-002 | Basis Of Design For Lf Foundation & Related Transfer Car | 01 | 2013-12-29 07:21 | Indeterminate | Miscellaneous(MISC) | Basic | Ladle Furnace | Civil and Steel Structure | INTECO |  | IFC | AFC | 100%
11943 | I491TC01-0MDCV09-001-002 | Basis Of Design For Outdoor Dri Mhs (Civil & Structure) | 01 | 2013-11-10 | Indeterminate | Miscellaneous(MISC) | Basic | Material Handling | Civil and Steel Structure | TAM |  | IFC | AFC | 100%
11755 | I491TC01-0MDIO91-001-004 | Lf Material Handling Systembasis Of Design (Civil & Steel Structure) | 01 | 2012-10-21 | Indeterminate | Miscellaneous(MISC) | Basic | Material Handling | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
11756 | I491TC01-0MDIO91-001-005 | Lf Material Handling Systembasis Of Design (Civil & Steel Structure) Structure | 01 | 2012-10-21 | Indeterminate | Drawing | Basic | Material Handling | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
11757 | I491TC01-0MDIO91-001-006 | Lf Material Handling Systembasis Of Design (Civil & Steel Structure) Loading | 01 | 2012-10-21 | Indeterminate | Drawing | Basic | Material Handling | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
113512 | I491TC01-0MEAA91-001-001 | Basis Of Design For Cable Tunnel (Civil & Steel Structure) | 01 | 2015-04-26 | Indeterminate | Miscellaneous(MISC) | Basic | General | Civil and Steel Structure | IKS | 2015-04-30 09:36 | IFC | AC |  | 95%
11947 | I491TC01-0MEAM91-001-003 | Basis Of Design For Smp Substation Building (Civil & Steel Structure) | 02 | 2012-10-22 | Indeterminate | Miscellaneous(MISC) | Basic | Steel Making Electrical Substation Building | Civil and Steel Structure | IKS |  | IFC | AFC | 100%
112396 | I491TC01-0MMAM91-001-001 | BASIS OF DESIGN FOR WTP SUBSTATION BUILDING (CIVIL & STRUCTURES) | 01 | 2014-06-12 11:03 | Indeterminate | Miscellaneous(MISC) | Basic | Water Treatment & Cooling System Substation Building | Civil and Steel Structure | TAM | 2014-06-12 11:03 | IFC | AFC | 100%
16626 | I491TC01-0MMCF01-001-001 | Sedimentation Basis Of Design Wtp Sedimentation System (Civil & Structure) | 01 | 2014-02-18 13:47 | Indeterminate | Miscellaneous(MISC) | Basic | Water Treatment & Cooling System | Civil and Steel Structure | TAM | 2014-02-18 13:47 | IFC | AFC | 100%
114650 | I491TC01-0MMTK01-001-001 | Emergency Tank Basic of Design_Civil - Structure | 00 | 2015-10-26 13:37 | Indeterminate | Miscellaneous(MISC) | Basic | Water Treatment & Cooling System | Civil and Steel Structure | TAM | 2015-10-26 13:37 | IFA | AC |  | 95%
114651 | I491TC01-0MMTK01-001-002 | Emergency Tank Structural Basic of Design (7 sheet) | 00 | 2015-10-26 13:37 | Indeterminate | Drawing | Basic | Water Treatment & Cooling System | Civil and Steel Structure | TAM | 2015-10-26 13:37 | IFA | A | 100%
11954 | I491TC01-0MVAA91-001-004 | Specification For Earth Work | 02 | 2011-10-26 | Indeterminate | Miscellaneous(MISC) | Basic | General | Civil and Steel Structure | TAM |  | IFA | AFC | 100%
11955 | I491TC01-0MXAA91-001-001 | Study Report On Using Septic Tanks For Sewer Treatment | 00 | 2013-02-18 | Indeterminate | Miscellaneous(MISC) | Basic | General | Civil and Steel Structure | TAM |  | IFA | AC |  | 95%
16561 | I491TC01-0MXAA91-001-002 | Steel Making Plan General Layout (Preliminary Positioning Of Utilities And Service Plants) | 03 | 2011-05-17 | Indeterminate | Drawing | Basic | General | Mechanical | TAM |  | IFA | AC |  | 95%
11959 | I491TC01-0MYAA91-001-004 | Basis Of Design For Workshop Civil And Steel Structures | 03 | 2012-03-04 | Indeterminate | Miscellaneous(MISC) | Basic | Melt Shop Maintenance Workshop | Civil and Steel Structure | IKS |  | IFC | AFC | 100%
11961 | I491TC01-0NBAA91-001-002 | Architectural Primary Study Of Administrative,Shower- Locker And Restaurant Buildings | 01 | 2012-10-24 | Indeterminate | Miscellaneous(MISC) | Basic | General Civil | Civil and Steel Structure | TAM |  | IFC | AFC | 100%
11962 | I491TC01-0OFAM91-001-001 | Architectural Primary Study For Administrative,Shower- Locker And Restaurant Buildings | 00 | 2013-07-27 | Indeterminate | Miscellaneous(MISC) | Basic | Office - Canteen - Locker & Shower For Melt Shop | Mechanical | Azhand Shahr |  | IFA | AC |  | 95%
11965 | I491TC01-0SHAA91-001-003 | Basis Of Design For Scrap Yard (Civil And Steel Structures) | 02 | 2012-01-28 | Indeterminate | Drawing | Basic | Melt Shop Scrap Yard | Civil and Steel Structure | INTECO |  | IFC | AFC | 100%
11969 | I491TC01-0TBAA91-001-004 | Basis Of Design For Warehouse (Civil And Steel Structures) | 02 | 2011-07-11 | Indeterminate | Miscellaneous(MISC) | Basic | Warehouse | Mechanical | IKS |  | IFC | AFC | 100%
11971 | I491TC01-0TBAA91-002-002 | Basis Of Design For Ferroalloy Storage Area (Civil & Steel Structures) | 01 | 2012-01-03 | Indeterminate | Drawing | Basic | Melt Shop Lime And Ferroalloy Storage | Civil and Steel Structure | IKS |  | IFC | AFC | 100%
11973 | I491TC01-0TBAM91-001-002 | Furnaces’ Buildings And Platforms Basis Of Design (Civil And Steel Structures) | 01 | 2013-04-24 | Indeterminate | Miscellaneous(MISC) | Basic | Melt Shop Main Building | Civil and Steel Structure | INTECO |  | IFC | AFC | 100%
135442 | I491TC02-0ASAM01-001-001 | Calculation Book for Ferroalloy Storage Security Office building (Structure) | 00 | 2019-06-01 | Indeterminate | Miscellaneous(MISC) | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2019-06-02 10:06 | IFA | AC |  | 95%
133193 | I491TC02-0ASAM91-001-001 | Calculation Book For ASP-CAP Substation Building (Civil& Concrete Structures) | 02 | 2018-05-28 | Indeterminate | Miscellaneous(MISC) | Basic | Air Separation Plant Main Building | Civil and Steel Structure | TAM | 2018-06-02 10:33 | IFC | AFC | 100%
11975 | I491TC02-0ASAM91-002-001 | Basis Of Design For Oxygen Plant Pump Room (Civil& Concrete Structures) | 00 | 2013-08-24 | Indeterminate | Miscellaneous(MISC) | Basic | Air Separation Plant Main Building | Civil and Steel Structure | TAM |  | IFA | AC |  | 95%
130351 | I491TC02-0ASAM91-002-002 | Air Separation Plant Compressor Room Calculation | 01 | 2017-02-28 13:22 | Indeterminate | Miscellaneous(MISC) | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2017-02-28 13:22 | IFC | AFC | 100%
135429 | I491TC02-0ASAM91-003-001 | Calculation Book for OXYGEN PLANTCONTROL ROOM(STRUCTURE) | 00 | 2019-05-29 10:34 | Indeterminate | Miscellaneous(MISC) | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2019-05-29 10:34 | IFA | AC |  | 95%
130694 | I491TC02-0ASAM91-006-001 | Calculation Book For Air Separation Plant Compressor Room Flooring | 03 | 2017-06-14 15:33 | Indeterminate | Miscellaneous(MISC) | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2017-06-14 15:33 | IFC | AFC | 100%
130300 | I491TC02-0ASCP01-001-001 | Calculation Book For Air Separation Plant Turbo Compressor Foundation | 02 | 2017-02-07 10:38 | Indeterminate | Miscellaneous(MISC) | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2017-02-07 10:38 | IFC | AFC | 100%
130301 | I491TC02-0ASCP02-001-001 | Calculation Book For Air Separation Plant Booster Air Compressor Foundation | 01 | 2017-02-07 10:38 | Indeterminate | Miscellaneous(MISC) | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2017-02-07 10:38 | IFC | AFC | 100%
129459 | I491TC02-0ASIJ01-001-001 | Calculation Book For Air Separation Plant Cold box Foundation | 01 | 2016-09-07 16:23 | Indeterminate | Miscellaneous(MISC) | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2016-09-07 16:23 | IFC | AC |  | 95%
130731 | I491TC02-0ASPS01-001-001 | Calculation Book For Air Separation Plant PPU Skid Foundation | 04 | 2017-07-01 13:55 | Indeterminate | Drawing | Detail | Air Separation Plant | Civil and Steel Structure | Fortune | 2017-07-01 13:55 | IFC | AFC | 100%
129484 | I491TC02-0ASPU04-001-001 | Calculation Book For Liquid Nitrogen Process Pump Foundation 34 | 01 | 2016-09-11 10:02 | Indeterminate | Miscellaneous(MISC) | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2016-09-11 10:02 | IFC | AFC | 100%
129465 | I491TC02-0ASPU91-001-001 | Calculation Book For Air Separation Plant Back up Pumps Foundation | 01 | 2016-09-10 | Indeterminate | Miscellaneous(MISC) | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2016-09-11 09:39 | IFC | AFC | 100%
115734 | I491TC02-0ASSB91-001-001 | Calculation Book For Air Separation Plant Equipment Foundation (Part1) Civil & Steel Structure | 01 | 2016-06-14 16:54 | Indeterminate | Miscellaneous(MISC) | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2016-06-14 16:54 | IFC | AFC | 100%
129447 | I491TC02-0ASSL91-001-001 | Calculation Book For Air Separation Plant Oxygen And Nitrogen Silencer 17-18 | 02 | 2016-09-05 10:38 | Indeterminate | Drawing | Detail | Air Separation Plant | Civil and Steel Structure | Fortune | 2016-09-05 10:38 | IFC | AC |  | 95%
130739 | I491TC02-0ASTK01-001-001 | Calculation Book For Air Separation Plant Liquid Oxygen Tank Foundation 21 | 03 | 2017-07-02 | Indeterminate | Miscellaneous(MISC) | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2017-07-04 13:39 | IFC | AFC | 100%
130736 | I491TC02-0ASTK02-001-001 | Calculation Book For Air Separation Plant Liquid Nitrogen Tank Foundation | 03 | 2017-07-02 | Indeterminate | Miscellaneous(MISC) | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2017-07-04 13:33 | IFC | AC |  | 95%
129238 | I491TC02-0ASTK03-001-001 | Calculation Book For Air Separation Plant Liquid Argon Tank Foundation 19 | 01 | 2016-08-10 | Indeterminate | Drawing | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2016-08-14 14:10 | IFC | AC |  | 95%
130335 | I491TC02-0ASTK04-001-001 | Calculation Book For Air Separation Plant Oxygen Buffer Tank Foundation | 05 | 2017-02-27 15:10 | Indeterminate | Miscellaneous(MISC) | Detail | Air Separation Plant | Civil and Steel Structure | Fortune | 2017-02-27 15:10 | IFC | AFC | 100%
115745 | I491TC02-0ASTK05-001-001 | Calculation Book For Air Separation Plant Nitrogen Buffer Tank Foundation Calculation | 01 | 2016-06-14 16:57 | Indeterminate | Miscellaneous(MISC) | Detail | Air Separation Plant | Civil and Steel Structure | DATIS | 2016-06-14 16:57 | IFC | AFC | 100%
115743 | I491TC02-0ASTK06-001-001 | Calculation Book For Air Separation Plant Argon Buffer Tank Foundation | 01 | 2016-06-14 16:57 | Indeterminate | Miscellaneous(MISC) | Detail | Air Separation Plant | Civil and Steel Structure | Fortune | 2016-06-14 16:57 | IFC | AFC | 100%
130725 | I491TC02-0ASVS01-001-001 | Calculation Book For Air Separation Plant Waste Liquid Vaporizer Foundation | 02 | 2017-06-25 09:33 | Indeterminate | Miscellaneous(MISC) | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2017-06-25 09:33 | IFC | AFC | 100%
129239 | I491TC02-0ASVS02-001-001 | Calculation Book For ASP Nitrogen Pressure Reducer Foundation 32 | 01 | 2016-08-10 | Indeterminate | Drawing | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2016-08-14 14:11 | IFC | AC |  | 95%
134174 | I491TC02-0ASVS05-001-001 | Calculation Book For Air Separation Plant Waste Nitrogen Silencer Foundation | 01 | 2018-09-17 | Indeterminate | Miscellaneous(MISC) | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2018-09-22 09:35 | IFC | AFC | 100%
134151 | I491TC02-0ASXX01-001-001 | Calculation Book For Air Separation Plant DCAC Skid Foundation | 04 | 2018-09-05 | Indeterminate | Miscellaneous(MISC) | Detail | Air Separation Plant | Civil and Steel Structure | Fortune | 2018-09-10 09:28 | IFC | AFC | 100%
130683 | I491TC02-0ASXX03-001-001 | Calculation Book For Air Separation Plant Argon Pressure Reducer Foundation 33 | 02 | 2017-06-12 | Indeterminate | Miscellaneous(MISC) | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2017-06-14 14:16 | IFC | AFC | 100%
130349 | I491TC02-0ASXX05-002-001 | Calculation Book For Air Separation Plant GO PRESSURE REDUCER BLAST WALL 31 | 02 | 2017-02-28 13:17 | Indeterminate | Miscellaneous(MISC) | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2017-02-28 13:17 | IFC | AFC | 100%
131168 | I491TC02-0CCAA91-001-001 | CCM PART1- LADLE TUEERT AREA CALCULATION REPORT | 01 | 2017-09-12 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | SANO | 2017-09-17 13:53 | IFC | AFC | 100%
135410 | I491TC02-0CCAA91-002-001 | Calculation Book For CCM part 2-cooling Bed Area | 01 | 2019-05-29 10:15 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | SANO | 2019-05-29 10:15 | IFC | AFC | 100%
135411 | I491TC02-0CCAA91-003-001 | Calculation Book For CCM part 3- Discharge Area | 01 | 2019-05-29 10:16 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | SANO | 2019-05-29 10:16 | IFC | AFC | 100%
114364 | I491TC02-0CCAA91-004-001 | CCM Control Cabin Calculation Book | 01 | 2015-09-08 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | SANO | 2015-09-13 16:25 | IFC | AFC | 100%
130392 | I491TC02-0CCAA91-005-001 | CCM RUN OUT CABIN HYDRAULIC ROOM CALCULATION BOOK | 01 | 2017-03-07 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | SANO | 2017-04-03 16:07 | IFC | AFC | 100%
134094 | I491TC02-0CCAA91-006-001 | CCM Batery Charging Room Calculation Book | 02 | 2018-08-18 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | SANO | 2018-09-01 12:25 | IFC | AFC | 100%
132895 | I491TC02-0CCAA91-007-001 | Calculation Book For CCM PART1-Steel Stairs | 01 | 2018-02-17 10:00 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | SANO | 2018-02-17 10:00 | IFC | AFC | 100%
11981 | I491TC02-0CCSB91-004-003 | Calculation Book For Ccm Foundation Tract 4 | 02 | 2013-08-20 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
114361 | I491TC02-0CCTH01-001-001 | Tundish Tilting Station Calculation Book | 01 | 2015-09-08 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | SANO | 2015-09-10 09:43 | IFC | AFC | 100%
114359 | I491TC02-0CCTH02-001-001 | Tundish Stand Foundation Calculation Book | 01 | 2015-09-08 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | SANO | 2015-09-10 09:38 | IFC | AFC | 100%
114161 | I491TC02-0CCTH03-001-001 | CCM Mould Maintenance Shop Calculation | 00 | 2015-07-05 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | SANO | 2015-07-11 09:46 | IFA | AC |  | 95%
114956 | I491TC02-0CCTK91-001-001 | Calculation Book For CCM Scale Pit | 02 | 2016-02-28 13:08 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | APEC | 2016-02-28 13:08 | IFC | AFC | 100%
114957 | I491TC02-0CCTK91-002-001 | Calculation Book For CCM Scale Pit Piles | 00 | 2016-02-28 13:09 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | APEC | 2016-02-28 13:09 | IFC | AFC | 100%
134844 | I491TC02-0CCTK91-003-001 | Calculation Book For Scale Pit Clam Shell Crane Support Structure | 00 | 2018-12-24 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | TAM | 2018-12-31 09:48 | IFA | AFC | 100%
134281 | I491TC02-0CHEU09-001-001 | Calculation Book FOR Jib Crane & CS Machine (foundation) | 05 | 2018-10-09 | Indeterminate | Miscellaneous(MISC) | Detail | Crane and Hiosts | Civil and Steel Structure | TAM | 2018-10-15 10:00 | IFC | AFC | 100%
135037 | I491TC02-0CHMI01-001-001 | Calculation Book For CCM Mould Workshop Jib Crane (foundation) | 04 | 2019-01-19 | Indeterminate | Miscellaneous(MISC) | Detail | Crane and Hiosts | Civil and Steel Structure | TAM | 2019-02-23 12:30 | IFC | AFC | 100%
11982 | I491TC02-0CPAM91-001-001 | Cap Compressor Room Cal Book | 00 | 2013-10-28 | Indeterminate | Miscellaneous(MISC) | Detail | Compressed Air Production Plant | Civil and Steel Structure | TAM |  | IFA | A | 100%
113316 | I491TC02-0CPAM91-002-001 | CALCULATION BOOK FOR CAP(CIVIL & CONCRETE STRUCTURE) | 01 | 2015-02-03 | Indeterminate | Miscellaneous(MISC) | Detail | Compressed Air Production Plant | Civil and Steel Structure | TAM | 2015-02-10 15:40 | IFC | AFC | 100%
112443 | I491TC02-0DTAM91-001-001 | CALCULATION BOOK FOR FUME-MHS SUBSTATION FOUNDATION AND CONCRETE STRUCTURE | 00 | 2014-06-29 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Plant Electrical Substation | Civil and Steel Structure | TAM | 2014-06-30 12:11 | IFA | AC |  | 95%
16587 | I491TC02-0DTCC01-001-001 | Calculation Book For Settling Chamber | 01 | 2013-12-08 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Equipment | Civil and Steel Structure | TAM | 2014-02-18 10:59 | IFC | AFC | 100%
113527 | I491TC02-0DTSB91-001-002 | Calculation Book For Fume Treatent Plant (Civil&Steel Structures) | 03 | 2015-05-27 12:07 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Equipment | Civil and Steel Structure | HASCON | 2015-05-27 12:07 | IFC | AC |  | 95%
11988 | I491TC02-0DTSS91-009-002 | Ftp Doct Support Calculation | 01 | 2013-11-23 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Equipment | Civil and Steel Structure | TAM |  | IFC | AFC | 100%
132746 | I491TC02-0EAAA01-001-001 | Calculation Book For Steel StairsCase (Civil & Structure) | 04 | 2018-01-21 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2018-02-01 11:31 | IFC | AFC | 100%
135308 | I491TC02-0EAAA01-003-001 | Calculation Book for Meltshop Staircase & Elevator (Type1) | 00 | 2019-05-06 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop | Civil and Steel Structure | TAM | 2019-05-08 13:45 | IFA | AC |  | 95%
133897 | I491TC02-0EAAA02-001-001 | Calculation Book For MELTSHOP STEEL STAIRCASE 2 (STRUCTURE) | 02 | 2018-08-01 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop | Civil and Steel Structure | TAM | 2018-08-07 09:04 | IFC | AFC | 100%
134067 | I491TC02-0EAAA03-001-001 | Calculation Book For MELTSHOP STEEL STAIRCASE 3 (STRUCTURE) | 01 | 2018-08-08 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2018-08-21 11:22 | IFC | AFC | 100%
134139 | I491TC02-0EAAA04-001-001 | Calculation Book For MELTSHOP STEEL STAIRCASE 4 North Side (Civil And STRUCTURE) | 01 | 2018-09-05 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2018-09-09 14:41 | IFC | AFC | 100%
11992 | I491TC02-0EAAA91-001-003 | Calculation Book For Foundation Of Meltshop Steel Structure | 02 | 2012-07-22 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFA | A | 100%
132910 | I491TC02-0EAAA91-002-003 | Calculation Book Meltshop Main Building (Runway Girders) | 03 | 2018-02-17 16:29 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2018-02-17 16:29 | IFC | AFC | 100%
115253 | I491TC02-0EAAA91-003-001 | Calculation Book Of Foundation For Wall Posts Of Steel Making Main Steel Structure | 02 | 2016-05-09 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2016-05-15 08:48 | IFC | AFC | 100%
130596 | I491TC02-0EAAA91-004-001 | Calculation Book Meltshop Main Building Structure | 04 | 2017-05-09 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2017-05-14 14:52 | IFC | AFC | 100%
134915 | I491TC02-0EAAM01-001-001 | Calculation Book For Lavatory (STRUCTURE) | 01 | 2018-12-31 12:28 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop | Civil and Steel Structure | TAM | 2018-12-31 12:28 | IFC | AFC | 100%
12077 | I491TC02-0EAAM91-006-002 | Calculation Book For Melt Shop And Eaf Building Foundation | 01 | 2013-05-12 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM |  | IFC | AFC | 100%
113610 | I491TC02-0EAFB91-001-001 | CALCULATION BOOK FOR EAF PLATFORM FOUNDATION AND STEEL STRUCTURAL | 01 | 2015-05-28 16:10 | Indeterminate | Miscellaneous(MISC) | Detail | Electric Arc Furnace | Civil and Steel Structure | APEC | 2015-05-28 16:10 | IFC | A | 100%
130554 | I491TC02-0EAFB91-001-002 | Calculation Book For Eaf Service Platform Foundation | 02 | 2017-05-07 | Indeterminate | Miscellaneous(MISC) | Detail | Electric Arc Furnace | Civil and Steel Structure | TAM | 2017-05-09 13:42 | IFC | AC |  | 95%
112202 | I491TC02-0EAFB91-003-001 | Calculation Book For LF SERVICE PLATFORM FOUNDATION | 02 | 2014-05-19 09:52 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Civil and Steel Structure | TAM | 2014-05-19 09:52 | IFC | AFC | 100%
11999 | I491TC02-0EAFM91-001-003 | Calculation Book For Eaf Foundation & Related Transfer Car | 02 | 2012-12-02 | Indeterminate | Miscellaneous(MISC) | Detail | Electric Arc Furnace | Civil and Steel Structure | TAM |  | IFC | AFC | 100%
134384 | I491TC02-0EASM02-001-001 | EAF SLAG DUMPING AREA GALLERY CALCULATION REPORT | 02 | 2018-11-15 10:17 | Indeterminate | Miscellaneous(MISC) | Detail | Slag Yard | Civil and Steel Structure | TAM | 2018-11-15 10:17 | IFC | AFC | 100%
134385 | I491TC02-0EASM03-001-001 | EAF SLAG COOLING PIT CALCULATION REPORT | 02 | 2018-11-15 10:17 | Indeterminate | Miscellaneous(MISC) | Detail | Slag Yard | Civil and Steel Structure | TAM | 2018-11-15 10:17 | IFC | AFC | 100%
133051 | I491TC02-0EASM91-001-001 | EAF & LF TEMPORARY SLAG YARDS CALCULATION REPORT | 01 | 2018-04-11 | Indeterminate | Miscellaneous(MISC) | Detail | Slag Yard | Civil and Steel Structure | TAM | 2018-04-16 09:24 | IFC | AFC | 100%
118137 | I491TC02-0LAAM91-001-001 | Calculation Book For Laboratory Building Concrete Structure And Foundation | 01 | 2016-08-07 | Indeterminate | Miscellaneous(MISC) | Detail | Laboratory | Civil and Steel Structure | TAM | 2016-08-08 09:36 | IFC | AFC | 100%
12002 | I491TC02-0LAFM91-001-002 | Calculation Note For Lf Foundation & Related Transfer Car | 01 | 2012-11-17 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Civil and Steel Structure | TAM |  | IFC | AFC | 100%
134099 | I491TC02-0LFAA91-001-001 | Calculation Book For Melt Shop Main Building , Lf Building & Mhs Lf Foundation | 01 | 2018-09-03 10:40 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2018-09-03 10:40 | IFC | AFC | 100%
112542 | I491TC02-0LFFB91-001-001 | CALCULATION BOOK FOR LF PLATFORM FOUNDATION AND STEEL STRUCTURAL | 01 | 2014-07-07 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Civil and Steel Structure | TAM | 2014-07-12 16:54 | IFC | AFC | 100%
132997 | I491TC02-0LFFB91-002-001 | Calculation Book For LF HVAC Platform Foundation and Steel Structure | 06 | 2018-03-17 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Civil and Steel Structure | TAM | 2018-03-18 10:05 | IFC | AFC | 100%
113067 | I491TC02-0MDAA91-001-001 | Transfer Tower Md-Tt-01-01 Steel Structure Calculation Book | 03 | 2014-11-12 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | DATIS | 2014-11-15 14:15 | IFC | AFC | 100%
130534 | I491TC02-0MDCV05-001-001 | CALCULATION BOOK FOR FERRO ALLOY CONVEYOR WALKWAY AND TRESTLE(Part 6) | 02 | 2017-04-29 | Indeterminate | Miscellaneous(MISC) | Detail | Material Handling | Civil and Steel Structure | IKS | 2017-04-30 15:56 | IFC | AC |  | 95%
111495 | I491TC02-0MDCV09-001-001 | CALCULATION BOOK FOR DRIMHS PART 7 (CIVIL & STRUCTURE) | 00 | 2014-01-08 | Indeterminate | Miscellaneous(MISC) | Detail | Material Handling | Civil and Steel Structure | IKS | 2014-04-22 12:08 | IFA | AC |  | 95%
129273 | I491TC02-0MDSB91-001-001 | Calculation Book For Melt Shop And Eaf Mhs Foundation | 01 | 2016-08-17 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2016-08-20 10:51 | IFC | AFC | 100%
115670 | I491TC02-0MDSS91-001-001 | CALCULATION BOOK FOR MATERIAL HANDLING SYSTEM EAF | 01 | 2016-06-07 08:49 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-06-07 08:49 | IFC | AFC | 100%
115608 | I491TC02-0MDSS91-002-001 | Calculation Book MATERIAL HANDLING LF Structure | 02 | 2016-05-28 09:22 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-28 09:22 | IFC | AFC | 100%
16659 | I491TC02-0MDTK01-001-001 | Calculation Book For Outdoor Ferroalloy Mhs Part 4 (Civil & Structure) | 01 | 2014-01-04 | Indeterminate | Miscellaneous(MISC) | Detail | Material Handling | Civil and Steel Structure | IKS | 2014-02-19 09:32 | IFC | AC |  | 95%
16763 | I491TC02-0MDTK02-001-001 | Calculation Book For Outdoor Ferroalloy Mhs Part 3&5 (Civil & Structure) | 02 | 2014-02-08 | Indeterminate | Miscellaneous(MISC) | Detail | Material Handling | Civil and Steel Structure | TAM | 2014-03-06 15:28 | IFC | AC |  | 95%
114217 | I491TC02-0MDTK04-001-001 | Calculation Book For Outdoor Ferroalloy Mhs Part 1&2 Civil & Structure | 02 | 2015-08-05 | Indeterminate | Miscellaneous(MISC) | Detail | Material Handling | Civil and Steel Structure | IKS | 2015-08-09 10:24 | IFC | AFC | 100%
130600 | I491TC02-0MDTT03-001-001 | Calculation Book For DRI Conveyor Transfer Tower Emergency Pit | 01 | 2017-05-10 | Indeterminate | Miscellaneous(MISC) | Detail | Material Handling | Civil and Steel Structure | TAM | 2017-05-14 15:22 | IFC | AFC | 100%
12010 | I491TC02-0MEAA91-001-003 | Calculation Book Cable Tunnel (Civil And Steel Structure) | 02 | 2012-05-12 | Indeterminate | Miscellaneous(MISC) | Basic | General | Civil and Steel Structure | IKS |  | IFC | AFC | 100%
12012 | I491TC02-0MEAA91-002-001 | Basis Of Design For Outdoor Ferroalloy Mhs Part#A (Civil & Structure) | 01 | 2013-08-04 | Indeterminate | Miscellaneous(MISC) | Basic | Melt Shop Lime And Ferroalloy Storage | Civil and Steel Structure | TAM |  | IFC | AFC | 100%
11777 | I491TC02-0MEAA91-002-002 | Basic Design Civil Structure For Outdoor Ferroalloy Mhs Parta-R1 | 01 | 2013-08-04 | Indeterminate | Drawing | Basic | Melt Shop Lime And Ferroalloy Storage | Civil and Steel Structure | TAM |  | IFC | AFC | 100%
16630 | I491TC02-0MEAA91-003-003 | Basic Design For Outdoor Ferroalloy Mhs Part#B (Civil & Structure) | 03 | 2014-02-19 09:00 | Indeterminate | Miscellaneous(MISC) | Basic | Material Handling | Civil and Steel Structure | IKS | 2014-02-19 09:00 | IFC | AFC | 100%
12017 | I491TC02-0MEAM91-001-002 | Calculation For Smp Substation (Civil & Concrete Structure) | 01 | 2012-11-20 | Indeterminate | Miscellaneous(MISC) | Detail | Steel Making Electrical Substation Building | Civil and Steel Structure | IKS |  | IFC | AFC | 100%
112520 | I491TC02-0MMAM91-001-001 | CALCULATION BOOK FOR WTP SUBSTATION FOUNDATION AND CONCRETE STRUCTURE | 00 | 2014-07-07 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System Substation Building | Civil and Steel Structure | TAM | 2014-07-09 11:59 | IFA | A | 100%
16636 | I491TC02-0MMCF91-001-001 | CALCULATION BOOK FOR API SEDIMENTATION SYSTEM | 01 | 2013-12-30 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Civil and Steel Structure | TAM | 2014-02-19 09:20 | IFC | AC |  | 95%
134457 | I491TC02-0MMCF91-002-001 | CALCULATION BOOK FOR Clamshel Bucket Hoist Foundation WCP SEDIMENTATION SYSTEM | 01 | 2018-12-02 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Civil and Steel Structure | TAM | 2018-12-08 09:17 | IFC | AFC | 100%
134255 | I491TC02-0MMCF91-003-001 | Calculation Book For Cover of Clean Warm Water Area Sedimentation | 01 | 2018-09-25 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Civil and Steel Structure | TAM | 2018-10-02 10:31 | IFC | AFC | 100%
133918 | I491TC02-0MMCT01-001-001 | Cooling Tower Calculation For CT01 | 02 | 2018-08-01 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD | 2018-08-07 10:31 | IFC | AFC | 100%
133908 | I491TC02-0MMCT01-003-001 | Structure Calculation Sheet For Pump Station Shelter | 01 | 2018-08-01 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Civil and Steel Structure | TAM | 2018-08-07 09:20 | IFC | AC |  | 95%
133920 | I491TC02-0MMCT01-004-001 | Structure Calculation Sheet For CT01 STAIR_CASE | 00 | 2018-08-01 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Civil and Steel Structure | TAM | 2018-08-07 10:33 | IFC | AFC | 100%
133921 | I491TC02-0MMCT02-001-001 | Cooling Tower Calculation For CT02 | 02 | 2018-08-01 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Civil and Steel Structure | TAM | 2018-08-07 10:33 | IFC | AFC | 100%
133923 | I491TC02-0MMCT02-002-001 | Structure Calculation Sheet For CT02 STAIR_CASE | 00 | 2018-08-01 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Civil and Steel Structure | TAM | 2018-08-07 10:35 | IFC | AFC | 100%
130618 | I491TC02-0MMFL91-001-001 | Calculation Book For Sand filter shelter structure (RC & Steel Structure) | 01 | 2017-05-15 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Civil and Steel Structure | TAM | 2017-05-27 11:05 | IFC | AFC | 100%
130914 | I491TC02-0MMSD91-001-001 | Basis Of Design For RO Substation Building (Civil & Steel Structure) | 00 | 2017-07-29 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment System | Civil and Steel Structure | TAM | 2017-07-30 11:12 | IFA | AC |  | 95%
133027 | I491TC02-0MMSN01-001-001 | Calculation Book For Sand Filter-Shelter (STRUCTURE) | 01 | 2018-04-08 08:27 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Civil and Steel Structure | TAM | 2018-04-08 08:27 | IFC | AFC | 100%
115755 | I491TC02-0MMTK01-001-001 | Calculations Book For Cooling Water System Emergency Elevated Water Tank | 01 | 2016-06-14 | Indeterminate | Miscellaneous(MISC) | Basic | Water Treatment & Cooling System | Civil and Steel Structure | TAM | 2016-06-21 13:17 | IFA | AC |  | 95%
115657 | I491TC02-0MMTK01-002-001 | Mechanicl Calculation Book For Cooling Water System Emergency Elevated Water Tank | 00 | 2016-05-31 11:45 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Civil and Steel Structure | TAM | 2016-05-31 11:45 | IFA | AC |  | 95%
130514 | I491TC02-0MMTK01-003-001 | Calculations Book For Cooling Water System Emergency Elevated Water Tank Foundation Design | 02 | 2017-04-26 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Civil and Steel Structure | TAM | 2017-04-30 10:18 | IFC | AC |  | 95%
12021 | I491TC02-0MXAA91-001-001 | Preliminary Technical Report For Geotechnical Study | 00 | 2011-05-02 | Indeterminate | Miscellaneous(MISC) | Basic | General | Mechanical | TAM |  | IFI | OB | 100%
12024 | I491TC02-0MXAA91-001-004 | Hydraulogical Study For Storm Drainage System | 01 | 2013-08-04 | Indeterminate | Miscellaneous(MISC) | Basic | General | Civil and Steel Structure | TAM |  | IFC | AFC | 100%
12025 | I491TC02-0MXAA91-002-001 | Intermediate Technical Report For Geotechnical Study | 00 | 2011-05-02 | Indeterminate | Miscellaneous(MISC) | Detail | General | Mechanical | TAM |  | IFI | OB | 100%
12026 | I491TC02-0MXAA91-002-002 | نقشه های لرزه خیزی منطقه(لوگهای صحرایی) ضمیمه | 00 | 2011-05-02 | Indeterminate | Miscellaneous(MISC) | Detail | General | Mechanical | TAM |  | IFI | OB | 100%
12027 | I491TC02-0MXAA91-003-001 | Preliminary Geotechnical Study For Warehouse | 00 | 2011-05-02 | Indeterminate | Miscellaneous(MISC) | Basic | General | Mechanical | TAM |  | IFI | OB | 100%
12035 | I491TC02-0MXAA91-004-008 | Final Technical Report For Geotechnical Study | 07 | 2013-02-20 | Indeterminate | Miscellaneous(MISC) | Detail | General | Civil and Steel Structure | TAM |  | IFC | AFC | 100%
130091 | I491TC02-0MXAA91-005-001 | Hydraulogical Study For Sand Filter Drinage Road 10-1 | 01 | 2017-01-08 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System Building | Civil and Steel Structure | TAM | 2017-01-09 08:47 | IFC | AFC | 100%
132531 | I491TC02-0MXEG01-001-001 | Calculation Book For DIESEL ROOM (FOUNDATION) | 03 | 2017-12-12 | Indeterminate | Miscellaneous(MISC) | Detail | General | Civil and Steel Structure | TAM | 2017-12-13 09:50 | IFC | AFC | 100%
132532 | I491TC02-0MXEG01-002-001 | CALCULATION BOOK FOR DIESEL ROOM (STRUCTURE) | 01 | 2017-12-12 | Indeterminate | Miscellaneous(MISC) | Detail | General | Civil and Steel Structure | TAM | 2017-12-13 09:50 | IFC | AFC | 100%
132533 | I491TC02-0MXEG01-003-001 | Calculation Book For DIESEL ROOM (FOUNDATION) | 01 | 2017-12-12 | Indeterminate | Miscellaneous(MISC) | Detail | General | Civil and Steel Structure | TAM | 2017-12-13 09:51 | IFC | AFC | 100%
133131 | I491TC02-0MXEG01-004-001 | CALCULATION BOOK FOR MELTSHOP DIESEL GENERATOR ROOM CABLE TRENCH | 02 | 2018-05-09 | Indeterminate | Miscellaneous(MISC) | Detail | General | Civil and Steel Structure | TAM | 2018-05-15 09:21 | IFC | AFC | 100%
12039 | I491TC02-0MYAA91-001-004 | Workshop Calculation Book (Civil & Steel Structures) | 03 | 2012-03-03 | Indeterminate | Miscellaneous(MISC) | Detail | Maintenance Workshop | Civil and Steel Structure | IKS |  | IFC | AFC | 100%
12044 | I491TC02-0MYAA91-002-005 | Ferro Alloy Storage Calculation Book (Civil & Steel Structures) | 04 | 2012-11-11 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop Lime And Ferroalloy Storage | Civil and Steel Structure | IKS |  | IFC | AFC | 100%
132975 | I491TC02-0MYAA91-003-001 | Calculation Book For 2nd Floor Workshop (STRUCTURE) | 01 | 2018-03-13 | Indeterminate | Miscellaneous(MISC) | Detail | Maintenance Workshop | Civil and Steel Structure | TAM | 2018-03-17 16:41 | IFC | AFC | 100%
135213 | I491TC02-0NGSB91-001-001 | Natural Gas Reduction Station Calculation (Civil& Steel Structures) | 01 | 2019-04-08 | Indeterminate | Miscellaneous(MISC) | Detail | Natural Gas Receiving Station Building | Civil and Steel Structure | IKS | 2019-04-14 15:43 | IFC | AFC | 100%
135436 | I491TC02-0OFAM01-001-001 | Calculation Book for Ferroalloy Storage Security Office building (Structure) | 00 | 2019-06-01 | Indeterminate | Miscellaneous(MISC) | Detail | Office - Canteen - Locker & Shower For Melt Shop | Civil and Steel Structure | TAM | 2019-06-02 09:58 | IFA | AC |  | 95%
113022 | I491TC02-0OFAM91-001-001 | Calculation Book for Non-industrial Buidings (Admin.Canteen.Shower and Locker) (CIVIL & STRUCTURE) | 02 | 2014-04-12 | Indeterminate | Miscellaneous(MISC) | Detail | General | Civil and Steel Structure | Azhand Shahr | 2014-10-19 17:03 | IFC | AFC | 100%
135142 | I491TC02-0PXAA91-001-001 | CALCULATION BOOK FOR Ladle SAND FILLING STATION Foundation | 01 | 2019-03-18 10:30 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop Auxiliaries | Civil and Steel Structure | TAM | 2019-03-18 10:30 | IFC | AFC | 100%
135143 | I491TC02-0PXAA91-002-001 | CALCULATION BOOK FOR Ladle SAND FILLING (STRUCTURE) | 01 | 2019-03-18 10:31 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop Auxiliaries | Civil and Steel Structure | TAM | 2019-03-18 10:31 | IFC | AFC | 100%
114630 | I491TC02-0PXLI01-001-001 | Ladle Relining Platform-16 | 01 | 2015-10-26 11:19 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | TAM | 2015-10-26 11:19 | IFC | AFC | 100%
113498 | I491TC02-0PXLM02-001-001 | CALCULATION BOOK FOR LADLE DEBRICKING STATION | 01 | 2015-04-21 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop Auxiliaries | Civil and Steel Structure | APEC | 2015-04-22 10:52 | IFC | AFC | 100%
12046 | I491TC02-0PXSB91-001-001 | Calculation Book For Lower Shell Parking Position | 00 | 2013-08-07 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop Auxiliaries | Civil and Steel Structure | APEC |  | IFA | AFC | 100%
112419 | I491TC02-0PXSM01-001-001 | CALCULATION BOOK FOR LADLE SLAG DUMPING AREA | 01 | 2014-06-21 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop Auxiliaries | Civil and Steel Structure | APEC | 2014-06-26 16:23 | IFC | AFC | 100%
112614 | I491TC02-0PXSM03-001-001 | CALCULATION BOOK FOR EMERGANCY PIT | 01 | 2014-07-14 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop Auxiliaries | Civil and Steel Structure | APEC | 2014-07-16 09:29 | IFC | AFC | 100%
135171 | I491TC02-0RXEA91-002-001 | Calculation Book For Purging Station Foundation | 03 | 2019-03-17 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop Auxiliaries | Civil and Steel Structure | APEC | 2019-03-18 11:41 | IFC | AFC | 100%
134357 | I491TC02-0RXEA91-003-001 | Calculation Book For PURGING STATION JIB CRANE (PEDESTAL) | 00 | 2018-11-04 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop Auxiliaries | Civil and Steel Structure | TAM | 2018-11-10 09:14 | IFA | AC |  | 95%
12053 | I491TC02-0SHAA91-001-006 | Scrap Yard Calculation Book (Civil & Steel Structure) | 05 | 2012-09-30 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop Scrap Yard | Civil and Steel Structure | IKS |  | IFC | AFC | 100%
12055 | I491TC02-0SHAA91-002-002 | Calculation Book For Retaning Wall ( Civil & Steel Structure) | 01 | 2013-02-24 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop Scrap Yard | Civil and Steel Structure | IKS |  | IFC | AFC | 100%
111658 | I491TC02-0SHAA91-003-001 | CALCULATION BOOK FOR FTP DUCTS PEDESTAL ON SCRAP YARD FOUNDATION | 00 | 2014-04-05 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop Scrap Yard | Civil and Steel Structure | TAM | 2014-04-24 16:40 | IFC | AC |  | 95%
111531 | I491TC02-0SXBT02-001-002 | Calculation Book For Empty Ladle Transfer Car Foundation | 03 | 2014-01-22 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop Auxiliaries | Civil and Steel Structure | APEC | 2014-04-23 10:00 | IFC | AFC | 100%
115099 | I491TC02-0SXFD91-001-002 | Calculation Book For EAF Shell Relining Structure | 02 | 2016-03-16 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop Auxiliaries | Civil and Steel Structure | TAM | 2016-04-02 16:46 | IFC | AFC | 100%
130439 | I491TC02-0SXHB01-001-001 | Calculation Book For Vertical Ladle Preheater Foundation | 03 | 2017-04-08 | Indeterminate | Miscellaneous(MISC) | Detail | Eaf Auxiliaries | Civil and Steel Structure | TAM | 2017-04-17 10:42 | IFC | AFC | 100%
129768 | I491TC02-0SXHB91-002-001 | CALCULATION BOOK FOR HORIZONTAL LADLE PREHEATER FOUNDATION | 01 | 2016-10-31 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop Auxiliaries | Civil and Steel Structure | CEBA | 2016-11-02 09:39 | IFC | AC |  | 95%
130412 | I491TC02-0SXLD01-001-001 | Calculation Book For Ladle Drayer Foundation | 02 | 2017-04-04 | Indeterminate | Miscellaneous(MISC) | Detail | Eaf Auxiliaries | Civil and Steel Structure | TAM | 2017-04-09 11:40 | IFC | AFC | 100%
132899 | I491TC02-0SXLI91-001-001 | Calculation Book For Ladle Relining Station | 02 | 2018-02-17 10:06 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop Auxiliaries | Civil and Steel Structure | APEC | 2018-02-17 10:06 | IFC | AC |  | 95%
12068 | I491TC02-0TBAA91-001-006 | Calculation Book For Warehouse Civil & Steel Structures | 04 | 2011-11-01 | Indeterminate | Miscellaneous(MISC) | Detail | Warehouse | Civil and Steel Structure | IKS |  | IFC | AFC | 100%
133810 | I491TC02-0TBAA91-002-001 | Calculation Book For Melt Shop Flooring | 02 | 2018-07-18 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2018-07-19 09:54 | IFC | AFC | 100%
115615 | I491TC02-0TBAM91-001-001 | Calculation Book For Eaf Building Structure | 03 | 2016-05-31 09:38 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2016-05-31 09:38 | IFC | AFC | 100%
113645 | I491TC02-0TBAM91-003-005 | Calculation Book For Lf Building Structure | 05 | 2015-05-19 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2015-05-30 09:21 | IFC | AC |  | 95%
130480 | I491TC03-0ASCP01-001-001 | 4-5-6 ASP Turbo Compressors Foundation Listoser | 00 | 2017-04-19 | Indeterminate | Drawing | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2017-04-29 13:22 | IFI | OB | 100%
130481 | I491TC03-0ASCP02-001-001 | 7 ASP Booster Air Compressor Foundation Listofer | 00 | 2017-04-19 | Indeterminate | Drawing | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2017-04-29 13:22 | IFI | OB | 100%
130482 | I491TC03-0ASIJ01-001-001 | 12 ASP Cold Box Foundation Listofer | 00 | 2017-04-19 | Indeterminate | Drawing | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2017-04-29 13:22 | IFI | OB | 100%
130483 | I491TC03-0ASPS01-001-001 | 11 ASP PPU SKID Foundation Listofer | 00 | 2017-04-19 | Indeterminate | Drawing | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2017-04-29 13:23 | IFI | OB | 100%
130484 | I491TC03-0ASPU01-001-001 | 24 ASP Liquid Oxygen Back Up Pump Listofer | 00 | 2017-04-19 | Indeterminate | Drawing | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2017-04-29 13:23 | IFI | OB | 100%
130506 | I491TC03-0ASPU02-001-001 | 22 ASP Liquid Argon Back Up Pump Listofer | 00 | 2017-04-19 | Indeterminate | Drawing | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2017-04-29 13:23 | IFI | OB | 100%
130507 | I491TC03-0ASPU03-001-001 | 23 ASP Liquid Nitrogen Back Up Pump Listofer | 00 | 2017-04-19 | Indeterminate | Drawing | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2017-04-29 13:24 | IFI | OB | 100%
130504 | I491TC03-0ASPU04-001-001 | 34 ASP Liquid Nitrogen Process Pump Foundation Listofer | 00 | 2017-04-19 | Indeterminate | Drawing | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2017-04-29 13:23 | IFI | OB | 100%
130505 | I491TC03-0ASSB91-001-001 | 1-2-3 Self Air Clean Filter Foundation | 00 | 2017-04-19 | Indeterminate | Drawing | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2017-04-29 13:23 | IFI | OB | 100%
130503 | I491TC03-0ASSB91-008-001 | 8 ASP Air Cooling Tower Foundation Listofer | 00 | 2017-04-19 | Indeterminate | Drawing | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2017-04-29 13:23 | IFI | OB | 100%
130500 | I491TC03-0ASSB91-009-001 | 9 ASP Water Cooling Tower Foundation Listofer | 00 | 2017-04-19 | Indeterminate | Drawing | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2017-04-29 13:23 | IFI | OB | 100%
130501 | I491TC03-0ASSB91-025-001 | 25 ASP Liquid Argon Vaporizer Foundation Listofer | 00 | 2017-04-19 | Indeterminate | Drawing | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2017-04-29 13:23 | IFI | OB | 100%
130502 | I491TC03-0ASSB91-026-001 | 26 ASP Liquid Nitrogen Vaporizer Foundation Listofer | 00 | 2017-04-19 | Indeterminate | Drawing | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2017-04-29 13:23 | IFI | OB | 100%
130499 | I491TC03-0ASSB91-027-001 | ASP Liquid Oxygen Vaporizer Foundation Listofer | 00 | 2017-04-19 | Indeterminate | Drawing | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2017-04-29 13:23 | IFI | OB | 100%
130485 | I491TC03-0ASSL02-001-001 | 18 ASP Oxygen Silencer Foundation Listofer | 00 | 2017-04-19 | Indeterminate | Drawing | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2017-04-29 13:23 | IFI | OB | 100%
130486 | I491TC03-0ASSL03-001-001 | 17 ASP Nitrogen Silencer Foundation Listofer | 00 | 2017-04-19 | Indeterminate | Drawing | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2017-04-29 13:23 | IFI | OB | 100%
130498 | I491TC03-0ASTK01-001-001 | 21 ASP Liquid Oxygen Tank Foundation Listofer | 00 | 2017-04-19 | Indeterminate | Drawing | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2017-04-29 13:23 | IFI | OB | 100%
131062 | I491TC03-0ASTK02-001-001 | 20 ASP Liquid Nitrogen Tank Foundation Listofer | 02 | 2017-08-16 | Indeterminate | Drawing | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2017-08-23 10:39 | IFI | OB | 100%
130488 | I491TC03-0ASTK03-001-001 | 19 ASP Liquid Argon Tank foundation | 00 | 2017-04-19 | Indeterminate | Drawing | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2017-04-29 13:23 | IFI | OB | 100%
130489 | I491TC03-0ASTK04-001-001 | 30 ASP Oxygen Buffer Tank Foundation Listofer | 00 | 2017-04-19 | Indeterminate | Drawing | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2017-04-29 13:23 | IFI | OB | 100%
130490 | I491TC03-0ASTK05-001-001 | 29 ASP Nitrogen Buffer Tank Foundation Listofer | 00 | 2017-04-19 | Indeterminate | Drawing | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2017-04-29 13:23 | IFI | OB | 100%
130491 | I491TC03-0ASTK06-001-001 | 28 ASP Argon Buffer Tank Foundation Listofer | 00 | 2017-04-19 | Indeterminate | Drawing | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2017-04-29 13:23 | IFI | OB | 100%
130492 | I491TC03-0ASVS01-001-001 | 15 ASP Waste Liquid Vaporizer Foundation Listofer | 00 | 2017-04-19 | Indeterminate | Drawing | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2017-04-29 13:23 | IFI | OB | 100%
130493 | I491TC03-0ASVS02-001-001 | 32 ASP Nitrogen Pressure Reducer Foundation Listofer | 00 | 2017-04-19 | Indeterminate | Drawing | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2017-04-29 13:23 | IFI | OB | 100%
130494 | I491TC03-0ASVS05-001-001 | ASP Waster Nitrogen Silencer Foundation Listofer | 00 | 2017-04-19 | Indeterminate | Drawing | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2017-04-29 13:23 | IFI | OB | 100%
130495 | I491TC03-0ASXX01-001-001 | 10 ASP DCAC SKID Foundation Listofer | 00 | 2017-04-19 | Indeterminate | Drawing | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2017-04-29 13:23 | IFI | OB | 100%
130496 | I491TC03-0ASXX03-001-001 | 33 ASP Argon Pressure Reducer Foundation Listofer | 00 | 2017-04-19 | Indeterminate | Drawing | Detail | Material Handling | Civil and Steel Structure | TAM | 2017-04-29 13:23 | IFI | OB | 100%
130497 | I491TC03-0ASXX05-002-001 | 31 ASP R0 Go Pressure Reducer Blast Wall Listofer | 00 | 2017-04-19 | Indeterminate | Drawing | Detail | Material Handling | Civil and Steel Structure | TAM | 2017-04-29 13:23 | IFI | OB | 100%
12080 | I491TC03-0CCSB91-001-002 | Ccm Foundation Tract4 -Bar Bending Schedule | 01 | 2013-08-20 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
114958 | I491TC03-0CCTK91-001-001 | Report Of Listofer | 01 | 2016-02-28 13:10 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | APEC | 2016-02-28 13:10 | IFC | AFC | 100%
111298 | I491TC03-0DTAA91-002-001 | Setteling Chamber Listofer | 00 | 2013-12-08 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Equipment | Civil and Steel Structure | TAM | 2014-04-15 13:51 | IFC | AFC | 100%
113528 | I491TC03-0DTSB91-001-001 | FTP Foundation Listofer | 00 | 2015-05-27 12:11 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | HASCON | 2015-05-27 12:11 | IFC | AC |  | 95%
12081 | I491TC03-0EAAA91-009-001 | Listofer Foundation | 01 | 2013-07-23 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM |  | IFA | A | 100%
111532 | I491TC03-0EABT92-006-001 | Reportof listofer EMPTY LADLE TRANSFER CAR | 02 | 2014-01-22 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Civil and Steel Structure | TAM | 2014-04-23 10:01 | IFC | AFC | 100%
112679 | I491TC03-0EAFB91-001-001 | EAF Platform Listofer-Bar Bending Schedule | 00 | 2014-08-09 | Indeterminate | Miscellaneous(MISC) | Detail | Electric Arc Furnace | Civil and Steel Structure | APEC | 2014-08-18 09:40 | IFC | AFC | 100%
12083 | I491TC03-0LFAA91-001-001 | Lifting Cylinder Roof Lifting Device Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | INTECO |  | IFI | OB | 100%
12084 | I491TC03-0LFAA91-001-002 | Furnace Foundation Civil Works Lf | 00 | 2012-03-14 | Indeterminate | Drawing | Basic | Ladle Furnace | Civil and Steel Structure | INTECO |  | IFI | OB | 100%
115117 | I491TC03-0LFAA91-002-001 | LF Building LF MHS Foundation Listofer | 00 | 2016-04-05 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop Main Building | Civil and Steel Structure | DATIS | 2016-04-09 13:36 | IFC | AFC | 100%
112203 | I491TC03-0LFFB91-001-001 | LF Platform Barbending Schedule listofer | 00 | 2014-05-19 09:52 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Civil and Steel Structure | TAM | 2014-05-19 09:52 | IFC | AFC | 100%
129274 | I491TC03-0MDSB91-001-001 | EAF MHS Foundation Bar Bending | 00 | 2016-08-17 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2016-08-20 10:54 | IFC | AFC | 100%
129731 | I491TC03-0MMTK01-001-001 | WCP Emergency Water Tank Foundation listofe | 00 | 2016-10-23 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Civil and Steel Structure | TAM | 2016-11-01 09:03 | IFC | AC |  | 95%
113499 | I491TC03-0PXLM02-001-001 | LADLE DEBRICKING STATION Listofer FOUNDATION -bar bending | 01 | 2015-04-21 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop Auxiliaries | Civil and Steel Structure | APEC | 2015-04-22 10:53 | IFC | AFC | 100%
12085 | I491TC03-0PXSB91-001-001 | Lower Shell Parking Position-Bar Bending Listofer | 01 | 2013-08-07 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop Auxiliaries | Civil and Steel Structure | TAM |  | IFC | AFC | 100%
112420 | I491TC03-0PXSM01-001-001 | LADLE SLAG DUMPING AREA Listofer FOUNDATION -bar bending | 00 | 2014-06-21 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop Auxiliaries | Civil and Steel Structure | APEC | 2014-06-26 16:24 | IFC | AFC | 100%
112775 | I491TC03-0PXSM03-001-001 | EMERGANCY PIT Listofer FOUNDATION -bar bending | 02 | 2014-09-03 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop Auxiliaries | Civil and Steel Structure | APEC | 2014-09-06 17:53 | IFC | AFC | 100%
12086 | I491TC03-0SXBT02-001-001 | Empty Ladle Transfer Car Listofer Foundation -Bar Bending | 02 | 2013-07-06 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop Auxiliaries | Civil and Steel Structure | APEC |  | IFA | AFC | 100%
115100 | I491TC03-0SXFD91-001-001 | EAF Shell Relining Station-Bar Bending Schedule | 00 | 2016-03-16 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop Auxiliaries | Civil and Steel Structure | TAM | 2016-04-02 16:46 | IFC | AFC | 100%
12090 | I491TC03-0SXLI91-001-001 | Ladle Relining Station-Bar Bending Schedule | 01 | 2015-04-30 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop Auxiliaries | Civil and Steel Structure | TAM |  | IFA | AC |  | 95%
12913 | I491TC03-0TBAA91-001-001 | Melt Shop Main Building , Eaf Buildingfoundation listofer | 05 | 2013-04-24 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
113033 | I491TC03-0TBAA91-007-001 | Report Of Listofer | 00 | 2014-10-18 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2014-10-21 09:00 | IFC | AC |  | 95%
113475 | I491TC03-0TBAM91-002-001 | Lf Building Bar Bending Listofer | 02 | 2013-11-23 | Indeterminate | Miscellaneous(MISC) | Basic | Melt Shop Main Building | Civil and Steel Structure | TAM | 2015-04-20 15:21 | IFC | AC |  | 95%
115616 | I491TC03-0TBAM91-004-001 | Report Of Listofer | 04 | 2016-05-31 10:44 | Indeterminate | Miscellaneous(MISC) | Basic | Melt Shop Main Building | Civil and Steel Structure | TAM | 2016-05-31 10:44 | IFC | AFC | 100%
130299 | I491TC04-0ASAA91-001-001 | EQUIPMENT FOUDATION LAYOUT 1-4 | 01 | 2017-02-07 10:29 | Indeterminate | Drawing | Basic | Air Separation Plant Main Building | Civil and Steel Structure | TAM | 2017-02-07 10:29 | IFC | AC |  | 95%
130296 | I491TC04-0ASAA91-001-002 | EQUIPMENT FOUDATION LAYOUT 2-4 | 00 | 2017-02-07 10:29 | Indeterminate | Drawing | Basic | Air Separation Plant Main Building | Civil and Steel Structure | TAM | 2017-02-07 10:29 | IFC | AFC | 100%
130297 | I491TC04-0ASAA91-001-003 | EQUIPMENT FOUDATION LAYOUT 3-4 | 00 | 2017-02-07 10:29 | Indeterminate | Drawing | Basic | Air Separation Plant Main Building | Civil and Steel Structure | TAM | 2017-02-07 10:29 | IFC | AC |  | 95%
130298 | I491TC04-0ASAA91-001-004 | EQUIPMENT FOUDATION LAYOUT 4-4 | 00 | 2017-02-07 10:29 | Indeterminate | Drawing | Basic | Air Separation Plant Main Building | Civil and Steel Structure | TAM | 2017-02-07 10:29 | IFC | AC |  | 95%
129791 | I491TC04-0ASCP01-001-001 | ASP Turbo Compressor Foundation Loading Plan 1-2 | 01 | 2016-11-12 09:25 | Indeterminate | Drawing | Basic | Air Separation Plant Main Building | Mechanical | TAM | 2016-11-12 09:25 | IFI | OB | 100%
129792 | I491TC04-0ASCP01-002-001 | ASP Turbo Compressor Foundation Loading Plan 2-2 | 00 | 2016-11-12 09:25 | Indeterminate | Drawing | Detail | Air Separation Plant Main Building | Mechanical | TAM | 2016-11-12 09:25 | IFI | OB | 100%
12091 | I491TC04-0CCAM91-001-001 | 6-Strand Billet Caster Foundation Tract-1Foundation Guide Plan | 00 | 2013-10-21 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Civil and Steel Structure | INTECO |  | IFA | A | 100%
113283 | I491TC04-0CCAM91-001-002 | CCM Cabin Foundation Plan Level 2.95 GP08VB-HC11-C0400-BD001_001_00 | 02 | 2015-01-24 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Civil and Steel Structure | INTECO | 2015-01-28 11:04 | IFC | AFC | 100%
12093 | I491TC04-0CCAM91-002-001 | 6-Strand Billet Caster Foundation Tract-2 Foundation Guide Plan | 00 | 2013-10-21 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Civil and Steel Structure | INTECO |  | IFA | A | 100%
12094 | I491TC04-0CCAM91-002-002 | 6-Strand Billet Caster Foundation Tract-2 Foundation Guide Plan | 00 | 2013-10-21 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Civil and Steel Structure | INTECO |  | IFA | A | 100%
113284 | I491TC04-0CCAM91-002-003 | CCM Cabin Foundation Plan Level 5.15 GP08VB-HC11-C0400-BD002_001_00 | 02 | 2015-01-24 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Civil and Steel Structure | INTECO | 2015-01-28 11:05 | IFC | AFC | 100%
12096 | I491TC04-0CCAM91-002-004 | 6-Strand Billet Caster Foundation Tract-2 Foundation Guide Plan 2-2 | 01 | 2013-11-22 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Civil and Steel Structure | INTECO |  | IFC | AFC | 100%
12097 | I491TC04-0CCAM91-003-001 | 6-Strand Billet Caster Foundation Tract-1+2 Anchore Detail | 00 | 2013-10-21 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Civil and Steel Structure | TAM |  | IFA | A | 100%
12098 | I491TC04-0CCAM91-003-002 | 6-Strand Billet Caster Foundation Tract-1+2 Anchore Detail | 00 | 2013-10-21 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Civil and Steel Structure | TAM |  | IFA | A | 100%
113285 | I491TC04-0CCAM91-003-003 | CCM Cabin Foundation Plan at Level 9.87 GP08VB-HC11-C0400-BD003_001_00 | 02 | 2015-01-24 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Civil and Steel Structure | TAM | 2015-01-28 11:05 | IFC | AFC | 100%
12100 | I491TC04-0CCAM91-003-004 | 6-Strand Billet Caster Foundation Tract-1+2 Anchore Detail 2-2 | 01 | 2013-11-22 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Civil and Steel Structure | TAM |  | IFC | AFC | 100%
12101 | I491TC04-0CCAM91-004-001 | 6-Strand Billet Caster Foundation Tract-1+2 Foundation Load Plan | 00 | 2013-10-21 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Civil and Steel Structure | TAM |  | IFA | A | 100%
113286 | I491TC04-0CCAM91-004-002 | CCM Cabin Foundation Section AA GP08VB-HC11-C0400-BD004_001_00 | 02 | 2015-01-24 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Civil and Steel Structure | TAM | 2015-01-28 11:05 | IFC | AFC | 100%
12103 | I491TC04-0CCAM91-005-001 | 6-Strand Billet Caster Fuondation Tract - 1+2 Center Of Gravity | 00 | 2013-10-21 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Civil and Steel Structure | TAM |  | IFA | A | 100%
113287 | I491TC04-0CCAM91-005-002 | CCM Cabin Foundation Section BB GP08VB-HC11-C0400-BD005_001_00 | 02 | 2015-01-24 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Civil and Steel Structure | TAM | 2015-01-28 11:05 | IFC | AFC | 100%
113288 | I491TC04-0CCAM91-010-001 | CCM Cabin Foundation Plan at Level 0 and 4.5 GP08VB-HC11-C0400-BD010_001_00 | 01 | 2015-01-24 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Civil and Steel Structure | TAM | 2015-01-28 11:06 | IFC | AFC | 100%
113289 | I491TC04-0CCAM91-011-001 | CCM Cabin Foundation Plan Section AA BB GP08VB-HC11-C0400-BD011_001_00 | 01 | 2015-01-24 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Civil and Steel Structure | TAM | 2015-01-28 11:06 | IFC | AFC | 100%
113290 | I491TC04-0CCAM91-015-001 | CCM Battery Charging Room GP08VB-HC11-C0400-BD015_001 | 00 | 2015-01-24 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Civil and Steel Structure | TAM | 2015-01-28 11:06 | IFC | AFC | 100%
134230 | I491TC04-0CCHB01-001-001 | TUNDISH PREHEATER GENERAL ASSEMBLY | 01 | 2018-09-23 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2018-10-02 08:55 | IFC | AFC | 100%
134231 | I491TC04-0CCHB02-001-001 | Preheating Stove GENERAL ASSEMBLY 020-DA-16941-1_GENERAL ASSEMBLY | 01 | 2018-09-23 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2018-10-02 08:56 | IFC | AFC | 100%
134232 | I491TC04-0CCHB03-001-001 | Sen and Nozzel Preheater General Assm 051-DA-16944-1_GENERAL_ASSEMBLY | 01 | 2018-09-23 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2018-10-02 08:56 | IFC | AFC | 100%
113267 | I491TC04-0CCSB91-001-001 | CCM Foundation General Plant veiw GP08VB-HC11-C0300-BD001_001_00 | 02 | 2015-01-24 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Civil and Steel Structure | APEC | 2015-01-28 11:01 | IFC | AFC | 100%
113268 | I491TC04-0CCSB91-002-001 | CCM Foundation Plan Area1 level0 GP08VB-HC11-C0300-BD002_001_00 | 02 | 2015-01-24 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Civil and Steel Structure | APEC | 2015-01-28 11:01 | IFC | AFC | 100%
12110 | I491TC04-0CCSB91-002-002 | 6 - Strand Billet Caster Foundation Tract-4 Anchore Detail | 00 | 2013-04-29 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Civil and Steel Structure | APEC |  | IFA | A | 100%
113269 | I491TC04-0CCSB91-003-001 | CCM Foundation Plant Area2 Level0 GP08VB-HC11-C0300-BD003_001_00 | 02 | 2015-01-24 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Civil and Steel Structure | APEC | 2015-01-28 11:01 | IFC | AFC | 100%
12112 | I491TC04-0CCSB91-003-002 | Equipment Loading Plan For Ccm Foundation (Tract 4) | 00 | 2013-05-26 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Civil and Steel Structure | APEC |  | IFA | A | 100%
113270 | I491TC04-0CCSB91-004-001 | CCM Foundation Plan Area3 Level0 GP08VB-HC11-C0300-BD004_001_00 | 02 | 2015-01-24 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Civil and Steel Structure | APEC | 2015-01-28 11:02 | IFC | AFC | 100%
113271 | I491TC04-0CCSB91-005-001 | CCM Foundation Plan Area1 Level 4.9 GP08VB-HC11-C0300-BD005_001_00 | 02 | 2015-01-24 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Civil and Steel Structure | APEC | 2015-01-28 11:02 | IFC | AFC | 100%
12120 | I491TC04-0CCSB91-005-002 | 6 - Strand Billet Caster Foundation Tract-3 Anchor Detail | 00 | 2013-04-30 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Civil and Steel Structure | APEC |  | IFA | AC |  | 95%
113272 | I491TC04-0CCSB91-006-001 | CCM Foundation Plan Area1 Level 9.82 GP08VB-HC11-C0300-BD006_001_00 | 01 | 2015-01-24 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Civil and Steel Structure | TAM | 2015-01-28 11:02 | IFC | AFC | 100%
113273 | I491TC04-0CCSB91-007-001 | CCM Foundation Plan Longitudinal Section AA GP08VB-HC11-C0300-BD007_001_00 | 02 | 2015-01-24 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Civil and Steel Structure | TAM | 2015-01-28 11:02 | IFC | AFC | 100%
113274 | I491TC04-0CCSB91-008-001 | CCM Foundation Section BB Level 2.7 GP08VB-HC11-C0300-BD008_001_00 | 02 | 2015-01-24 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Civil and Steel Structure | TAM | 2015-01-28 11:02 | IFC | AFC | 100%
113275 | I491TC04-0CCSB91-009-001 | CCM Foundation Section CC and DD GP08VB-HC11-C0300-BD009_001_00 | 02 | 2015-01-24 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Civil and Steel Structure | TAM | 2015-01-28 11:03 | IFC | AFC | 100%
16616 | I491TC04-0CCSB91-009-002 | 6-Strand Billet Caster Foundation Track-5 Anchore Detail | 01 | 2013-12-18 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Civil and Steel Structure | TAM | 2014-02-18 13:13 | IFC | AFC | 100%
113276 | I491TC04-0CCSB91-010-001 | CCM Foundation Section EE FFGG MM PP GP08VB-HC11-C0300-BD010_001_00 | 02 | 2015-01-24 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Civil and Steel Structure | TAM | 2015-01-28 11:03 | IFC | AFC | 100%
16618 | I491TC04-0CCSB91-010-002 | 6-Strand Billet Caster Foundation Tract-5 Center Of Gravity | 01 | 2013-12-18 | Indeterminate | Miscellaneous(MISC) | Basic | Continuous Casting Machine (CCM) | Civil and Steel Structure | TAM | 2014-02-18 13:13 | IFC | AFC | 100%
113277 | I491TC04-0CCSB91-011-001 | CCM Foundation Section HH JJ KK NN GP08VB-HC11-C0300-BD011_001_00 | 01 | 2015-01-24 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Civil and Steel Structure | TAM | 2015-01-28 11:03 | IFC | AFC | 100%
113278 | I491TC04-0CCSB91-012-001 | CCM Foundation Loads on Foundation GP08VB-HC11-C0300-BD012_001_00 | 01 | 2015-01-24 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Civil and Steel Structure | TAM | 2015-01-28 11:04 | IFC | AFC | 100%
113279 | I491TC04-0CCSB91-013-001 | CCM Foundation Loads Table GP08VB-HC11-C0300-BD013_001_00 | 01 | 2015-01-24 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Civil and Steel Structure | TAM | 2015-01-28 11:04 | IFC | AFC | 100%
113280 | I491TC04-0CCSB91-014-001 | CCM Foundation Note and Detail GP08VB-HC11-C0300-BD014_001_00 | 01 | 2015-01-24 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Civil and Steel Structure | TAM | 2015-01-28 11:04 | IFC | AFC | 100%
113281 | I491TC04-0CCSB91-015-001 | CCM Foundation Datum Point GP08VB-HC11-C0300-BD015_001_00 | 01 | 2015-01-24 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Civil and Steel Structure | TAM | 2015-01-28 11:04 | IFC | AFC | 100%
113282 | I491TC04-0CCSB91-016-001 | CCM Foundation Electrical Canduits and Pit GP08VB-HC11-C0300-BD016_001_00 | 01 | 2015-01-24 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Civil and Steel Structure | TAM | 2015-01-28 11:04 | IFC | AFC | 100%
113291 | I491TC04-0CCSB91-017-001 | CCM Auxilliary Foundation GP08VB-HY11-C0300-BD001_001_00 | 01 | 2015-01-24 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Civil and Steel Structure | TAM | 2015-01-28 11:06 | IFC | AFC | 100%
112999 | I491TC04-0CCSB91-018-001 | CCM Tundish Tilting Foundation GP08VB-HY11-C0300-BD002_001_00 | 00 | 2014-09-27 11:07 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Civil and Steel Structure | TAM | 2014-09-27 11:07 | IFI | OB | 100%
113292 | I491TC04-0CCSB91-019-001 | CCM Tundish Relining Foundation GP08VB-HY11-C0300-BD003_001_00 | 01 | 2015-01-24 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Civil and Steel Structure | TAM | 2015-01-28 11:06 | IFC | AFC | 100%
113293 | I491TC04-0CCSB91-020-001 | CCM Tundish Stand and FNC Foundation GP08VB-HY11-C0300-BD004_001_00 | 01 | 2015-01-24 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Civil and Steel Structure | TAM | 2015-01-28 11:07 | IFC | AFC | 100%
113002 | I491TC04-0CCSB91-021-001 | CCM Tundigh Drying Station Foundation GP08VB-HY11-C0300-BD005_001_00 | 00 | 2014-09-27 11:07 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Civil and Steel Structure | TAM | 2014-09-27 11:07 | IFI | OB | 100%
113294 | I491TC04-0CCSB91-022-001 | CCM Mould Maintenance Area Foundation GP08VB-HY11-C0300-BD010_001_00 | 01 | 2015-01-24 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Civil and Steel Structure | TAM | 2015-01-28 11:07 | IFC | AFC | 100%
134233 | I491TC04-0CCTD10-001-001 | Tundish Drying Station General Assembly 002-DA-16960-3 | 01 | 2018-09-23 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2018-10-02 08:58 | IFC | AFC | 100%
114821 | I491TC04-0DTAA91-001-001 | Dedusting System Furnace 140 Ton Eaf+Lf & Mh FOUNDATION PLANS - ASSEMBLY 6519-C01(1-23) | 01 | 2016-01-24 09:49 | Indeterminate | Drawing | Basic | Fume Treatment Equipment | Civil and Steel Structure | TAM | 2016-01-24 09:49 | IFC | AFC | 100%
114822 | I491TC04-0DTAA91-001-002 | Dedusting System Furnace 140 Ton Eaf+Lf & Mh Foundation Plans - FILTER FOUNDATION LOADS 6519-C02(2-23) | 01 | 2016-01-24 09:51 | Indeterminate | Drawing | Basic | Fume Treatment Equipment | Civil and Steel Structure | TAM | 2016-01-24 09:51 | IFC | AFC | 100%
114823 | I491TC04-0DTAA91-001-003 | Dedusting System Furnace 140 Ton Eaf+Lf & Mh Foundation Plans - SILO AND STAIRS FOUNDATIONS 6519-C03(3-23) | 01 | 2016-01-24 09:51 | Indeterminate | Drawing | Basic | Fume Treatment Equipment | Civil and Steel Structure | TAM | 2016-01-24 09:51 | IFC | AFC | 100%
112908 | I491TC04-0DTAA91-001-004 | Dedusting System Furnace 140 Ton Eaf+Lf & Mh Foundation Plans - Assembly Stack and fan(4-23) | 01 | 2014-09-21 | Indeterminate | Drawing | Basic | Fume Treatment Equipment | Civil and Steel Structure | TAM | 2014-09-22 09:24 | IFC | AFC | 100%
114828 | I491TC04-0DTAA91-001-005 | Dedusting System Furnace 140 Ton Eaf+Lf & Mh Foundation Plans - MAIN FAN FOUNDATION LOAD 6519-C05(5-23) | 02 | 2016-01-24 09:51 | Indeterminate | Drawing | Basic | Fume Treatment Equipment | Civil and Steel Structure | TAM | 2016-01-24 09:51 | IFC | AFC | 100%
114824 | I491TC04-0DTAA91-001-006 | Dedusting System Furnace 140 Ton Eaf+Lf & Mh Foundation Plans - MIXING CHAMBER FOUNDATION LOADS 6519-C06(6-23) | 01 | 2016-01-24 09:51 | Indeterminate | Drawing | Basic | Fume Treatment Equipment | Civil and Steel Structure | TAM | 2016-01-24 09:51 | IFC | AFC | 100%
114829 | I491TC04-0DTAA91-001-007 | Dedusting SystemFOURNACE 140 Ton EAF+LF & MH SETLLING CHAMBER FOUNDATION LOADS 6519-C08 (8-23) | 04 | 2016-01-24 09:51 | Indeterminate | Drawing | Basic | Fume Treatment Equipment | Civil and Steel Structure | TAM | 2016-01-24 09:51 | IFC | AFC | 100%
112910 | I491TC04-0DTAA91-001-008 | Dedusting System Furnace 140 Ton Eaf+Lf & Mh Foundation Plans - Assembly Stack(10-23) | 01 | 2014-09-21 | Indeterminate | Drawing | Basic | Fume Treatment Equipment | Civil and Steel Structure | TAM | 2014-09-22 09:24 | IFC | AFC | 100%
114825 | I491TC04-0DTAA91-001-009 | Dedusting System Furnace 140 Ton Eaf+Lf & Mh Foundation Plans - NATURAL COOLER LOAD 6519-C11(11-23) | 01 | 2016-01-24 09:51 | Indeterminate | Drawing | Basic | Fume Treatment Equipment | Civil and Steel Structure | TAM | 2016-01-24 09:51 | IFC | AFC | 100%
114826 | I491TC04-0DTAA91-001-010 | Dedusting System Furnace 140 Ton Eaf+Lf & Mh Foundation Plans - DRI FILTER FOUNDATION LOAD 6519-C12(12-23) | 01 | 2016-01-24 09:51 | Indeterminate | Drawing | Basic | Fume Treatment Equipment | Civil and Steel Structure | TAM | 2016-01-24 09:51 | IFC | AFC | 100%
112911 | I491TC04-0DTAA91-001-011 | Dedusting System Furnace 140 Ton Eaf+Lf & Mh Foundation Plans - Assembly Cyclon(13-23) | 01 | 2014-09-21 | Indeterminate | Drawing | Basic | Fume Treatment Equipment | Civil and Steel Structure | TAM | 2014-09-22 09:24 | IFC | AFC | 100%
114827 | I491TC04-0DTAA91-001-012 | Dedusting System Furnace 140 Ton Eaf+Lf & Mh Foundation Plans - MHS EAF FAN FOUNDATION LOADS 6519-C14(14-23) | 01 | 2016-01-24 09:51 | Indeterminate | Drawing | Basic | Fume Treatment Equipment | Civil and Steel Structure | TAM | 2016-01-24 09:51 | IFC | AFC | 100%
112912 | I491TC04-0DTAA91-001-013 | Dedusting System Furnace 140 Ton Eaf+Lf & Mh Foundation Plans - Assembly Primary booster fan(15-23) | 01 | 2014-09-21 | Indeterminate | Drawing | Basic | Fume Treatment Equipment | Civil and Steel Structure | TAM | 2014-09-22 09:24 | IFC | AFC | 100%
12131 | I491TC04-0DTAA91-001-014 | Dedusting System Furnace 140 Ton Eaf+Lf & Mh Foundation Plans - Assembly General plan(2-23) | 01 | 2013-05-06 | Indeterminate | Drawing | Basic | Fume Treatment Equipment | Civil and Steel Structure | TAM |  | IFC | AFC | 100%
114830 | I491TC04-0DTAA91-001-015 | Dedusting System Duct Fournace 140 Ton Eaf+Lf & Mh DUCT AND SLIDING DUCT FOUNDATION LOADS 6519-C09 (09-23) | 04 | 2016-01-24 09:51 | Indeterminate | Drawing | Basic | Fume Treatment Equipment | Civil and Steel Structure | TAM | 2016-01-24 09:51 | IFC | AFC | 100%
114837 | I491TC04-0DTAA91-001-016 | Dedusting System Duct Fournace 140 Ton Eaf+Lf & Mh COOLED DUCT SUPPORT FOUNDATION LOADS POS.15 (17-23) | 03 | 2016-01-24 09:58 | Indeterminate | Drawing | Basic | Fume Treatment Equipment | Civil and Steel Structure | TAM | 2016-01-24 09:58 | IFC | AFC | 100%
12134 | I491TC04-0DTAA91-001-017 | Dedusting System Duct Fournace 140 Ton Eaf+Lf & Mh & Sliding Anchor Bolts Detail (18-23) | 01 | 2013-08-18 | Indeterminate | Drawing | Basic | Fume Treatment Equipment | Civil and Steel Structure | TAM |  | IFA | A | 100%
114836 | I491TC04-0DTAA91-001-018 | Dedusting System Duct Fournace 140 Ton Eaf+Lf & Mh SUPPORT DUCTS - FOUNDATION LOADS POS. 18 6519-C18(19-23) | 02 | 2016-01-24 09:57 | Indeterminate | Drawing | Basic | Fume Treatment Equipment | Civil and Steel Structure | TAM | 2016-01-24 09:57 | IFC | AFC | 100%
114832 | I491TC04-0DTAA91-001-019 | Dedusting System Duct Fournace 140 Ton Eaf+Lf & Mh CROSSING DUCTS FOUNDATION LOADS 6519-C19 (20-23) | 01 | 2016-01-24 09:51 | Indeterminate | Drawing | Basic | Fume Treatment Equipment | Civil and Steel Structure | TAM | 2016-01-24 09:51 | IFC | AFC | 100%
114833 | I491TC04-0DTAA91-001-020 | Dedusting System Duct Fournace 140 Ton Eaf+Lf & Mh COOLED DUCT SUPPORT FOUNDATION LOADS POS. 16 6519-C20 (21-23) | 01 | 2016-01-24 09:51 | Indeterminate | Drawing | Basic | Fume Treatment Equipment | Civil and Steel Structure | TAM | 2016-01-24 09:51 | IFC | AFC | 100%
114834 | I491TC04-0DTAA91-001-021 | Dedusting System Duct Fournace 140 Ton Eaf+Lf & Mh SUPPORT DUCT - FOUNDATION LOADS POS.19 6519-C21(22-23) | 03 | 2016-01-24 09:51 | Indeterminate | Drawing | Basic | Fume Treatment Equipment | Civil and Steel Structure | TAM | 2016-01-24 09:51 | IFC | AFC | 100%
114835 | I491TC04-0DTAA91-001-022 | Dedusting System Duct Fournace 140 Ton Eaf+Lf & Mh SUPPORT DUCTS - FOUNDATION LOADS POS.20 6519-C22 (23-23) | 01 | 2016-01-24 09:52 | Indeterminate | Drawing | Basic | Fume Treatment Equipment | Civil and Steel Structure | TAM | 2016-01-24 09:52 | IFC | AFC | 100%
114820 | I491TC04-0DTAA91-001-023 | DEDUSTING SYSTEM FURNACE 140 TON EAF+LF & MH FOUNDATION PLANS - MHS LF Fan Foundation Loads (16-23) | 00 | 2016-01-24 09:48 | Indeterminate | Drawing | Basic | Fume Treatment Equipment | Civil and Steel Structure | TAM | 2016-01-24 09:48 | IFC | AFC | 100%
130348 | I491TC04-0DTCC01-001-001 | Dedusting System Setlling Chamber Foundation Loads | 01 | 2017-02-27 | Indeterminate | Drawing | Basic | Fume Treatment Equipment | Civil and Steel Structure | TAM | 2017-02-28 13:14 | IFC | AFC | 100%
12149 | I491TC04-0DTPP01-001-001 | Dedusting System Fournace 140 Ton Eaf+Lf & Mh Duct And Sliding Duct Foundation Loads | 00 | 2012-12-23 | Indeterminate | Drawing | Basic | Fume Treatment Equipment | Civil and Steel Structure | TAM |  | IFA | AC |  | 95%
12150 | I491TC04-0EAFB91-001-001 | Operating Platform Eaf | 00 | 2012-11-13 | Indeterminate | Drawing | Basic | Electric Arc Furnace | Mechanical | TAM |  | IFA | AC |  | 95%
12151 | I491TC04-0EAFM91-001-001 | Furnace Foundation | 03 | 2012-09-18 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | TAM |  | IFA | AC |  | 95%
12154 | I491TC04-0EAFM91-001-002 | Furnace Foundation-Bom | 00 | 2012-09-18 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | TAM |  | IFA | AC |  | 95%
12155 | I491TC04-0EAFM91-001-003 | Foundation Anchoring Eaf | 03 | 2012-09-18 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | TAM |  | IFA | AC |  | 95%
12156 | I491TC04-0EAFM91-001-004 | Swivel Platform Sp1-Foundation Anchoring Eaf | 03 | 2012-09-18 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | TAM |  | IFA | AC |  | 95%
12157 | I491TC04-0EAFM91-001-005 | Locking Device-Foundation Anchoring Eaf | 03 | 2012-09-18 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | TAM |  | IFA | AC |  | 95%
12158 | I491TC04-0EAFM91-001-006 | Rocker 3- R3 -Foundation Anchoring Eaf | 03 | 2012-09-18 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | TAM |  | IFA | AC |  | 95%
12159 | I491TC04-0EAFM91-001-007 | Tilting Cylinder Tc1 -Foundation Anchoring Eaf | 02 | 2012-09-18 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | TAM |  | IFA | AC |  | 95%
12160 | I491TC04-0EAFM91-001-008 | Civil Works Eaf-Rail System Eaf CW.02.400.DED-D-31.00.000.099 | 00 | 2012-09-18 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | TAM |  | IFA | AC |  | 95%
12161 | I491TC04-0EAFM91-001-009 | Civil Works Eaf-Rail System Eaf | 00 | 2012-09-18 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | TAM |  | IFA | AC |  | 95%
12152 | I491TC04-0EAFM91-001-010 | Foundation Rail System Eaf-Rail System For Ladle Car | 00 | 2012-09-18 | Indeterminate | Drawing | Detail | Eaf Auxiliaries | Civil and Steel Structure | TAM |  | IFA | AC |  | 95%
12153 | I491TC04-0EAFM91-001-011 | Ladle Operation Cycle-Ladle Transfer Car At Eaf | 03 | 2012-09-18 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Civil and Steel Structure | TAM |  | IFA | AC |  | 95%
135290 | I491TC04-0EASM91-001-001 | EAF TEMPORARY SLAG YARD PLAN VIEW 1-2 | 02 | 2019-05-04 | Indeterminate | Drawing | Detail | Slag Yard | Mechanical | TAM | 2019-05-05 09:35 | IFC | AFC | 100%
135289 | I491TC04-0EASM91-001-002 | LF TEMPORARY SLAG YARD PLAN VIEW 2-2 | 01 | 2019-05-04 | Indeterminate | Drawing | Detail | Slag Yard | Mechanical | TAM | 2019-05-05 09:35 | IFC | AFC | 100%
16586 | I491TC04-0LFFB91-001-001 | Operating Platform Lf | 01 | 2013-12-03 | Indeterminate | Drawing | Basic | Ladle Furnace | Mechanical | INTECO | 2014-02-18 10:53 | IFC | AC |  | 95%
132996 | I491TC04-0LFFB91-002-001 | LF AIR HANDELING UNIT SUPPORT LOADING PLAN | 03 | 2018-03-17 | Indeterminate | Drawing | Basic | Ladle Furnace | Mechanical | TAM | 2018-03-18 09:37 | IFI | OB | 100%
12163 | I491TC04-0LFLE91-001-001 | Furnace Foundation -Civil Works Lf | 03 | 2012-09-18 | Indeterminate | Drawing | Basic | Ladle Furnace | Mechanical | TAM |  | IFA | AC |  | 95%
12164 | I491TC04-0LFLE91-001-002 | Furnace Foundation -Civil Works Lf-Bom | 03 | 2012-09-18 | Indeterminate | Drawing | Basic | Ladle Furnace | Mechanical | TAM |  | IFA | AC |  | 95%
12165 | I491TC04-0LFLE91-001-003 | Ladle Operation Cycle-Ladle Transfer Car At Lf | 00 | 2012-09-18 | Indeterminate | Drawing | Basic | Ladle Furnace | Mechanical | TAM |  | IFA | AC |  | 95%
114717 | I491TC04-0RXWH91-001-001 | Wire Feeder-TS Mani-emergency Lance FOUNDATION 072-DA-11960-3 | 00 | 2015-11-28 | Indeterminate | Drawing | Detail | Ladle Furnace Auxiliary | Mechanical | TAM | 2015-12-01 10:05 | IFA | A | 100%
114745 | I491TC04-0SXCJ91-001-001 | Carbon Injection Foundation Load Plan D-36.00.000.007 | 00 | 2015-12-06 | Indeterminate | Drawing | Basic | Eaf Auxiliaries | Mechanical | FUCHS | 2015-12-07 11:10 | IFA | AC |  | 95%
12168 | I491TC05-0ASAA91-001-002 | Oxygen Excavation Plan | 01 | 2012-02-20 | Indeterminate | Drawing | Detail | Air Separation Plant Main Building | Civil and Steel Structure | TAM |  | IFC | AFC | 100%
12170 | I491TC05-0DTAA91-001-002 | FTP Area General Excavation | 01 | 2012-11-28 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | HASCON |  | IFC | AFC | 100%
12172 | I491TC05-0EAAA91-001-002 | Steel Making Plant Battery Limits | 01 | 2011-11-13 | Indeterminate | Drawing | Basic | Melt Shop | Mechanical | TAM |  | IFA | AC |  | 95%
12179 | I491TC05-0EAAA91-002-007 | Meltshop Battery Limit | 05 | 2011-11-13 | Indeterminate | Drawing | Basic | Melt Shop | Mechanical | TAM |  | IFA | AC |  | 95%
12180 | I491TC05-0EAAA91-003-003 | Steel Making Plant Finishing Floor Level | 02 | 2012-05-12 | Indeterminate | Miscellaneous(MISC) | Basic | General | Mechanical | TAM |  | IFC | AFC | 100%
113425 | I491TC05-0LAAA91-001-001 | Laboratory Battery Limit | 00 | 2015-02-23 | Indeterminate | Drawing | Detail | Laboratory | Mechanical | TAM | 2015-02-24 14:50 | IFA | AC |  | 95%
12184 | I491TC05-0MEAA91-001-002 | Main Electrical Sub Station Topogeraphy | 00 | 2011-08-16 | Indeterminate | Drawing | Basic | Main Electrical Substation And Distribution Network | Mechanical | PARSIAN |  | IFC | AFC | 100%
16563 | I491TC05-0MXAA01-001-002 | Billet Storage Area General Layout(Option2) | 00 | 2011-04-24 | Indeterminate | Drawing | Basic | Melt Shop | Mechanical | TAM |  | IFA | AFC | 100%
16562 | I491TC05-0MXAA01-001-003 | Billet Storage Area General Layout(Option3) | 00 | 2011-04-24 | Indeterminate | Drawing | Basic | Melt Shop | Mechanical | TAM |  | IFA | AFC | 100%
16564 | I491TC05-0MXAA01-001-004 | Billet Storage Area General Layout(Option1) | 00 | 2011-04-24 | Indeterminate | Drawing | Basic | Melt Shop | Mechanical | TAM |  | IFA | AFC | 100%
12188 | I491TC05-0MYAA91-002-002 | Workshop Battery Limit | 01 | 2012-04-28 | Indeterminate | Drawing | Basic | Maintenance Workshop | Mechanical | TAM |  | IFC | AFC | 100%
115101 | I491TC05-0SXFD91-001-001 | EAF SHELL RELINING STATION EXVACATION | 01 | 2016-03-16 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Civil and Steel Structure | TAM | 2016-04-02 16:46 | IFC | AFC | 100%
12190 | I491TC05-0TBAA91-001-001 | Warehouses Battery Limit | 02 | 2012-04-28 | Indeterminate | Miscellaneous(MISC) | Basic | Warehouse | Mechanical | TAM |  | IFC | AFC | 100%
12192 | I491TC05-0TBAA91-002-002 | Warehouses Battery Limit | 01 | 2011-11-02 | Indeterminate | Drawing | Basic | Warehouse | Mechanical | TAM |  | IFA | AC |  | 95%
12194 | I491TC05-0TBAA91-003-002 | Ferroalloy Storage General Excavation Plan | 01 | 2012-02-20 | Indeterminate | Drawing | Basic | Melt Shop Lime And Ferroalloy Storage | Mechanical | TAM |  | IFC | AFC | 100%
112369 | I491TC06-0ASAM91-003-001 | ASP-CAP SUBSTATION ARCHITECTURAL Phase I FIRST FLOOR PLAN | 01 | 2014-06-08 | Indeterminate | Drawing | Basic | Air Separation Plant Main Building | Civil and Steel Structure | TAM | 2014-06-09 16:51 | IFC | AFC | 100%
112370 | I491TC06-0ASAM91-003-002 | ASP-CAP SUBSTATION ARCHITECTURAL Phase I ROOF PLAN | 01 | 2014-06-08 | Indeterminate | Drawing | Basic | Air Separation Plant Main Building | Civil and Steel Structure | TAM | 2014-06-09 16:51 | IFC | AFC | 100%
112371 | I491TC06-0ASAM91-003-003 | ASP-CAP SUBSTATION ARCHITECTURAL Phase I SECTIONS | 01 | 2014-06-08 | Indeterminate | Drawing | Basic | Air Separation Plant Main Building | Civil and Steel Structure | TAM | 2014-06-09 16:51 | IFC | AFC | 100%
112372 | I491TC06-0ASAM91-003-004 | ASP-CAP SUBSTATION ARCHITECTURAL Phase I SECTIONS | 01 | 2014-06-08 | Indeterminate | Drawing | Basic | Air Separation Plant Main Building | Civil and Steel Structure | TAM | 2014-06-09 16:51 | IFC | AFC | 100%
112373 | I491TC06-0ASAM91-003-005 | ASP-CAP SUBSTATION ARCHITECTURAL Phase I ELEVATION | 01 | 2014-06-08 | Indeterminate | Drawing | Basic | Air Separation Plant Main Building | Civil and Steel Structure | TAM | 2014-06-09 16:51 | IFC | AFC | 100%
134124 | I491TC06-0ASAM91-003-006 | Layout And Sections for Main Workshop Room of Air Separation Plant | 02 | 2017-02-27 | Indeterminate | Drawing | Basic | Air Separation Plant Electrical substation Building | Civil and Steel Structure | TAM | 2018-09-09 11:03 | IFC | AFC | 100%
12197 | I491TC06-0CCAM91-001-001 | Ccm Tract 3 Electric And Hydraulic Room Architectural - Key Plan & List Of Drawing 1/2 | 00 | 2013-05-28 | Indeterminate | Drawing | Basic | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFA | A | 100%
12198 | I491TC06-0CCAM91-001-002 | Ccm Tract 3 Ccm Tract 3 Electric And Hydraulic Room Architectural 2/2 | 00 | 2013-05-28 | Indeterminate | Drawing | Basic | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFA | A | 100%
12199 | I491TC06-0CCAM91-002-001 | Ccm Tract 3 Cooling Water & Scale Pit Pump Room Architectural - Key Plan & List Of Drawing 1/2 | 00 | 2013-05-28 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFA | A | 100%
12200 | I491TC06-0CCAM91-002-002 | Ccm Tract 3 Cooling Water & Scale Pit Pump Room Architectural 2/2 | 00 | 2013-05-28 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFA | A | 100%
112379 | I491TC06-0DTAM91-001-001 | FTP-MHS SUBSTATION ARCHITECTURAL PHASE1GROUND FLOOR PLAN | 01 | 2014-06-09 17:29 | Indeterminate | Drawing | Basic | Fume Treatment Plant Electrical Substation Building | Civil and Steel Structure | TAM | 2014-06-09 17:29 | IFC | AFC | 100%
112380 | I491TC06-0DTAM91-001-002 | FTP-MHS SUBSTATION ARCHITECTURAL PHASE1 FIRST FLOOR PLAN | 01 | 2014-06-09 17:29 | Indeterminate | Drawing | Basic | Fume Treatment Plant Electrical Substation Building | Civil and Steel Structure | TAM | 2014-06-09 17:29 | IFC | AFC | 100%
112381 | I491TC06-0DTAM91-001-003 | FTP-MHS SUBSTATION ARCHITECTURAL PHASE1 ROOF PLAN | 01 | 2014-06-09 17:29 | Indeterminate | Drawing | Basic | Fume Treatment Plant Electrical Substation Building | Civil and Steel Structure | TAM | 2014-06-09 17:29 | IFC | AFC | 100%
112382 | I491TC06-0DTAM91-001-004 | FTP-MHS SUBSTATION ARCHITECTURAL PHASE1 SECTIONS | 01 | 2014-06-09 17:29 | Indeterminate | Drawing | Basic | Fume Treatment Plant Electrical Substation Building | Civil and Steel Structure | TAM | 2014-06-09 17:29 | IFC | AC |  | 95%
112383 | I491TC06-0DTAM91-001-005 | FTP-MHS SUBSTATION ARCHITECTURAL PHASE1 ELEVATION | 01 | 2014-06-09 17:29 | Indeterminate | Drawing | Basic | Fume Treatment Plant Electrical Substation Building | Civil and Steel Structure | TAM | 2014-06-09 17:29 | IFC | AFC | 100%
12203 | I491TC06-0EAAA91-001-011 | Melt Shop Main Building Melt Typical Elevation | 02 | 2013-03-04 | Indeterminate | Drawing | Basic | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12204 | I491TC06-0EAAA91-001-012 | Melt Shop Main Building Melt Typical Elevation | 02 | 2013-03-04 | Indeterminate | Drawing | Basic | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12205 | I491TC06-0EAAA91-001-013 | Melt Shop Main Building Melt Typical Elevation | 02 | 2013-03-04 | Indeterminate | Drawing | Basic | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12206 | I491TC06-0EAAA91-001-014 | Melt Shop Main Building Melt Typical Elevation | 02 | 2013-03-04 | Indeterminate | Drawing | Basic | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12207 | I491TC06-0EAAA91-001-015 | Melt Shop Main Building Melt Typical Elevation | 02 | 2013-03-04 | Indeterminate | Drawing | Basic | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
133414 | I491TC06-0EAAA91-002-001 | SITE CIVIL DRAWING NON INDUSTRIAL BUILDINGS OUTDOOR LAVATORY | 00 | 2018-07-02 | Indeterminate | Drawing | Detail | Melt Shop | Civil and Steel Structure | TAM | 2018-07-08 16:42 | IFA | A | 100%
12222 | I491TC06-0EAFB91-001-006 | Melt Shop Main Bulding Basic Drawing Eaf Service Plat Form Column Layout Plan At El +3.900 & +5.100 | 05 | 2013-09-01 | Indeterminate | Drawing | Basic | Electric Arc Furnace | Civil and Steel Structure | TAM |  | IFC | AFC | 100%
12223 | I491TC06-0EAFB91-001-007 | Melt Shop Main Bulding Basic Drawin G Eaf Service Plat Form Column Layout Plan At El +8.50 | 05 | 2013-09-01 | Indeterminate | Drawing | Basic | Electric Arc Furnace | Civil and Steel Structure | TAM |  | IFC | AFC | 100%
12224 | I491TC06-0EAFB91-001-008 | Melt Shop Main Bulding Basic Drawing Eaf Service Plat Form Column Layout Plan At El +21.200,+21.00,+18.60,+19.50 | 05 | 2013-09-01 | Indeterminate | Drawing | Basic | Electric Arc Furnace | Civil and Steel Structure | TAM |  | IFC | AFC | 100%
12225 | I491TC06-0EAFB91-001-009 | Melt Shop Main Bulding Basic Drawing Eaf Service Plat Form Column Layout Plan At El +21.500 & Sections | 05 | 2013-09-01 | Indeterminate | Drawing | Basic | Electric Arc Furnace | Civil and Steel Structure | TAM |  | IFC | AFC | 100%
12217 | I491TC06-0EAFB91-001-010 | Melt Shop Main Bulding Basic Drawing Eaf Service Plat Form Details | 05 | 2013-09-01 | Indeterminate | Miscellaneous(MISC) | Detail | Electric Arc Furnace | Civil and Steel Structure | TAM |  | IFC | AFC | 100%
12226 | I491TC06-0GCAA91-001-001 | Mobilization Office Plan | 00 | 2011-02-06 | Indeterminate | Drawing | Basic | General | Mechanical | TAM |  | IFI | AFC | 100%
12227 | I491TC06-0GCAA91-001-002 | Mobilization Office Typical Sections And Veiw | 00 | 2011-02-06 | Indeterminate | Drawing | Basic | General | Mechanical | TAM |  | IFI | AFC | 100%
132566 | I491TC06-0LAAM91-001-001 | BASIC DESIGN OF ARCHITECTURAL DRAWING MELT SHOP MAIN BUILDING LF & CCM LABORATORY LAYOUT LIST OF DRAWINGS | 01 | 2017-12-18 | Indeterminate | Drawing | Detail | Laboratory | Civil and Steel Structure | APEC | 2017-12-20 09:15 | IFC | AFC | 100%
132567 | I491TC06-0LAAM91-002-001 | BASIC DESIGN OF ARCHITECTURAL DRAWING MELT SHOP MAIN BUILDING LF & CCM LABORATORY LAYOUT SITE PLAN | 01 | 2017-12-18 | Indeterminate | Drawing | Detail | Laboratory | Civil and Steel Structure | APEC | 2017-12-20 09:16 | IFC | AFC | 100%
132568 | I491TC06-0LAAM91-003-001 | BASIC DESIGN OF ARCHITECTURAL DRAWING MELT SHOP MAIN BUILDING LF & CCM LABORATORY LAYOUT PLAN AT LEVEL +0.200 | 01 | 2017-12-18 | Indeterminate | Drawing | Detail | Laboratory | Civil and Steel Structure | APEC | 2017-12-20 09:16 | IFC | AFC | 100%
132569 | I491TC06-0LAAM91-004-001 | BASIC DESIGN OF ARCHITECTURAL DRAWING MELT SHOP MAIN BUILDING LF & CCM LABORATORY LAYOUT PLAN AT LEVEL +4.600 | 01 | 2017-12-18 | Indeterminate | Drawing | Detail | Laboratory | Civil and Steel Structure | APEC | 2017-12-20 09:16 | IFC | AFC | 100%
132570 | I491TC06-0LAAM91-005-001 | BASIC DESIGN OF ARCHITECTURAL DRAWING MELT SHOP MAIN BUILDING LF & CCM LABORATORY LAYOUT VIEW 1 | 01 | 2017-12-18 | Indeterminate | Drawing | Detail | Laboratory | Civil and Steel Structure | APEC | 2017-12-20 09:16 | IFC | AFC | 100%
132571 | I491TC06-0LAAM91-006-001 | BASIC DESIGN OF ARCHITECTURAL DRAWING MELT SHOP MAIN BUILDING LF & CCM LABORATORY LAYOUT VIEW 2 & ROOF PLAN | 01 | 2017-12-18 | Indeterminate | Drawing | Detail | Laboratory | Civil and Steel Structure | APEC | 2017-12-20 09:17 | IFC | AFC | 100%
132572 | I491TC06-0LAAM91-007-001 | BASIC DESIGN OF ARCHITECTURAL DRAWING MELT SHOP MAIN BUILDING LF & CCM LABORATORY LAYOUT Section A-A , B-B | 01 | 2017-12-18 | Indeterminate | Drawing | Detail | Laboratory | Civil and Steel Structure | APEC | 2017-12-20 09:17 | IFC | AFC | 100%
12228 | I491TC06-0LFAA91-001-001 | Transformer Building Civil Works Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Basic | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFI | OB | 100%
12229 | I491TC06-0LFAA91-002-001 | Transformer Building Civil Works Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Basic | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFI | OB | 100%
12231 | I491TC06-0MEAM01-101-003 | 400/33 Kv Substation Architectural Drawing Of Control Bulding | 02 | 2012-07-29 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
12238 | I491TC06-0MEAM91-001-013 | Smp Substation Building Plan First Plan | 02 | 2012-10-22 | Indeterminate | Drawing | Basic | Steel Making Electrical Substation Building | Civil and Steel Structure | IKS |  | IFC | AFC | 100%
12239 | I491TC06-0MEAM91-001-014 | Smp Substation Building Plan Ground Floor Plan | 02 | 2012-10-22 | Indeterminate | Drawing | Basic | Steel Making Electrical Substation Building | Civil and Steel Structure | IKS |  | IFC | AFC | 100%
12240 | I491TC06-0MEAM91-001-015 | Smp Substation Building Plan Roof Plan | 02 | 2012-10-22 | Indeterminate | Drawing | Basic | Steel Making Electrical Substation Building | Civil and Steel Structure | IKS |  | IFC | AFC | 100%
12241 | I491TC06-0MEAM91-001-016 | Smp Substation Building Plan Plan & Section 1 | 02 | 2012-10-22 | Indeterminate | Drawing | Basic | Steel Making Electrical Substation Building | Civil and Steel Structure | IKS |  | IFC | AFC | 100%
12242 | I491TC06-0MEAM91-001-017 | Smp Substation Building Plan Plan & Section 2 | 02 | 2012-10-22 | Indeterminate | Drawing | Basic | Steel Making Electrical Substation Building | Civil and Steel Structure | IKS |  | IFC | AFC | 100%
12243 | I491TC06-0MEAM91-001-018 | Smp Substation Building Plan Elevationes | 02 | 2012-10-22 | Indeterminate | Drawing | Basic | Steel Making Electrical Substation Building | Civil and Steel Structure | IKS |  | IFC | AFC | 100%
114875 | I491TC06-0MEIR91-001-001 | SVC System Control Building Architectural Drawing | 01 | 2016-02-02 | Indeterminate | Drawing | Detail | Main Electrical substation Building | Civil and Steel Structure | NR Electric | 2016-02-03 12:40 | IFI | OB | 100%
114876 | I491TC06-0MEIR91-002-001 | SVC System Control Building Detail Drawing | 01 | 2016-02-02 | Indeterminate | Drawing | Detail | Main Electrical substation Building | Civil and Steel Structure | NR Electric | 2016-02-03 12:40 | IFI | OB | 100%
112402 | I491TC06-0MMAM91-001-001 | WTP SUBSTATION ARCHITECTURAL GROUND FLOOR PLAN | 01 | 2014-06-12 11:03 | Indeterminate | Drawing | Basic | Water Treatment & Cooling System Substation Building | Civil and Steel Structure | TAM | 2014-06-12 11:03 | IFC | AFC | 100%
112401 | I491TC06-0MMAM91-001-002 | WTP SUBSTATION ARCHITECTURAL FIRST FLOOR PLAN | 01 | 2014-06-12 11:03 | Indeterminate | Drawing | Basic | Water Treatment & Cooling System Substation Building | Civil and Steel Structure | TAM | 2014-06-12 11:03 | IFC | AFC | 100%
112400 | I491TC06-0MMAM91-001-003 | WTP SUBSTATION ARCHITECTURAL ROOF PLAN | 01 | 2014-06-12 11:03 | Indeterminate | Drawing | Basic | Water Treatment & Cooling System Substation Building | Civil and Steel Structure | TAM | 2014-06-12 11:03 | IFC | AFC | 100%
112399 | I491TC06-0MMAM91-001-004 | WTP SUBSTATION ARCHITECTURAL SECTIONS | 01 | 2014-06-12 11:03 | Indeterminate | Drawing | Basic | Water Treatment & Cooling System Substation Building | Civil and Steel Structure | TAM | 2014-06-12 11:03 | IFC | AC |  | 95%
112398 | I491TC06-0MMAM91-001-005 | WTP SUBSTATION ARCHITECTURAL SECTIONS & ELEVATION | 01 | 2014-06-12 11:03 | Indeterminate | Drawing | Basic | Water Treatment & Cooling System Substation Building | Civil and Steel Structure | TAM | 2014-06-12 11:03 | IFC | AFC | 100%
12281 | I491TC06-0MMCF91-001-009 | Architectural Basic Drawing Api Sedimentation System (1-8) | 03 | 2013-08-21 | Indeterminate | Drawing | Basic | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD |  | IFC | AFC | 100%
12267 | I491TC06-0MMCF91-001-010 | Architectural Basic Drawing Api Sedimentation System (2-8) | 03 | 2013-08-21 | Indeterminate | Drawing | Basic | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD |  | IFC | AFC | 100%
12268 | I491TC06-0MMCF91-001-011 | Architectural Basic Drawing Api Sedimentation System (3-8) | 03 | 2013-08-21 | Indeterminate | Drawing | Basic | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD |  | IFC | AFC | 100%
12269 | I491TC06-0MMCF91-001-012 | Architectural Basic Drawing Api Sedimentation System (4-8) | 03 | 2013-08-21 | Indeterminate | Drawing | Basic | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD |  | IFC | AFC | 100%
12270 | I491TC06-0MMCF91-001-013 | Architectural Basic Drawing Api Sedimentation System (5-8) | 03 | 2013-08-21 | Indeterminate | Drawing | Basic | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD |  | IFC | AFC | 100%
12271 | I491TC06-0MMCF91-001-014 | Architectural Basic Drawing Api Sedimentation System (6-8) | 03 | 2013-08-21 | Indeterminate | Drawing | Basic | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD |  | IFC | AFC | 100%
12272 | I491TC06-0MMCF91-001-015 | Architectural Basic Drawing Api Sedimentation System (7-8) | 03 | 2013-08-21 | Indeterminate | Drawing | Basic | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD |  | IFC | AFC | 100%
12273 | I491TC06-0MMCF91-001-016 | Architectural Basic Drawing Api Sedimentation System (8-8) | 03 | 2013-08-21 | Indeterminate | Drawing | Basic | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD |  | IFC | AFC | 100%
12284 | I491TC06-0MVAA91-001-003 | Civil Drawings Storm Drainage System | 02 | 2013-05-14 | Indeterminate | Drawing | Basic | General | Civil and Steel Structure | TAM |  | IFC | AC |  | 95%
12285 | I491TC06-0MVAA91-001-004 | Civil Drawings Storm Drainage System Part 1 | 02 | 2013-05-14 | Indeterminate | Drawing | Basic | General | Civil and Steel Structure | TAM |  | IFC | AC |  | 95%
12286 | I491TC06-0MVAA91-001-005 | Civil Drawings Storm Drainage System Part 2 | 02 | 2013-05-14 | Indeterminate | Drawing | Basic | General | Civil and Steel Structure | TAM |  | IFC | AC |  | 95%
12287 | I491TC06-0MVAA91-001-006 | Civil Drawings Storm Drainage System Part 3 | 02 | 2013-05-14 | Indeterminate | Drawing | Basic | General | Civil and Steel Structure | TAM |  | IFC | AC |  | 95%
12288 | I491TC06-0MVAA91-001-007 | Civil Drawings Storm Drainage System Part 4 | 02 | 2013-05-14 | Indeterminate | Drawing | Basic | General | Civil and Steel Structure | TAM |  | IFC | AC |  | 95%
12289 | I491TC06-0MVAA91-001-008 | Civil Drawings Storm Drainage System Part 5 | 02 | 2013-05-14 | Indeterminate | Drawing | Basic | General | Civil and Steel Structure | TAM |  | IFC | AC |  | 95%
12290 | I491TC06-0MVAA91-002-001 | Streets Channel Longitudinal Profiles St. 22-1 St. 20-1 | 00 | 2012-05-08 | Indeterminate | Drawing | Basic | General | Civil and Steel Structure | TAM |  | IFA | AC |  | 95%
12299 | I491TC06-0MVAA91-002-002 | Streets Channel Longitudinal Profiles St. 18-1 /10--1/18-2 | 00 | 2012-05-08 | Indeterminate | Drawing | Basic | General | Civil and Steel Structure | TAM |  | IFA | AC |  | 95%
12300 | I491TC06-0MVAA91-002-003 | Streets Channel Longitudinal Profiles St. 18-3 | 00 | 2012-05-08 | Indeterminate | Drawing | Basic | General | Civil and Steel Structure | TAM |  | IFA | AC |  | 95%
12301 | I491TC06-0MVAA91-002-004 | Streets Channel Longitudinal Profiles St. 18-4 St. 18--5 | 00 | 2012-05-08 | Indeterminate | Drawing | Basic | General | Civil and Steel Structure | TAM |  | IFA | AC |  | 95%
12302 | I491TC06-0MVAA91-002-005 | Streets Channel Longitudinal Profiles St. 18-6 | 00 | 2012-05-08 | Indeterminate | Drawing | Basic | General | Civil and Steel Structure | TAM |  | IFA | AC |  | 95%
12303 | I491TC06-0MVAA91-002-006 | Streets Channel Longitudinal Profiles St. 18-6(Cont.)St. 12-1 | 00 | 2012-05-08 | Indeterminate | Drawing | Basic | General | Civil and Steel Structure | TAM |  | IFA | AC |  | 95%
12304 | I491TC06-0MVAA91-002-007 | Streets Channel Longitudinal Profiles St. 10-1 | 00 | 2012-05-08 | Indeterminate | Drawing | Basic | General | Civil and Steel Structure | TAM |  | IFA | AC |  | 95%
12305 | I491TC06-0MVAA91-002-008 | Streets Channel Longitudinal Profiles St. 10-2 | 00 | 2012-05-08 | Indeterminate | Drawing | Basic | General | Civil and Steel Structure | TAM |  | IFA | AC |  | 95%
12306 | I491TC06-0MVAA91-002-009 | Streets Channel Longitudinal Profiles 22-1 20-1 | 02 | 2013-05-14 | Indeterminate | Drawing | Basic | General | Civil and Steel Structure | TAM |  | IFC | AC |  | 95%
12291 | I491TC06-0MVAA91-002-010 | Streets Channel Longitudinal Profiles 18-1 10-3 18-2 | 02 | 2013-05-14 | Indeterminate | Drawing | Basic | General | Civil and Steel Structure | TAM |  | IFC | AC |  | 95%
12292 | I491TC06-0MVAA91-002-011 | Streets Channel Longitudinal Profiles 18-3 | 02 | 2013-05-14 | Indeterminate | Drawing | Basic | General | Civil and Steel Structure | TAM |  | IFC | AC |  | 95%
12293 | I491TC06-0MVAA91-002-012 | Streets Channel Longitudinal Profiles St 18-4 18-5 | 02 | 2013-05-14 | Indeterminate | Drawing | Basic | General | Civil and Steel Structure | TAM |  | IFC | AC |  | 95%
12294 | I491TC06-0MVAA91-002-013 | Streets Channel Longitudinal Profiles St. 18-6 | 02 | 2013-05-14 | Indeterminate | Drawing | Basic | General | Civil and Steel Structure | TAM |  | IFC | AC |  | 95%
12295 | I491TC06-0MVAA91-002-014 | Streets Channel Longitudinal Profiles 18-6(Cont.) St-12-1 | 02 | 2013-05-14 | Indeterminate | Drawing | Basic | General | Civil and Steel Structure | TAM |  | IFC | AC |  | 95%
12296 | I491TC06-0MVAA91-002-015 | Streets Channel Longitudinal Profiles St 10-1 | 02 | 2013-05-14 | Indeterminate | Drawing | Basic | General | Civil and Steel Structure | TAM |  | IFC | AC |  | 95%
12297 | I491TC06-0MVAA91-002-016 | Streets Channel Longitudinal Profiles 10-2 | 02 | 2013-05-14 | Indeterminate | Drawing | Basic | General | Civil and Steel Structure | TAM |  | IFC | AC |  | 95%
12298 | I491TC06-0MVAA91-002-017 | Streets Channel Longitudinal Profiles 10-4 | 02 | 2013-05-14 | Indeterminate | Drawing | Basic | General | Civil and Steel Structure | TAM |  | IFC | AC |  | 95%
129722 | I491TC06-0MVAA91-003-003 | CIVIL DRAWING STREET, DRAINAGE AND FINISHED ELEVATION PLAN SECTION AND DETAILS | 06 | 2016-10-18 | Indeterminate | Drawing | Detail | General | Civil and Steel Structure | TAM | 2016-10-19 13:20 | IFC | AFC | 100%
12310 | I491TC06-0MVAA91-003-004 | CIVIL DRAWING STREET, DRAINAGE AND FINISHED ELEVATION PLAN SECTION AND DETAILS 17-17 | 02 | 2013-05-14 | Indeterminate | Drawing | Detail | General | Civil and Steel Structure | TAM |  | IFC | AC |  | 95%
134177 | I491TC06-0MYAA91-001-001 | WORKSHOP TYPICAL ELEVATION FLOOR PLAN 1-3 | 01 | 2018-09-17 | Indeterminate | Drawing | Basic | Maintenance Workshop | Civil and Steel Structure | IKS | 2018-09-22 09:49 | IFC | AFC | 100%
134178 | I491TC06-0MYAA91-001-002 | WORKSHOP TYPICAL ELEVATION ROOF PLAN 2-3 | 01 | 2018-09-17 | Indeterminate | Drawing | Basic | Maintenance Workshop | Civil and Steel Structure | IKS | 2018-09-22 09:49 | IFC | AFC | 100%
134179 | I491TC06-0MYAA91-001-003 | WORKSHOP TYPICAL ELEVATION TYPICAL ELEVATION 3-3 | 01 | 2018-09-17 | Indeterminate | Drawing | Basic | Maintenance Workshop | Civil and Steel Structure | IKS | 2018-09-22 09:49 | IFC | AFC | 100%
12324 | I491TC06-0MYAA91-002-019 | Workshop Architecture Drawing Plan & Layout "A" | 03 | 2013-07-20 | Indeterminate | Drawing | Detail | Melt Shop Maintenance Workshop | Civil and Steel Structure | IKS |  | IFC | AFC | 100%
12326 | I491TC06-0MYAA91-002-020 | Workshop Architecture Drawing Roof Plan & Site Plan | 03 | 2013-07-20 | Indeterminate | Miscellaneous(MISC) | Basic | Melt Shop Maintenance Workshop | Civil and Steel Structure | IKS |  | IFC | AFC | 100%
12327 | I491TC06-0MYAA91-002-021 | Workshop Architecture Drawing Section "A-A" | 03 | 2013-07-20 | Indeterminate | Miscellaneous(MISC) | Basic | Melt Shop Maintenance Workshop | Civil and Steel Structure | IKS |  | IFC | AFC | 100%
12328 | I491TC06-0MYAA91-002-022 | Workshop Architecture Drawing Section "B-B" | 03 | 2013-07-20 | Indeterminate | Miscellaneous(MISC) | Basic | Melt Shop Maintenance Workshop | Civil and Steel Structure | IKS |  | IFC | AFC | 100%
12329 | I491TC06-0MYAA91-002-023 | Workshop Architecture Drawing Elevations | 03 | 2013-07-20 | Indeterminate | Miscellaneous(MISC) | Basic | Melt Shop Maintenance Workshop | Civil and Steel Structure | IKS |  | IFC | AFC | 100%
12330 | I491TC06-0MYAA91-002-024 | Workshop Architecture Drawing Windows & Door | 03 | 2013-07-20 | Indeterminate | Miscellaneous(MISC) | Basic | Melt Shop Maintenance Workshop | Civil and Steel Structure | IKS |  | IFC | AFC | 100%
12339 | I491TC06-0MYAA91-003-002 | Workshop Waste Water Drainage System Roof Plan&Details | 01 | 2012-07-02 | Indeterminate | Drawing | Detail | Maintenance Workshop | Civil and Steel Structure | IKS |  | IFC | AFC | 100%
111576 | I491TC06-0OFAM91-001-001 | NON INDUSTRIAL BUILDINGS (ADMIN - CANTEEN - SHOWER & LOCKER) GROUND FLOOR DIMENSION PLAN | 02 | 2014-02-09 | Indeterminate | Drawing | Basic | Office - Canteen - Locker & Shower For Melt Shop | Civil and Steel Structure | Azhand Shahr | 2014-04-23 17:27 | IFC | AFC | 100%
111570 | I491TC06-0OFAM91-001-002 | NON INDUSTRIAL BUILDINGS (ADMIN - CANTEEN - SHOWER & LOCKER) FIRST FLOOR DIMENSION PLAN | 02 | 2014-02-09 | Indeterminate | Drawing | Basic | Office - Canteen - Locker & Shower For Melt Shop | Civil and Steel Structure | Azhand Shahr | 2014-04-23 17:22 | IFC | AFC | 100%
111571 | I491TC06-0OFAM91-001-003 | NON INDUSTRIAL BUILDINGS (ADMIN - CANTEEN - SHOWER & LOCKER) ELEVATIONS | 02 | 2014-02-09 | Indeterminate | Drawing | Basic | Office - Canteen - Locker & Shower For Melt Shop | Civil and Steel Structure | Azhand Shahr | 2014-04-23 17:22 | IFC | AFC | 100%
111572 | I491TC06-0OFAM91-001-004 | NON INDUSTRIAL BUILDINGS (ADMIN - CANTEEN - SHOWER & LOCKER) SECTION A-A & B-B | 02 | 2014-02-09 | Indeterminate | Drawing | Basic | Office - Canteen - Locker & Shower For Melt Shop | Civil and Steel Structure | Azhand Shahr | 2014-04-23 17:22 | IFC | AFC | 100%
111573 | I491TC06-0OFAM91-001-005 | NON INDUSTRIAL BUILDINGS (ADMIN - CANTEEN - SHOWER & LOCKER) SITE PLAN | 02 | 2014-02-09 | Indeterminate | Drawing | Basic | Office - Canteen - Locker & Shower For Melt Shop | Civil and Steel Structure | Azhand Shahr | 2014-04-23 17:22 | IFC | AFC | 100%
111574 | I491TC06-0OFAM91-001-006 | NON INDUSTRIAL BUILDINGS (ADMIN - CANTEEN - SHOWER & LOCKER) GROUND FLOOR FURNISHED PLAN | 02 | 2014-02-09 | Indeterminate | Drawing | Basic | Office - Canteen - Locker & Shower For Melt Shop | Civil and Steel Structure | Azhand Shahr | 2014-04-23 17:22 | IFC | AFC | 100%
111575 | I491TC06-0OFAM91-001-007 | NON INDUSTRIAL BUILDINGS (ADMIN - CANTEEN - SHOWER & LOCKER) FIRST FLOOR FURNISHED PLAN | 02 | 2014-02-09 | Indeterminate | Drawing | Basic | Office - Canteen - Locker & Shower For Melt Shop | Civil and Steel Structure | Azhand Shahr | 2014-04-23 17:22 | IFC | AFC | 100%
12348 | I491TC06-0OFAM91-002-001 | Non Industrial Buildings (Admin - Canteen - Shower & Locker) Site Plan (Option 1) | 00 | 2013-09-08 | Indeterminate | Drawing | Basic | Office - Canteen - Locker & Shower For Melt Shop | Civil and Steel Structure | TAM |  | IFA | AC |  | 95%
12349 | I491TC06-0OFAM91-002-002 | Non Industrial Buildings (Admin - Canteen - Shower & Locker) Dimension Plan (Option 1) | 00 | 2013-09-08 | Indeterminate | Drawing | Basic | Office - Canteen - Locker & Shower For Melt Shop | Civil and Steel Structure | TAM |  | IFA | AC |  | 95%
12351 | I491TC06-0OFAM91-003-001 | Non Industrial Buildings (Admin - Canteen - Shower & Locker) Site Plan (Option 2) | 00 | 2013-09-08 | Indeterminate | Drawing | Basic | Office - Canteen - Locker & Shower For Melt Shop | Civil and Steel Structure | TAM |  | IFA | AC |  | 95%
12352 | I491TC06-0OFAM91-003-002 | Non Industrial Buildings (Admin - Canteen - Shower & Locker) Furnished & Dimension Plan (Option 2) | 00 | 2013-09-08 | Indeterminate | Drawing | Basic | Office - Canteen - Locker & Shower For Melt Shop | Civil and Steel Structure | TAM |  | IFA | AC |  | 95%
12353 | I491TC06-0OFAM91-004-001 | Non Industrial Buildings (Admin - Canteen - Shower & Locker) Site Plan (Option 3) | 00 | 2013-09-08 | Indeterminate | Drawing | Basic | Office - Canteen - Locker & Shower For Melt Shop | Civil and Steel Structure | TAM |  | IFA | AC |  | 95%
12354 | I491TC06-0OFAM91-004-002 | Non Industrial Buildings (Admin - Canteen - Shower & Locker) Dimension Plan (Option 3) | 00 | 2013-09-08 | Indeterminate | Drawing | Basic | Office - Canteen - Locker & Shower For Melt Shop | Civil and Steel Structure | TAM |  | IFA | AC |  | 95%
12367 | I491TC06-0SHAA91-001-008 | Scrap Yard Elevations Plan | 01 | 2012-12-15 | Indeterminate | Drawing | Detail | Melt Shop Scrap Yard | Civil and Steel Structure | IKS |  | IFC | AC |  | 95%
12368 | I491TC06-0SHAA91-001-009 | Scrap Yard Elevations South Elevation & West Elevation | 01 | 2012-12-15 | Indeterminate | Drawing | Detail | Melt Shop Scrap Yard | Civil and Steel Structure | IKS |  | IFC | AC |  | 95%
12356 | I491TC06-0SHAA91-001-010 | Scrap Yard Elevations North Elevation & East Elevation | 01 | 2012-12-15 | Indeterminate | Drawing | Detail | Melt Shop Scrap Yard | Civil and Steel Structure | IKS |  | IFC | AC |  | 95%
12357 | I491TC06-0SHAA91-001-011 | Scrap Yard Elevations Section A-A & B-B | 01 | 2012-12-15 | Indeterminate | Drawing | Detail | Melt Shop Scrap Yard | Civil and Steel Structure | IKS |  | IFC | AC |  | 95%
12358 | I491TC06-0SHAA91-001-012 | Scrap Yard Elevations Section C-C | 01 | 2012-12-15 | Indeterminate | Drawing | Detail | Melt Shop Scrap Yard | Civil and Steel Structure | IKS |  | IFC | AC |  | 95%
12359 | I491TC06-0SHAA91-001-013 | Scrap Yard Elevations Roof Plan | 01 | 2012-12-15 | Indeterminate | Drawing | Detail | Melt Shop Scrap Yard | Civil and Steel Structure | IKS |  | IFC | AC |  | 95%
12360 | I491TC06-0SHAA91-001-014 | Scrap Yard Elevations Site Plan | 01 | 2012-12-15 | Indeterminate | Drawing | Detail | Melt Shop Scrap Yard | Civil and Steel Structure | IKS |  | IFC | AC |  | 95%
133917 | I491TC06-0SHAM91-001-001 | Scrap Yard Pulpit Layout | 00 | 2018-08-05 | Indeterminate | Drawing | Detail | Scrap Yard Equipment | Mechanical | TAM | 2018-08-07 10:04 | IFI | OB | 100%
12375 | I491TC06-0TBAA91-001-007 | Warehouse Typical Elevations | 02 | 2011-07-11 | Indeterminate | Drawing | Detail | Warehouse | Civil and Steel Structure | TAM |  | IFC | AFC | 100%
12376 | I491TC06-0TBAA91-001-008 | Warehouse Streets & Plan | 02 | 2011-07-11 | Indeterminate | Drawing | Detail | Warehouse | Civil and Steel Structure | TAM |  | IFC | AFC | 100%
12403 | I491TC06-0TBAA91-003-002 | Warehouse Water Drainage System \ Gutter | 01 | 2012-02-08 | Indeterminate | Drawing | Detail | Warehouse | Civil and Steel Structure | IKS |  | IFC | AFC | 100%
12408 | I491TC06-0TBAA91-004-013 | Ferro Alloy Architecture Plan | 02 | 2013-01-28 | Indeterminate | Drawing | Basic | Melt Shop Lime And Ferroalloy Storage | Civil and Steel Structure | IKS |  | IFC | AFC | 100%
12409 | I491TC06-0TBAA91-004-014 | Ferro Alloy Architecture North Elevation & East Elevation | 02 | 2013-01-28 | Indeterminate | Drawing | Basic | Melt Shop Lime And Ferroalloy Storage | Civil and Steel Structure | IKS |  | IFC | AFC | 100%
12410 | I491TC06-0TBAA91-004-015 | Ferro Alloy Architecture South Elevation & West Elevation | 02 | 2013-01-28 | Indeterminate | Drawing | Basic | Melt Shop Lime And Ferroalloy Storage | Civil and Steel Structure | IKS |  | IFC | AFC | 100%
12411 | I491TC06-0TBAA91-004-016 | Ferro Alloy Architecture Section A & Wallsection | 02 | 2013-01-28 | Indeterminate | Drawing | Basic | Melt Shop Lime And Ferroalloy Storage | Civil and Steel Structure | IKS |  | IFC | AFC | 100%
12412 | I491TC06-0TBAA91-004-017 | Ferro Alloy Architecture Roof Plan | 02 | 2013-01-28 | Indeterminate | Drawing | Basic | Melt Shop Lime And Ferroalloy Storage | Civil and Steel Structure | IKS |  | IFC | AFC | 100%
12413 | I491TC06-0TBAA91-004-018 | Ferro Alloy Architecture Site Plan | 02 | 2013-01-28 | Indeterminate | Drawing | Basic | Melt Shop Lime And Ferroalloy Storage | Civil and Steel Structure | IKS |  | IFC | AFC | 100%
12422 | I491TC06-0TBAM91-001-001 | Control Room Eaf Hall & Foundation | 00 | 2012-07-30 | Indeterminate | Drawing | Basic | Melt Shop Main Building | Mechanical | APEC |  | IFA | AC |  | 95%
12423 | I491TC06-0TBAM91-001-002 | Control Room Eaf Hall & Foundation | 00 | 2012-07-30 | Indeterminate | Drawing | Basic | Melt Shop Main Building | Mechanical | APEC |  | IFA | AC |  | 95%
12424 | I491TC06-0TBAM91-001-003 | Control Room Eaf Hall & Foundation | 00 | 2012-07-30 | Indeterminate | Drawing | Basic | Melt Shop Main Building | Mechanical | APEC |  | IFA | AC |  | 95%
12425 | I491TC06-0TBAM91-001-004 | Control Room Eaf Hall & Foundation | 00 | 2012-07-30 | Indeterminate | Drawing | Basic | Melt Shop Main Building | Mechanical | APEC |  | IFA | AC |  | 95%
12426 | I491TC06-0TBAM91-002-001 | Control Room Lf Hall & Foundation | 00 | 2012-07-30 | Indeterminate | Drawing | Basic | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFA | AC |  | 95%
12436 | I491TC06-0TBAM91-002-002 | Control Room Lf Hall & Foundation | 00 | 2012-07-30 | Indeterminate | Drawing | Basic | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFA | AC |  | 95%
12437 | I491TC06-0TBAM91-002-003 | Control Room Lf Hall & Foundation | 00 | 2012-07-30 | Indeterminate | Drawing | Basic | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFA | AC |  | 95%
12428 | I491TC06-0TBAM91-002-011 | Melt Shop Main Building Lf Building Architectural Basic Drawing Key Plan | 08 | 2013-04-16 | Indeterminate | Drawing | Basic | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12429 | I491TC06-0TBAM91-002-012 | Melt Shop Main Building Lf Building Architectural Basic Drawing Plan At Level -3.20 & Plan At Level ±0.00 | 08 | 2013-04-16 | Indeterminate | Drawing | Basic | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12430 | I491TC06-0TBAM91-002-013 | Melt Shop Main Building Lf Building Architectural Basic Drawing Plan At Level +5.970 | 08 | 2013-04-16 | Indeterminate | Drawing | Basic | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12431 | I491TC06-0TBAM91-002-014 | Melt Shop Main Building Lf Building Architectural Basic Drawing Roof Plan | 08 | 2013-04-16 | Indeterminate | Drawing | Basic | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12432 | I491TC06-0TBAM91-002-015 | Melt Shop Main Building Lf Building Architectural Basic Drawing Section A & 3D Lf | 08 | 2013-04-16 | Indeterminate | Drawing | Basic | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12433 | I491TC06-0TBAM91-002-016 | Melt Shop Main Building Lf Building Architectural Basic Drawing Section B & Veiw C | 08 | 2013-04-16 | Indeterminate | Drawing | Basic | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12434 | I491TC06-0TBAM91-002-017 | Melt Shop Main Building Lf Building Architectural Basic Drawing Veiw A & Veiw B | 08 | 2013-04-16 | Indeterminate | Drawing | Basic | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12435 | I491TC06-0TBAM91-002-018 | Melt Shop Main Building Lf Building Architectural Basic Drawing Veiw D | 08 | 2013-04-16 | Indeterminate | Drawing | Basic | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12475 | I491TC06-0TBAM91-003-038 | Melt Shop Main Building Eaf Building Architectural Basic Drawing Plan&List Of Drawing | 10 | 2013-09-11 | Indeterminate | Drawing | Basic | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12476 | I491TC06-0TBAM91-003-039 | Melt Shop Main Building Eaf Building Architectural Basic Drawing Plan At Level -3.200 | 10 | 2013-09-11 | Indeterminate | Drawing | Basic | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12478 | I491TC06-0TBAM91-003-040 | Melt Shop Main Building Eaf Building Architectural Basic Drawing Plan At Level +4.750 | 10 | 2013-09-11 | Indeterminate | Drawing | Basic | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12479 | I491TC06-0TBAM91-003-041 | Melt Shop Main Building Eaf Building Architectural Basic Drawing Plan At Level +8.500 | 10 | 2013-09-11 | Indeterminate | Drawing | Basic | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12480 | I491TC06-0TBAM91-003-042 | Melt Shop Main Building Eaf Building Architectural Basic Drawing Plan At Level +14.000 | 10 | 2013-09-11 | Indeterminate | Drawing | Basic | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12481 | I491TC06-0TBAM91-003-043 | Melt Shop Main Building Eaf Building Architectural Basic Drawing Roof Plan | 10 | 2013-09-11 | Indeterminate | Drawing | Basic | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12482 | I491TC06-0TBAM91-003-044 | Melt Shop Main Building Eaf Building Architectural Basic Drawing Veiw A | 10 | 2013-09-11 | Indeterminate | Drawing | Basic | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12483 | I491TC06-0TBAM91-003-045 | Melt Shop Main Building Eaf Building Architectural Basic Drawing Veiw B | 10 | 2013-09-11 | Indeterminate | Drawing | Basic | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12484 | I491TC06-0TBAM91-003-046 | Melt Shop Main Building Eaf Building Architectural Basic Drawing Veiw C | 10 | 2013-09-11 | Indeterminate | Drawing | Basic | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12485 | I491TC06-0TBAM91-003-047 | Melt Shop Main Building Lf Building Architectural Basic Drawing Veiw D | 10 | 2013-09-11 | Indeterminate | Drawing | Basic | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12486 | I491TC06-0TBAM91-003-048 | Melt Shop Main Building Eaf Building Architectural Basic Drawing Section A - Section & Details | 10 | 2013-09-11 | Indeterminate | Drawing | Basic | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12487 | I491TC06-0TBAM91-003-049 | Melt Shop Main Building Eaf Building Architectural Basic Drawing Plan At Level ±0.00 | 10 | 2013-09-11 | Indeterminate | Drawing | Basic | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12489 | I491TC06-0TBAM91-003-050 | Melt Shop Main Building Eaf Building Architectural Basic Drawing Section B | 10 | 2013-09-11 | Indeterminate | Drawing | Basic | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12498 | I491TC06-0TBAM91-005-005 | Melt Shop Main Building Architectural Drawing (Basic) Site Plan | 02 | 2013-07-24 | Indeterminate | Miscellaneous(MISC) | Basic | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12499 | I491TC06-0TBAM91-005-006 | Melt Shop Main Building Architectural Drawing (Basic) Plan At ±0.00 ,Plan Of Ligthing &Crane Walk Way | 02 | 2013-07-24 | Indeterminate | Miscellaneous(MISC) | Basic | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12500 | I491TC06-0TBAM91-005-007 | Melt Shop Main Building Architectural Drawing (Basic) View Roof Plan & Section A-A,B-B | 02 | 2013-07-24 | Indeterminate | Miscellaneous(MISC) | Basic | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12501 | I491TC06-0TBAM91-005-008 | Melt Shop Main Building Architectural Drawing (Basic) View A - B - C - D | 02 | 2013-07-24 | Indeterminate | Miscellaneous(MISC) | Basic | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
135464 | I491TC07-0ASAM01-001-001 | PHASE II- ARCHITECTURE (LAVATORY ASP) | 00 | 2019-06-24 | Indeterminate | Drawing | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2019-07-01 09:25 | IFA | AC |  | 95%
129602 | I491TC07-0ASAM91-002-001 | NORTH VIEW COMPRESSOR ROOM ARCHITECTURE AIR SEPARATION PLANT 1-6 | 01 | 2016-09-27 | Indeterminate | Drawing | Detail | Air Separation Plant Main Building | Civil and Steel Structure | TAM | 2016-09-29 09:59 | IFC | AFC | 100%
129603 | I491TC07-0ASAM91-002-002 | SOUTH VIEW COMPRESSOR ROOM ARCHITECTURE AIR SEPARATION PLANT 2-6 | 01 | 2016-09-27 | Indeterminate | Drawing | Detail | Air Separation Plant Main Building | Civil and Steel Structure | TAM | 2016-09-29 09:59 | IFC | AFC | 100%
129604 | I491TC07-0ASAM91-002-003 | EAST AND WEST VIEWS COMPRESSOR ROOM ARCHITECTURE AIR SEPARATION PLANT 3-6 | 01 | 2016-09-27 | Indeterminate | Drawing | Detail | Air Separation Plant Main Building | Civil and Steel Structure | TAM | 2016-09-29 09:59 | IFC | AFC | 100%
129605 | I491TC07-0ASAM91-002-004 | WALL SECTION & DETAILS COMPRESSOR ROOM ARCHITECTURE AIR SEPARATION PLANT 4-6 | 01 | 2016-09-27 | Indeterminate | Drawing | Detail | Air Separation Plant Main Building | Civil and Steel Structure | TAM | 2016-09-29 09:59 | IFC | AFC | 100%
129606 | I491TC07-0ASAM91-002-005 | PLAN COMPRESSOR ROOM ARCHITECTURE AIR SEPARATION PLANT 5-6 | 00 | 2016-09-27 | Indeterminate | Drawing | Detail | Air Separation Plant Main Building | Civil and Steel Structure | TAM | 2016-09-29 09:59 | IFC | AFC | 100%
129607 | I491TC07-0ASAM91-002-006 | ROOF PLAN COMPRESSOR ROOM ARCHITECTURE AIR SEPARATION PLANT 6-6 | 00 | 2016-09-27 | Indeterminate | Drawing | Detail | Air Separation Plant Main Building | Civil and Steel Structure | TAM | 2016-09-29 09:59 | IFC | AFC | 100%
133194 | I491TC07-0ASAM91-003-002 | ASP-CAP SUBSTATION ARCHITECTURAL Phase II FIRST FLOOR PLAN | 03 | 2018-05-28 | Indeterminate | Drawing | Detail | Air Separation Plant Electrical substation Building | Civil and Steel Structure | TAM | 2018-06-02 10:35 | IFC | AFC | 100%
133195 | I491TC07-0ASAM91-003-006 | ASP-CAP SUBSTATION ARCHITECTURAL Phase II ELEVATION | 03 | 2018-05-28 | Indeterminate | Drawing | Detail | Air Separation Plant Electrical substation Building | Civil and Steel Structure | TAM | 2018-06-02 10:35 | IFC | AFC | 100%
116009 | I491TC07-0CCAM91-001-001 | CCM CONTROL CABIN PLAN AT LEVEL -2.95 1-12 | 01 | 2016-07-03 13:05 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | APEC | 2016-07-03 13:05 | IFC | AFC | 100%
116010 | I491TC07-0CCAM91-002-001 | CCM CONTROL CABIN PLAN AT LEVEL +0.05 2-12 | 01 | 2016-07-03 13:05 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | APEC | 2016-07-03 13:05 | IFC | AFC | 100%
116011 | I491TC07-0CCAM91-003-001 | CCM CONTROL CABIN PLAN AT LEVEL +5.15 3-12 | 01 | 2016-07-03 13:05 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | APEC | 2016-07-03 13:05 | IFC | AFC | 100%
116012 | I491TC07-0CCAM91-004-001 | CCM CONTROL CABIN PLAN AT LEVEL +9.87 4-12 | 01 | 2016-07-03 13:05 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | APEC | 2016-07-03 13:05 | IFC | AFC | 100%
116013 | I491TC07-0CCAM91-005-001 | CCM CONTROL CABIN FALSE CEILING PLAN +12.55 5-12 | 01 | 2016-07-03 13:05 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | APEC | 2016-07-03 13:05 | IFC | AFC | 100%
116014 | I491TC07-0CCAM91-006-001 | CCM CONTROL CABIN ROOF PLAN 6-12 | 01 | 2016-07-03 13:05 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | APEC | 2016-07-03 13:05 | IFC | AFC | 100%
129785 | I491TC07-0CCAM91-007-001 | CCM CONTROL CABIN VIEW A 7-12 | 02 | 2016-11-09 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | APEC | 2016-11-12 09:15 | IFC | AFC | 100%
129786 | I491TC07-0CCAM91-008-001 | CCM CONTROL CABIN VIEW B 8-12 | 02 | 2016-11-09 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | APEC | 2016-11-12 09:15 | IFC | AFC | 100%
129787 | I491TC07-0CCAM91-009-001 | CCM CONTROL CABIN VIEW C 9-12 | 02 | 2016-11-09 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | APEC | 2016-11-12 09:15 | IFC | AFC | 100%
129788 | I491TC07-0CCAM91-010-001 | CCM CONTROL CABIN SECTION A- A 10-12 | 02 | 2016-11-09 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | APEC | 2016-11-12 09:15 | IFC | AFC | 100%
129789 | I491TC07-0CCAM91-011-001 | CCM CONTROL CABIN SECTION B-B 11-12 | 02 | 2016-11-09 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | APEC | 2016-11-12 09:15 | IFC | AFC | 100%
118072 | I491TC07-0CCAM91-012-001 | CCM CONTROL CABIN SCHEDULES | 02 | 2016-08-01 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | APEC | 2016-08-04 09:33 | IFC | AFC | 100%
131188 | I491TC07-0CCAM91-013-001 | CCM Control Cabin Architectural Details (51 Sheet) | 02 | 2017-09-18 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | SANO | 2017-09-19 09:31 | IFC | AFC | 100%
130018 | I491TC07-0CCAM91-014-001 | CCM LADLE TURRET PLAN AT LEVEL -2.70 | 02 | 2016-12-26 08:54 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | SANO | 2016-12-26 08:54 | IFC | AFC | 100%
130019 | I491TC07-0CCAM91-015-001 | CCM LADLE TURRET PLAN AT LEVEL +0.05 | 02 | 2016-12-26 08:54 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | SANO | 2016-12-26 08:54 | IFC | AFC | 100%
130020 | I491TC07-0CCAM91-016-001 | CCM LADLE TURRET PLAN AT LEVEL +4.90 | 02 | 2016-12-26 08:54 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | SANO | 2016-12-26 08:54 | IFC | AFC | 100%
130021 | I491TC07-0CCAM91-017-001 | CCM LADLE TURRET PLAN AT LEVEL +9.82 | 02 | 2016-12-26 08:54 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | SANO | 2016-12-26 08:54 | IFC | AFC | 100%
118078 | I491TC07-0CCAM91-018-001 | CCM LADLE TURRET VIEW A | 01 | 2016-08-01 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | SANO | 2016-08-04 09:35 | IFC | AFC | 100%
118079 | I491TC07-0CCAM91-019-001 | CCM LADLE TURRET VIEW B | 01 | 2016-08-01 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | SANO | 2016-08-04 09:35 | IFC | AFC | 100%
118080 | I491TC07-0CCAM91-020-001 | CCM LADLE TURRET VIEW C | 01 | 2016-08-01 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | SANO | 2016-08-04 09:35 | IFC | AFC | 100%
118081 | I491TC07-0CCAM91-021-001 | CCM LADLE TURRET VIEW D | 01 | 2016-08-01 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | SANO | 2016-08-04 09:35 | IFC | AFC | 100%
118082 | I491TC07-0CCAM91-022-001 | CCM LADLE TURRET SECTION A-A | 01 | 2016-08-01 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | SANO | 2016-08-04 09:35 | IFC | AFC | 100%
118083 | I491TC07-0CCAM91-023-001 | CCM LADLE TURRET SECTION B-B & SCHEDULES | 01 | 2016-08-01 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | SANO | 2016-08-04 09:35 | IFC | AFC | 100%
118084 | I491TC07-0CCAM91-024-001 | CCM RUN OUT CABIN PLAN AT LEVEL +0.20 | 01 | 2016-08-01 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | SANO | 2016-08-04 09:35 | IFC | AFC | 100%
118085 | I491TC07-0CCAM91-025-001 | CCM RUN OUT CABIN PLAN AT LEVEL +4.50 | 01 | 2016-08-01 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | SANO | 2016-08-04 09:35 | IFC | AFC | 100%
118086 | I491TC07-0CCAM91-026-001 | CCM RUN OUT CABIN ROOF PLAN AT LEVEL +8.50 | 01 | 2016-08-01 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | SANO | 2016-08-04 09:35 | IFC | AFC | 100%
118087 | I491TC07-0CCAM91-027-001 | CCM RUN OUT CABIN VIEW A - VIEW B | 01 | 2016-08-01 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | SANO | 2016-08-04 09:35 | IFC | AFC | 100%
118088 | I491TC07-0CCAM91-028-001 | CCM RUN OUT CABIN PLAN AT LEVEL +0.20 | 01 | 2016-08-01 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | SANO | 2016-08-04 09:35 | IFC | AFC | 100%
118089 | I491TC07-0CCAM91-029-001 | CCM RUN OUT CABIN SECTIONS | 01 | 2016-08-01 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | SANO | 2016-08-04 09:35 | IFC | AFC | 100%
133451 | I491TC07-0CCAM91-030-001 | CCM FNC MAINTENANCE ROOM PLANS | 03 | 2018-07-09 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | SANO | 2018-07-10 09:38 | IFC | AFC | 100%
133452 | I491TC07-0CCAM91-031-001 | CCM FNC MAINTENANCE ROOM VIEWS & SECTIONS & SCHEDULES | 03 | 2018-07-09 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | SANO | 2018-07-10 09:39 | IFC | AFC | 100%
129266 | I491TC07-0CCSB91-001-001 | CCM PART 2-COOLING BED PLAN AT LEVEL -1.50 | 01 | 2016-08-14 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | SANO | 2016-08-15 14:05 | IFC | AFC | 100%
129267 | I491TC07-0CCSB91-002-001 | CCM PART 2-COOLING BED PLAN AT LEVEL +-0.00 | 01 | 2016-08-14 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | SANO | 2016-08-15 14:05 | IFC | AFC | 100%
129268 | I491TC07-0CCSB91-003-001 | CCM PART 2-COOLING BED SECTIONS | 01 | 2016-08-14 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | SANO | 2016-08-15 14:05 | IFC | AFC | 100%
114260 | I491TC07-0CPAM91-001-001 | Compressed Air Plant Architecture North And South View Compressed Air Plant | 01 | 2015-08-08 | Indeterminate | Drawing | Detail | Compressed Air Production Plant | Civil and Steel Structure | TAM | 2015-08-10 10:39 | IFC | AFC | 100%
114261 | I491TC07-0CPAM91-001-002 | Compressed Air Plant Architecture East View Compressed Air Plant | 01 | 2015-08-08 | Indeterminate | Drawing | Detail | Compressed Air Production Plant | Civil and Steel Structure | TAM | 2015-08-10 10:39 | IFC | AFC | 100%
114262 | I491TC07-0CPAM91-001-003 | Compressed Air Plant Architecture West View Compressed Air Plant | 01 | 2015-08-08 | Indeterminate | Drawing | Detail | Compressed Air Production Plant | Civil and Steel Structure | TAM | 2015-08-10 10:39 | IFC | AFC | 100%
114263 | I491TC07-0CPAM91-001-004 | Compressed Air Plant Architecture Details | 01 | 2015-08-08 | Indeterminate | Drawing | Detail | Compressed Air Production Plant | Civil and Steel Structure | TAM | 2015-08-10 10:39 | IFC | AFC | 100%
114264 | I491TC07-0CPAM91-001-005 | COMPRESSED AIR PLANT ARCHITECTURE ROOF PLAN COMPRESSED AIR PLANT | 00 | 2015-08-08 | Indeterminate | Drawing | Detail | Compressed Air Production Plant | Civil and Steel Structure | TAM | 2015-08-10 10:39 | IFC | AFC | 100%
113223 | I491TC07-0DTAM91-001-001 | FTP-MHS SUBSTATION ARCHITECTURAL Phase II GROUND FLOOR PLAN | 01 | 2015-01-10 | Indeterminate | Drawing | Detail | Fume Treatment Plant Electrical Substation | Civil and Steel Structure | TAM | 2015-01-11 13:10 | IFC | AC |  | 95%
113224 | I491TC07-0DTAM91-001-002 | FTP-MHS SUBSTATION ARCHITECTURAL Phase II FIRST FLOOR PLAN | 01 | 2015-01-10 | Indeterminate | Drawing | Detail | Fume Treatment Plant Electrical Substation Building | Civil and Steel Structure | TAM | 2015-01-11 13:10 | IFC | AC |  | 95%
113225 | I491TC07-0DTAM91-001-003 | FTP-MHS SUBSTATION ARCHITECTURAL Phase II ROOF PLAN | 01 | 2015-01-10 | Indeterminate | Drawing | Detail | Fume Treatment Plant Electrical Substation Building | Civil and Steel Structure | TAM | 2015-01-11 13:10 | IFC | AC |  | 95%
113226 | I491TC07-0DTAM91-001-004 | FTP-MHS SUBSTATION ARCHITECTURAL Phase II LOCATION OF TRANS ON PLAN | 01 | 2015-01-10 | Indeterminate | Drawing | Detail | Fume Treatment Plant Electrical Substation Building | Civil and Steel Structure | TAM | 2015-01-11 13:10 | IFC | AC |  | 95%
113227 | I491TC07-0DTAM91-001-005 | FTP-MHS SUBSTATION ARCHITECTURAL Phase II SECTIONS | 01 | 2015-01-10 | Indeterminate | Drawing | Detail | Fume Treatment Plant Electrical Substation Building | Civil and Steel Structure | TAM | 2015-01-11 13:10 | IFC | AC |  | 95%
113228 | I491TC07-0DTAM91-001-006 | FTP-MHS SUBSTATION ARCHITECTURAL Phase II SECTIONS | 01 | 2015-01-10 | Indeterminate | Drawing | Detail | Fume Treatment Plant Electrical Substation Building | Civil and Steel Structure | TAM | 2015-01-11 13:10 | IFC | AC |  | 95%
113229 | I491TC07-0DTAM91-001-007 | FTP-MHS SUBSTATION ARCHITECTURAL Phase II DETAIL | 01 | 2015-01-10 | Indeterminate | Drawing | Detail | Fume Treatment Plant Electrical Substation Building | Civil and Steel Structure | TAM | 2015-01-11 13:10 | IFC | AC |  | 95%
113230 | I491TC07-0DTAM91-001-008 | FTP-MHS SUBSTATION ARCHITECTURAL Phase II FINISHING LIST | 00 | 2015-01-10 | Indeterminate | Drawing | Detail | Fume Treatment Plant Electrical Substation Building | Civil and Steel Structure | TAM | 2015-01-11 13:10 | IFC | AC |  | 95%
129420 | I491TC07-0EAAM91-004-001 | Melt Shop Main Building Aerator 1800-Plan & Section | 01 | 2016-08-30 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-08-31 10:36 | IFC | AFC | 100%
129421 | I491TC07-0EAAM91-004-002 | Melt Shop Main Building Aerator 1800- Section&Details | 01 | 2016-08-30 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-08-31 10:36 | IFC | AFC | 100%
129422 | I491TC07-0EAAM91-004-003 | Melt Shop Main Building Aerator 1800-Details | 01 | 2016-08-30 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-08-31 10:36 | IFC | AFC | 100%
12514 | I491TC07-0EAAM91-005-001 | Melt Shop Main Building Louvers 1500*2160 Assembly | 00 | 2013-04-07 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | A | 100%
12515 | I491TC07-0EAAM91-005-002 | Melt Shop Main Building Louvers 1500*2160 Details | 00 | 2013-04-07 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | A | 100%
12516 | I491TC07-0EAAM91-006-001 | Melt Shop Main Building Louvers 1000*2160 Assembly | 00 | 2013-04-07 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | A | 100%
12517 | I491TC07-0EAAM91-006-002 | Melt Shop Main Building Louvers 1000*2160 Details | 00 | 2013-04-07 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | A | 100%
129843 | I491TC07-0EAFB91-001-001 | EAF PLATFORM TILT CONTROL ROOM | 02 | 2016-11-22 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2016-11-24 11:10 | IFC | AFC | 100%
130117 | I491TC07-0EASM04-001-001 | EAF-Slag Dumping False Ceiling | 00 | 2017-01-08 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Civil and Steel Structure | TAM | 2017-01-09 09:53 | IFA | AC |  | 95%
131068 | I491TC07-0LAAM91-003-002 | DETAIL DESIGN OF HVAC DRAWING LF & CCM LABORATORY LAYOUT Section A-A , B-B 2-2 | 00 | 2017-08-20 | Indeterminate | Drawing | Detail | Laboratory | Civil and Steel Structure | APEC | 2017-08-23 11:37 | IFC | AC |  | 95%
12519 | I491TC07-0MEAM01-109-002 | 400/33 Kv Substaion Control Building Architectural Detail Drawings | 01 | 2012-07-29 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
129608 | I491TC07-0MMAA91-001-001 | PUMP HOUSE ARCHITECTURAL DRAWINGS WATER COOLING SYSTEM 1-4 | 00 | 2016-09-27 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System Building | Civil and Steel Structure | TAM | 2016-09-29 10:07 | IFA | A | 100%
129609 | I491TC07-0MMAA91-001-002 | PUMP HOUSE ARCHITECTURAL DRAWINGS WATER COOLING SYSTEM 2-4 | 00 | 2016-09-27 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System Building | Civil and Steel Structure | TAM | 2016-09-29 10:07 | IFA | A | 100%
129610 | I491TC07-0MMAA91-001-003 | PUMP HOUSE ARCHITECTURAL DRAWINGS WATER COOLING SYSTEM 3-4 | 00 | 2016-09-27 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System Building | Civil and Steel Structure | TAM | 2016-09-29 10:07 | IFA | A | 100%
129611 | I491TC07-0MMAA91-001-004 | PUMP HOUSE ARCHITECTURAL DRAWINGS WATER COOLING SYSTEM 4-4 | 00 | 2016-09-27 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System Building | Civil and Steel Structure | TAM | 2016-09-29 10:07 | IFA | A | 100%
113234 | I491TC07-0MMAM91-001-001 | WTP SUBSTATION ARCHITECTURAL Phase II GROUND FLOOR PLAN 1-8 | 01 | 2015-01-10 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System Substation | Civil and Steel Structure | TAM | 2015-01-18 11:11 | IFC | AC |  | 95%
113235 | I491TC07-0MMAM91-001-002 | WTP SUBSTATION ARCHITECTURAL Phase II FIRST FLOOR PLAN 2-8 | 01 | 2015-01-10 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System Substation | Civil and Steel Structure | TAM | 2015-01-18 11:11 | IFC | AC |  | 95%
113236 | I491TC07-0MMAM91-001-003 | WTP SUBSTATION ARCHITECTURAL Phase II ROOF PLAN 3-8 | 01 | 2015-01-10 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System Substation | Civil and Steel Structure | TAM | 2015-01-18 11:11 | IFC | AC |  | 95%
113237 | I491TC07-0MMAM91-001-004 | WTP SUBSTATION ARCHITECTURAL Phase II LOCATION OF TRANS ON PLAN 4-8 | 01 | 2015-01-10 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System Substation | Civil and Steel Structure | TAM | 2015-01-18 11:11 | IFC | AC |  | 95%
113238 | I491TC07-0MMAM91-001-005 | WTP SUBSTATION ARCHITECTURAL Phase II SECTIONS SECTIONS 5-8 | 01 | 2015-01-10 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System Substation | Civil and Steel Structure | TAM | 2015-01-18 11:11 | IFC | AC |  | 95%
113239 | I491TC07-0MMAM91-001-006 | WTP SUBSTATION ARCHITECTURAL Phase II SECTIONS 6-8 | 01 | 2015-01-10 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System Substation | Civil and Steel Structure | TAM | 2015-01-18 11:11 | IFC | AC |  | 95%
113240 | I491TC07-0MMAM91-001-007 | WTP SUBSTATION ARCHITECTURAL Phase II DETAIL 7-8 | 01 | 2015-01-10 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System Substation | Civil and Steel Structure | TAM | 2015-01-18 11:11 | IFC | AC |  | 95%
113241 | I491TC07-0MMAM91-001-008 | WTP SUBSTATION ARCHITECTURAL Phase II FINISHING LIST 8-8 | 00 | 2015-01-10 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System Substation | Civil and Steel Structure | TAM | 2015-01-18 11:11 | IFA | AC |  | 95%
132802 | I491TC07-0MMCP91-001-001 | BLOWER ROOM ATCHITECTURAL PLANS,VIEWS & DETAILS 1-2 | 02 | 2018-01-27 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | TAM | 2018-02-03 15:19 | IFC | AC |  | 95%
132803 | I491TC07-0MMCP91-001-002 | BLOWER ROOM ATCHITECTURAL DETAILS 2-2 | 02 | 2018-01-27 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | TAM | 2018-02-03 15:19 | IFC | AC |  | 95%
132973 | I491TC07-0MYAA91-001-001 | Workshop Architecture Drawing First Floor Plan-Section 1-2 | 01 | 2018-03-12 | Indeterminate | Drawing | Detail | Maintenance Workshop | Mechanical | TAM | 2018-03-17 16:36 | IFC | AFC | 100%
132974 | I491TC07-0MYAA91-001-002 | Workshop Architecture Drawing Wall Section-Details 2-2 | 01 | 2018-03-12 | Indeterminate | Drawing | Detail | Maintenance Workshop | Mechanical | TAM | 2018-03-17 16:36 | IFC | AFC | 100%
112584 | I491TC07-0OFAM91-001-001 | NON INDUSTRIAL BUILDINGS (ADMIN - CANTEEN - SHOWER & LOCKER) SITE PLAN | 01 | 2014-07-12 | Indeterminate | Drawing | Detail | Office - Canteen - Locker & Shower For Melt Shop | Civil and Steel Structure | Azhand Shahr | 2014-07-13 14:10 | IFC | AFC | 100%
112585 | I491TC07-0OFAM91-001-002 | NON INDUSTRIAL BUILDINGS (ADMIN - CANTEEN - SHOWER & LOCKER) GROUND FLOOR FURNISHED PLAN | 01 | 2014-07-12 | Indeterminate | Drawing | Detail | Office - Canteen - Locker & Shower For Melt Shop | Civil and Steel Structure | Azhand Shahr | 2014-07-13 14:10 | IFC | AFC | 100%
112586 | I491TC07-0OFAM91-001-003 | NON INDUSTRIAL BUILDINGS (ADMIN - CANTEEN - SHOWER & LOCKER) FIRST FLOOR FURNISHED PLAN | 01 | 2014-07-12 | Indeterminate | Drawing | Detail | Office - Canteen - Locker & Shower For Melt Shop | Civil and Steel Structure | Azhand Shahr | 2014-07-13 14:10 | IFC | AFC | 100%
112587 | I491TC07-0OFAM91-001-004 | NON INDUSTRIAL BUILDINGS (ADMIN - CANTEEN - SHOWER & LOCKER) Ground Floor Dimension Plan | 01 | 2014-07-12 | Indeterminate | Drawing | Detail | Office - Canteen - Locker & Shower For Melt Shop | Civil and Steel Structure | Azhand Shahr | 2014-07-13 14:10 | IFC | AFC | 100%
112588 | I491TC07-0OFAM91-001-005 | NON INDUSTRIAL BUILDINGS (ADMIN - CANTEEN - SHOWER & LOCKER) First Floor Dimension Plan | 01 | 2014-07-12 | Indeterminate | Drawing | Detail | Office - Canteen - Locker & Shower For Melt Shop | Civil and Steel Structure | Azhand Shahr | 2014-07-13 14:10 | IFC | AFC | 100%
112589 | I491TC07-0OFAM91-001-006 | NON INDUSTRIAL BUILDINGS (ADMIN - CANTEEN - SHOWER & LOCKER) First Floor Dimension Plan | 01 | 2014-07-12 | Indeterminate | Drawing | Detail | Office - Canteen - Locker & Shower For Melt Shop | Civil and Steel Structure | Azhand Shahr | 2014-07-13 14:10 | IFC | AFC | 100%
112590 | I491TC07-0OFAM91-001-007 | NON INDUSTRIAL BUILDINGS (ADMIN - CANTEEN - SHOWER & LOCKER) Roof Plan | 01 | 2014-07-12 | Indeterminate | Drawing | Detail | Office - Canteen - Locker & Shower For Melt Shop | Civil and Steel Structure | Azhand Shahr | 2014-07-13 14:10 | IFC | AFC | 100%
112591 | I491TC07-0OFAM91-001-008 | NON INDUSTRIAL BUILDINGS (ADMIN - CANTEEN - SHOWER & LOCKER) Ground Floor Suspended Ceiling | 01 | 2014-07-12 | Indeterminate | Drawing | Detail | Office - Canteen - Locker & Shower For Melt Shop | Civil and Steel Structure | Azhand Shahr | 2014-07-13 14:10 | IFC | AFC | 100%
112592 | I491TC07-0OFAM91-001-009 | NON INDUSTRIAL BUILDINGS (ADMIN - CANTEEN - SHOWER & LOCKER) FIRST FLOOR FURNISHED PLAN | 01 | 2014-07-12 | Indeterminate | Drawing | Detail | Office - Canteen - Locker & Shower For Melt Shop | Civil and Steel Structure | Azhand Shahr | 2014-07-13 14:10 | IFC | AFC | 100%
112593 | I491TC07-0OFAM91-001-010 | NON INDUSTRIAL BUILDINGS (ADMIN - CANTEEN - SHOWER & LOCKER) FIRST FLOOR FURNISHED PLAN | 01 | 2014-07-12 | Indeterminate | Drawing | Detail | Office - Canteen - Locker & Shower For Melt Shop | Civil and Steel Structure | Azhand Shahr | 2014-07-13 14:10 | IFC | AFC | 100%
112594 | I491TC07-0OFAM91-001-011 | NON INDUSTRIAL BUILDINGS (ADMIN - CANTEEN - SHOWER & LOCKER) FIRST FLOOR FURNISHED PLAN | 01 | 2014-07-12 | Indeterminate | Drawing | Detail | Office - Canteen - Locker & Shower For Melt Shop | Civil and Steel Structure | Azhand Shahr | 2014-07-13 14:10 | IFC | AFC | 100%
112595 | I491TC07-0OFAM91-001-012 | NON INDUSTRIAL BUILDINGS (ADMIN - CANTEEN - SHOWER & LOCKER) SECTION A-A , B-B , C-C | 01 | 2014-07-12 | Indeterminate | Drawing | Detail | Office - Canteen - Locker & Shower For Melt Shop | Civil and Steel Structure | Azhand Shahr | 2014-07-13 14:10 | IFC | AFC | 100%
112596 | I491TC07-0OFAM91-001-013 | NON INDUSTRIAL BUILDINGS (ADMIN - CANTEEN - SHOWER & LOCKER) WALL SECTION | 01 | 2014-07-12 | Indeterminate | Drawing | Detail | Office - Canteen - Locker & Shower For Melt Shop | Civil and Steel Structure | Azhand Shahr | 2014-07-13 14:10 | IFC | AFC | 100%
112597 | I491TC07-0OFAM91-001-014 | NON INDUSTRIAL BUILDINGS (ADMIN - CANTEEN - SHOWER & LOCKER) DOOR & WINDOW TYPES | 01 | 2014-07-12 | Indeterminate | Drawing | Detail | Office - Canteen - Locker & Shower For Melt Shop | Civil and Steel Structure | Azhand Shahr | 2014-07-13 14:10 | IFC | AFC | 100%
112598 | I491TC07-0OFAM91-001-015 | NON INDUSTRIAL BUILDINGS (ADMIN - CANTEEN - SHOWER & LOCKER) STAIR LAYOUT | 01 | 2014-07-12 | Indeterminate | Drawing | Detail | Office - Canteen - Locker & Shower For Melt Shop | Civil and Steel Structure | Azhand Shahr | 2014-07-13 14:10 | IFC | AFC | 100%
112599 | I491TC07-0OFAM91-001-016 | NON INDUSTRIAL BUILDINGS (ADMIN - CANTEEN - SHOWER & LOCKER) LAYOUT LAVATORY PLAN | 01 | 2014-07-12 | Indeterminate | Drawing | Detail | Office - Canteen - Locker & Shower For Melt Shop | Civil and Steel Structure | Azhand Shahr | 2014-07-13 14:10 | IFC | AFC | 100%
112600 | I491TC07-0OFAM91-001-017 | NON INDUSTRIAL BUILDINGS (ADMIN - CANTEEN - SHOWER & LOCKER) LAYOUT LAVATORY PLAN | 01 | 2014-07-12 | Indeterminate | Drawing | Detail | Office - Canteen - Locker & Shower For Melt Shop | Civil and Steel Structure | Azhand Shahr | 2014-07-13 14:10 | IFC | AFC | 100%
112601 | I491TC07-0OFAM91-001-018 | NON INDUSTRIAL BUILDINGS (ADMIN - CANTEEN - SHOWER & LOCKER) LAYOUT LAVATORY PLAN | 01 | 2014-07-12 | Indeterminate | Drawing | Detail | Office - Canteen - Locker & Shower For Melt Shop | Civil and Steel Structure | Azhand Shahr | 2014-07-13 14:10 | IFC | AFC | 100%
112602 | I491TC07-0OFAM91-001-019 | NON INDUSTRIAL BUILDINGS (ADMIN - CANTEEN - SHOWER & LOCKER) LAYOUT LAVATORY PLAN | 01 | 2014-07-12 | Indeterminate | Drawing | Detail | Office - Canteen - Locker & Shower For Melt Shop | Civil and Steel Structure | Azhand Shahr | 2014-07-13 14:10 | IFC | AFC | 100%
112603 | I491TC07-0OFAM91-001-020 | NON INDUSTRIAL BUILDINGS (ADMIN - CANTEEN - SHOWER & LOCKER) LAYOUT KITCHEN PLAN | 01 | 2014-07-12 | Indeterminate | Drawing | Detail | Office - Canteen - Locker & Shower For Melt Shop | Civil and Steel Structure | Azhand Shahr | 2014-07-13 14:10 | IFC | AFC | 100%
112604 | I491TC07-0OFAM91-001-021 | NON INDUSTRIAL BUILDINGS (ADMIN - CANTEEN - SHOWER & LOCKER) CLOSET TYPES | 01 | 2014-07-12 | Indeterminate | Drawing | Detail | Office - Canteen - Locker & Shower For Melt Shop | Civil and Steel Structure | Azhand Shahr | 2014-07-13 14:10 | IFC | AFC | 100%
112605 | I491TC07-0OFAM91-001-022 | NON INDUSTRIAL BUILDINGS (ADMIN - CANTEEN - SHOWER & LOCKER) FINISHING LIST | 01 | 2014-07-12 | Indeterminate | Drawing | Detail | Office - Canteen - Locker & Shower For Melt Shop | Civil and Steel Structure | Azhand Shahr | 2014-07-13 14:10 | IFC | AFC | 100%
112606 | I491TC07-0OFAM91-001-023 | NON INDUSTRIAL BUILDINGS (ADMIN - CANTEEN - SHOWER & LOCKER) FINISHING LIST | 01 | 2014-07-12 | Indeterminate | Drawing | Detail | Office - Canteen - Locker & Shower For Melt Shop | Civil and Steel Structure | Azhand Shahr | 2014-07-13 14:10 | IFC | AFC | 100%
12562 | I491TC07-0TBAM91-001-035 | Melt Shop Main Building - Key Plan | 03 | 2013-05-19 | Indeterminate | Drawing | Detail | Ladle Furnace | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12563 | I491TC07-0TBAM91-001-036 | Melt Shop Main Building - Plan At Level -3.200 & ±0.00 | 03 | 2013-05-19 | Indeterminate | Drawing | Detail | Ladle Furnace | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12564 | I491TC07-0TBAM91-001-037 | Melt Shop Main Building - Plan At Level +5.970 | 03 | 2013-05-19 | Indeterminate | Drawing | Detail | Ladle Furnace | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12565 | I491TC07-0TBAM91-001-038 | Melt Shop Main Building - Roof Plan | 03 | 2013-05-19 | Indeterminate | Drawing | Detail | Ladle Furnace | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12566 | I491TC07-0TBAM91-001-039 | Melt Shop Main Building - Section A & Details | 03 | 2013-05-19 | Indeterminate | Drawing | Detail | Ladle Furnace | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12568 | I491TC07-0TBAM91-001-040 | Melt Shop Main Building - Section B & View A | 03 | 2013-05-19 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12569 | I491TC07-0TBAM91-001-041 | Melt Shop Main Building - View B & View C | 03 | 2013-05-19 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12570 | I491TC07-0TBAM91-001-042 | Melt Shop Main Building - View D | 03 | 2013-05-19 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12571 | I491TC07-0TBAM91-001-043 | Melt Shop Main Building - Details Of Stairs | 03 | 2013-05-19 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12572 | I491TC07-0TBAM91-001-044 | Melt Shop Main Building - Flooring Details | 03 | 2013-05-19 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12573 | I491TC07-0TBAM91-001-045 | Melt Shop Main Building - Details Of Door | 03 | 2013-05-19 | Indeterminate | Drawing | Detail | Ladle Furnace | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12574 | I491TC07-0TBAM91-001-046 | Melt Shop Main Building - Details Of Windows | 03 | 2013-05-19 | Indeterminate | Drawing | Detail | Ladle Furnace | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12575 | I491TC07-0TBAM91-001-047 | Melt Shop Main Building - Layout Of Lavatory | 03 | 2013-05-19 | Indeterminate | Drawing | Detail | Ladle Furnace | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12576 | I491TC07-0TBAM91-001-048 | Melt Shop Main Building - Suspended Ceiling Plan | 03 | 2013-05-19 | Indeterminate | Drawing | Detail | Ladle Furnace | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12577 | I491TC07-0TBAM91-001-049 | Melt Shop Main Building - Layout Of Transformator | 03 | 2013-05-19 | Indeterminate | Drawing | Detail | Ladle Furnace | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12579 | I491TC07-0TBAM91-001-050 | Melt Shop Main Building - Details | 03 | 2013-05-19 | Indeterminate | Drawing | Detail | Ladle Furnace | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12580 | I491TC07-0TBAM91-001-051 | Melt Shop Main Building - Details Of Ladder & Steel Stairs | 03 | 2013-05-19 | Indeterminate | Drawing | Detail | Ladle Furnace | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12581 | I491TC07-0TBAM91-001-052 | Melt Shop Main Building Lf Building Architectural - Key Plan | 04 | 2013-06-16 | Indeterminate | Drawing | Detail | Ladle Furnace | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12582 | I491TC07-0TBAM91-001-053 | Melt Shop Main Building Lf Building Architectural - Plan At Level -3.30 & Plan At Level ±0.00 | 04 | 2013-06-16 | Indeterminate | Drawing | Detail | Ladle Furnace | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12583 | I491TC07-0TBAM91-001-054 | Melt Shop Main Building Lf Building Architectural - Plan At Level +5.970 | 04 | 2013-06-16 | Indeterminate | Drawing | Detail | Ladle Furnace | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12584 | I491TC07-0TBAM91-001-055 | Melt Shop Main Building Lf Building Architectural - Roof Plan | 04 | 2013-06-16 | Indeterminate | Drawing | Detail | Ladle Furnace | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12585 | I491TC07-0TBAM91-001-056 | Melt Shop Main Building Lf Building Architectural - Section A & Details | 04 | 2013-06-16 | Indeterminate | Drawing | Detail | Ladle Furnace | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12586 | I491TC07-0TBAM91-001-057 | Melt Shop Main Building Lf Building Architectural - Section B & View A | 04 | 2013-06-16 | Indeterminate | Drawing | Detail | Ladle Furnace | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12587 | I491TC07-0TBAM91-001-058 | Melt Shop Main Building Lf Building Architectural - View B & View C | 04 | 2013-06-16 | Indeterminate | Drawing | Detail | Ladle Furnace | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12588 | I491TC07-0TBAM91-001-059 | Melt Shop Main Building Lf Building Architectural - View D | 04 | 2013-06-16 | Indeterminate | Drawing | Detail | Ladle Furnace | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12590 | I491TC07-0TBAM91-001-060 | Melt Shop Main Building Lf Building Architectural - Details Of Stairs | 04 | 2013-06-16 | Indeterminate | Drawing | Detail | Ladle Furnace | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12591 | I491TC07-0TBAM91-001-061 | Melt Shop Main Building Lf Building Architectural - Flooring Details | 04 | 2013-06-16 | Indeterminate | Drawing | Detail | Ladle Furnace | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12592 | I491TC07-0TBAM91-001-062 | Melt Shop Main Building Lf Building Architectural - Details Of Door | 04 | 2013-06-16 | Indeterminate | Drawing | Detail | Ladle Furnace | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12593 | I491TC07-0TBAM91-001-063 | Melt Shop Main Building Lf Building Architectural - Details Of Windows | 04 | 2013-06-16 | Indeterminate | Drawing | Detail | Ladle Furnace | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12594 | I491TC07-0TBAM91-001-064 | Melt Shop Main Building Lf Building Architectural - Layout Of Lavatory | 04 | 2013-06-16 | Indeterminate | Drawing | Detail | Ladle Furnace | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12595 | I491TC07-0TBAM91-001-065 | Melt Shop Main Building Lf Building Architectural - Suspended Ceiling Plan | 04 | 2013-06-16 | Indeterminate | Drawing | Detail | Ladle Furnace | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12596 | I491TC07-0TBAM91-001-066 | Melt Shop Main Building Lf Building Architectural - Layout Of Transformator | 04 | 2013-06-16 | Indeterminate | Drawing | Detail | Ladle Furnace | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12597 | I491TC07-0TBAM91-001-067 | Melt Shop Main Building Lf Building Architectural - Details | 04 | 2013-06-16 | Indeterminate | Drawing | Detail | Ladle Furnace | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12598 | I491TC07-0TBAM91-001-068 | Melt Shop Main Building Lf Building Architectural - Details Of Ladder & Steel Stairs | 04 | 2013-06-16 | Indeterminate | Drawing | Detail | Ladle Furnace | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12643 | I491TC07-0TBAM91-002-047 | Melt Shop Main Building Eaf Building Architectural Details Drawing Key Plan&List Of Drawing | 06 | 2013-11-03 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12644 | I491TC07-0TBAM91-002-048 | Melt Shop Main Building Eaf Building Architectural Details Drawing Plan At Level -3.200 | 06 | 2013-11-03 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12645 | I491TC07-0TBAM91-002-049 | Melt Shop Main Building Eaf Building Architectural Details Drawing Plan At Level ±0.00 | 06 | 2013-11-03 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12647 | I491TC07-0TBAM91-002-050 | Melt Shop Main Building Eaf Building Architectural Details Drawing Plan At Level +4.750 | 06 | 2013-11-03 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12648 | I491TC07-0TBAM91-002-051 | Melt Shop Main Building Eaf Building Architectural Details Drawing Plan At Level +8.500 | 06 | 2013-11-03 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12649 | I491TC07-0TBAM91-002-052 | Melt Shop Main Building Eaf Building Architectural Details Drawing Plan At Level +14.000 | 06 | 2013-11-03 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12650 | I491TC07-0TBAM91-002-053 | Melt Shop Main Building Eaf Building Architectural Details Drawing Roof Plan | 06 | 2013-11-03 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12651 | I491TC07-0TBAM91-002-054 | Melt Shop Main Building Eaf Building Architectural Details Drawing Veiw A | 06 | 2013-11-03 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12652 | I491TC07-0TBAM91-002-055 | Melt Shop Main Building Eaf Building Architectural Details Drawing Veiw B | 06 | 2013-11-03 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12653 | I491TC07-0TBAM91-002-056 | Melt Shop Main Building Eaf Building Architectural Details Drawing Veiw C | 06 | 2013-11-03 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12654 | I491TC07-0TBAM91-002-057 | Melt Shop Main Building Eaf Building Architectural Details Drawing Veiw D | 06 | 2013-11-03 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12655 | I491TC07-0TBAM91-002-058 | Melt Shop Main Building Eaf Building Architectural Details Drawing Section A | 06 | 2013-11-03 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12656 | I491TC07-0TBAM91-002-059 | Melt Shop Main Building Eaf Building Architectural Details Drawing Section B | 06 | 2013-11-03 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12658 | I491TC07-0TBAM91-002-060 | Melt Shop Main Building Eaf Building Architectural Details Drawing Suspended Ceiling Plan | 06 | 2013-11-03 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12659 | I491TC07-0TBAM91-002-061 | Melt Shop Main Building Eaf Building Architectural Details Drawing Typical Windows & Details | 06 | 2013-11-03 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12660 | I491TC07-0TBAM91-002-062 | Melt Shop Main Building Eaf Building Architectural Details Drawing Typical Doors | 06 | 2013-11-03 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12661 | I491TC07-0TBAM91-002-063 | Melt Shop Main Building Eaf Building Architectural Details Drawing Typical Doors Details | 06 | 2013-11-03 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12662 | I491TC07-0TBAM91-002-064 | Melt Shop Main Building Eaf Building Architectural Details Drawing Flooring Details | 06 | 2013-11-03 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12663 | I491TC07-0TBAM91-002-065 | Melt Shop Main Building Eaf Building Architectural Details Drawing Leyout Of Transformer | 06 | 2013-11-03 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12664 | I491TC07-0TBAM91-002-066 | Melt Shop Main Building Eaf Building Architectural Details Drawing Details | 06 | 2013-11-03 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12665 | I491TC07-0TBAM91-002-067 | Melt Shop Main Building Eaf Building Architectural Details Drawing Leyout Of Lavatory | 06 | 2013-11-03 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12666 | I491TC07-0TBAM91-002-068 | Melt Shop Main Building Eaf Building Architectural Details Drawing Details Of Handrail | 06 | 2013-11-03 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12667 | I491TC07-0TBAM91-002-069 | Melt Shop Main Building Eaf Building Architectural Details Drawing Section W & Section K | 06 | 2013-11-03 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
130415 | I491TC07-0TBAM91-005-001 | Details Design Of Architectural Drawing Melt Shop Main Building List Of Drawings & General Notes & Finishing Table | 02 | 2017-04-08 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2017-04-15 09:18 | IFC | AFC | 100%
130416 | I491TC07-0TBAM91-005-002 | Details Design Of Architectural Drawing Melt Shop Main Building Site Plan | 02 | 2017-04-08 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2017-04-15 09:18 | IFC | AFC | 100%
130417 | I491TC07-0TBAM91-005-003 | Details Design Of Architectural Drawing Melt Shop Main Building Plan At ±0.00 ,Plan Of Ligthing &Crane Walk Way | 02 | 2017-04-08 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2017-04-15 09:18 | IFC | AFC | 100%
130423 | I491TC07-0TBAM91-005-004 | Details Design Of Architectural Drawing Melt Shop Main Building View Roof Plan & Section A-A,B-B & Details | 03 | 2017-04-08 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2017-04-15 09:20 | IFC | AFC | 100%
130424 | I491TC07-0TBAM91-005-005 | Details Design Of Architectural Drawing Melt Shop Main Building View A - B - C - D | 03 | 2017-04-08 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2017-04-15 09:20 | IFC | AFC | 100%
130419 | I491TC07-0TBAM91-005-006 | Details Design Of Architectural Drawing Melt Shop Main Building Plat Form Of Ligthing & Crane Walk Way & Eaf,Lf Typical Detail Of Grating & Corner & Ladders | 02 | 2017-04-08 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2017-04-15 09:20 | IFC | AFC | 100%
130420 | I491TC07-0TBAM91-005-007 | Details Design Of Architectural Drawing Melt Shop Main Building Stair Access To +11.5M And +25 M(Type 1) Stair Plan & Section & Detail | 02 | 2017-04-08 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2017-04-15 09:20 | IFC | AFC | 100%
130421 | I491TC07-0TBAM91-005-008 | Details Design Of Architectural Drawing Melt Shop Main Building Stair Access To Lf And Eaf Platform (Type 2) Detail Of Ladder&Handrail | 02 | 2017-04-08 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2017-04-15 09:20 | IFC | AFC | 100%
130422 | I491TC07-0TBAM91-005-009 | Details Design Of Architectural Drawing Melt Shop Main Building Stair Access To Lf And Eaf Platform (Type 3) | 02 | 2017-04-08 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2017-04-15 09:20 | IFC | AFC | 100%
130418 | I491TC07-0TBAM91-005-010 | Details Design Of Architectural Drawing Melt Shop Main Building Stair Access To Lf And Eaf Platform (Type 4) | 02 | 2017-04-08 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2017-04-15 09:20 | IFC | AFC | 100%
130425 | I491TC07-0TBAM91-005-011 | Details Design Of Architectural Drawing Melt Shop Main Building Stair Access To +11.5M And +100M & Lighting Walkway(Type 5) | 02 | 2017-04-08 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2017-04-15 09:21 | IFC | AFC | 100%
130426 | I491TC07-0TBAM91-005-012 | Details Design Of Architectural Drawing Melt Shop Main Building Details Cable Trench Plan & Section & Details | 02 | 2017-04-08 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2017-04-15 09:21 | IFC | AFC | 100%
130432 | I491TC07-0TBAM91-005-013 | Details Design Of Architectural Drawing Melt Shop Main Building Wall Section 1 & Details | 03 | 2017-04-08 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2017-04-15 09:21 | IFC | AFC | 100%
130427 | I491TC07-0TBAM91-005-014 | Details Design Of Architectural Drawing Melt Shop Main Building Wall Section 2 & Details | 02 | 2017-04-08 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2017-04-15 09:21 | IFC | AFC | 100%
130428 | I491TC07-0TBAM91-005-015 | Details Design Of Architectural Drawing Melt Shop Main Building Canopy Hood Load On Roof | 02 | 2017-04-08 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2017-04-15 09:21 | IFC | AFC | 100%
130429 | I491TC07-0TBAM91-005-016 | Details Design Of Architectural Drawing Melt Shop Main Building Aerator 1800-Plan & Section&Details | 02 | 2017-04-08 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2017-04-15 09:21 | IFC | AFC | 100%
130430 | I491TC07-0TBAM91-005-017 | Details Design Of Architectural Drawing Melt Shop Main Building Louvers Type 1 | 02 | 2017-04-08 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2017-04-15 09:21 | IFC | AFC | 100%
130431 | I491TC07-0TBAM91-005-018 | Details Design Of Architectural Drawing Melt Shop Main Building Louvers Type 2 | 02 | 2017-04-08 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2017-04-15 09:21 | IFC | AFC | 100%
130433 | I491TC07-0TBAM91-005-019 | Details Design Of Architectural Drawing Melt Shop Main Building Window Type & Details | 02 | 2017-04-08 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2017-04-15 09:22 | IFC | AFC | 100%
12683 | I491TC07-0TBAM91-005-020 | Details Design Of Architectural Drawing Melt Shop Main Building Wall Section 1 And Details | 02 | 2013-10-09 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
135445 | I491TC08-0ASAM01-001-001 | ASP LAVATORY 1-3 | 00 | 2019-06-01 | Indeterminate | Drawing | Detail | Air Separation Plant Main Building | Civil and Steel Structure | TAM | 2019-06-02 10:06 | IFA | AC |  | 95%
135444 | I491TC08-0ASAM01-001-002 | ASP LAVATORY 2-3 | 00 | 2019-06-01 | Indeterminate | Drawing | Detail | Air Separation Plant Main Building | Civil and Steel Structure | TAM | 2019-06-02 10:06 | IFA | AC |  | 95%
135443 | I491TC08-0ASAM01-001-003 | ASP LAVATORY 3-3 | 00 | 2019-06-01 | Indeterminate | Drawing | Detail | Air Separation Plant Main Building | Civil and Steel Structure | TAM | 2019-06-02 10:06 | IFA | AC |  | 95%
135430 | I491TC08-0ASAM91-001-001 | Oxygen Plant Control Room Structure Excavtion , Foundation & Columns Plan | 01 | 2019-05-29 10:39 | Indeterminate | Drawing | Detail | Air Separation Plant Main Building | Civil and Steel Structure | TAM | 2019-05-29 10:39 | IFC | AC |  | 95%
135431 | I491TC08-0ASAM91-001-002 | Oxygen Plant Control Room Structure Control Room Structure | 01 | 2019-05-29 10:39 | Indeterminate | Drawing | Detail | Air Separation Plant Main Building | Civil and Steel Structure | TAM | 2019-05-29 10:39 | IFC | AC |  | 95%
135432 | I491TC08-0ASAM91-001-003 | Oxygen Plant Control Room Structure Beam Plan& Detailing | 01 | 2019-05-29 10:39 | Indeterminate | Drawing | Detail | Air Separation Plant Main Building | Civil and Steel Structure | TAM | 2019-05-29 10:39 | IFC | AC |  | 95%
135433 | I491TC08-0ASAM91-001-004 | Oxygen Plant Control Room Structure Beam Plan& Detailing | 01 | 2019-05-29 10:39 | Indeterminate | Drawing | Detail | Air Separation Plant Main Building | Civil and Steel Structure | TAM | 2019-05-29 10:39 | IFC | AC |  | 95%
12695 | I491TC08-0ASAM91-001-005 | Basis Of Design For Oxygen Plant Main Work Shop | 00 | 2013-08-24 | Indeterminate | Miscellaneous(MISC) | Basic | Air Separation Plant Main Building | Civil and Steel Structure | TAM |  | IFA | AC |  | 95%
12696 | I491TC08-0ASAM91-002-001 | Oxygen Plant Main Workshop Room Basic Data Compressor Room Plan & Details | 00 | 2013-08-24 | Indeterminate | Drawing | Detail | Air Separation Plant Main Building | Civil and Steel Structure | TAM |  | IFA | AC |  | 95%
12697 | I491TC08-0ASAM91-002-002 | Oxygen Plant Main Workshop Room Basic Data Compressor Room View | 00 | 2013-08-24 | Indeterminate | Drawing | Detail | Air Separation Plant Main Building | Civil and Steel Structure | TAM |  | IFA | AC |  | 95%
12698 | I491TC08-0ASAM91-002-003 | Oxygen Plant Main Workshop Room Basic Data Compressor Room Structure 3-5 | 00 | 2013-08-24 | Indeterminate | Drawing | Detail | Air Separation Plant Main Building | Civil and Steel Structure | TAM |  | IFA | AC |  | 95%
12699 | I491TC08-0ASAM91-002-004 | Oxygen Main Workshop Room Basic Data Compressor Room Structure 4-5 | 00 | 2013-08-24 | Indeterminate | Drawing | Detail | Air Separation Plant Main Building | Civil and Steel Structure | TAM |  | IFA | AC |  | 95%
130352 | I491TC08-0ASAM91-002-005 | Excavation Plan And Section Compressor Room Air Separation Plant | 01 | 2017-02-28 13:23 | Indeterminate | Drawing | Detail | Air Separation Plant Main Building | Civil and Steel Structure | TAM | 2017-02-28 13:23 | IFC | AFC | 100%
130353 | I491TC08-0ASAM91-002-006 | Foundation Plan And Details Compressor Room Air Separation Plant | 01 | 2017-02-28 13:23 | Indeterminate | Drawing | Detail | Air Separation Plant Main Building | Civil and Steel Structure | TAM | 2017-02-28 13:23 | IFC | AFC | 100%
130354 | I491TC08-0ASAM91-002-007 | Foundation Reinforcement And Details Compressor Room Air Separation Plant | 01 | 2017-02-28 13:23 | Indeterminate | Drawing | Detail | Air Separation Plant Main Building | Civil and Steel Structure | TAM | 2017-02-28 13:23 | IFC | AFC | 100%
12703 | I491TC08-0ASAM91-003-001 | Oxygen Plant Pump Room Structure Beam Plan& Detailing | 00 | 2013-08-24 | Indeterminate | Drawing | Detail | Air Separation Plant Main Building | Civil and Steel Structure | TAM |  | IFA | AC |  | 95%
12704 | I491TC08-0ASAM91-003-002 | Oxygen Plant Pump Room Structure Excavtion , Foundation & Columns Plan | 00 | 2013-08-24 | Indeterminate | Drawing | Detail | Air Separation Plant Main Building | Civil and Steel Structure | TAM |  | IFA | AC |  | 95%
130345 | I491TC08-0ASAM91-004-001 | Compressor Room Plan Basic Drawing Compressor Room Air Separation Plant | 02 | 2017-02-27 | Indeterminate | Drawing | Detail | Air Separation Plant Main Building | Civil and Steel Structure | TAM | 2017-02-28 10:47 | IFC | AFC | 100%
130346 | I491TC08-0ASAM91-004-002 | Compressor Room Structure Basic Drawing Main Workshop Room Basic Data Air Separation Plant | 02 | 2017-02-27 | Indeterminate | Drawing | Detail | Air Separation Plant Main Building | Civil and Steel Structure | TAM | 2017-02-28 10:49 | IFC | AFC | 100%
112374 | I491TC08-0ASAM91-004-007 | ASP-CAP SUBSTATION COLUMNS PLAN | 01 | 2014-06-08 | Indeterminate | Drawing | Detail | Air Separation Plant Main Building | Civil and Steel Structure | TAM | 2014-06-09 16:51 | IFC | AFC | 100%
112375 | I491TC08-0ASAM91-004-008 | ASP-CAP SUBSTATION FOUNDATION PLAN & SECTION | 01 | 2014-06-08 | Indeterminate | Drawing | Detail | Air Separation Plant Main Building | Civil and Steel Structure | TAM | 2014-06-09 16:51 | IFC | AFC | 100%
112376 | I491TC08-0ASAM91-004-009 | ASP-CAP SUBSTATION FIRST FRAMING PLAN | 01 | 2014-06-08 | Indeterminate | Drawing | Detail | Air Separation Plant Main Building | Civil and Steel Structure | TAM | 2014-06-09 16:51 | IFC | AFC | 100%
112377 | I491TC08-0ASAM91-004-010 | ASP-CAP SUBSTATION ROOF FRAMING PLAN | 01 | 2014-06-08 | Indeterminate | Drawing | Detail | Air Separation Plant Main Building | Civil and Steel Structure | TAM | 2014-06-09 16:51 | IFC | AFC | 100%
133412 | I491TC08-0ASAM91-005-017 | ASP-CAP SUBSTATION TRANSFORMER AREA Diesel Generator Flooring 17-17 | 02 | 2018-07-02 | Indeterminate | Drawing | Detail | Air Separation Plant Electrical substation Building | Civil and Steel Structure | TAM | 2018-07-08 16:33 | IFC | AFC | 100%
130695 | I491TC08-0ASAM91-006-001 | FLOORING PLAN AIR SEPARATION PLANT 1-4 | 01 | 2017-06-14 15:33 | Indeterminate | Drawing | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2017-06-14 15:33 | IFC | AFC | 100%
130696 | I491TC08-0ASAM91-006-002 | FLOORING PLAN AIR SEPARATION PLANT 2-4 | 01 | 2017-06-14 15:33 | Indeterminate | Drawing | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2017-06-14 15:33 | IFC | AC |  | 95%
130697 | I491TC08-0ASAM91-006-003 | FLOORING PLAN AIR SEPARATION PLANT 3-4 | 01 | 2017-06-14 15:33 | Indeterminate | Drawing | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2017-06-14 15:33 | IFC | AFC | 100%
130698 | I491TC08-0ASAM91-006-004 | FLOORING PLAN AIR SEPARATION PLANT 4-4 | 01 | 2017-06-14 15:33 | Indeterminate | Drawing | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2017-06-14 15:33 | IFC | AFC | 100%
129923 | I491TC08-0ASCP01-001-001 | MAIN AIR COMPRESSORS FOUNDATION AIR SEPARATION PLANT 1-3 | 01 | 2016-12-05 | Indeterminate | Drawing | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2016-12-12 15:06 | IFC | AFC | 100%
129924 | I491TC08-0ASCP01-001-002 | MAIN AIR COMPRESSORS FOUNDATION AIR SEPARATION PLANT 2-2 | 01 | 2016-12-05 | Indeterminate | Drawing | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2016-12-12 15:06 | IFC | AFC | 100%
129922 | I491TC08-0ASCP01-001-003 | MAIN AIR COMPRESSORS FOUNDATION AIR SEPARATION PLANT 3-3 | 00 | 2016-12-05 | Indeterminate | Drawing | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2016-12-12 15:06 | IFC | AFC | 100%
130302 | I491TC08-0ASCP02-001-001 | BOOSTER AIR COMPRESSOR FOUNDATION AIR SEPARATION PLANT 1-2 | 01 | 2017-02-07 10:39 | Indeterminate | Drawing | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2017-02-07 10:39 | IFC | AFC | 100%
130303 | I491TC08-0ASCP02-001-002 | BOOSTER AIR COMPRESSOR FOUNDATION AIR SEPARATION PLANT 2-2 | 01 | 2017-02-07 10:39 | Indeterminate | Drawing | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2017-02-07 10:39 | IFC | AFC | 100%
129460 | I491TC08-0ASIJ01-001-001 | Cold box foundation drawing 1-5 | 01 | 2016-09-07 16:23 | Indeterminate | Drawing | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2016-09-07 16:23 | IFC | AFC | 100%
129461 | I491TC08-0ASIJ01-001-002 | Cold box foundation drawing 2-5 | 01 | 2016-09-07 16:23 | Indeterminate | Drawing | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2016-09-07 16:23 | IFC | AC |  | 95%
129462 | I491TC08-0ASIJ01-001-003 | Cold box foundation drawing 3-5 | 01 | 2016-09-07 16:23 | Indeterminate | Drawing | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2016-09-07 16:23 | IFC | AFC | 100%
129463 | I491TC08-0ASIJ01-001-004 | Cold box foundation drawing 4-5 | 01 | 2016-09-07 16:23 | Indeterminate | Drawing | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2016-09-07 16:23 | IFC | AFC | 100%
129464 | I491TC08-0ASIJ01-001-005 | Cold box foundation drawing 5-5 | 01 | 2016-09-07 16:23 | Indeterminate | Drawing | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2016-09-07 16:23 | IFC | AC |  | 95%
129230 | I491TC08-0ASPS01-001-001 | PPU Skid foundation drawing 11 | 01 | 2016-08-10 | Indeterminate | Drawing | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2016-08-14 14:08 | IFC | AC |  | 95%
129466 | I491TC08-0ASPU01-001-001 | 24Liquid Oxygen Back up Pump | 01 | 2016-09-10 | Indeterminate | Drawing | Detail | Air Separation Plant | Civil and Steel Structure | Fortune | 2016-09-11 09:39 | IFC | AFC | 100%
129467 | I491TC08-0ASPU02-001-001 | 22Liquid Argon Back up Pump | 01 | 2016-09-10 | Indeterminate | Drawing | Detail | Air Separation Plant | Civil and Steel Structure | Fortune | 2016-09-11 09:39 | IFC | AFC | 100%
129468 | I491TC08-0ASPU03-001-001 | 23Liquid Nitrogen Back up Pump | 01 | 2016-09-10 | Indeterminate | Drawing | Detail | Air Separation Plant | Civil and Steel Structure | Fortune | 2016-09-11 09:39 | IFC | AFC | 100%
129488 | I491TC08-0ASPU04-001-001 | LIQUID NITROGEN PROCESS PUMP FOUNDATION AIR SEPARATION PLANT | 01 | 2016-09-11 13:55 | Indeterminate | Drawing | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2016-09-11 13:55 | IFC | AC |  | 95%
115736 | I491TC08-0ASSB91-001-001 | SELF-CLEAN AIR FILTER FOUNDATION AIR SEPARATION PLANT 1-2 | 01 | 2016-06-14 16:55 | Indeterminate | Drawing | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2016-06-14 16:55 | IFC | AFC | 100%
115735 | I491TC08-0ASSB91-001-002 | SAND FILTER FOUNDATION AIR SEPARATION PLANT 2-2 | 01 | 2016-06-14 16:55 | Indeterminate | Drawing | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2016-06-14 16:55 | IFC | AFC | 100%
115741 | I491TC08-0ASSB91-027-001 | LIQUID OXYGEN VAPORIZER FOUNDATION AIR SEPARATION PLANT 1-2 | 01 | 2016-06-14 16:56 | Indeterminate | Drawing | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2016-06-14 16:56 | IFC | AFC | 100%
115742 | I491TC08-0ASSB91-027-002 | LIQUID OXYGEN VAPORIZER FOUNDATION AIR SEPARATION PLANT 2-2 | 01 | 2016-06-14 16:56 | Indeterminate | Drawing | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2016-06-14 16:56 | IFC | AFC | 100%
129231 | I491TC08-0ASSL02-001-001 | OXYGEN SILENCER FOUNDATION AIR SEPARATION PLANT 17 | 01 | 2016-08-10 | Indeterminate | Drawing | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2016-08-14 14:08 | IFC | AC |  | 95%
129232 | I491TC08-0ASSL03-001-001 | NITROGEN SILENCER FOUNDATION AIR SEPARATION PLANT 18 | 01 | 2016-08-10 | Indeterminate | Drawing | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2016-08-14 14:08 | IFC | AC |  | 95%
130740 | I491TC08-0ASTK01-001-001 | Liquid Oxygen Tank foundation drawing 21 | 03 | 2017-07-02 | Indeterminate | Drawing | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2017-07-04 13:41 | IFC | AFC | 100%
129233 | I491TC08-0ASTK03-001-001 | Liquid Argon Tank Foundation Drawing 19 | 01 | 2016-08-10 | Indeterminate | Drawing | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2016-08-14 14:09 | IFC | AC |  | 95%
130336 | I491TC08-0ASTK04-001-001 | Oxygen buffer tank foundation drawing | 04 | 2017-02-27 15:10 | Indeterminate | Drawing | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2017-02-27 15:10 | IFC | AFC | 100%
115746 | I491TC08-0ASTK05-001-001 | Nitrogen buffer tank foundation drawing | 01 | 2016-06-14 16:58 | Indeterminate | Drawing | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2016-06-14 16:58 | IFC | AFC | 100%
115744 | I491TC08-0ASTK06-001-001 | Argon buffer tank foundation drawing | 01 | 2016-06-14 16:57 | Indeterminate | Drawing | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2016-06-14 16:57 | IFC | AFC | 100%
130881 | I491TC08-0ASVS01-001-001 | WASTE LIQUID VAPORIZER FOUNDATION AIR SEPARATION PLANT | 04 | 2017-07-23 | Indeterminate | Drawing | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2017-07-24 12:56 | IFC | AFC | 100%
129449 | I491TC08-0ASVS02-001-001 | NITROGEN PRESSURE REDUCER FOUNDATION 32 | 02 | 2016-09-05 10:39 | Indeterminate | Drawing | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2016-09-05 10:39 | IFC | AC |  | 95%
134175 | I491TC08-0ASVS05-001-001 | WASTER NITROGEN SILENCER FOUNDATION AIR SEPARATION PLANT | 01 | 2018-09-17 | Indeterminate | Drawing | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2018-09-22 09:36 | IFC | AFC | 100%
129229 | I491TC08-0ASXX01-001-001 | DCAC Skid foundation drawing 10 | 01 | 2016-08-10 | Indeterminate | Drawing | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2016-08-14 14:07 | IFC | AC |  | 95%
129471 | I491TC08-0ASXX05-002-001 | GO PRESSURE REDUCER BLAST WALL AIR SEPARATION PLANT 1-4 | 01 | 2016-09-11 09:48 | Indeterminate | Drawing | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2016-09-11 09:48 | IFC | AFC | 100%
129472 | I491TC08-0ASXX05-002-002 | GO PRESSURE REDUCER BLAST WALL AIR SEPARATION PLANT 2-4 | 01 | 2016-09-11 09:48 | Indeterminate | Drawing | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2016-09-11 09:48 | IFC | AFC | 100%
129473 | I491TC08-0ASXX05-002-003 | GO PRESSURE REDUCER BLAST WALL AIR SEPARATION PLANT 3-4 | 01 | 2016-09-11 09:48 | Indeterminate | Drawing | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2016-09-11 09:48 | IFC | AFC | 100%
129474 | I491TC08-0ASXX05-002-004 | GO PRESSURE REDUCER BLAST WALL AIR SEPARATION PLANT 4-4 | 01 | 2016-09-11 09:48 | Indeterminate | Drawing | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2016-09-11 09:48 | IFC | AFC | 100%
114266 | I491TC08-0CCAM91-011-001 | CCM LADLE TURRET FOUNDATION FORMWORK PLAN | 00 | 2019-05-15 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | SANO | 2015-08-17 13:31 | IFA | AC |  | 95%
114267 | I491TC08-0CCAM91-012-001 | CCM LADLE TURRET FORMWORK PLAN AT LEVEL +0.050 | 00 | 2019-05-15 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | SANO | 2015-08-17 13:31 | IFA | AC |  | 95%
114268 | I491TC08-0CCAM91-013-001 | CCM LADLE TURRET FORMWORK PLAN AT LEVEL +4.900 | 00 | 2019-05-15 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | SANO | 2015-08-17 13:31 | IFA | AC |  | 95%
130396 | I491TC08-0CCAM91-014-001 | CCM LADLE TURRET FORM. PLAN FROM LEV. +8.970 TO +12.010 | 01 | 2017-03-07 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | SANO | 2017-04-04 09:03 | IFC | AFC | 100%
114270 | I491TC08-0CCAM91-016-001 | CCM LADLE TURRET SECTIONS 5 AND 6 | 00 | 2019-05-15 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | SANO | 2015-08-17 13:31 | IFA | AC |  | 95%
114365 | I491TC08-0CCAM91-018-001 | CCM CONTROL CABIN FOUNDATION & FORMWORK PLAN | 01 | 2015-09-08 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | SANO | 2015-09-13 16:26 | IFC | AFC | 100%
114366 | I491TC08-0CCAM91-019-001 | CCM CONTROL CABIN FORMWORK SECTIONS | 01 | 2015-09-08 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | SANO | 2015-09-13 16:26 | IFC | AFC | 100%
114367 | I491TC08-0CCAM91-021-001 | CCM CONTROL CABIN FOUNDATION REINFORCEMENT | 01 | 2015-09-08 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | SANO | 2015-09-13 16:26 | IFC | AFC | 100%
114368 | I491TC08-0CCAM91-022-001 | CCM CONTROL CABIN COLUMN REINFORCEMENT | 01 | 2015-09-08 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | SANO | 2015-09-13 16:26 | IFC | AFC | 100%
114369 | I491TC08-0CCAM91-023-001 | CCM CONTROL CABIN BEAM REINFORCEMENT | 01 | 2015-09-08 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | SANO | 2015-09-13 16:26 | IFC | AFC | 100%
114370 | I491TC08-0CCAM91-024-001 | CCM CONTROL CABIN SLAB REINFORCEMENT | 01 | 2015-09-08 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | SANO | 2015-09-13 16:26 | IFC | AFC | 100%
114371 | I491TC08-0CCAM91-025-001 | CCM CONTROL CABIN COLUMN REINFORCEMENT | 01 | 2015-09-08 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | SANO | 2015-09-13 16:26 | IFC | AFC | 100%
114271 | I491TC08-0CCAM91-027-001 | CCM LADLE TURRET FOUNDATION REINFORCEMENT PLAN (1/2) | 00 | 2019-05-15 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | SANO | 2015-08-17 13:31 | IFA | AC |  | 95%
114272 | I491TC08-0CCAM91-028-001 | CCM LADLE TURRET FOUNDATION REINFORCEMENT PLAN (2/2) | 00 | 2019-05-15 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | SANO | 2015-08-17 13:31 | IFA | AC |  | 95%
114273 | I491TC08-0CCAM91-030-001 | CCM LADLE TURRET SECTIONS "5" TO "8" REINFORCEMENT | 00 | 2019-05-15 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | SANO | 2015-08-17 13:31 | IFA | AC |  | 95%
114274 | I491TC08-0CCAM91-031-001 | CCM LADLE TURRET SECTIONS "9" TO "12" REINFORCEMENT | 00 | 2019-05-15 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | SANO | 2015-08-17 13:31 | IFA | AC |  | 95%
134097 | I491TC08-0CCAM91-033-001 | CCM LADLE TURRET SLAB REINFORCEMENT PLAN AT LEVEL +8.970 TO +12.010 | 02 | 2018-08-26 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | SANO | 2018-09-01 12:34 | IFC | AFC | 100%
114276 | I491TC08-0CCAM91-034-001 | CCM LADLE TURRET COLUMNS C1 TO C3a REINF | 00 | 2019-05-15 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | SANO | 2015-08-17 13:31 | IFA | AC |  | 95%
130398 | I491TC08-0CCAM91-036-001 | CCM LADLE TURRET BEAM B1 TO B16a REINFORCEMENT | 01 | 2017-03-07 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | SANO | 2017-04-04 09:04 | IFC | AFC | 100%
130399 | I491TC08-0CCAM91-037-001 | CCM LADLE TURRET BEAM B17 TO B27 REINFORCEMENT & B.B.S. | 00 | 2017-03-07 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | SANO | 2017-04-04 09:13 | IFC | AFC | 100%
114291 | I491TC08-0CCAM91-042-001 | CCM RUN OUT CABIN COLUMNS REINF. DETAIL | 00 | 2015-08-29 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | SANO | 2015-08-31 09:56 | IFA | AC |  | 95%
114290 | I491TC08-0CCAM91-043-001 | CCM RUN OUT CABIN BEAMS & SLABS REINF. DETAIL | 00 | 2015-08-29 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | SANO | 2015-08-31 09:53 | IFA | AC |  | 95%
134095 | I491TC08-0CCAM91-044-001 | CCM BATTERY CHARGING ROOM FORMWORK DETAILS | 01 | 2018-08-18 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | SANO | 2018-09-01 12:26 | IFC | AFC | 100%
134098 | I491TC08-0CCAM91-046-001 | CCM SLAB ON GRADE PLAN & SECTION | 01 | 2018-08-26 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | SANO | 2018-09-01 12:34 | IFC | AC |  | 95%
130401 | I491TC08-0CCAM91-047-001 | CCM SLAB ON GRADE TYPE 1 TO 3 & FORMWORK SECTIONS | 00 | 2017-03-07 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | SANO | 2017-04-04 09:13 | IFC | AFC | 100%
130402 | I491TC08-0CCAM91-048-001 | CCM PITS AND CONDUITS LAYOUT PLAN & SECTION | 00 | 2017-03-07 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | SANO | 2017-04-04 09:13 | IFC | AFC | 100%
132972 | I491TC08-0CCAM91-050-001 | CCM STEEL STAIR ST-1 FOUNDATION & STEEL STRUCTURE | 02 | 2018-03-12 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | SANO | 2018-03-17 15:51 | IFC | AFC | 100%
132897 | I491TC08-0CCAM91-051-001 | CCM STEEL STAIR ST-2 FOUNDATION & STEEL STRUCTURE | 01 | 2018-02-17 10:01 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | SANO | 2018-02-17 10:01 | IFC | AFC | 100%
132898 | I491TC08-0CCAM91-052-001 | CCM STEEL STAIR ST-3 FOUNDATION & STEEL STRUCTURE | 01 | 2018-02-17 10:01 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | SANO | 2018-02-17 10:01 | IFC | AFC | 100%
133024 | I491TC08-0CCFF91-001-001 | CCM Complex Brick Layout | 01 | 2018-03-17 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2018-03-18 16:26 | IFI | OB | 100%
12763 | I491TC08-0CCSB91-004-016 | Ccm Foundation Tract-4 (3) Soil Excavation Plan | 02 | 2013-07-27 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12764 | I491TC08-0CCSB91-004-017 | Ccm Foundation Tract-4 (3) Soil Excavation Sections | 02 | 2013-07-27 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12765 | I491TC08-0CCSB91-004-018 | Ccm Foundation Tract-4 (3) Foundation Formwork Plan & Sections | 02 | 2013-07-27 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12766 | I491TC08-0CCSB91-004-019 | Ccm Foundation Tract-4 (3) Formwork Of Walls & Section | 02 | 2013-07-27 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12768 | I491TC08-0CCSB91-004-020 | Ccm Foundation Tract-4 (3) Foundation Reinforcement Plan & Section | 02 | 2013-07-27 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12769 | I491TC08-0CCSB91-004-021 | Ccm Foundation Tract-4 (3) Foundation Reinforcement Plan & Section | 02 | 2013-07-27 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12770 | I491TC08-0CCSB91-004-022 | Ccm Foundation Tract-4 (3) Reinforcement Of Walls & Section | 02 | 2013-07-27 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12771 | I491TC08-0CCSB91-004-023 | Ccm Foundation Tract-4 (3) Base Plate Layout Plan | 02 | 2013-07-27 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
12772 | I491TC08-0CCSB91-004-024 | Ccm Foundation Tract-4 (3) Anchor Bolt Detail | 02 | 2013-07-27 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
112985 | I491TC08-0CCSB91-005-001 | CCM Anchor Bolt 5018074R_001 | 00 | 2014-09-27 10:54 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Civil and Steel Structure | TAM | 2014-09-27 10:54 | IFI | OB | 100%
112986 | I491TC08-0CCSB91-006-001 | CCM Turret Anchor Bolt 8304454L_001 | 00 | 2014-09-27 10:55 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Civil and Steel Structure | TAM | 2014-09-27 10:55 | IFI | OB | 100%
135412 | I491TC08-0CCSB91-010-001 | CCM AREA PART 2 & 3 EXCAVATION PLAN | 01 | 2019-05-29 10:18 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | SANO | 2019-05-29 10:18 | IFC | AFC | 100%
135413 | I491TC08-0CCSB91-011-001 | CCM AREA PART 2 (COOLING BED) FORMWORK PLAN (1/2) | 01 | 2019-05-29 10:18 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | SANO | 2019-05-29 10:18 | IFC | AFC | 100%
135414 | I491TC08-0CCSB91-012-001 | CCM AREA PART 2 (COOLING BED) FORMWORK PLAN (2/2) | 01 | 2019-05-29 10:18 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | SANO | 2019-05-29 10:18 | IFC | AFC | 100%
135415 | I491TC08-0CCSB91-013-001 | CCM AREA PART 2 (COOLING BED) SECTION (1/2) | 01 | 2019-05-29 10:18 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | SANO | 2019-05-29 10:18 | IFC | AFC | 100%
135416 | I491TC08-0CCSB91-014-001 | CCM AREA PART 2 (COOLING BED) SECTION (2/2) | 01 | 2019-05-29 10:18 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | SANO | 2019-05-29 10:18 | IFC | AFC | 100%
135417 | I491TC08-0CCSB91-015-001 | CCM AREA PART 2 (COOLING BED) FOUND. & SLAB REINF. (1/2) | 01 | 2019-05-29 10:18 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | SANO | 2019-05-29 10:18 | IFC | AFC | 100%
135418 | I491TC08-0CCSB91-016-001 | CCM AREA PART 2 (COOLING BED) FOUND. & SLAB REINF. (2/2) | 01 | 2019-05-29 10:18 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | SANO | 2019-05-29 10:18 | IFC | AFC | 100%
135419 | I491TC08-0CCSB91-017-001 | CCM AREA PART 2 (COOLING BED) WALL REINFORCEMENT (1/2) | 01 | 2019-05-29 10:18 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | SANO | 2019-05-29 10:18 | IFC | AFC | 100%
135420 | I491TC08-0CCSB91-018-001 | CCM AREA PART 2 (COOLING BED) WALL REINFORCEMENT (2/2) | 01 | 2019-05-29 10:18 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | SANO | 2019-05-29 10:18 | IFC | AFC | 100%
135421 | I491TC08-0CCSB91-019-001 | CCM AREA PART 2 (COOLING BED) PEDESTAL REINF. (1/2) | 01 | 2019-05-29 10:18 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | SANO | 2019-05-29 10:18 | IFC | AFC | 100%
135422 | I491TC08-0CCSB91-020-001 | CCM AREA PART 2 (COOLING BED)PEDESTAL REINF. (2/2) | 01 | 2019-05-29 10:18 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | SANO | 2019-05-29 10:18 | IFC | AFC | 100%
135423 | I491TC08-0CCSB91-021-001 | CCM AREA PART 2 (COOLING BED) FORMWORK PLAN (1/2) | 01 | 2019-05-29 10:18 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | SANO | 2019-05-29 10:18 | IFC | AFC | 100%
135424 | I491TC08-0CCSB91-022-001 | CCM AREA PART 2 (COOLING BED) FORMWORK PLAN (2/2) | 01 | 2019-05-29 10:18 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | SANO | 2019-05-29 10:18 | IFC | AFC | 100%
135425 | I491TC08-0CCSB91-023-001 | CCM AREA PART 2 (COOLING BED) SECTION | 01 | 2019-05-29 10:18 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | SANO | 2019-05-29 10:18 | IFC | AFC | 100%
135426 | I491TC08-0CCSB91-024-001 | CCM AREA PART 2 (COOLING BED) REINFORCEMENT (1/2) | 01 | 2019-05-29 10:18 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | SANO | 2019-05-29 10:18 | IFC | AFC | 100%
135427 | I491TC08-0CCSB91-025-001 | CCM AREA PART 2 (COOLING BED) REINFORCEMENT (2/2) | 01 | 2019-05-29 10:18 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | SANO | 2019-05-29 10:18 | IFC | AFC | 100%
114362 | I491TC08-0CCTH01-001-001 | HY11 (TUNDISH PREP. & MTNC. AREA) TUNDISH TILTING STATION FORMWORK & REINFORCEMENT | 01 | 2015-09-08 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | SANO | 2015-09-10 09:43 | IFC | AFC | 100%
130912 | I491TC08-0CCTH02-001-001 | HY11 (TUNDISH PREP. & MTNC. AREA) TUNDISH STAND FOUNDATIONS FORMWORK & REINFORCEMENT | 02 | 2017-07-26 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | SANO | 2017-07-30 11:03 | IFC | AFC | 100%
114162 | I491TC08-0CCTH03-001-001 | HY11 (TUNDISH PREP. & MTNC. AREA) MOULD MAINTENANCE SHOP FORMWORK & REINFORCEMENT | 00 | 2015-07-05 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | SANO | 2015-07-11 09:46 | IFA | AC |  | 95%
114959 | I491TC08-0CCTK91-001-001 | SCALE PIT FOR CCM FOUNDATION FORMWORK PLAN 1-15 | 02 | 2016-02-28 13:12 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | APEC | 2016-02-28 13:12 | IFC | AFC | 100%
114960 | I491TC08-0CCTK91-001-002 | SCALE PIT FOR CCM FORMWORK SECTION 2-15 | 02 | 2016-02-28 13:12 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | APEC | 2016-02-28 13:12 | IFC | AFC | 100%
114961 | I491TC08-0CCTK91-001-003 | SCALE PIT FOR CCM FORMWORK SECTIONS 3-15 | 02 | 2016-02-28 13:12 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | APEC | 2016-02-28 13:12 | IFC | AFC | 100%
114962 | I491TC08-0CCTK91-001-004 | SCALE PIT FOR CCM FORMWORK PLAN AT EL. -10.850 & -7.250-6.550 & -4.550 4-15 | 02 | 2016-02-28 13:12 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | APEC | 2016-02-28 13:12 | IFC | AFC | 100%
114963 | I491TC08-0CCTK91-001-005 | SCALE PIT FOR CCM FORMWORK PLAN AT EL. -0.200 & -7.350 5-15 | 02 | 2016-02-28 13:12 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | APEC | 2016-02-28 13:12 | IFC | AFC | 100%
114964 | I491TC08-0CCTK91-001-006 | SCALE PIT FOR CCM FORMWORK WALL-1 TO 6 6-15 | 02 | 2016-02-28 13:12 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | APEC | 2016-02-28 13:12 | IFC | AFC | 100%
114965 | I491TC08-0CCTK91-001-007 | SCALE PIT FOR CCM FORMWORK WALL-7 TO 13 7-15 | 02 | 2016-02-28 13:12 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | APEC | 2016-02-28 13:12 | IFC | AFC | 100%
114966 | I491TC08-0CCTK91-001-008 | SCALE PIT FOR CCM REINFORCEMENT SECTION 8-15 | 02 | 2016-02-28 13:12 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | APEC | 2016-02-28 13:12 | IFC | AFC | 100%
114967 | I491TC08-0CCTK91-001-009 | SCALE PIT FOR CCM REINFORCEMENT SECTIONS 9-15 | 02 | 2016-02-28 13:12 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | APEC | 2016-02-28 13:12 | IFC | AFC | 100%
114968 | I491TC08-0CCTK91-001-010 | SCALE PIT FOR CCM REINFORCEMENT PLAN AT EL. -10.850 & -7.250 -6.550 & -4.550 10-15 | 02 | 2016-02-28 13:12 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | APEC | 2016-02-28 13:12 | IFC | AFC | 100%
114969 | I491TC08-0CCTK91-001-011 | SCALE PIT FOR CCM REINFORCEMENT PLAN AT EL. -0.200 & -7.350 11-15 | 02 | 2016-02-28 13:12 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | APEC | 2016-02-28 13:12 | IFC | AFC | 100%
114970 | I491TC08-0CCTK91-001-012 | SCALE PIT FOR CCM REINFORCEMENT WALL-1 TO 6 12-15 | 02 | 2016-02-28 13:12 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | APEC | 2016-02-28 13:12 | IFC | AFC | 100%
114971 | I491TC08-0CCTK91-001-013 | SCALE PIT FOR CCM REINFORCEMENT WALL-7 TO 13 13-15 | 02 | 2016-02-28 13:12 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | APEC | 2016-02-28 13:12 | IFC | AFC | 100%
114972 | I491TC08-0CCTK91-001-014 | SCALE PIT FOR CCM STAIR TYPE 1 & SECTIONS 14-15 | 02 | 2016-02-28 13:12 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | APEC | 2016-02-28 13:12 | IFC | AFC | 100%
114973 | I491TC08-0CCTK91-001-015 | SCALE PIT FOR CCM STAIR TYPE 1 & SECTIONS 15-15 | 00 | 2016-02-28 13:13 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | APEC | 2016-02-28 13:13 | IFC | AFC | 100%
114974 | I491TC08-0CCTK91-002-001 | CCM Scale Pit Piles Arrangment 1-5 | 02 | 2016-02-28 13:29 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | APEC | 2016-02-28 13:29 | IFC | AFC | 100%
114975 | I491TC08-0CCTK91-002-002 | CCM Scale Pit Piles Section 2-5 | 02 | 2016-02-28 13:29 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | APEC | 2016-02-28 13:29 | IFC | AFC | 100%
114976 | I491TC08-0CCTK91-002-003 | CCM Scale Pit Piles Formwork 3-5 | 02 | 2016-02-28 13:29 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | APEC | 2016-02-28 13:29 | IFC | AFC | 100%
114977 | I491TC08-0CCTK91-002-004 | CCM Scale Pit Piles Reinforcement Details 4-5 | 02 | 2016-02-28 13:29 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | APEC | 2016-02-28 13:29 | IFC | AFC | 100%
114978 | I491TC08-0CCTK91-002-005 | CCM Scale Pit Piles Piles Bar Bending Schedule 5-5 | 02 | 2016-02-28 13:29 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | APEC | 2016-02-28 13:29 | IFC | AFC | 100%
134101 | I491TC08-0CHEU09-001-001 | FOUNDATION PLAN FOR JIB CRANE AND CS MACHINE 1-3 | 03 | 2018-09-03 10:43 | Indeterminate | Drawing | Detail | Crane and Hiosts | Civil and Steel Structure | TAM | 2018-09-03 10:43 | IFC | AFC | 100%
134102 | I491TC08-0CHEU09-001-002 | FOUNDATION PLAN FOR JIB CRANE AND CS MACHINE 2-3 | 03 | 2018-09-03 10:43 | Indeterminate | Drawing | Detail | Crane and Hiosts | Civil and Steel Structure | TAM | 2018-09-03 10:43 | IFC | AFC | 100%
134103 | I491TC08-0CHEU09-001-003 | FOUNDATION PLAN FOR JIB CRANE AND CS MACHINE 3-3 | 03 | 2018-09-03 10:43 | Indeterminate | Drawing | Detail | Crane and Hiosts | Civil and Steel Structure | TAM | 2018-09-03 10:43 | IFC | AFC | 100%
134423 | I491TC08-0CHMI01-001-001 | CCM MAINTENANCE MOULD WORKSHOP FOUNDATION FOR JIB CRANE 1-3 | 03 | 2018-11-27 | Indeterminate | Drawing | Detail | Crane and Hiosts | Civil and Steel Structure | TAM | 2018-12-01 10:03 | IFC | AFC | 100%
134424 | I491TC08-0CHMI01-001-002 | CCM MAINTENANCE MOULD WORKSHOP FOUNDATION FOR JIB CRANE 2-3 | 03 | 2018-11-27 | Indeterminate | Drawing | Detail | Crane and Hiosts | Civil and Steel Structure | TAM | 2018-12-01 10:03 | IFC | AFC | 100%
133124 | I491TC08-0CHMI01-001-003 | CCM MAINTENANCE MOULD WORKSHOP FOUNDATION FOR JIB CRANE 3-3 | 02 | 2018-05-14 16:47 | Indeterminate | Drawing | Detail | Crane and Hiosts | Civil and Steel Structure | TAM | 2018-05-14 16:47 | IFC | AFC | 100%
12780 | I491TC08-0CPAM91-001-001 | Excavation Plan And Section Compressed Air Plant | 00 | 2013-10-28 | Indeterminate | Drawing | Detail | Compressed Air Production Plant | Civil and Steel Structure | TAM |  | IFA | A | 100%
12781 | I491TC08-0CPAM91-001-002 | Foundation Plan And Details Compressed Air Plant | 00 | 2013-10-28 | Indeterminate | Drawing | Detail | Compressed Air Production Plant | Civil and Steel Structure | TAM |  | IFA | A | 100%
12782 | I491TC08-0CPAM91-001-003 | Foundation Reinforcement And Details Compressed Air Plant | 00 | 2013-10-28 | Indeterminate | Drawing | Detail | Compressed Air Production Plant | Civil and Steel Structure | TAM |  | IFA | A | 100%
12783 | I491TC08-0CPAM91-002-001 | Basic Design Compressed Air Plant | 00 | 2013-10-28 | Indeterminate | Drawing | Basic | Compressed Air Production Plant | Civil and Steel Structure | TAM |  | IFA | A | 100%
113318 | I491TC08-0CPAM91-003-001 | Flooring Plan Compressed Air Plant 1-3 | 02 | 2015-02-03 | Indeterminate | Drawing | Detail | Compressed Air Production Plant | Civil and Steel Structure | TAM | 2015-02-10 15:45 | IFC | AC |  | 95%
113319 | I491TC08-0CPAM91-003-002 | Flooring Details Compressed Air Plant 2-3 | 02 | 2015-02-03 | Indeterminate | Drawing | Detail | Compressed Air Production Plant | Civil and Steel Structure | TAM | 2015-02-10 15:45 | IFC | AC |  | 95%
113320 | I491TC08-0CPAM91-003-003 | FLOORING PLAN REINFORCEMENT AND BAR BENDING SCHEDULE COMPRESSED AIR PLANT 3-3 | 00 | 2015-02-03 | Indeterminate | Drawing | Detail | Compressed Air Production Plant | Civil and Steel Structure | TAM | 2015-02-10 15:45 | IFC | AFC | 100%
112384 | I491TC08-0DTAM91-001-007 | FTP-MHS SUBSTATION COLUMNS PLAN | 01 | 2014-06-09 17:30 | Indeterminate | Drawing | Detail | Fume Treatment Plant Electrical Substation Building | Civil and Steel Structure | TAM | 2014-06-09 17:30 | IFC | AFC | 100%
112385 | I491TC08-0DTAM91-001-008 | FTP-MHS SUBSTATION FOUNDATION PLAN & SECTION | 01 | 2014-06-09 17:30 | Indeterminate | Drawing | Detail | Fume Treatment Plant Electrical Substation Building | Civil and Steel Structure | TAM | 2014-06-09 17:30 | IFC | AFC | 100%
112386 | I491TC08-0DTAM91-001-009 | FTP-MHS SUBSTATION FIRST FRAMING PLAN | 01 | 2014-06-09 17:30 | Indeterminate | Drawing | Detail | Fume Treatment Plant Electrical Substation Building | Civil and Steel Structure | TAM | 2014-06-09 17:30 | IFC | AFC | 100%
112387 | I491TC08-0DTAM91-001-010 | FTP-MHS SUBSTATION ROOF FRAMING PLAN | 01 | 2014-06-09 17:30 | Indeterminate | Drawing | Detail | Fume Treatment Plant Electrical Substation Building | Civil and Steel Structure | TAM | 2014-06-09 17:30 | IFC | AFC | 100%
131545 | I491TC08-0DTFF91-001-001 | Anchor for Settling Chamber Assembly | 02 | 2017-10-25 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | TAM | 2017-10-30 09:02 | IFI | OB | 100%
131546 | I491TC08-0DTFF91-002-001 | Anchor for Settling Chamber (Part 1) | 02 | 2017-10-25 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | TAM | 2017-10-30 09:14 | IFI | OB | 100%
131547 | I491TC08-0DTFF91-003-001 | Anchor for Settling Chamber (Part2) | 02 | 2017-10-25 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | TAM | 2017-10-30 09:14 | IFI | OB | 100%
12796 | I491TC08-0DTSB91-001-013 | F. T. P. Foundations Filter Dri & Natural Cooler Foundation Formwork Plan & Reinforcement Details | 00 | 2012-10-27 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | TAM |  | IFA | AC |  | 95%
12797 | I491TC08-0DTSB91-001-014 | F. T. P. Foundations Filter Dri & Natural Cooler Foundation Formwork Plan & Reinforcement Details | 00 | 2012-10-27 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | TAM |  | IFA | AC |  | 95%
12798 | I491TC08-0DTSB91-001-015 | F. T. P. Foundations Filter Dri & Natural Cooler Foundation Formwork Plan & Reinforcement Details | 00 | 2012-10-27 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | TAM |  | IFA | AC |  | 95%
12799 | I491TC08-0DTSB91-001-016 | F. T. P. Foundations Filter Dri & Natural Cooler Foundation Formwork Plan & Reinforcement Details | 00 | 2012-10-27 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | TAM |  | IFA | AC |  | 95%
12800 | I491TC08-0DTSB91-001-017 | F. T. P. Foundations Cyclon & Fan Foundation Formwork Plan | 00 | 2012-10-27 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | TAM |  | IFA | AC |  | 95%
12801 | I491TC08-0DTSB91-001-018 | F. T. P. Foundations Cyclon & Fan Foundation Formwork Plan | 00 | 2012-10-27 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | TAM |  | IFA | AC |  | 95%
113529 | I491TC08-0DTSB91-001-019 | Fume Treatment Plant General Plan List Of Drawings | 05 | 2015-05-27 13:23 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | TAM | 2015-05-27 13:23 | IFC | AC |  | 95%
113530 | I491TC08-0DTSB91-001-020 | Fume Treatment Plant General Plan | 05 | 2015-05-27 13:25 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | TAM | 2015-05-27 13:25 | IFC | AC |  | 95%
113531 | I491TC08-0DTSB91-001-021 | F. T. P. Foundations Part-1 | 05 | 2015-05-27 13:25 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | TAM | 2015-05-27 13:25 | IFC | AC |  | 95%
113532 | I491TC08-0DTSB91-001-022 | F. T. P. Foundations Stack & Fan Foundation Formwork Plan & Reinforcement Details | 05 | 2015-05-27 13:26 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | TAM | 2015-05-27 13:26 | IFC | AC |  | 95%
113533 | I491TC08-0DTSB91-001-023 | F. T. P. Foundations Stack & Fan Foundation Formwork Plan & Reinforcement Details | 05 | 2015-05-27 13:26 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | TAM | 2015-05-27 13:26 | IFC | AC |  | 95%
113534 | I491TC08-0DTSB91-001-024 | F. T. P. Foundations Stack & Fan Foundation Formwork Plan & Reinforcement Details | 05 | 2015-05-27 13:26 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | TAM | 2015-05-27 13:26 | IFC | AC |  | 95%
113535 | I491TC08-0DTSB91-001-025 | F. T. P. Foundations Stack & Fan Foundation Formwork Plan & Reinforcement Details | 05 | 2015-05-27 13:26 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | TAM | 2015-05-27 13:26 | IFC | AC |  | 95%
113536 | I491TC08-0DTSB91-001-026 | F. T. P. Foundations Filter & Silo Foundation Formwork Plan & Reinforcement Details | 05 | 2015-05-27 13:26 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | TAM | 2015-05-27 13:26 | IFC | AC |  | 95%
113537 | I491TC08-0DTSB91-001-027 | F. T. P. Foundations Filter & Silo Foundation Formwork Plan & Reinforcement Details | 05 | 2015-05-27 13:26 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | TAM | 2015-05-27 13:26 | IFC | AC |  | 95%
113538 | I491TC08-0DTSB91-001-028 | F. T. P. Foundations Filter & Silo Foundation Formwork Plan & Reinforcement Details | 05 | 2015-05-27 13:26 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | TAM | 2015-05-27 13:26 | IFC | AC |  | 95%
113539 | I491TC08-0DTSB91-001-029 | F. T. P. Foundations Filter & Silo Foundation Formwork Plan & Reinforcement Details | 05 | 2015-05-27 13:26 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | TAM | 2015-05-27 13:26 | IFC | AC |  | 95%
113540 | I491TC08-0DTSB91-001-030 | F. T. P. Foundations Filter & Silo Foundation Formwork Plan & Reinforcement Details | 05 | 2015-05-27 13:27 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | TAM | 2015-05-27 13:27 | IFC | AC |  | 95%
113541 | I491TC08-0DTSB91-001-031 | F. T. P. Foundations Filter & Silo Foundation Formwork Plan & Reinforcement Details | 05 | 2015-05-27 13:27 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | TAM | 2015-05-27 13:27 | IFC | AC |  | 95%
113542 | I491TC08-0DTSB91-001-032 | F. T. P. Foundations Mixing Chamber Foundation Formwork Plan & Reinforcement Details | 05 | 2015-05-27 13:27 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | TAM | 2015-05-27 13:27 | IFC | AC |  | 95%
113543 | I491TC08-0DTSB91-001-033 | F. T. P. Foundations Mixing Chamber Foundation Formwork Plan & Reinforcement Details | 05 | 2015-05-27 13:27 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | TAM | 2015-05-27 13:27 | IFC | AC |  | 95%
113544 | I491TC08-0DTSB91-001-034 | F. T. P. Foundations Mixing Chamber Foundation Formwork Plan & Reinforcement Details | 05 | 2015-05-27 13:27 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | TAM | 2015-05-27 13:27 | IFC | AC |  | 95%
113545 | I491TC08-0DTSB91-001-035 | F. T. P. Foundations Mixing Chamber Foundation Formwork Plan & Reinforcement Details | 05 | 2015-05-27 13:27 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | TAM | 2015-05-27 13:27 | IFC | AC |  | 95%
113546 | I491TC08-0DTSB91-001-036 | F. T. P. Foundations Filter Dry & Natural Cooler Foundation Formwork Plan & Reinforcement Details | 05 | 2015-05-27 13:27 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | TAM | 2015-05-27 13:27 | IFC | AC |  | 95%
113547 | I491TC08-0DTSB91-001-037 | F. T. P. Foundations Filter Dry & Natural Cooler Foundation Formwork Plan & Reinforcement Details | 05 | 2015-05-27 13:27 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | TAM | 2015-05-27 13:27 | IFC | AC |  | 95%
113548 | I491TC08-0DTSB91-001-038 | F. T. P. Foundations Filter Dry & Natural Cooler Foundation Formwork Plan & Reinforcement Details | 05 | 2015-05-27 13:27 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | TAM | 2015-05-27 13:27 | IFC | AC |  | 95%
113549 | I491TC08-0DTSB91-001-039 | F. T. P. Foundations Filter Dry & Natural Cooler Foundation Formwork Plan & Reinforcement Details | 05 | 2015-05-27 13:27 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | TAM | 2015-05-27 13:27 | IFC | AC |  | 95%
113560 | I491TC08-0DTSB91-001-040 | F. T. P. Foundations Filter Dry & Natural Cooler Foundation Formwork Plan & Reinforcement Details | 05 | 2015-05-27 13:44 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | TAM | 2015-05-27 13:44 | IFC | AC |  | 95%
112025 | I491TC08-0DTSB91-001-041 | F. T. P. FOUNDATIONS STACK & FAN FOUNDATION FORMWORK PLAN & REINFORCEMENT DETAILS | 00 | 2014-05-03 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | TAM | 2014-05-14 13:24 | IFC | AC |  | 95%
112026 | I491TC08-0DTSB91-001-042 | F. T. P. FOUNDATIONS STACK & FAN FOUNDATION FORMWORK PLAN & REINFORCEMENT DETAILS | 00 | 2014-05-03 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | TAM | 2014-05-14 13:24 | IFC | AC |  | 95%
112027 | I491TC08-0DTSB91-001-043 | F. T. P. FOUNDATIONS STACK & FAN FOUNDATION FORMWORK PLAN & REINFORCEMENT DETAILS | 00 | 2014-05-03 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | TAM | 2014-05-14 13:24 | IFC | AC |  | 95%
112028 | I491TC08-0DTSB91-001-044 | F. T. P. FOUNDATIONS STACK & FAN FOUNDATION FORMWORK PLAN & REINFORCEMENT DETAILS | 00 | 2014-05-03 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | TAM | 2014-05-14 13:24 | IFC | AC |  | 95%
112029 | I491TC08-0DTSB91-001-045 | F. T. P. FOUNDATIONS STACK & FAN FOUNDATION FORMWORK PLAN & REINFORCEMENT DETAILS | 00 | 2014-05-03 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | TAM | 2014-05-14 13:24 | IFC | AC |  | 95%
112030 | I491TC08-0DTSB91-001-046 | F. T. P. FOUNDATIONS STACK & FAN FOUNDATION FORMWORK PLAN & REINFORCEMENT DETAILS | 00 | 2014-05-03 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | TAM | 2014-05-14 13:24 | IFC | AC |  | 95%
112031 | I491TC08-0DTSB91-001-047 | F. T. P. FOUNDATIONS STACK & FAN FOUNDATION FORMWORK PLAN & REINFORCEMENT DETAILS | 00 | 2014-05-03 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | TAM | 2014-05-14 13:24 | IFC | AC |  | 95%
112032 | I491TC08-0DTSB91-001-048 | F. T. P. FOUNDATIONS FILTER DRY & NATURAL COOLER FOUNDATION FORMWORK PLAN & REINFORCEMENT DETAILS | 00 | 2014-05-03 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | TAM | 2014-05-14 13:24 | IFC | AC |  | 95%
112033 | I491TC08-0DTSB91-001-049 | F. T. P. FOUNDATIONS FILTER DRY & NATURAL COOLER FOUNDATION FORMWORK PLAN & REINFORCEMENT DETAILS | 00 | 2014-05-03 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | TAM | 2014-05-14 13:24 | IFC | AC |  | 95%
113554 | I491TC08-0DTSB91-001-050 | F. T. P. FOUNDATIONS SUPPORT COOLED DUCT FOUNDATION FORMWORK PLAN & REINFORCEMENT DETAILS | 01 | 2015-05-27 13:29 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | TAM | 2015-05-27 13:29 | IFC | AC |  | 95%
113555 | I491TC08-0DTSB91-001-051 | F. T. P. FOUNDATIONS SUPPORT COOLED DUCT FOUNDATION FORMWORK PLAN & REINFORCEMENT DETAILS | 01 | 2015-05-27 13:29 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | TAM | 2015-05-27 13:29 | IFC | AC |  | 95%
113556 | I491TC08-0DTSB91-001-052 | F. T. P. FOUNDATIONS SUPPORT COOLED DUCT FOUNDATION FORMWORK PLAN & REINFORCEMENT DETAILS | 01 | 2015-05-27 13:29 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | TAM | 2015-05-27 13:29 | IFC | AC |  | 95%
113557 | I491TC08-0DTSB91-001-053 | F. T. P. FOUNDATIONS SUPPORT COOLED DUCT FOUNDATION FORMWORK PLAN & REINFORCEMENT DETAILS | 01 | 2015-05-27 13:29 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | TAM | 2015-05-27 13:29 | IFC | AC |  | 95%
113558 | I491TC08-0DTSB91-001-054 | F. T. P. FOUNDATIONS HORIZONTAL CYCLON FOUNDATION FORMWORK PLAN & REINFORCEMENT DETAILS | 01 | 2015-05-27 13:44 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | TAM | 2015-05-27 13:44 | IFC | AC |  | 95%
113559 | I491TC08-0DTSB91-001-055 | F. T. P. FOUNDATIONS HORIZONTAL CYCLON FOUNDATION FORMWORK PLAN & REINFORCEMENT DETAILS | 01 | 2015-05-27 13:44 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | TAM | 2015-05-27 13:44 | IFC | AC |  | 95%
113561 | I491TC08-0DTSB91-001-056 | F. T. P. FOUNDATIONS MIXING CHAMBER FOUNDATION FORMWORK PLAN & REINFORCEMENT DETAILS | 00 | 2015-05-27 15:02 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | TAM | 2015-05-27 15:02 | IFC | AC |  | 95%
113562 | I491TC08-0DTSB91-001-057 | F. T. P. FOUNDATIONS HORIZONTAL CYCLON FOUNDATION FORMWORK PLAN & REINFORCEMENT DETAILS | 00 | 2015-05-27 15:02 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | TAM | 2015-05-27 15:02 | IFC | AC |  | 95%
113563 | I491TC08-0DTSB91-001-058 | F. T. P. FOUNDATIONS FILTER & SILO FOUNDATION FLOORING | 00 | 2015-05-27 15:02 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | TAM | 2015-05-27 15:02 | IFC | AC |  | 95%
113564 | I491TC08-0DTSB91-001-059 | F. T. P. FOUNDATIONS SUPPORT COOLED DUCT FOUNDATION FORMWORK PLAN & REINFORCEMENT DETAILS | 00 | 2015-05-27 15:02 | Indeterminate | Drawing | Detail | Fume Treatment Plant Electrical Substation Building | Civil and Steel Structure | TAM | 2015-05-27 15:02 | IFC | AC |  | 95%
132628 | I491TC08-0EAAA01-001-001 | STAIRCASE SOIL EXCAVATION PLAN FOR STAIR TYPE 4 | 02 | 2017-12-31 09:07 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2017-12-31 09:07 | IFC | AFC | 100%
132629 | I491TC08-0EAAA01-001-002 | STAIRCASE FOUNDATION FORMWORK & REINFORCEMENT PLAN FOR STAIR TYPE 2 | 02 | 2017-12-31 09:07 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2017-12-31 09:07 | IFC | AFC | 100%
132630 | I491TC08-0EAAA01-001-003 | STAIRCASE PEDESTAL & BASE PLATE DETAILS | 02 | 2017-12-31 09:07 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2017-12-31 09:07 | IFC | AFC | 100%
133898 | I491TC08-0EAAA02-001-001 | STAIRCASE 2 SOIL EXCAVATION PLAN FOR STAIR TYPE 2 1-10 | 02 | 2018-08-01 | Indeterminate | Drawing | Detail | Melt Shop | Civil and Steel Structure | TAM | 2018-08-07 09:05 | IFC | AFC | 100%
133899 | I491TC08-0EAAA02-001-002 | STAIRCASE 2 FOUNDATION FORMWORK & REINFORCEMENT PLAN 2-10 | 02 | 2018-08-01 | Indeterminate | Drawing | Detail | Melt Shop | Civil and Steel Structure | TAM | 2018-08-07 09:05 | IFC | AFC | 100%
133900 | I491TC08-0EAAA02-001-003 | STAIRCASE 2 STEEL STRUCTURE FRAME 3-10 | 02 | 2018-08-01 | Indeterminate | Drawing | Detail | Melt Shop | Civil and Steel Structure | TAM | 2018-08-07 09:05 | IFC | AFC | 100%
133901 | I491TC08-0EAAA02-001-004 | STAIRCASE 2 STEEL STRUCTURE SECTIONS 4-10 | 02 | 2018-08-01 | Indeterminate | Drawing | Detail | Melt Shop | Civil and Steel Structure | TAM | 2018-08-07 09:05 | IFC | AFC | 100%
133902 | I491TC08-0EAAA02-001-005 | STAIRCASE 2 COLUMN SPLICE DETAIL 5-10 | 02 | 2018-08-01 | Indeterminate | Drawing | Detail | Melt Shop | Civil and Steel Structure | TAM | 2018-08-07 09:05 | IFC | AFC | 100%
133903 | I491TC08-0EAAA02-001-006 | STAIRCASE 2 BRACING DETAILS 6-10 | 02 | 2018-08-01 | Indeterminate | Drawing | Detail | Melt Shop | Civil and Steel Structure | TAM | 2018-08-07 09:05 | IFC | AFC | 100%
133904 | I491TC08-0EAAA02-001-007 | STAIRCASE 2 ROOF DETAILS 7-10 | 02 | 2018-08-01 | Indeterminate | Drawing | Detail | Melt Shop | Civil and Steel Structure | TAM | 2018-08-07 09:05 | IFC | AFC | 100%
133905 | I491TC08-0EAAA02-001-008 | STAIRCASE 2 ROOF DETAILS 8-10 | 02 | 2018-08-01 | Indeterminate | Drawing | Detail | Melt Shop | Civil and Steel Structure | TAM | 2018-08-07 09:05 | IFC | AFC | 100%
133906 | I491TC08-0EAAA02-001-009 | STAIRCASE 2 HAND RAIL DETAILS 9-10 | 02 | 2018-08-01 | Indeterminate | Drawing | Detail | Melt Shop | Civil and Steel Structure | TAM | 2018-08-07 09:05 | IFC | AFC | 100%
133907 | I491TC08-0EAAA02-001-010 | STAIRCASE 2 GRATING DETAILS 10-10 | 02 | 2018-08-01 | Indeterminate | Drawing | Detail | Melt Shop | Civil and Steel Structure | TAM | 2018-08-07 09:05 | IFC | AFC | 100%
134068 | I491TC08-0EAAA03-001-001 | STAIRCASE 3 SOIL EXCAVATION PLAN FOR STAIR TYPE 3 1-10 | 01 | 2018-08-08 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2018-08-21 11:22 | IFC | AFC | 100%
134069 | I491TC08-0EAAA03-001-002 | STAIRCASE 3 FOUNDATION FORMWORK & REINFORCEMENT PLAN 2-10 | 01 | 2018-08-08 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2018-08-21 11:22 | IFC | AFC | 100%
134070 | I491TC08-0EAAA03-001-003 | STAIRCASE 3 STEEL STRUCTURE FRAME 3-10 | 01 | 2018-08-08 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2018-08-21 11:23 | IFC | AFC | 100%
134071 | I491TC08-0EAAA03-001-004 | STAIRCASE 3 STEEL STRUCTURE SECTIONS 4-10 | 01 | 2018-08-08 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2018-08-21 11:23 | IFC | AFC | 100%
134072 | I491TC08-0EAAA03-001-005 | STAIRCASE 3 CONNECTION DETAILS 5-10 | 01 | 2018-08-08 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2018-08-21 11:23 | IFC | AFC | 100%
134073 | I491TC08-0EAAA03-001-006 | STAIRCASE 3 CONNECTION DETAILS 6-10 | 01 | 2018-08-08 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2018-08-21 11:23 | IFC | AFC | 100%
134074 | I491TC08-0EAAA03-001-007 | STAIRCASE 3 CONNECTION DETAILS 7-10 | 01 | 2018-08-08 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2018-08-21 11:23 | IFC | AFC | 100%
134075 | I491TC08-0EAAA03-001-008 | STAIRCASE 3 COLUMN SPLICE DETAIL 8-10 | 01 | 2018-08-08 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2018-08-21 11:23 | IFC | AFC | 100%
134076 | I491TC08-0EAAA03-001-009 | STAIRCASE 3 GRATING DETAILS 9-10 | 01 | 2018-08-08 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2018-08-21 11:23 | IFC | AFC | 100%
134077 | I491TC08-0EAAA03-001-010 | STAIRCASE 3 HAND RAIL DETAILS 10-10 | 01 | 2018-08-08 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2018-08-21 11:23 | IFC | AFC | 100%
134140 | I491TC08-0EAAA04-001-001 | STAIRCASE 4 (North Side) SOIL EXCAVATION PLAN FOR STAIR TYPE 4 (1-10) | 01 | 2018-09-05 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2018-09-09 15:01 | IFC | AFC | 100%
134141 | I491TC08-0EAAA04-001-002 | STAIRCASE 4 FOUNDATION FORMWORK & REINFORCEMENT PLAN (2-10) | 01 | 2018-09-05 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2018-09-09 15:01 | IFC | AFC | 100%
134143 | I491TC08-0EAAA04-001-004 | STAIRCASE 4 STEEL STRUCTURE SECTIONS (4-10) | 01 | 2018-09-05 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2018-09-09 15:01 | IFC | AFC | 100%
134144 | I491TC08-0EAAA04-001-005 | STAIRCASE 4 CONNECTION DETAILS (5-10) | 01 | 2018-09-05 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2018-09-09 15:01 | IFC | AFC | 100%
134145 | I491TC08-0EAAA04-001-006 | STAIRCASE 4 CONNECTION DETAILS (6-10) | 01 | 2018-09-05 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2018-09-09 15:01 | IFC | AFC | 100%
134146 | I491TC08-0EAAA04-001-007 | STAIRCASE 4 CONNECTION DETAILS (7-10) | 01 | 2018-09-05 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2018-09-09 15:01 | IFC | AFC | 100%
134147 | I491TC08-0EAAA04-001-008 | STAIRCASE 4 COLUMN SPLICE DETAIL (8-10) | 01 | 2018-09-05 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2018-09-09 15:01 | IFC | AFC | 100%
134148 | I491TC08-0EAAA04-001-009 | STAIRCASE 4 GRATING DETAILS (9-10) | 01 | 2018-09-05 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2018-09-09 15:01 | IFC | AFC | 100%
134149 | I491TC08-0EAAA04-001-010 | STAIRCASE 4 HAND RAIL DETAILS (10-10) | 01 | 2018-09-05 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2018-09-09 15:01 | IFC | AFC | 100%
130798 | I491TC08-0EAAA91-001-001 | Melt Shop Main Building Foundation Plan Formwork | 01 | 2017-07-11 | Indeterminate | Drawing | Basic | Melt Shop Main Building | Civil and Steel Structure | APEC | 2017-07-22 09:14 | IFC | AC |  | 95%
130799 | I491TC08-0EAAA91-001-002 | Melt Shop Main Building Foundation Plan Formwork | 01 | 2017-07-11 | Indeterminate | Drawing | Basic | Melt Shop Main Building | Civil and Steel Structure | APEC | 2017-07-22 09:14 | IFC | AC |  | 95%
130800 | I491TC08-0EAAA91-001-003 | Melt Shop Main Building Foundation F1 & F2 Formwork | 01 | 2017-07-11 | Indeterminate | Drawing | Basic | Melt Shop Main Building | Civil and Steel Structure | APEC | 2017-07-22 09:14 | IFC | AC |  | 95%
130801 | I491TC08-0EAAA91-001-004 | Melt Shop Main Building Foundation F4 & F5 Formwork | 01 | 2017-07-11 | Indeterminate | Drawing | Basic | Melt Shop Main Building | Civil and Steel Structure | APEC | 2017-07-22 09:14 | IFC | AC |  | 95%
130802 | I491TC08-0EAAA91-001-005 | Melt Shop Main Building Foundation F6 & F7 Formwork | 01 | 2017-07-11 | Indeterminate | Drawing | Basic | Melt Shop Main Building | Civil and Steel Structure | APEC | 2017-07-22 09:14 | IFC | AFC | 100%
130803 | I491TC08-0EAAA91-001-006 | Melt Shop Main Building Foundation F8 & F9 Formwork | 01 | 2017-07-11 | Indeterminate | Drawing | Basic | Melt Shop Main Building | Civil and Steel Structure | APEC | 2017-07-22 09:14 | IFC | AFC | 100%
130804 | I491TC08-0EAAA91-001-007 | Melt Shop Main Building Foundation F10 & F11 Formwork | 01 | 2017-07-11 | Indeterminate | Drawing | Basic | Melt Shop Main Building | Civil and Steel Structure | APEC | 2017-07-22 09:14 | IFC | AFC | 100%
130805 | I491TC08-0EAAA91-001-008 | Melt Shop Main Building Foundation F12 & F13 Formwork | 01 | 2017-07-11 | Indeterminate | Drawing | Basic | Melt Shop Main Building | Civil and Steel Structure | APEC | 2017-07-22 09:14 | IFC | AFC | 100%
12851 | I491TC08-0EAAA91-002-005 | Melt Shop Foundation Layout Plan At Axis "A" | 04 | 2012-04-21 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFA | AFC | 100%
12852 | I491TC08-0EAAA91-002-006 | Melt Shop Foundation Layout Plan At Axis "B" | 02 | 2012-04-21 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFA | AFC | 100%
12853 | I491TC08-0EAAA91-002-007 | Melt Shop Foundation Layout Plan At Axis "C" & "D" | 02 | 2012-04-21 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFA | AFC | 100%
12841 | I491TC08-0EAAA91-002-010 | Melt Shop Main Bulding Foundation F-8 Formwork & Reinforcement | 03 | 2012-05-26 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFA | AFC | 100%
12842 | I491TC08-0EAAA91-002-011 | Melt Shop Main Bulding Foundation Layout Plan At Axis "C"&"D" | 04 | 2012-08-15 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFA | AFC | 100%
12843 | I491TC08-0EAAA91-002-012 | Melt Shop Main Bulding Tie Beam Reinforcement Section | 04 | 2012-08-15 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFA | AFC | 100%
12844 | I491TC08-0EAAA91-002-013 | Melt Shop Main Bulding Foundation F-9 Formwork & Reinforcement | 03 | 2012-08-15 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFA | AFC | 100%
12845 | I491TC08-0EAAA91-002-014 | Melt Shop Main Bulding Foundation F-13 Formwork & Reinforcement | 00 | 2012-08-15 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFA | AFC | 100%
130934 | I491TC08-0EAAA91-002-015 | MELT SHOP MAIN BULDING FOUNDATION LAYOUT PLAN AT AXIS "A" SHEET 1 1-23 | 08 | 2017-08-01 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2017-08-02 09:59 | IFC | AFC | 100%
130935 | I491TC08-0EAAA91-002-016 | MELT SHOP MAIN BULDING FOUNDATION F-4 & TIE BEAM FORMWORK & REINFORCEMENT 4-23 | 08 | 2017-08-01 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2017-08-02 09:59 | IFC | AFC | 100%
134150 | I491TC08-0EAAA91-005-001 | Melt Shop Main Building Electric Arc Furnace Foundation Excavation | 01 | 2018-09-05 | Indeterminate | Miscellaneous(MISC) | Detail | Electric Arc Furnace | Civil and Steel Structure | TAM | 2018-09-10 09:26 | IFC | AFC | 100%
134924 | I491TC08-0EAAM01-001-001 | SMP LAVATORY ( SOUTH-WEST) 1-9 | 01 | 2018-12-31 12:29 | Indeterminate | Drawing | Detail | Melt Shop | Civil and Steel Structure | TAM | 2018-12-31 12:29 | IFC | AFC | 100%
134923 | I491TC08-0EAAM01-001-002 | SMP LAVATORY ( SOUTH-WEST) 2-9 | 01 | 2018-12-31 12:29 | Indeterminate | Drawing | Detail | Melt Shop | Civil and Steel Structure | TAM | 2018-12-31 12:29 | IFC | AFC | 100%
134922 | I491TC08-0EAAM01-001-003 | SMP LAVATORY ( SOUTH-WEST) 3-9 | 01 | 2018-12-31 12:29 | Indeterminate | Drawing | Detail | Melt Shop | Civil and Steel Structure | TAM | 2018-12-31 12:29 | IFC | AFC | 100%
134921 | I491TC08-0EAAM01-001-004 | SMP LAVATORY ( SOUTH-WEST) 4-9 | 01 | 2018-12-31 12:29 | Indeterminate | Drawing | Detail | Melt Shop | Civil and Steel Structure | TAM | 2018-12-31 12:29 | IFC | AFC | 100%
134920 | I491TC08-0EAAM01-001-005 | SMP LAVATORY ( SOUTH-WEST) 5-9 | 01 | 2018-12-31 12:29 | Indeterminate | Drawing | Detail | Melt Shop | Civil and Steel Structure | TAM | 2018-12-31 12:29 | IFC | AFC | 100%
134919 | I491TC08-0EAAM01-001-006 | SMP LAVATORY ( SOUTH-WEST) 6-9 | 01 | 2018-12-31 12:29 | Indeterminate | Drawing | Detail | Melt Shop | Civil and Steel Structure | TAM | 2018-12-31 12:29 | IFC | AFC | 100%
134918 | I491TC08-0EAAM01-001-007 | SMP LAVATORY ( SOUTH-WEST) 7-9 | 01 | 2018-12-31 12:28 | Indeterminate | Drawing | Detail | Melt Shop | Civil and Steel Structure | TAM | 2018-12-31 12:28 | IFC | AFC | 100%
134917 | I491TC08-0EAAM01-001-008 | SMP LAVATORY ( SOUTH-WEST) 8-9 | 01 | 2018-12-31 12:28 | Indeterminate | Drawing | Detail | Melt Shop | Civil and Steel Structure | TAM | 2018-12-31 12:28 | IFC | AFC | 100%
134916 | I491TC08-0EAAM01-001-009 | SMP LAVATORY ( SOUTH-WEST) 9-9 | 01 | 2018-12-31 12:28 | Indeterminate | Drawing | Detail | Melt Shop | Civil and Steel Structure | TAM | 2018-12-31 12:28 | IFI | AFC | 100%
130555 | I491TC08-0EAFB91-001-001 | Eaf Platform Foundation Soil Excavation Plan & Section | 04 | 2017-05-07 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Civil and Steel Structure | APEC | 2017-05-09 13:47 | IFC | AC |  | 95%
130556 | I491TC08-0EAFB91-001-002 | Eaf Platform Foundation Formwork Plan | 04 | 2017-05-07 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Civil and Steel Structure | APEC | 2017-05-09 13:47 | IFC | AC |  | 95%
130557 | I491TC08-0EAFB91-001-003 | Eaf Platform Foundation Sections | 04 | 2017-05-07 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Civil and Steel Structure | APEC | 2017-05-09 13:47 | IFC | AC |  | 95%
130558 | I491TC08-0EAFB91-001-004 | Eaf Platform Foundation Typical Reinforcement Plans & Sections | 04 | 2017-05-07 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Civil and Steel Structure | APEC | 2017-05-09 13:47 | IFC | AC |  | 95%
130559 | I491TC08-0EAFB91-001-005 | Eaf Platform Foundation Add Bar Reinforcement Plans (X Direction) | 04 | 2017-05-07 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Civil and Steel Structure | APEC | 2017-05-09 13:47 | IFC | AC |  | 95%
130560 | I491TC08-0EAFB91-001-006 | Eaf Platform Foundation Add Bar Reinforcement Plans (Y Direction) | 04 | 2017-05-07 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Civil and Steel Structure | APEC | 2017-05-09 13:47 | IFC | AC |  | 95%
130561 | I491TC08-0EAFB91-001-007 | Eaf Platform Foundation Formwork & Reinforcement Of Ped-1 & Ped-2 | 04 | 2017-05-07 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Civil and Steel Structure | APEC | 2017-05-09 13:48 | IFC | AC |  | 95%
130562 | I491TC08-0EAFB91-001-008 | Eaf Platform Foundation Formwork & Reinforcement Of Ped-3 & Ped-4 | 04 | 2017-05-07 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Civil and Steel Structure | APEC | 2017-05-09 13:48 | IFC | AC |  | 95%
130563 | I491TC08-0EAFB91-001-009 | Eaf Platform Foundation Formwork & Reinforcement Of Ped-5 & Ped-6 | 04 | 2017-05-07 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Civil and Steel Structure | APEC | 2017-05-09 13:48 | IFC | AC |  | 95%
130564 | I491TC08-0EAFB91-001-010 | Eaf Platform Foundation Formwork & Reinforcement Of Ped-7 & Ped8 | 04 | 2017-05-07 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Civil and Steel Structure | APEC | 2017-05-09 13:48 | IFC | AC |  | 95%
130565 | I491TC08-0EAFB91-001-011 | Eaf Platform Foundation Formwork & Reinforcement Of Ped-9 & Ped-10 | 04 | 2017-05-07 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Civil and Steel Structure | APEC | 2017-05-09 13:48 | IFC | AC |  | 95%
130566 | I491TC08-0EAFB91-001-012 | Eaf Platform Foundation Formwork & Reinforcement Of Ped-11 & Ped-12 | 04 | 2017-05-07 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Civil and Steel Structure | APEC | 2017-05-09 13:48 | IFC | AC |  | 95%
130567 | I491TC08-0EAFB91-001-013 | Eaf Platform Foundation Formwork & Reinforcement Of Ped-13 | 04 | 2017-05-07 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Civil and Steel Structure | APEC | 2017-05-09 13:48 | IFC | AC |  | 95%
130568 | I491TC08-0EAFB91-001-014 | Eaf Platform Foundation Anchor Bolt Details | 04 | 2017-05-07 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Civil and Steel Structure | APEC | 2017-05-09 13:48 | IFC | AC |  | 95%
132677 | I491TC08-0EAFF91-001-001 | EAF-Slag Dumping Area | 07 | 2018-01-10 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | TAM | 2018-01-13 13:13 | IFC | AC |  | 95%
134954 | I491TC08-0EAFF91-003-001 | Schematic of refractory bricks and related supports for Meltshop columns | 01 | 2019-01-09 | Indeterminate | Drawing | Detail | Melt Shop | Mechanical | TAM | 2019-01-12 11:15 | IFI | OB | 100%
12992 | I491TC08-0EAFM91-001-063 | Electric Arc Furnac (Eaf) Foundation Bar Bending Scdhule | 04 | 2012-11-14 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM |  | IFC | AFC | 100%
134392 | I491TC08-0EASM02-001-001 | EAF SLAG DUMPING GALLERY 1-7 | 02 | 2018-11-15 10:17 | Indeterminate | Drawing | Detail | Slag Yard | Civil and Steel Structure | TAM | 2018-11-15 10:17 | IFC | AFC | 100%
134391 | I491TC08-0EASM02-001-002 | EAF SLAG DUMPING GALLERY 2-7 | 02 | 2018-11-15 10:17 | Indeterminate | Drawing | Detail | Slag Yard | Civil and Steel Structure | TAM | 2018-11-15 10:17 | IFC | AFC | 100%
134390 | I491TC08-0EASM02-001-003 | EAF SLAG DUMPING GALLERY 3-7 | 02 | 2018-11-15 10:17 | Indeterminate | Drawing | Detail | Slag Yard | Civil and Steel Structure | TAM | 2018-11-15 10:17 | IFC | AFC | 100%
134389 | I491TC08-0EASM02-001-004 | EAF SLAG DUMPING GALLERY 4-7 | 02 | 2018-11-15 10:17 | Indeterminate | Drawing | Detail | Slag Yard | Civil and Steel Structure | TAM | 2018-11-15 10:17 | IFC | AFC | 100%
134388 | I491TC08-0EASM02-001-005 | EAF SLAG DUMPING GALLERY 5-7 | 02 | 2018-11-15 10:17 | Indeterminate | Drawing | Detail | Slag Yard | Civil and Steel Structure | TAM | 2018-11-15 10:17 | IFC | AFC | 100%
134387 | I491TC08-0EASM02-001-006 | EAF SLAG DUMPING GALLERY 6-7 | 02 | 2018-11-15 10:17 | Indeterminate | Drawing | Detail | Slag Yard | Civil and Steel Structure | TAM | 2018-11-15 10:17 | IFC | AFC | 100%
134386 | I491TC08-0EASM02-001-007 | EAF SLAG DUMPING GALLERY 7-7 | 02 | 2018-11-15 10:17 | Indeterminate | Drawing | Detail | Slag Yard | Civil and Steel Structure | TAM | 2018-11-15 10:17 | IFC | AFC | 100%
134398 | I491TC08-0EASM03-001-001 | EAF SLAG COOLING PIT 1-6 | 02 | 2018-11-15 10:18 | Indeterminate | Drawing | Detail | Slag Yard | Civil and Steel Structure | TAM | 2018-11-15 10:18 | IFC | AFC | 100%
134397 | I491TC08-0EASM03-001-002 | EAF SLAG COOLING PIT 2-6 | 02 | 2018-11-15 10:18 | Indeterminate | Drawing | Detail | Slag Yard | Civil and Steel Structure | TAM | 2018-11-15 10:18 | IFC | AFC | 100%
134396 | I491TC08-0EASM03-001-003 | EAF SLAG COOLING PIT 3-6 | 02 | 2018-11-15 10:18 | Indeterminate | Drawing | Detail | Slag Yard | Civil and Steel Structure | TAM | 2018-11-15 10:18 | IFC | AFC | 100%
134395 | I491TC08-0EASM03-001-004 | EAF SLAG COOLING PIT 4-6 | 02 | 2018-11-15 10:18 | Indeterminate | Drawing | Detail | Slag Yard | Civil and Steel Structure | TAM | 2018-11-15 10:18 | IFC | AFC | 100%
134394 | I491TC08-0EASM03-001-005 | EAF SLAG COOLING PIT 5-6 | 02 | 2018-11-15 10:18 | Indeterminate | Drawing | Detail | Slag Yard | Civil and Steel Structure | TAM | 2018-11-15 10:18 | IFC | AFC | 100%
134249 | I491TC08-0EASM03-001-006 | EAF SLAG COOLING PIT 6-6 | 01 | 2018-10-02 09:08 | Indeterminate | Drawing | Detail | Slag Yard | Civil and Steel Structure | TAM | 2018-10-02 09:08 | IFC | AC |  | 95%
133055 | I491TC08-0EASM91-001-001 | MELT SHOP AREA EAF & LF TEMPORARY SLAG YARDS EAF SLAG YARD PLAN & SECTION '1, & DETAIL 'A, | 01 | 2018-04-11 | Indeterminate | Drawing | Detail | Slag Yard | Civil and Steel Structure | TAM | 2018-04-16 09:25 | IFC | AC |  | 95%
133054 | I491TC08-0EASM91-002-001 | MELT SHOP AREA EAF & LF TEMPORARY SLAG YARDS LF SLAG YARD PLAN & SECTIONS '2, '3, & DETAILS 'B, 'C, | 01 | 2018-04-11 | Indeterminate | Drawing | Detail | Slag Yard | Civil and Steel Structure | TAM | 2018-04-16 09:25 | IFC | AC |  | 95%
133053 | I491TC08-0EASM91-003-001 | MELT SHOP AREA EAF & LF TEMPORARY SLAG YARDS EAF SLAG YARD REINFORCEMENT PLAN & SECTION '1, | 01 | 2018-04-11 | Indeterminate | Drawing | Detail | Slag Yard | Civil and Steel Structure | TAM | 2018-04-16 09:25 | IFC | AC |  | 95%
133052 | I491TC08-0EASM91-004-001 | MELT SHOP AREA EAF & LF TEMPORARY SLAG YARDS EAF SLAG YARD REINFORCEMENT SECTIONS '2,3, & PIT | 01 | 2018-04-11 | Indeterminate | Drawing | Detail | Slag Yard | Civil and Steel Structure | TAM | 2018-04-16 09:24 | IFC | AC |  | 95%
133056 | I491TC08-0EASM91-005-001 | MELT SHOP AREA EAF & LF TEMPORARY SLAG YARDS LF SLAG YARD REINFORCEMENT PLAN | 01 | 2018-04-11 | Indeterminate | Drawing | Detail | Slag Yard | Civil and Steel Structure | TAM | 2018-04-16 09:25 | IFC | AC |  | 95%
133057 | I491TC08-0EASM91-006-001 | MELT SHOP AREA EAF & LF TEMPORARY SLAG YARDS LF SLAG YARD REINFORCEMENT PLAN | 01 | 2018-04-11 | Indeterminate | Drawing | Detail | Slag Yard | Civil and Steel Structure | TAM | 2018-04-16 09:25 | IFC | AC |  | 95%
132999 | I491TC08-0LFFB91-002-001 | LF AIR HANDELING UNIT SUPPORT 1-4 | 07 | 2018-03-17 | Indeterminate | Drawing | Detail | Ladle Furnace | Civil and Steel Structure | TAM | 2018-03-18 10:05 | IFC | AFC | 100%
133116 | I491TC08-0LFFB91-002-002 | LF AIR HANDELING UNIT SUPPORT 2-4 | 08 | 2018-05-06 | Indeterminate | Drawing | Detail | Ladle Furnace | Civil and Steel Structure | TAM | 2018-05-07 13:52 | IFC | AFC | 100%
133000 | I491TC08-0LFFB91-002-003 | LF AIR HANDELING UNIT SUPPORT 3-4 | 07 | 2018-03-17 | Indeterminate | Drawing | Detail | Ladle Furnace | Civil and Steel Structure | TAM | 2018-03-18 10:05 | IFC | AFC | 100%
132998 | I491TC08-0LFFB91-002-004 | LF AIR HANDELING UNIT SUPPORT 4-4 | 05 | 2018-03-17 | Indeterminate | Drawing | Detail | Ladle Furnace | Civil and Steel Structure | TAM | 2018-03-18 10:05 | IFC | AFC | 100%
131123 | I491TC08-0LFFF91-001-001 | INSULATION FOR BELOW OF LF PLATFORM | 01 | 2017-08-28 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | APEC | 2017-08-30 14:33 | IFI | OB | 100%
134953 | I491TC08-0LFSM91-001-001 | LADLE SLAG DUMPING AREA WALL REFRACTORY | 00 | 2019-01-09 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | TAM | 2019-01-12 11:13 | IFA | AC |  | 95%
129301 | I491TC08-0MDCV05-001-001 | OUTDOOR FERROALLOY MHS PART - 6 FOUNDATION PLAN & DET. 1-2 | 02 | 2016-08-20 11:24 | Indeterminate | Drawing | Detail | Material Handling | Civil and Steel Structure | TAM | 2016-08-20 11:24 | IFC | AC |  | 95%
111496 | I491TC08-0MDCV09-001-001 | BIN CHARGHIMG (DRI) PART - 7 FOUNDATION PLAN & DET. 1-3 | 00 | 2014-01-08 | Indeterminate | Drawing | Detail | Material Handling | Civil and Steel Structure | IKS | 2014-04-22 12:09 | IFA | AC |  | 95%
111497 | I491TC08-0MDCV09-001-002 | BIN CHARGHIMG (DRI) PART - 7 FOUNDATION DET. 2-3 | 00 | 2014-01-08 | Indeterminate | Drawing | Detail | Material Handling | Civil and Steel Structure | IKS | 2014-04-22 12:09 | IFA | AC |  | 95%
111498 | I491TC08-0MDCV09-001-003 | BIN CHARGHIMG (DRI) PART - 7 FOUNDATION DET. 3-3 | 00 | 2014-01-08 | Indeterminate | Drawing | Detail | Material Handling | Civil and Steel Structure | IKS | 2014-04-22 12:09 | IFA | AC |  | 95%
135187 | I491TC08-0MDSI01-001-001 | LIME & CARBONE INJ. SILOS FOUNDATION FORMWORK PLANS, SECTIONS & ANCHOR BOLT DET. | 03 | 2019-03-18 12:38 | Indeterminate | Drawing | Detail | Material Handling | Civil and Steel Structure | TAM | 2019-03-18 12:38 | IFC | AC |  | 95%
135188 | I491TC08-0MDSI01-002-001 | LIME & CARBONE INJ. SILOS FOUNDATION REINFORCEMENT REINFORCEMENT DETAILS | 03 | 2019-03-18 12:38 | Indeterminate | Drawing | Detail | Material Handling | Civil and Steel Structure | TAM | 2019-03-18 12:38 | IFC | AC |  | 95%
130601 | I491TC08-0MDTT03-001-001 | EMERGENCY PIT FOR DRI CONVEYOR TRANSFER TOWER | 01 | 2017-05-10 | Indeterminate | Drawing | Detail | Material Handling | Civil and Steel Structure | TAM | 2017-05-14 17:14 | IFC | AFC | 100%
112406 | I491TC08-0MMAM91-001-006 | WTP SUBSTATION COLUMNS PLAN | 01 | 2014-06-12 11:04 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System Substation Building | Civil and Steel Structure | TAM | 2014-06-12 11:04 | IFC | AFC | 100%
112405 | I491TC08-0MMAM91-001-007 | WTP SUBSTATION FOUNDATION PLAN & SECTION | 01 | 2014-06-12 11:04 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System Substation Building | Civil and Steel Structure | TAM | 2014-06-12 11:04 | IFC | AFC | 100%
112404 | I491TC08-0MMAM91-001-008 | WTP SUBSTATION FIRST FRAMING PLAN | 01 | 2014-06-12 11:04 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System Substation Building | Civil and Steel Structure | TAM | 2014-06-12 11:04 | IFC | AFC | 100%
112403 | I491TC08-0MMAM91-001-009 | WTP SUBSTATION ROOF FRAMING PLAN | 01 | 2014-06-12 11:04 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System Substation Building | Civil and Steel Structure | TAM | 2014-06-12 11:04 | IFC | AFC | 100%
112521 | I491TC08-0MMAM91-003-001 | WTP SUBSTATION EXCAVATION PLAN | 00 | 2014-07-07 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System Substation Building | Civil and Steel Structure | TAM | 2014-07-09 13:22 | IFA | A | 100%
112522 | I491TC08-0MMAM91-003-002 | WTP SUBSTATION FOUNDATION PLAN & DETAILS | 00 | 2014-07-07 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System Substation Building | Civil and Steel Structure | TAM | 2014-07-09 13:22 | IFA | A | 100%
112523 | I491TC08-0MMAM91-003-003 | WTP SUBSTATION FOUNDATION PLAN & DETAILS | 00 | 2014-07-07 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System Substation Building | Civil and Steel Structure | TAM | 2014-07-09 13:22 | IFA | A | 100%
112524 | I491TC08-0MMAM91-003-004 | WTP SUBSTATION COLUMNS PLAN RETAINING WALLS PLAN | 00 | 2014-07-07 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System Substation Building | Civil and Steel Structure | TAM | 2014-07-09 13:22 | IFA | A | 100%
112525 | I491TC08-0MMAM91-003-005 | WTP SUBSTATION SLAB DETAIL | 00 | 2014-07-07 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System Substation Building | Civil and Steel Structure | TAM | 2014-07-09 13:22 | IFA | A | 100%
112529 | I491TC08-0MMAM91-003-006 | WTP SUBSTATION RETAINING WALLS DETAIL | 00 | 2014-07-07 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System Substation Building | Civil and Steel Structure | TAM | 2014-07-09 13:22 | IFA | A | 100%
112526 | I491TC08-0MMAM91-003-007 | WTP SUBSTATION SLAB DETAIL | 00 | 2014-07-07 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System Substation Building | Civil and Steel Structure | TAM | 2014-07-09 13:22 | IFA | A | 100%
112527 | I491TC08-0MMAM91-003-008 | WTP SUBSTATION RETAINING WALLS DETAIL | 00 | 2014-07-07 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System Substation Building | Civil and Steel Structure | TAM | 2014-07-09 13:22 | IFA | A | 100%
112528 | I491TC08-0MMAM91-003-009 | WTP SUBSTATION TRANSFORMER AREA DETAILS | 00 | 2014-07-07 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System Substation Building | Civil and Steel Structure | TAM | 2014-07-09 13:22 | IFA | A | 100%
112530 | I491TC08-0MMAM91-003-010 | WTP SUBSTATION COLUMNS DETAIL | 00 | 2014-07-07 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System Substation Building | Civil and Steel Structure | TAM | 2014-07-09 13:22 | IFA | A | 100%
112531 | I491TC08-0MMAM91-003-011 | WTP SUBSTATION TRANSFORMER AREA DETAILS | 00 | 2014-07-07 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System Substation Building | Civil and Steel Structure | TAM | 2014-07-09 13:22 | IFA | A | 100%
112532 | I491TC08-0MMAM91-003-012 | WTP SUBSTATION FRAMING PLAN +1.00 FRAMING PLAN +5.70 | 00 | 2014-07-07 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System Substation Building | Civil and Steel Structure | TAM | 2014-07-09 13:22 | IFA | A | 100%
112533 | I491TC08-0MMAM91-003-013 | WTP SUBSTATION BEAMS DETAIL | 00 | 2014-07-07 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System Substation Building | Civil and Steel Structure | TAM | 2014-07-09 13:22 | IFA | A | 100%
112534 | I491TC08-0MMAM91-003-014 | WTP SUBSTATION BEAMS DETAIL | 00 | 2014-07-07 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System Substation Building | Civil and Steel Structure | TAM | 2014-07-09 13:22 | IFA | A | 100%
112535 | I491TC08-0MMAM91-003-015 | WTP SUBSTATION BEAMS DETAIL | 00 | 2014-07-07 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System Substation Building | Civil and Steel Structure | TAM | 2014-07-09 13:22 | IFA | A | 100%
16746 | I491TC08-0MMCF91-001-001 | Excavation Plan And Section Sedimentation System | 02 | 2014-02-01 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | TAM | 2014-02-20 15:06 | IFC | AC |  | 95%
16751 | I491TC08-0MMCF91-001-002 | FOUNDATION FORMWORK PLAN SEDIMENTATION SYSTEM | 02 | 2014-02-01 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | TAM | 2014-02-20 15:06 | IFC | AC |  | 95%
16752 | I491TC08-0MMCF91-001-003 | Foundation Reinforcement Plan Sedimentation System | 02 | 2014-02-01 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | TAM | 2014-02-20 15:06 | IFC | AC |  | 95%
16740 | I491TC08-0MMCF91-001-004 | Formwork Plan El:-0.98 & Reinforcement Plan El:-0.98 Sedimentation System | 02 | 2014-02-01 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | TAM | 2014-02-20 15:06 | IFC | AC |  | 95%
16741 | I491TC08-0MMCF91-001-005 | Reinforcement Of Walls & Roof Sedimentation System | 02 | 2014-02-01 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | TAM | 2014-02-20 15:06 | IFC | AC |  | 95%
16742 | I491TC08-0MMCF91-001-006 | Reinforcement Of Walls 1,2,3,7,8 Sedimentation System | 02 | 2014-02-01 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | TAM | 2014-02-20 15:06 | IFC | AC |  | 95%
16743 | I491TC08-0MMCF91-001-007 | Reinforcement Of 'Slopped Floor' & Reinforcement Of 'Wall 10' & Section 3-3 Sedimentation System | 02 | 2014-02-01 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | TAM | 2014-02-20 15:06 | IFC | AC |  | 95%
16744 | I491TC08-0MMCF91-001-008 | Manhole Reinforcement Section & Section J-J & 4-4 Sedimentation System | 02 | 2014-02-01 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | TAM | 2014-02-20 15:06 | IFC | AC |  | 95%
16745 | I491TC08-0MMCF91-001-009 | Hot Water Pump Room Steel Structure Sedimentation System | 02 | 2014-02-01 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | TAM | 2014-02-20 15:06 | IFC | AC |  | 95%
16747 | I491TC08-0MMCF91-001-010 | Api Sedimentation System Architecture Plan Sedimentation System & Sec A-A | 02 | 2014-02-01 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | TAM | 2014-02-20 15:06 | IFC | AC |  | 95%
16748 | I491TC08-0MMCF91-001-011 | Sedimentation System Architecture Section B-B&C-C&D-D&E-E | 02 | 2014-02-01 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | TAM | 2014-02-20 15:06 | IFC | AC |  | 95%
16749 | I491TC08-0MMCF91-001-012 | Sedimentation System Architecture Section H-H&G-G&J-J&F-F | 02 | 2014-02-01 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | TAM | 2014-02-20 15:06 | IFC | AC |  | 95%
16750 | I491TC08-0MMCF91-001-013 | Sedimentation System Architecture North Elevation & East Elevation | 02 | 2014-02-01 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | TAM | 2014-02-20 15:06 | IFC | AC |  | 95%
134458 | I491TC08-0MMCF91-002-001 | Clamshel Bucket Hoist Foundation WCP Sedimentation | 01 | 2018-12-02 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | TAM | 2018-12-08 09:17 | IFC | AFC | 100%
134256 | I491TC08-0MMCF91-003-001 | WTP Sedimentation Clean Warm Water Area Cover 1-6 | 01 | 2018-09-25 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | TAM | 2018-10-02 10:31 | IFC | AFC | 100%
134257 | I491TC08-0MMCF91-003-002 | WTP Sedimentation Clean Warm Water Area Cover 2-6 | 01 | 2018-09-25 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | TAM | 2018-10-02 10:31 | IFC | AFC | 100%
134258 | I491TC08-0MMCF91-003-003 | WTP Sedimentation Clean Warm Water Area Cover 3-6 | 01 | 2018-09-25 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | TAM | 2018-10-02 10:31 | IFC | AFC | 100%
134259 | I491TC08-0MMCF91-003-004 | WTP Sedimentation Clean Warm Water Area Cover 4-6 | 01 | 2018-09-25 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | TAM | 2018-10-02 10:31 | IFC | AFC | 100%
134260 | I491TC08-0MMCF91-003-005 | WTP Sedimentation Clean Warm Water Area Cover 5-6 | 01 | 2018-09-25 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | TAM | 2018-10-02 10:31 | IFC | AFC | 100%
134261 | I491TC08-0MMCF91-003-006 | WTP Sedimentation Clean Warm Water Area Cover 6-6 | 01 | 2018-09-25 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | TAM | 2018-10-02 10:31 | IFC | AFC | 100%
131066 | I491TC08-0MMCP91-001-001 | Sand Filter Blower Room Foundation and Concrete Structure | 01 | 2017-08-20 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | TAM | 2017-08-23 11:05 | IFC | AC |  | 95%
132804 | I491TC08-0MMCP91-002-001 | BLOWER ROOM FLOORING & CHNNEL PLAN & DETAILS | 01 | 2018-01-27 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | TAM | 2018-02-03 15:19 | IFC | AC |  | 95%
13112 | I491TC08-0MMCT01-002-004 | Lean Concrete Details For Ct01 & Ct02 For Cooling Water System 1-4 | 00 | 2013-11-10 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD |  | IFA | AC |  | 95%
13113 | I491TC08-0MMCT01-002-005 | Lean Concrete Details For Ct01 & Ct02 For Cooling Water System 2-4 | 00 | 2013-11-10 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD |  | IFA | AC |  | 95%
13114 | I491TC08-0MMCT01-002-006 | Lean Concrete Details For Ct01 & Ct02 For Cooling Water System 3-4 | 00 | 2013-11-10 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD |  | IFA | AC |  | 95%
133938 | I491TC08-0MMCT01-003-008 | Foundation Details For CT01 & CT02 1-10 | 02 | 2018-08-01 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD | 2018-08-07 10:37 | IFC | AFC | 100%
133939 | I491TC08-0MMCT01-003-009 | Foundation Details For CT01 & CT02 2-10 | 02 | 2018-08-01 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD | 2018-08-07 10:37 | IFC | AFC | 100%
133930 | I491TC08-0MMCT01-003-010 | Foundation Details For CT01 & CT02 3-10 | 02 | 2018-08-01 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD | 2018-08-07 10:37 | IFC | AFC | 100%
133931 | I491TC08-0MMCT01-003-011 | Foundation Details For CT01 & CT02 4-10 | 02 | 2018-08-01 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD | 2018-08-07 10:37 | IFC | AFC | 100%
133932 | I491TC08-0MMCT01-003-012 | Foundation Details For CT01 & CT02 5-10 | 02 | 2018-08-01 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD | 2018-08-07 10:37 | IFC | AFC | 100%
133933 | I491TC08-0MMCT01-003-013 | Foundation Details For CT01 & CT02 6-10 | 02 | 2018-08-01 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD | 2018-08-07 10:37 | IFC | AFC | 100%
133934 | I491TC08-0MMCT01-003-014 | Foundation Details For CT01 & CT02 7-10 | 02 | 2018-08-01 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD | 2018-08-07 10:37 | IFC | AFC | 100%
133935 | I491TC08-0MMCT01-003-015 | Foundation Details For CT01 & CT02 8-10 | 02 | 2018-08-01 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD | 2018-08-07 10:37 | IFC | AFC | 100%
133936 | I491TC08-0MMCT01-003-016 | Foundation Details For CT01 & CT02 9-10 | 02 | 2018-08-01 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD | 2018-08-07 10:37 | IFC | AFC | 100%
133937 | I491TC08-0MMCT01-003-017 | Foundation Details For CT01 & CT02 10-10 | 02 | 2018-08-01 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD | 2018-08-07 10:37 | IFC | AFC | 100%
13124 | I491TC08-0MMCT01-003-018 | Foundation Details For Ct01 & Ct02 For Cooling Water System 11-11 | 00 | 2013-11-10 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD |  | IFA | AC |  | 95%
133940 | I491TC08-0MMCT01-004-001 | Column Details For CT01 & CT02 1-4 | 02 | 2018-08-01 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD | 2018-08-07 10:38 | IFC | AFC | 100%
133941 | I491TC08-0MMCT01-004-002 | Column Details For CT01 & CT02 2-4 | 02 | 2018-08-01 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD | 2018-08-07 10:38 | IFC | AFC | 100%
133942 | I491TC08-0MMCT01-004-003 | Column Details For CT01 & CT02 3-4 | 02 | 2018-08-01 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD | 2018-08-07 10:38 | IFC | AFC | 100%
133943 | I491TC08-0MMCT01-004-004 | Column Details For CT01 & CT02 4-4 | 01 | 2018-08-01 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD | 2018-08-07 10:38 | IFC | AFC | 100%
133944 | I491TC08-0MMCT01-005-001 | Wall Details For CT01 & CT02 1-30 | 02 | 2018-08-01 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD | 2018-08-09 10:45 | IFC | AC |  | 95%
133955 | I491TC08-0MMCT01-005-002 | Wall Details For CT01 & CT02 2-30 | 02 | 2018-08-01 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD | 2018-08-09 10:45 | IFC | AC |  | 95%
133966 | I491TC08-0MMCT01-005-003 | Wall Details For CT01 & CT02 3-30 | 02 | 2018-08-01 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD | 2018-08-09 10:46 | IFC | AC |  | 95%
133967 | I491TC08-0MMCT01-005-004 | Wall Details For CT01 & CT02 4-30 | 02 | 2018-08-01 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD | 2018-08-09 10:46 | IFC | AC |  | 95%
133968 | I491TC08-0MMCT01-005-005 | Wall Details For CT01 & CT02 5-30 | 02 | 2018-08-01 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD | 2018-08-09 10:46 | IFC | AC |  | 95%
133969 | I491TC08-0MMCT01-005-006 | Wall Details For CT01 & CT02 6-30 | 02 | 2018-08-01 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD | 2018-08-09 10:46 | IFC | AC |  | 95%
133970 | I491TC08-0MMCT01-005-007 | Wall Details For CT01 & CT02 7-30 | 02 | 2018-08-01 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD | 2018-08-09 10:46 | IFC | AC |  | 95%
133971 | I491TC08-0MMCT01-005-008 | Wall Details For CT01 & CT02 8-30 | 02 | 2018-08-01 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD | 2018-08-09 10:46 | IFC | AC |  | 95%
133972 | I491TC08-0MMCT01-005-009 | Wall Details For CT01 & CT02 9-30 | 02 | 2018-08-01 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD | 2018-08-09 10:46 | IFC | AC |  | 95%
133945 | I491TC08-0MMCT01-005-010 | Wall Details For CT01 & CT02 10-30 | 02 | 2018-08-01 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD | 2018-08-09 10:45 | IFC | AC |  | 95%
133946 | I491TC08-0MMCT01-005-011 | Wall Details For CT01 & CT02 11-30 | 02 | 2018-08-01 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD | 2018-08-09 10:45 | IFC | AC |  | 95%
133947 | I491TC08-0MMCT01-005-012 | Wall Details For CT01 & CT02 12-30 | 02 | 2018-08-01 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD | 2018-08-09 10:45 | IFC | AC |  | 95%
133948 | I491TC08-0MMCT01-005-013 | Wall Details For CT01 & CT02 13-30 | 02 | 2018-08-01 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD | 2018-08-09 10:45 | IFC | AC |  | 95%
133949 | I491TC08-0MMCT01-005-014 | Wall Details For CT01 & CT02 14-30 | 02 | 2018-08-01 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD | 2018-08-09 10:45 | IFC | AC |  | 95%
133950 | I491TC08-0MMCT01-005-015 | Wall Details For CT01 & CT02 15-30 | 02 | 2018-08-01 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD | 2018-08-09 10:45 | IFC | AC |  | 95%
133951 | I491TC08-0MMCT01-005-016 | Wall Details For CT01 & CT02 16-30 | 02 | 2018-08-01 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD | 2018-08-09 10:45 | IFC | AC |  | 95%
133952 | I491TC08-0MMCT01-005-017 | Wall Details For CT01 & CT02 17-30 | 02 | 2018-08-01 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD | 2018-08-09 10:45 | IFC | AC |  | 95%
133953 | I491TC08-0MMCT01-005-018 | Wall Details For CT01 & CT02 18-30 | 02 | 2018-08-01 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD | 2018-08-09 10:45 | IFC | AC |  | 95%
133954 | I491TC08-0MMCT01-005-019 | Wall Details For CT01 & CT02 19-30 | 02 | 2018-08-01 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD | 2018-08-09 10:45 | IFC | AC |  | 95%
133956 | I491TC08-0MMCT01-005-020 | Wall Details For CT01 & CT02 20-30 | 02 | 2018-08-01 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD | 2018-08-09 10:45 | IFC | AC |  | 95%
133957 | I491TC08-0MMCT01-005-021 | Wall Details For CT01 & CT02 21-30 | 02 | 2018-08-01 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD | 2018-08-09 10:45 | IFC | AC |  | 95%
133958 | I491TC08-0MMCT01-005-022 | Wall Details For CT01 & CT02 22-30 | 02 | 2018-08-01 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD | 2018-08-09 10:45 | IFC | AC |  | 95%
133959 | I491TC08-0MMCT01-005-023 | Wall Details For CT01 & CT02 23-30 | 02 | 2018-08-01 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD | 2018-08-09 10:45 | IFC | AC |  | 95%
133960 | I491TC08-0MMCT01-005-024 | Wall Details For CT01 & CT02 24-30 | 02 | 2018-08-01 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD | 2018-08-09 10:45 | IFC | AC |  | 95%
133961 | I491TC08-0MMCT01-005-025 | Wall Details For CT01 & CT02 25-30 | 02 | 2018-08-01 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD | 2018-08-09 10:46 | IFC | AC |  | 95%
133962 | I491TC08-0MMCT01-005-026 | Wall Details For CT01 & CT02 26-30 | 02 | 2018-08-01 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD | 2018-08-09 10:46 | IFC | AC |  | 95%
133963 | I491TC08-0MMCT01-005-027 | Wall Details For CT01 & CT02 27-30 | 02 | 2018-08-01 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD | 2018-08-09 10:46 | IFC | AC |  | 95%
133964 | I491TC08-0MMCT01-005-028 | Wall Details For CT01 & CT02 28-30 | 02 | 2018-08-01 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD | 2018-08-09 10:46 | IFC | AC |  | 95%
133965 | I491TC08-0MMCT01-005-029 | Wall Details For CT01 & CT02 29-30 | 02 | 2018-08-01 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD | 2018-08-09 10:46 | IFC | AC |  | 95%
133974 | I491TC08-0MMCT01-005-030 | Wall Details For CT01 & CT02 30-30 | 01 | 2018-08-01 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD | 2018-08-11 12:29 | IFC | AC |  | 95%
134461 | I491TC08-0MMCT01-006-001 | Main Beams Details For CT01 & CT02 1-17 | 03 | 2018-12-03 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD | 2018-12-08 09:25 | IFC | AFC | 100%
134462 | I491TC08-0MMCT01-006-002 | Main Beams Details For CT01 & CT02 2-17 | 03 | 2018-12-03 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD | 2018-12-08 09:25 | IFC | AFC | 100%
134463 | I491TC08-0MMCT01-006-003 | Main Beams Details For CT01 & CT02 3-17 | 03 | 2018-12-03 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD | 2018-12-08 09:25 | IFC | AFC | 100%
134464 | I491TC08-0MMCT01-006-004 | Main Beams Details For CT01 & CT02 4-17 | 03 | 2018-12-03 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD | 2018-12-08 09:25 | IFC | AFC | 100%
135454 | I491TC08-0MMCT01-006-005 | Main Beams Details For CT01 & CT02 5-17 | 04 | 2019-06-18 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD | 2019-06-19 10:10 | IFC | AFC | 100%
135455 | I491TC08-0MMCT01-006-006 | Main Beams Details For CT01 & CT02 6-17 | 04 | 2019-06-18 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD | 2019-06-19 10:10 | IFC | AFC | 100%
134467 | I491TC08-0MMCT01-006-007 | Main Beams Details For CT01 & CT02 7-17 | 03 | 2018-12-03 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD | 2018-12-08 09:25 | IFC | AFC | 100%
134468 | I491TC08-0MMCT01-006-008 | Main Beams Details For CT01 & CT02 8-17 | 03 | 2018-12-03 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD | 2018-12-08 09:25 | IFC | AFC | 100%
134469 | I491TC08-0MMCT01-006-009 | Main Beams Details For CT01 & CT02 9-17 | 03 | 2018-12-03 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD | 2018-12-08 09:25 | IFC | AFC | 100%
134470 | I491TC08-0MMCT01-006-010 | Main Beams Details For CT01 & CT02 10-17 | 03 | 2018-12-03 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD | 2018-12-08 09:25 | IFC | AC |  | 95%
134471 | I491TC08-0MMCT01-006-011 | Main Beams Details For CT01 & CT02 11-17 | 03 | 2018-12-03 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD | 2018-12-08 09:25 | IFC | AC |  | 95%
134472 | I491TC08-0MMCT01-006-012 | Main Beams Details For CT01 & CT02 12-17 | 03 | 2018-12-03 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD | 2018-12-08 09:25 | IFC | AFC | 100%
134473 | I491TC08-0MMCT01-006-013 | Main Beams Details For CT01 & CT02 13-17 | 03 | 2018-12-03 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD | 2018-12-08 09:25 | IFC | AFC | 100%
134474 | I491TC08-0MMCT01-006-014 | Main Beams Details For CT01 & CT02 14-17 | 03 | 2018-12-03 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD | 2018-12-08 09:25 | IFC | AC |  | 95%
134475 | I491TC08-0MMCT01-006-015 | Main Beams Details For CT01 & CT02 15-17 | 03 | 2018-12-03 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD | 2018-12-08 09:25 | IFC | AC |  | 95%
135456 | I491TC08-0MMCT01-006-016 | Main Beams Details For CT01 & CT02 16-17 | 04 | 2019-06-18 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD | 2019-06-19 10:10 | IFC | AFC | 100%
135457 | I491TC08-0MMCT01-006-017 | Main Beams Details For CT01 & CT02 17-17 | 04 | 2019-06-18 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD | 2019-06-19 10:10 | IFC | AFC | 100%
133994 | I491TC08-0MMCT01-007-001 | Secondary Beams Details For CT01 & CT02 2-2 | 01 | 2018-08-01 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD | 2018-08-12 14:39 | IFC | AFC | 100%
133993 | I491TC08-0MMCT01-007-002 | Secondary Beams Details For CT01 & CT02 1-2 | 01 | 2018-08-01 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD | 2018-08-12 14:39 | IFC | AFC | 100%
134046 | I491TC08-0MMCT01-011-001 | Cable Trench Details For CT01 & CT02 1-2 | 00 | 2018-08-01 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD | 2018-08-16 12:17 | IFC | AFC | 100%
134047 | I491TC08-0MMCT01-011-002 | Cable Trench Details For CT01 & CT02 2-2 | 00 | 2018-08-01 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD | 2018-08-16 12:17 | IFC | AFC | 100%
13182 | I491TC08-0MMCT01-012-001 | Lean Concrete Details For Ct01 For Cooling Water System | 00 | 2013-03-11 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | TAM |  | IFA | AC |  | 95%
134063 | I491TC08-0MMCT01-014-001 | Sump Slab Details For CT01 & CT02 1-4 | 01 | 2018-08-01 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD | 2018-08-16 12:26 | IFC | AFC | 100%
134064 | I491TC08-0MMCT01-014-002 | Sump Slab Details For CT01 & CT02 2-4 | 01 | 2018-08-01 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD | 2018-08-16 12:26 | IFC | AFC | 100%
134065 | I491TC08-0MMCT01-014-003 | Sump Slab Details For CT01 & CT02 3-4 | 01 | 2018-08-01 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD | 2018-08-16 12:26 | IFC | AFC | 100%
134066 | I491TC08-0MMCT01-014-004 | Sump Slab Details For CT01 & CT02 4-4 | 01 | 2018-08-01 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD | 2018-08-16 12:26 | IFC | AFC | 100%
13183 | I491TC08-0MMCT02-001-001 | Excavation Details For Ct02 For Cooling Water System | 00 | 2013-03-11 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD |  | IFA | AC |  | 95%
13184 | I491TC08-0MMCT02-012-001 | Lean Concrete Details For Ct02 For Cooling Water System | 00 | 2013-03-11 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | TAM |  | IFA | AC |  | 95%
130092 | I491TC08-0MMFL91-002-001 | Water Channle for WTP Clarifer Sand Filter 1-2 | 03 | 2017-01-08 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System Building | Civil and Steel Structure | TAM | 2017-01-09 08:47 | IFC | AFC | 100%
130093 | I491TC08-0MMFL91-002-002 | Water Channle for WTP Clarifer Sand Filter Rainforcement 2-2 | 03 | 2017-01-08 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System Building | Civil and Steel Structure | TAM | 2017-01-09 08:47 | IFC | AFC | 100%
114398 | I491TC08-0MMHE01-001-001 | WTP Heat Exchanger Foundation Plan View | 00 | 2015-09-22 10:04 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System Building | Civil and Steel Structure | TAM | 2015-09-22 10:04 | IFI | OB | 100%
114399 | I491TC08-0MMHE01-001-002 | WTP Heat Exchanger Foundation Reinforcement | 00 | 2015-09-22 10:04 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System Building | Civil and Steel Structure | TAM | 2015-09-22 10:04 | IFI | OB | 100%
134131 | I491TC08-0MMTK01-002-001 | WTP - EMERGENCY TANK - PIPE RACK FOUNDATION DETAIL DRAWING | 00 | 2018-09-04 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | TAM | 2018-09-09 14:26 | IFI | OB | 100%
13185 | I491TC08-0MXAA91-001-001 | Concrete Mixture Design | 00 | 2011-09-25 | Indeterminate | Miscellaneous(MISC) | Basic | General | Mechanical | TAM |  | IFA | AC |  | 95%
13191 | I491TC08-0MXAA91-002-006 | Cable Tunnel Foundation Detail Tunnel Layout Plan | 04 | 2012-08-15 | Indeterminate | Drawing | Detail | General | Civil and Steel Structure | TAM |  | IFC | AC |  | 95%
13192 | I491TC08-0MXAA91-002-007 | Cable Tunnel Foundation Detail Tunnel Section And Joints | 04 | 2012-08-15 | Indeterminate | Drawing | Detail | General | Civil and Steel Structure | TAM |  | IFC | AC |  | 95%
13197 | I491TC08-0MXAA91-003-005 | Cable Tunnel Excavation Plan Plan And Sections | 04 | 2012-08-15 | Indeterminate | Drawing | Detail | General | Civil and Steel Structure | TAM |  | IFC | AC |  | 95%
13209 | I491TC08-0MXAA91-004-004 | Cable Tunnel Concrete Structure Detail Form Work And Reinforcement Details | 03 | 2012-08-18 | Indeterminate | Drawing | Detail | General | Civil and Steel Structure | TAM |  | IFC | AC |  | 95%
13210 | I491TC08-0MXAA91-004-005 | Cable Tunnel Concrete Structure Detail Form Work And Reinforcement Details | 03 | 2012-08-18 | Indeterminate | Drawing | Detail | General | Civil and Steel Structure | TAM |  | IFC | AC |  | 95%
13211 | I491TC08-0MXAA91-004-006 | Cable Tunnel Concrete Structure Detail Form Work And Reinforcement Details | 03 | 2012-08-18 | Indeterminate | Drawing | Detail | General | Civil and Steel Structure | TAM |  | IFC | AC |  | 95%
13212 | I491TC08-0MXAA91-004-007 | Cable Tunnel Concrete Structure Detail Form Work And Reinforcement Details | 03 | 2012-08-18 | Indeterminate | Drawing | Detail | General | Civil and Steel Structure | TAM |  | IFC | AC |  | 95%
13213 | I491TC08-0MXAA91-004-008 | Cable Tunnel Concrete Structure Detail Form Work And Reinforcement Details | 03 | 2012-08-18 | Indeterminate | Drawing | Detail | General | Civil and Steel Structure | TAM |  | IFC | AC |  | 95%
13214 | I491TC08-0MXAA91-004-009 | Cable Tunnel Concrete Structure Detail Form Work And Reinforcement Details | 03 | 2012-08-18 | Indeterminate | Drawing | Detail | General | Civil and Steel Structure | TAM |  | IFC | AC |  | 95%
13199 | I491TC08-0MXAA91-004-010 | Cable Tunnel Concrete Structure Detail Form Work And Reinforcement Details | 03 | 2012-08-18 | Indeterminate | Drawing | Detail | General | Civil and Steel Structure | TAM |  | IFC | AC |  | 95%
13200 | I491TC08-0MXAA91-004-011 | Cable Tunnel Concrete Structure Detail Form Work And Reinforcement Details | 03 | 2012-08-18 | Indeterminate | Drawing | Detail | General | Civil and Steel Structure | TAM |  | IFC | AC |  | 95%
13201 | I491TC08-0MXAA91-004-012 | Cable Tunnel Concrete Structure Detail Form Work And Reinforcement Details | 03 | 2012-08-18 | Indeterminate | Drawing | Detail | General | Civil and Steel Structure | TAM |  | IFC | AC |  | 95%
13202 | I491TC08-0MXAA91-004-013 | Cable Tunnel Concrete Structure Detail Form Work And Reinforcement Details | 03 | 2012-08-18 | Indeterminate | Drawing | Detail | General | Civil and Steel Structure | TAM |  | IFC | AC |  | 95%
13203 | I491TC08-0MXAA91-004-014 | Cable Tunnel Concrete Structure Detail Form Work And Reinforcement Details | 03 | 2012-08-18 | Indeterminate | Drawing | Detail | General | Civil and Steel Structure | TAM |  | IFC | AC |  | 95%
13204 | I491TC08-0MXAA91-004-015 | Cable Tunnel Concrete Structure Detail Form Work And Reinforcement Details | 03 | 2012-08-18 | Indeterminate | Drawing | Detail | General | Civil and Steel Structure | TAM |  | IFC | AC |  | 95%
13205 | I491TC08-0MXAA91-004-016 | Cable Tunnel Concrete Structure Detail Form Work And Reinforcement Details | 03 | 2012-08-18 | Indeterminate | Drawing | Detail | General | Civil and Steel Structure | TAM |  | IFC | AC |  | 95%
13206 | I491TC08-0MXAA91-004-017 | Cable Tunnel Concrete Structure Detail Form Work And Reinforcement Details | 03 | 2012-08-18 | Indeterminate | Drawing | Detail | General | Civil and Steel Structure | TAM |  | IFC | AC |  | 95%
129322 | I491TC08-0MXAA91-005-001 | Cable Routing from SMP to WorkShop Warehouse | 02 | 2016-08-21 | Indeterminate | Drawing | Detail | General | Civil and Steel Structure | TAM | 2016-08-22 14:50 | IFC | AFC | 100%
132534 | I491TC08-0MXEG01-001-001 | BASIS OF DESIGN (CIVIL & STEEL STRUCTURE) FOR DIESEL ROOM FOUNDATION PLAN 1-3 | 03 | 2017-12-12 | Indeterminate | Drawing | Detail | General | Civil and Steel Structure | TAM | 2017-12-13 09:52 | IFC | AFC | 100%
132535 | I491TC08-0MXEG01-001-002 | BASIS OF DESIGN (CIVIL & STEEL STRUCTURE) FOR DIESEL ROOM FOUNDATION PLAN 2-3 | 03 | 2017-12-12 | Indeterminate | Drawing | Detail | General | Civil and Steel Structure | TAM | 2017-12-13 09:52 | IFC | AFC | 100%
132536 | I491TC08-0MXEG01-001-003 | BASIS OF DESIGN (CIVIL & STEEL STRUCTURE) FOR DIESEL ROOM FOUNDATION PLAN 3-3 | 03 | 2017-12-12 | Indeterminate | Drawing | Detail | General | Civil and Steel Structure | TAM | 2017-12-13 09:52 | IFC | AFC | 100%
132653 | I491TC08-0MXEG01-002-001 | DIESEL ROOM FLOORING 1-5 | 02 | 2018-01-07 09:17 | Indeterminate | Drawing | Detail | General | Civil and Steel Structure | TAM | 2018-01-07 09:17 | IFC | AFC | 100%
132654 | I491TC08-0MXEG01-002-002 | DIESEL ROOM FLOORING 2-5 | 02 | 2018-01-07 09:17 | Indeterminate | Drawing | Detail | General | Civil and Steel Structure | TAM | 2018-01-07 09:17 | IFC | AFC | 100%
132655 | I491TC08-0MXEG01-002-003 | DIESEL ROOM FLOORING 3-5 | 02 | 2018-01-07 09:17 | Indeterminate | Drawing | Detail | General | Civil and Steel Structure | TAM | 2018-01-07 09:17 | IFC | AFC | 100%
132651 | I491TC08-0MXEG01-002-004 | DIESEL ROOM FLOORING 4-5 | 01 | 2018-01-07 09:17 | Indeterminate | Drawing | Detail | General | Civil and Steel Structure | TAM | 2018-01-07 09:17 | IFC | AFC | 100%
132652 | I491TC08-0MXEG01-002-005 | DIESEL ROOM FLOORING 5-5 | 01 | 2018-01-07 09:17 | Indeterminate | Drawing | Detail | General | Civil and Steel Structure | TAM | 2018-01-07 09:17 | IFC | AFC | 100%
133314 | I491TC08-0MXEG01-003-001 | MELTSHOP DIESEL ROOM CABLE TRENCH 1-9 | 03 | 2018-06-19 | Indeterminate | Drawing | Detail | General | Civil and Steel Structure | TAM | 2018-06-26 10:36 | IFC | AFC | 100%
133315 | I491TC08-0MXEG01-003-002 | MELTSHOP DIESEL ROOM CABLE TRENCH 2-9 | 03 | 2018-06-19 | Indeterminate | Drawing | Detail | General | Civil and Steel Structure | TAM | 2018-06-26 10:36 | IFC | AFC | 100%
133316 | I491TC08-0MXEG01-003-003 | MELTSHOP DIESEL ROOM CABLE TRENCH 3-9 | 03 | 2018-06-19 | Indeterminate | Drawing | Detail | General | Civil and Steel Structure | TAM | 2018-06-26 10:36 | IFC | AFC | 100%
133317 | I491TC08-0MXEG01-003-004 | MELTSHOP DIESEL ROOM CABLE TRENCH 4-9 | 03 | 2018-06-19 | Indeterminate | Drawing | Detail | General | Civil and Steel Structure | TAM | 2018-06-26 10:36 | IFC | AFC | 100%
133318 | I491TC08-0MXEG01-003-005 | MELTSHOP DIESEL ROOM CABLE TRENCH 5-9 | 03 | 2018-06-19 | Indeterminate | Drawing | Detail | General | Civil and Steel Structure | TAM | 2018-06-26 10:36 | IFC | AFC | 100%
133319 | I491TC08-0MXEG01-003-006 | MELTSHOP DIESEL ROOM CABLE TRENCH 6-9 | 03 | 2018-06-19 | Indeterminate | Drawing | Detail | General | Civil and Steel Structure | TAM | 2018-06-26 10:36 | IFC | AFC | 100%
133320 | I491TC08-0MXEG01-003-007 | MELTSHOP DIESEL ROOM CABLE TRENCH 7-9 | 02 | 2018-06-19 | Indeterminate | Drawing | Detail | General | Civil and Steel Structure | TAM | 2018-06-26 10:36 | IFC | AFC | 100%
133321 | I491TC08-0MXEG01-003-008 | MELTSHOP DIESEL ROOM CABLE TRENCH 8-9 | 00 | 2018-06-19 | Indeterminate | Drawing | Detail | General | Civil and Steel Structure | TAM | 2018-06-26 10:36 | IFC | AFC | 100%
133322 | I491TC08-0MXEG01-003-009 | MELTSHOP DIESEL ROOM CABLE TRENCH 9-9 | 00 | 2018-06-19 | Indeterminate | Drawing | Detail | General | Civil and Steel Structure | TAM | 2018-06-26 10:36 | IFC | AFC | 100%
13219 | I491TC08-0MYAA91-001-005 | Workshop Foundation Details Drawing | 04 | 2012-02-28 | Indeterminate | Drawing | Detail | Maintenance Workshop | Civil and Steel Structure | IKS |  | IFC | AFC | 100%
131365 | I491TC08-0MYAA91-002-002 | Workshop Flooring Detail | 02 | 2017-10-08 | Indeterminate | Drawing | Detail | Melt Shop Maintenance Workshop | Civil and Steel Structure | IKS | 2017-10-11 14:14 | IFC | AC |  | 95%
13223 | I491TC08-0MYAA91-003-002 | Workshop Excavation Plan | 01 | 2012-02-25 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop Maintenance Workshop | Civil and Steel Structure | IKS |  | IFC | AFC | 100%
135437 | I491TC08-0OFAM01-001-001 | Security Office for Ferro alloy Storage | 00 | 2019-06-01 | Indeterminate | Drawing | Detail | Office - Canteen - Locker & Shower For Melt Shop | Civil and Steel Structure | TAM | 2019-06-02 09:58 | IFA | AC |  | 95%
135144 | I491TC08-0PXAA91-001-001 | Ladle Sand Filling Station Foundation 1-2 | 01 | 2019-03-18 10:31 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Civil and Steel Structure | TAM | 2019-03-18 10:31 | IFC | AFC | 100%
135145 | I491TC08-0PXAA91-001-002 | Ladle Sand Filling Station Foundation 2-2 | 01 | 2019-03-18 10:31 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Civil and Steel Structure | TAM | 2019-03-18 10:31 | IFC | AFC | 100%
112421 | I491TC08-0PXSM01-001-001 | LADLE SLAG DUMPING AREA WALL & FOUNDATION FORM WORK PLAN AND EXCAVATION | 01 | 2014-06-21 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Civil and Steel Structure | APEC | 2014-06-26 16:24 | IFC | AFC | 100%
112422 | I491TC08-0PXSM01-001-002 | LADLE SLAG DUMPING AREA WALL & FOUNDATION FORM WORK | 01 | 2014-06-21 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Civil and Steel Structure | APEC | 2014-06-26 16:24 | IFC | AFC | 100%
112423 | I491TC08-0PXSM01-001-003 | LADLE SLAG DUMPING AREA WALL & FOUNDATION REINFORCEMENT PLAN & SECTION | 01 | 2014-06-21 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Civil and Steel Structure | APEC | 2014-06-26 16:24 | IFC | AFC | 100%
135173 | I491TC08-0RXEA91-002-002 | Purging Station Foundation Formwork Plan | 06 | 2019-03-17 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Civil and Steel Structure | APEC | 2019-03-18 11:52 | IFC | AFC | 100%
135174 | I491TC08-0RXEA91-002-003 | Purging Station Foundation Reinforcement Plan | 06 | 2019-03-17 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Civil and Steel Structure | APEC | 2019-03-18 11:52 | IFC | AFC | 100%
135172 | I491TC08-0RXEA91-002-004 | PURGING STATION JIB CRANE STAND | 03 | 2019-03-17 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Civil and Steel Structure | APEC | 2019-03-18 11:52 | IFC | AFC | 100%
13237 | I491TC08-0SHAA91-001-007 | Scrap Yard Foundation And Wall Sections | 01 | 2011-06-26 | Indeterminate | Drawing | Detail | Melt Shop Scrap Yard | Civil and Steel Structure | IKS |  | IFA | A | 100%
13238 | I491TC08-0SHAA91-001-008 | Scrap Yard Foundation And Walls Plan & Det. | 01 | 2011-06-26 | Indeterminate | Drawing | Detail | Melt Shop Scrap Yard | Civil and Steel Structure | IKS |  | IFA | A | 100%
13239 | I491TC08-0SHAA91-001-009 | Scrap Yard Foundation And Wall Sections | 01 | 2011-07-11 | Indeterminate | Drawing | Detail | Melt Shop Scrap Yard | Civil and Steel Structure | IKS |  | IFC | AFC | 100%
13240 | I491TC08-0SHAA91-001-010 | Scrap Yard Foundation And Walls Plan & Det. | 01 | 2011-07-11 | Indeterminate | Drawing | Detail | Melt Shop Scrap Yard | Civil and Steel Structure | IKS |  | IFC | AFC | 100%
13241 | I491TC08-0SHAA91-001-011 | Scrap Yard Foundation And Walls Plan | 01 | 2011-12-04 | Indeterminate | Drawing | Detail | Melt Shop Scrap Yard | Civil and Steel Structure | IKS |  | IFA | A | 100%
13242 | I491TC08-0SHAA91-001-012 | Scrap Yard Foundation And Walls Plan | 01 | 2011-12-19 | Indeterminate | Drawing | Detail | Melt Shop Scrap Yard | Civil and Steel Structure | IKS |  | IFC | AFC | 100%
13306 | I491TC08-0SHAA91-002-067 | Scrap Yard-Foundation & Wall Listofer | 03 | 2012-06-25 | Indeterminate | Drawing | Detail | Melt Shop Scrap Yard | Civil and Steel Structure | IKS |  | IFC | AFC | 100%
13313 | I491TC08-0SHAA91-004-002 | Retaining Wall Plan & Section | 01 | 2013-02-24 | Indeterminate | Drawing | Detail | Melt Shop Scrap Yard | Civil and Steel Structure | IKS |  | IFC | AFC | 100%
13320 | I491TC08-0SHSB91-005-001 | Scrap Transfer Car Foundation Listofer | 00 | 2013-06-12 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop Scrap Yard | Civil and Steel Structure | IKS |  | IFA | AC |  | 95%
115102 | I491TC08-0SXFD91-001-001 | EAF SHELL RELINING STATION FOUNDATION & WALL FORMWORK PLAN & SECTIONS | 01 | 2016-03-16 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Civil and Steel Structure | TAM | 2016-04-02 16:46 | IFC | AFC | 100%
115103 | I491TC08-0SXFD91-001-002 | EAF SHELL RELINING STATION STAIR FORMWORK PLAN & SECTIONS | 01 | 2016-03-16 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Civil and Steel Structure | TAM | 2016-04-02 16:46 | IFC | AFC | 100%
115104 | I491TC08-0SXFD91-001-003 | EAF SHELL RELINING STATION FOUNDATION REINFORCEMENT PLAN & SECTIONS | 01 | 2016-03-16 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Civil and Steel Structure | TAM | 2016-04-02 16:46 | IFC | AFC | 100%
115105 | I491TC08-0SXFD91-001-004 | EAF SHELL RELINING STATION WALL REINFORCEMENT PLAN & SECTIONS | 01 | 2016-03-16 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Civil and Steel Structure | TAM | 2016-04-02 16:46 | IFC | AFC | 100%
115106 | I491TC08-0SXFD91-001-005 | EAF SHELL RELINING STATION ARRANGEMENT & DETAILS OF BASE PLATES | 01 | 2016-03-16 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Civil and Steel Structure | TAM | 2016-04-02 16:46 | IFC | AFC | 100%
130441 | I491TC08-0SXHB01-001-001 | MELT SHOP MAIN BUILDING ELECTRIC ARC FURNACE (EAF) FOUNDATION VERTICAL LADER PER HEATER FOUNDATION | 03 | 2017-04-08 | Indeterminate | Drawing | Detail | Eaf Auxiliaries | Civil and Steel Structure | TAM | 2017-04-17 10:44 | IFC | AFC | 100%
130440 | I491TC08-0SXHB01-001-002 | MELT SHOP MAIN BUILDING ELECTRIC ARC FURNACE (EAF) FOUNDATION VERTICAL LADER PER HEATER FOUNDATION | 03 | 2017-04-08 | Indeterminate | Drawing | Detail | Eaf Auxiliaries | Civil and Steel Structure | TAM | 2017-04-17 10:43 | IFC | AFC | 100%
129770 | I491TC08-0SXHB91-002-001 | HORIZONTAL LADLE PREHEATER FOUNDATION 1-2 | 01 | 2016-10-31 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Civil and Steel Structure | TAM | 2016-11-02 09:39 | IFC | AC |  | 95%
129769 | I491TC08-0SXHB91-002-002 | HORIZONTAL LADLE PREHEATER FOUNDATION 2-2 | 01 | 2016-10-31 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Civil and Steel Structure | TAM | 2016-11-02 09:39 | IFC | AC |  | 95%
130413 | I491TC08-0SXLD91-001-001 | Last Minute Burner+Ladle Dryer Foundation 1-2 | 02 | 2017-04-04 | Indeterminate | Drawing | Detail | Eaf Auxiliaries | Civil and Steel Structure | TAM | 2017-04-09 11:41 | IFC | AFC | 100%
130414 | I491TC08-0SXLD91-001-002 | Last Minute Burner+Ladle Dryer Foundation 2-2 | 01 | 2017-04-04 | Indeterminate | Drawing | Detail | Eaf Auxiliaries | Civil and Steel Structure | TAM | 2017-04-09 11:41 | IFC | AFC | 100%
13349 | I491TC08-0TBAA91-002-002 | Warehouse Flooring Detail | 01 | 2012-02-18 | Indeterminate | Miscellaneous(MISC) | Basic | Warehouse | Civil and Steel Structure | IKS |  | IFC | AFC | 100%
13351 | I491TC08-0TBAA91-003-002 | Ferro Alloy Storage (Foundation Area) | 00 | 2011-12-19 | Indeterminate | Drawing | Detail | Melt Shop Lime And Ferroalloy Storage | Civil and Steel Structure | IKS |  | IFC | AFC | 100%
132042 | I491TC08-0TBAA91-004-003 | Ferro Alloy Storage Foundation & Walls Details Pedestals & Concrete Walls Layout Plan | 03 | 2017-11-25 09:56 | Indeterminate | Drawing | Detail | Melt Shop Lime And Ferroalloy Storage | Civil and Steel Structure | IKS | 2017-11-25 09:56 | IFC | AFC | 100%
132043 | I491TC08-0TBAA91-004-004 | Ferro Alloy Storage Foundation & Walls Details Foundation Reinforcement Plan | 03 | 2017-11-25 09:56 | Indeterminate | Drawing | Detail | Melt Shop Lime And Ferroalloy Storage | Civil and Steel Structure | IKS | 2017-11-25 09:56 | IFC | AFC | 100%
132044 | I491TC08-0TBAA91-004-005 | Ferro Alloy Storage Foundation & Walls Details Foundation Reinforcement Plan | 03 | 2017-11-25 09:56 | Indeterminate | Drawing | Detail | Melt Shop Lime And Ferroalloy Storage | Civil and Steel Structure | IKS | 2017-11-25 09:56 | IFC | AFC | 100%
132045 | I491TC08-0TBAA91-004-006 | Ferro Alloy Storage Foundation & Walls Details Section Of Pedestal & Wall & Foundation | 03 | 2017-11-25 09:56 | Indeterminate | Drawing | Detail | Melt Shop Lime And Ferroalloy Storage | Civil and Steel Structure | IKS | 2017-11-25 09:56 | IFC | AFC | 100%
132046 | I491TC08-0TBAA91-004-007 | Ferro Alloy Storage Foundation & Walls Details Reinforcement Of Wall 1 | 03 | 2017-11-25 09:56 | Indeterminate | Drawing | Detail | Melt Shop Lime And Ferroalloy Storage | Civil and Steel Structure | IKS | 2017-11-25 09:56 | IFC | AFC | 100%
132047 | I491TC08-0TBAA91-004-008 | Ferro Alloy Storage Foundation & Walls Details Reinforcement Of Wall 2 | 03 | 2017-11-25 09:56 | Indeterminate | Drawing | Detail | Melt Shop Lime And Ferroalloy Storage | Civil and Steel Structure | IKS | 2017-11-25 09:56 | IFC | AFC | 100%
132048 | I491TC08-0TBAA91-004-009 | Ferro Alloy Storage Foundation & Walls Details Reinforcement Of Wall 3,4,5 | 03 | 2017-11-25 09:56 | Indeterminate | Drawing | Detail | Melt Shop Lime And Ferroalloy Storage | Civil and Steel Structure | IKS | 2017-11-25 09:56 | IFC | AFC | 100%
132037 | I491TC08-0TBAA91-004-010 | Ferro Alloy Storage Foundation & Walls Details Reinforcement Of Wall 6,7,8 | 03 | 2017-11-25 09:55 | Indeterminate | Drawing | Detail | Melt Shop Lime And Ferroalloy Storage | Civil and Steel Structure | IKS | 2017-11-25 09:55 | IFC | AFC | 100%
132038 | I491TC08-0TBAA91-004-011 | Ferro Alloy Storage Foundation & Walls Details Reinforcement Of Wall 9,10,11 | 03 | 2017-11-25 09:55 | Indeterminate | Drawing | Detail | Melt Shop Lime And Ferroalloy Storage | Civil and Steel Structure | IKS | 2017-11-25 09:55 | IFC | AFC | 100%
132039 | I491TC08-0TBAA91-004-012 | Ferro Alloy Storage Foundation & Walls Details Reinforcement Of Wall 12,13,14 | 03 | 2017-11-25 09:56 | Indeterminate | Drawing | Detail | Melt Shop Lime And Ferroalloy Storage | Civil and Steel Structure | IKS | 2017-11-25 09:56 | IFC | AFC | 100%
132040 | I491TC08-0TBAA91-004-013 | Ferro Alloy Storage Foundation & Walls Details Reinforcement Of Wall 12,13,14 pedestal & WALL & base plate List | 03 | 2017-11-25 09:56 | Indeterminate | Drawing | Detail | Melt Shop Lime And Ferroalloy Storage | Civil and Steel Structure | IKS | 2017-11-25 09:56 | IFC | AFC | 100%
132041 | I491TC08-0TBAA91-004-014 | Ferro Alloy Storage Foundation & Walls Details Reinforcement Of Wall 12,13,14 | 03 | 2017-11-25 09:56 | Indeterminate | Drawing | Detail | Melt Shop Lime And Ferroalloy Storage | Civil and Steel Structure | IKS | 2017-11-25 09:56 | IFC | AFC | 100%
135337 | I491TC08-0TBAA91-004-015 | Ferro Alloy Storage Foundation & Walls Details Material List | 03 | 2017-11-25 | Indeterminate | Drawing | Detail | Melt Shop Lime And Ferroalloy Storage | Civil and Steel Structure | IKS | 2019-05-12 12:26 | IFC | AFC | 100%
130510 | I491TC08-0TBAA91-007-001 | MELT SHOP FLOORING (PART 1) GENERAL NOTE | 03 | 2017-04-24 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2017-04-30 10:11 | IFC | AC |  | 95%
130511 | I491TC08-0TBAA91-007-002 | MELT SHOP FLOORING (PART 1) SLAB FORMWORK PLAN & SECTIONS | 03 | 2017-04-24 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2017-04-30 10:12 | IFC | AC |  | 95%
130513 | I491TC08-0TBAA91-007-003 | MELT SHOP FLOORING (PART 1) SLAB REINFORCEMENT PLAN & DETAILS | 03 | 2017-04-24 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2017-04-30 10:12 | IFC | AC |  | 95%
130512 | I491TC08-0TBAA91-007-004 | MELT SHOP FLOORING (PART 1) FOUNDATION REINFORCEMENT PLAN OF TRAIN | 03 | 2017-04-24 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2017-04-30 10:12 | IFC | AC |  | 95%
132053 | I491TC08-0TBAA91-008-001 | MELT SHOP FLOORING (PART 2) AREA OF FLOORING 1-11 | 02 | 2017-11-29 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2017-12-02 08:27 | IFC | AC |  | 95%
132054 | I491TC08-0TBAA91-008-002 | MELT SHOP FLOORING (PART 2) MEASURING PLAN 2-11 | 02 | 2017-11-29 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2017-12-02 08:27 | IFC | AC |  | 95%
132055 | I491TC08-0TBAA91-008-003 | MELT SHOP FLOORING (PART 2) LOCATION OF JOINTS 3-11 | 02 | 2017-11-29 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2017-12-02 08:27 | IFC | AC |  | 95%
132056 | I491TC08-0TBAA91-008-004 | MELT SHOP FLOORING (PART 2) SECTION OF SLAB 4-11 | 02 | 2017-11-29 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2017-12-02 08:27 | IFC | AC |  | 95%
132057 | I491TC08-0TBAA91-008-005 | MELT SHOP FLOORING (PART 2) Details of Joints 5-11 | 02 | 2017-11-29 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2017-12-02 08:27 | IFC | AC |  | 95%
132058 | I491TC08-0TBAA91-008-006 | MELT SHOP FLOORING (PART 2) TYPICAL CONCRETE & BRICK WALL CONNECTION 6-11 | 02 | 2017-11-29 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2017-12-02 08:27 | IFC | AC |  | 95%
132059 | I491TC08-0TBAA91-008-007 | MELT SHOP FLOORING (PART 2) SECTION OF CONCRETE & BRICK WALL 7-11 | 02 | 2017-11-29 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2017-12-02 08:27 | IFC | AC |  | 95%
132060 | I491TC08-0TBAA91-008-008 | MELT SHOP FLOORING (PART 2) Slab Bot. Reinforcement Plan-Direction: Y 8-11 | 02 | 2017-11-29 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2017-12-02 08:28 | IFC | AC |  | 95%
132061 | I491TC08-0TBAA91-008-009 | MELT SHOP FLOORING (PART 2) Slab Bot & Top Reinforcement Plan-Direction: X 9-11 | 02 | 2017-11-29 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2017-12-02 08:28 | IFC | AC |  | 95%
132062 | I491TC08-0TBAA91-008-010 | MELT SHOP FLOORING (PART 2) Slab Top Reinforcement Plan-Direction: Y 10-11 | 02 | 2017-11-29 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2017-12-02 08:28 | IFC | AC |  | 95%
132063 | I491TC08-0TBAA91-008-011 | MELT SHOP FLOORING (PART 2) CABLE ROUTING LAYOUT 11-11 | 01 | 2017-11-29 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2017-12-02 08:28 | IFC | AC |  | 95%
133816 | I491TC08-0TBAA91-009-001 | MELT SHOP FLOORING (PART 3) AREA OF FLOORING 1-7 | 02 | 2018-07-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2018-07-19 09:59 | IFC | AFC | 100%
133815 | I491TC08-0TBAA91-009-002 | MELT SHOP FLOORING (PART 3) AREA OF FLOORING 2-7 | 02 | 2018-07-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2018-07-19 09:59 | IFC | AFC | 100%
133814 | I491TC08-0TBAA91-009-003 | MELT SHOP FLOORING (PART 3) AREA OF FLOORING 3-7 | 02 | 2018-07-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2018-07-19 09:59 | IFC | AFC | 100%
133817 | I491TC08-0TBAA91-009-004 | MELT SHOP FLOORING (PART 3) AREA OF FLOORING 4-7 | 03 | 2018-07-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2018-07-19 09:59 | IFC | AFC | 100%
133813 | I491TC08-0TBAA91-009-005 | MELT SHOP FLOORING (PART 3) AREA OF FLOORING 5-7 | 02 | 2018-07-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2018-07-19 09:59 | IFC | AFC | 100%
133812 | I491TC08-0TBAA91-009-006 | MELT SHOP FLOORING (PART 3) AREA OF FLOORING 6-7 | 02 | 2018-07-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2018-07-19 09:59 | IFC | AFC | 100%
133811 | I491TC08-0TBAA91-009-007 | MELT SHOP FLOORING (PART 3) AREA OF FLOORING 7-7 | 02 | 2018-07-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2018-07-19 09:59 | IFC | AFC | 100%
131675 | I491TC08-0TBAA91-010-001 | MELT SHOP FLOORING (PART 4) AREA OF FLOORING 1-6 | 01 | 2017-11-05 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2017-11-18 08:13 | IFC | AFC | 100%
131674 | I491TC08-0TBAA91-010-002 | MELT SHOP FLOORING (PART 4) MEASURING PLAN 2-6 | 01 | 2017-11-05 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2017-11-18 08:13 | IFC | AFC | 100%
131673 | I491TC08-0TBAA91-010-003 | MELT SHOP FLOORING (PART 4) LOCATION OF JOINTS 3-6 | 01 | 2017-11-05 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2017-11-18 08:13 | IFC | AFC | 100%
132065 | I491TC08-0TBAA91-010-004 | MELT SHOP FLOORING (PART 4) SECTION OF SLAB 4-6 | 02 | 2017-11-29 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2017-12-02 08:29 | IFC | AFC | 100%
131671 | I491TC08-0TBAA91-010-005 | MELT SHOP FLOORING (PART 4) Details of Joints 5-6 | 01 | 2017-11-05 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2017-11-18 08:13 | IFC | AFC | 100%
131670 | I491TC08-0TBAA91-010-006 | MELT SHOP FLOORING (PART 4) CABLE ROUTING LAYOUT 6-6 | 01 | 2017-11-05 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2017-11-18 08:13 | IFC | AFC | 100%
133825 | I491TC08-0TBAA91-011-001 | MELT SHOP FLOORING (PART 5) AREA OF FLOORING 1-7 | 00 | 2018-07-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2018-07-19 10:08 | IFC | AFC | 100%
133826 | I491TC08-0TBAA91-011-002 | MELT SHOP FLOORING (PART 5) AREA OF FLOORING 2-7 | 00 | 2018-07-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2018-07-19 10:08 | IFC | AFC | 100%
133827 | I491TC08-0TBAA91-011-003 | MELT SHOP FLOORING (PART 5) AREA OF FLOORING 3-7 | 00 | 2018-07-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2018-07-19 10:08 | IFC | AFC | 100%
133828 | I491TC08-0TBAA91-011-004 | MELT SHOP FLOORING (PART 5) AREA OF FLOORING 4-7 | 00 | 2018-07-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2018-07-19 10:08 | IFC | AFC | 100%
133829 | I491TC08-0TBAA91-011-005 | MELT SHOP FLOORING (PART 5) AREA OF FLOORING 5-7 | 00 | 2018-07-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2018-07-19 10:08 | IFC | AFC | 100%
133830 | I491TC08-0TBAA91-011-006 | MELT SHOP FLOORING (PART 5) AREA OF FLOORING 6-7 | 00 | 2018-07-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2018-07-19 10:09 | IFC | AFC | 100%
133831 | I491TC08-0TBAA91-011-007 | MELT SHOP FLOORING (PART 5) AREA OF FLOORING 7-7 | 00 | 2018-07-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2018-07-19 10:09 | IFC | AFC | 100%
130355 | I491TC09-0ASAM91-002-001 | Frame Of Rows " 1 " To " 6 " Compressor Room Air Separation Plant 1-10 | 01 | 2017-02-28 13:24 | Indeterminate | Drawing | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2017-02-28 13:24 | IFC | AFC | 100%
130357 | I491TC09-0ASAM91-002-002 | Details "1", "2", And "4" Compressor Room Air Separation Plant 2-10 | 01 | 2017-02-28 13:24 | Indeterminate | Drawing | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2017-02-28 13:24 | IFC | AFC | 100%
130358 | I491TC09-0ASAM91-002-003 | Detail "3" And Walkway Compressor Room Air Separation Plant 3-10 | 01 | 2017-02-28 13:24 | Indeterminate | Drawing | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2017-02-28 13:24 | IFC | AFC | 100%
130359 | I491TC09-0ASAM91-002-004 | Column Arrangement Plan Compressor Room Air Separation Plant 4-10 | 01 | 2017-02-28 13:24 | Indeterminate | Drawing | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2017-02-28 13:24 | IFC | AFC | 100%
130360 | I491TC09-0ASAM91-002-005 | Ceiling Framing Plan Compressor Room Air Separation Plant 5-10 | 01 | 2017-02-28 13:24 | Indeterminate | Drawing | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2017-02-28 13:24 | IFC | AFC | 100%
130361 | I491TC09-0ASAM91-002-006 | Frame Of Rows "1" And "6" Compressor Room Air Separation Plant 6-10 | 01 | 2017-02-28 13:24 | Indeterminate | Drawing | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2017-02-28 13:24 | IFC | AFC | 100%
130362 | I491TC09-0ASAM91-002-007 | Row "A" And "D" Framing And Bracing Compressor Room Air Separation Plant 7-10 | 01 | 2017-02-28 13:24 | Indeterminate | Drawing | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2017-02-28 13:24 | IFC | AFC | 100%
134441 | I491TC09-0ASAM91-002-008 | ROW "A" AND "D" WALLS COMPRESSOR ROOM AIR SEPARATION PLANT 8-10 | 03 | 2018-11-28 | Indeterminate | Drawing | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2018-12-01 10:35 | IFC | AFC | 100%
130364 | I491TC09-0ASAM91-002-009 | Row "6" Wall Compressor Room Air Separation Plant 9-10 | 01 | 2017-02-28 13:25 | Indeterminate | Drawing | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2017-02-28 13:25 | IFC | AFC | 100%
130356 | I491TC09-0ASAM91-002-010 | Row "1" Wall Compressor Room Air Separation Plant 10-10 | 01 | 2017-02-28 13:24 | Indeterminate | Drawing | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2017-02-28 13:24 | IFC | AFC | 100%
130347 | I491TC09-0ASAM91-004-001 | Compressor Room Structure Basic Drawing Compressor Room Air Separation Plant | 02 | 2017-02-27 | Indeterminate | Drawing | Detail | Air Separation Plant Main Building | Civil and Steel Structure | TAM | 2017-02-28 10:50 | IFC | AFC | 100%
114531 | I491TC09-0CCAA01-001-001 | CCM Anchor Bolt 5.018074.R_001_03B Layout1 | 00 | 2015-10-13 10:14 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-13 10:14 | IFI | OB | 100%
114292 | I491TC09-0CCDF01-001-001 | 8.146813.V_001_00B CCM Dummy Bar Parking Support | 00 | 2015-08-29 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | DANIELI | 2015-09-02 10:48 | IFI | OB | 100%
114293 | I491TC09-0CCDF02-001-001 | 8.346468.T_001_00 Rummy Bar Stop Unit | 00 | 2015-08-29 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | DANIELI | 2015-09-02 10:48 | IFI | OB | 100%
114249 | I491TC09-0CCLK91-001-001 | CCM Turret Service Steel Work 8.566961.F_001_00 | 00 | 2015-08-08 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-08-10 09:51 | IFI | OB | 100%
114250 | I491TC09-0CCLK91-002-001 | CCM Turret Service Steel Work 8.566961.F_002_00 | 00 | 2015-08-08 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-08-10 09:51 | IFI | OB | 100%
114251 | I491TC09-0CCLK91-002-002 | CCM Turret Service Steel Work 8.566961.F_003_00 | 00 | 2015-08-08 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-08-10 09:51 | IFI | OB | 100%
114294 | I491TC09-0CCSS01-001-001 | 8.566964.B_001_00 CCM Steel Structure | 00 | 2015-08-29 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | DANIELI | 2015-09-02 10:48 | IFI | OB | 100%
114295 | I491TC09-0CCSS01-002-001 | 8.566971.A_001_00 CCM Steel Structure | 00 | 2015-08-29 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | DANIELI | 2015-09-02 10:48 | IFI | OB | 100%
114296 | I491TC09-0CCSS01-003-001 | 8.566971.A_002_00 CCM Steel Structure | 00 | 2015-08-29 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | DANIELI | 2015-09-02 10:49 | IFI | OB | 100%
114297 | I491TC09-0CCSS01-004-001 | 8.566971.A_003_00 CCM Steel Structure | 00 | 2015-08-29 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | DANIELI | 2015-09-02 10:49 | IFI | OB | 100%
114298 | I491TC09-0CCSS01-005-001 | 8.566971.A_004_00 CCM Steel Structure | 00 | 2015-08-29 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | DANIELI | 2015-09-02 10:49 | IFI | OB | 100%
114299 | I491TC09-0CCSS01-006-001 | 8.566971.A_005_00 CCM Steel Structure | 00 | 2015-08-29 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | DANIELI | 2015-09-02 10:49 | IFI | OB | 100%
114300 | I491TC09-0CCSS01-007-001 | 8.566971.A_006_00 CCM Steel Structure | 00 | 2015-08-29 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | DANIELI | 2015-09-02 10:49 | IFI | OB | 100%
114252 | I491TC09-0CCSS91-001-001 | CCM Service Steel Work 8.566965.C_001_00 | 00 | 2015-08-08 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-08-10 09:52 | IFI | OB | 100%
114253 | I491TC09-0CCSS91-002-001 | CCM Service Steel Work 8.566965.C_002_00 | 00 | 2015-08-08 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-08-10 09:52 | IFI | OB | 100%
114254 | I491TC09-0CCSS91-003-001 | CCM Service Steel Work 8.566965.C_003_00 | 00 | 2015-08-08 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-08-10 09:52 | IFI | OB | 100%
114255 | I491TC09-0CCSS91-004-001 | CCM Service Steel Work 8.566965.C_004_00 | 00 | 2015-08-08 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-08-10 09:52 | IFI | OB | 100%
114301 | I491TC09-0CCTD01-001-001 | 8.566970.M_001_00 CCM Tundish Car Runway Structure | 00 | 2015-08-29 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | DANIELI | 2015-09-02 10:50 | IFI | OB | 100%
114302 | I491TC09-0CCTD01-002-001 | 8.566970.M_002_00 CCM Tundish Car Runway Structure | 00 | 2015-08-29 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | DANIELI | 2015-09-02 10:50 | IFI | OB | 100%
114466 | I491TC09-0CCTH02-001-001 | Sheet 1of2 Tundish Relining Stand Structure 8.680136.B_001_00 | 00 | 2015-10-07 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-11 11:47 | IFI | OB | 100%
114467 | I491TC09-0CCTH02-001-002 | Sheet 2of2 Tundish Relining Stand Structure 8.680136.B_002_00 | 00 | 2015-10-07 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-11 11:47 | IFI | OB | 100%
114468 | I491TC09-0CCTH02-002-001 | CCM Tundish Stand Structure 8.231640.X_001_04K | 00 | 2015-10-07 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-11 11:47 | IFI | OB | 100%
114469 | I491TC09-0CCTH02-003-001 | CCM FNC Maintenance Station 8.120644.M_001_02G | 00 | 2015-10-07 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-11 11:47 | IFI | OB | 100%
135477 | I491TC09-0CCTH02-006-008 | TUNDISH RELINING STAND PLATFORM EXTENSION 8-8 | 00 | 2019-07-07 10:05 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | TAM | 2019-07-07 10:05 | IFI | OB | 100%
134849 | I491TC09-0CCTK91-001-001 | SUPPORT STRUCTURE FOR SCALE PIT CLAM SHELL CRANE 1-5 | 00 | 2018-12-24 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | TAM | 2018-12-31 10:02 | IFA | AFC | 100%
134848 | I491TC09-0CCTK91-001-002 | SUPPORT STRUCTURE FOR SCALE PIT CLAM SHELL CRANE 2-5 | 00 | 2018-12-24 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | TAM | 2018-12-31 10:02 | IFA | AFC | 100%
134847 | I491TC09-0CCTK91-001-003 | SUPPORT STRUCTURE FOR SCALE PIT CLAM SHELL CRANE 3-5 | 00 | 2018-12-24 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | TAM | 2018-12-31 10:02 | IFA | AFC | 100%
134846 | I491TC09-0CCTK91-001-004 | SUPPORT STRUCTURE FOR SCALE PIT CLAM SHELL CRANE 4-5 | 00 | 2018-12-24 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | TAM | 2018-12-31 10:02 | IFA | AFC | 100%
134845 | I491TC09-0CCTK91-001-005 | SUPPORT STRUCTURE FOR SCALE PIT CLAM SHELL CRANE 5-5 | 00 | 2018-12-24 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | TAM | 2018-12-31 10:02 | IFA | AFC | 100%
13382 | I491TC09-0CPAM91-001-001 | Frames Of Rows " 1 " To " 5 " Compressed Air Plant | 00 | 2013-10-28 | Indeterminate | Drawing | Detail | Compressed Air Production Plant | Civil and Steel Structure | TAM |  | IFA | A | 100%
13384 | I491TC09-0CPAM91-001-002 | Details "1", "2", And "4" Compressed Air Plant | 00 | 2013-10-28 | Indeterminate | Drawing | Detail | Compressed Air Production Plant | Civil and Steel Structure | TAM |  | IFA | A | 100%
13385 | I491TC09-0CPAM91-001-003 | Detail "E" And Walkway Compressed Air Plant | 00 | 2013-10-28 | Indeterminate | Drawing | Detail | Compressed Air Production Plant | Civil and Steel Structure | TAM |  | IFA | A | 100%
13386 | I491TC09-0CPAM91-001-004 | Column Arrangement Plan Roof Bracing Plan And Details Compressed Air Plant | 00 | 2013-10-28 | Unchecked | Drawing | Detail | Compressed Air Production Plant | Civil and Steel Structure | TAM |  | IFA | A | 100%
13387 | I491TC09-0CPAM91-001-005 | Ceiling Framing Plan Compressed Air Plant | 00 | 2013-10-28 | Indeterminate | Drawing | Detail | Compressed Air Production Plant | Civil and Steel Structure | TAM |  | IFA | A | 100%
13388 | I491TC09-0CPAM91-001-006 | Row " 1 " Framing And Bracing Compressed Air Plant | 00 | 2013-10-28 | Indeterminate | Drawing | Detail | Compressed Air Production Plant | Civil and Steel Structure | TAM |  | IFA | A | 100%
13389 | I491TC09-0CPAM91-001-007 | Row " 5 " Framing And Bracing Compressed Air Plant | 00 | 2013-10-28 | Indeterminate | Drawing | Detail | Compressed Air Production Plant | Civil and Steel Structure | TAM |  | IFA | A | 100%
13390 | I491TC09-0CPAM91-001-008 | Row "A" And "G" Framing And Bracing Compressed Air Plant | 00 | 2013-10-28 | Indeterminate | Drawing | Detail | Compressed Air Production Plant | Civil and Steel Structure | TAM |  | IFA | A | 100%
13391 | I491TC09-0CPAM91-001-009 | Excavation Plan And Section Compressed Air Plant | 00 | 2013-10-28 | Indeterminate | Drawing | Detail | Compressed Air Production Plant | Civil and Steel Structure | TAM |  | IFA | A | 100%
13383 | I491TC09-0CPAM91-001-010 | Row "A" And "G" Walls Compressed Air Plant | 00 | 2013-10-28 | Indeterminate | Drawing | Detail | Compressed Air Production Plant | Civil and Steel Structure | TAM |  | IFA | A | 100%
132631 | I491TC09-0EAAA01-001-001 | STAIRCASE LIST OF DRAWINGS 1-17 | 02 | 2017-12-31 09:08 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2017-12-31 09:08 | IFC | AFC | 100%
132636 | I491TC09-0EAAA01-001-002 | STAIRCASE GENERAL NOTES 2-17 | 02 | 2017-12-31 09:08 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2017-12-31 09:08 | IFC | AFC | 100%
132632 | I491TC09-0EAAA01-001-003 | STAIRCASE WELDING SPECIFICATION 3-17 | 02 | 2017-12-31 09:08 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2017-12-31 09:08 | IFC | AFC | 100%
132634 | I491TC09-0EAAA01-001-004 | STAIRCASE FRAME AT ROWS A & B FOR STAIR TYPE 4 4-17 | 02 | 2017-12-31 09:08 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2017-12-31 09:08 | IFC | AFC | 100%
132635 | I491TC09-0EAAA01-001-005 | STAIRCASE FRAME AT ROWS 1 & 2 FOR STAIR TYPE 4 5-17 | 02 | 2017-12-31 09:08 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2017-12-31 09:08 | IFC | AFC | 100%
132637 | I491TC09-0EAAA01-001-006 | STAIRCASE ACCESS WAY OF STAIR TYPE 4 6-17 | 02 | 2017-12-31 09:08 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2017-12-31 09:08 | IFC | AFC | 100%
132747 | I491TC09-0EAAA01-001-007 | STAIRCASE STAIR TYPE 4 SECTIONS (1 OF 3) 7-17 | 03 | 2018-01-21 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2018-02-01 11:32 | IFC | AFC | 100%
132639 | I491TC09-0EAAA01-001-008 | STAIRCASE STAIR TYPE 4 SECTIONS (2 OF 3) 8-17 | 02 | 2017-12-31 09:08 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2017-12-31 09:08 | IFC | AFC | 100%
132640 | I491TC09-0EAAA01-001-009 | STAIRCASE STAIR TYPE 4 SECTIONS (3 OF 3) 9-17 | 02 | 2017-12-31 09:08 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2017-12-31 09:08 | IFC | AFC | 100%
132641 | I491TC09-0EAAA01-001-010 | STAIRCASE COLUMN SPLICE DETAIL 10-17 | 02 | 2017-12-31 09:08 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2017-12-31 09:08 | IFC | AFC | 100%
132642 | I491TC09-0EAAA01-001-011 | STAIRCASE TYPICAL VERTICAL BRACING (1 OF 2) 11-17 | 02 | 2017-12-31 09:08 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2017-12-31 09:08 | IFC | AFC | 100%
132643 | I491TC09-0EAAA01-001-012 | STAIRCASE TYPICAL VERTICAL BRACING (1 OF 2) 12-17 | 02 | 2017-12-31 09:08 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2017-12-31 09:08 | IFC | AFC | 100%
132644 | I491TC09-0EAAA01-001-013 | STAIRCASE TYPICAL STAIR CONNECTION DETAILS 13-17 | 02 | 2017-12-31 09:08 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2017-12-31 09:08 | IFC | AFC | 100%
132645 | I491TC09-0EAAA01-001-014 | STAIRCASE TYPICAL STITCHES OF BRACINGS 14-17 | 02 | 2017-12-31 09:08 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2017-12-31 09:08 | IFC | AFC | 100%
132646 | I491TC09-0EAAA01-001-015 | STAIRCASE GRATING STRUCTURE DETAILS 15-17 | 02 | 2017-12-31 09:08 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2017-12-31 09:08 | IFC | AFC | 100%
132748 | I491TC09-0EAAA01-001-016 | STAIRCASE TYPICAL DETAIL OF HANDRAIL 16-17 | 03 | 2018-01-21 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2018-02-01 11:32 | IFC | AFC | 100%
132633 | I491TC09-0EAAA01-001-017 | STAIRCASE TYPICAL DETAIL OF HANDRAIL 17-17 | 02 | 2017-12-31 09:08 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2017-12-31 09:08 | IFC | AFC | 100%
129360 | I491TC09-0EAAA01-001-020 | STAIRCASE FOUNDATION FORMWORK & REINFORCEMENT PLAN FOR STAIR TYPE 1 18-18 | 00 | 2016-08-27 09:21 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2016-08-27 09:21 | IFA | AC |  | 95%
135170 | I491TC09-0EAAA01-002-001 | BASIC DESIGN FOR MELTSHOP ELEVATOR & STAIR CASE 1-9 | 00 | 2019-03-17 | Indeterminate | Drawing | Detail | Melt Shop | Civil and Steel Structure | TAM | 2019-03-18 11:19 | IFA | A | 100%
135169 | I491TC09-0EAAA01-002-002 | BASIC DESIGN FOR ELEVATOR & STAIR CASE 2-9 | 00 | 2019-03-17 | Indeterminate | Drawing | Detail | Melt Shop | Civil and Steel Structure | TAM | 2019-03-18 11:19 | IFA | A | 100%
135168 | I491TC09-0EAAA01-002-003 | BASIC DESIGN FOR ELEVATOR & STAIR CASE 3-9 | 00 | 2019-03-17 | Indeterminate | Drawing | Detail | Melt Shop | Civil and Steel Structure | TAM | 2019-03-18 11:19 | IFA | A | 100%
135167 | I491TC09-0EAAA01-002-004 | BASIC DESIGN FOR ELEVATOR & STAIR CASE 4-9 | 00 | 2019-03-17 | Indeterminate | Drawing | Detail | Melt Shop | Civil and Steel Structure | TAM | 2019-03-18 11:19 | IFA | A | 100%
135166 | I491TC09-0EAAA01-002-005 | BASIC DESIGN FOR MELTSHOP ELEVATOR & STAIR CASE 5-9 | 00 | 2019-03-17 | Indeterminate | Drawing | Detail | Melt Shop | Civil and Steel Structure | TAM | 2019-03-18 11:19 | IFA | A | 100%
135165 | I491TC09-0EAAA01-002-006 | BASIC DESIGN FOR MELTSHOP ELEVATOR & STAIR CASE 6-9 | 00 | 2019-03-17 | Indeterminate | Drawing | Detail | Melt Shop | Civil and Steel Structure | TAM | 2019-03-18 11:19 | IFA | A | 100%
135164 | I491TC09-0EAAA01-002-007 | BASIC DESIGN FOR MELTSHOP ELEVATOR & STAIR CASE 7-9 | 00 | 2019-03-17 | Indeterminate | Drawing | Detail | Melt Shop | Civil and Steel Structure | TAM | 2019-03-18 11:19 | IFA | A | 100%
135163 | I491TC09-0EAAA01-002-008 | BASIC DESIGN FOR MELTSHOP ELEVATOR & STAIR CASE 8-9 | 00 | 2019-03-17 | Indeterminate | Drawing | Detail | Melt Shop | Civil and Steel Structure | TAM | 2019-03-18 11:19 | IFA | A | 100%
135162 | I491TC09-0EAAA01-002-009 | BASIC DESIGN FOR MELTSHOP ELEVATOR & STAIR CASE 9-9 | 00 | 2019-03-17 | Indeterminate | Drawing | Detail | Melt Shop | Civil and Steel Structure | TAM | 2019-03-18 11:19 | IFA | A | 100%
135324 | I491TC09-0EAAA01-003-001 | MELTSHOP ELEVATOR & STAIR TYPE 1 1-16 | 00 | 2019-05-06 | Indeterminate | Drawing | Detail | Melt Shop | Civil and Steel Structure | TAM | 2019-05-08 13:45 | IFA | AC |  | 95%
135323 | I491TC09-0EAAA01-003-002 | MELTSHOP ELEVATOR & STAIR CASE 2-16 | 00 | 2019-05-06 | Indeterminate | Drawing | Detail | Melt Shop | Civil and Steel Structure | TAM | 2019-05-08 13:45 | IFA | AC |  | 95%
135322 | I491TC09-0EAAA01-003-003 | MELTSHOP ELEVATOR & STAIR CASE 3-16 | 00 | 2019-05-06 | Indeterminate | Drawing | Detail | Melt Shop | Civil and Steel Structure | TAM | 2019-05-08 13:45 | IFA | AC |  | 95%
135321 | I491TC09-0EAAA01-003-004 | MELTSHOP ELEVATOR & STAIR CASE 4-16 | 00 | 2019-05-06 | Indeterminate | Drawing | Detail | Melt Shop | Civil and Steel Structure | TAM | 2019-05-08 13:45 | IFA | AC |  | 95%
135320 | I491TC09-0EAAA01-003-005 | MELTSHOP ELEVATOR & STAIR CASE 5-16 | 00 | 2019-05-06 | Indeterminate | Drawing | Detail | Melt Shop | Civil and Steel Structure | TAM | 2019-05-08 13:45 | IFA | AC |  | 95%
135319 | I491TC09-0EAAA01-003-006 | MELTSHOP ELEVATOR & STAIR CASE 6-16 | 00 | 2019-05-06 | Indeterminate | Drawing | Detail | Melt Shop | Civil and Steel Structure | TAM | 2019-05-08 13:45 | IFA | AC |  | 95%
135318 | I491TC09-0EAAA01-003-007 | MELTSHOP ELEVATOR & STAIR CASE 7-16 | 00 | 2019-05-06 | Indeterminate | Drawing | Detail | Melt Shop | Civil and Steel Structure | TAM | 2019-05-08 13:45 | IFA | AC |  | 95%
135317 | I491TC09-0EAAA01-003-008 | MELTSHOP ELEVATOR & STAIR CASE 8-16 | 00 | 2019-05-06 | Indeterminate | Drawing | Detail | Melt Shop | Civil and Steel Structure | TAM | 2019-05-08 13:45 | IFA | AC |  | 95%
135316 | I491TC09-0EAAA01-003-009 | MELTSHOP ELEVATOR & STAIR CASE 9-16 | 00 | 2019-05-06 | Indeterminate | Drawing | Detail | Melt Shop | Civil and Steel Structure | TAM | 2019-05-08 13:45 | IFA | AC |  | 95%
135315 | I491TC09-0EAAA01-003-010 | MELTSHOP ELEVATOR & STAIR CASE 10-16 | 00 | 2019-05-06 | Indeterminate | Drawing | Detail | Melt Shop | Civil and Steel Structure | TAM | 2019-05-08 13:45 | IFA | AC |  | 95%
135314 | I491TC09-0EAAA01-003-011 | STAIRCASE GRATING STRUCTURE DETAILS 11-16 | 00 | 2019-05-06 | Indeterminate | Drawing | Detail | Melt Shop | Civil and Steel Structure | TAM | 2019-05-08 13:45 | IFA | AFC | 100%
135313 | I491TC09-0EAAA01-003-012 | STAIRCASE TYPICAL DETAIL OF HANDRAIL 12-16 | 00 | 2019-05-06 | Indeterminate | Drawing | Detail | Melt Shop | Civil and Steel Structure | TAM | 2019-05-08 13:45 | IFA | AC |  | 95%
135312 | I491TC09-0EAAA01-003-013 | MELTSHOP ELEVATOR & STAIR CASE 13-16 | 00 | 2019-05-06 | Indeterminate | Drawing | Detail | Melt Shop | Civil and Steel Structure | TAM | 2019-05-08 13:45 | IFA | AC |  | 95%
135311 | I491TC09-0EAAA01-003-014 | MELTSHOP ELEVATOR & STAIR CASE 14-16 | 00 | 2019-05-06 | Indeterminate | Drawing | Detail | Melt Shop | Civil and Steel Structure | TAM | 2019-05-08 13:45 | IFA | AC |  | 95%
135310 | I491TC09-0EAAA01-003-015 | MELTSHOP ELEVATOR & STAIR CASE 15-16 | 00 | 2019-05-06 | Indeterminate | Drawing | Detail | Melt Shop | Civil and Steel Structure | TAM | 2019-05-08 13:45 | IFA | AC |  | 95%
135309 | I491TC09-0EAAA01-003-016 | MELTSHOP ELEVATOR & STAIR CASE 16-16 | 00 | 2019-05-06 | Indeterminate | Drawing | Detail | Melt Shop | Civil and Steel Structure | TAM | 2019-05-08 13:45 | IFA | AC |  | 95%
115733 | I491TC09-0EAAA91-001-023 | MELT SHOP MAIN BUILDING COLUMNS,FRAMING ROOF & BRACING PLAN 1 | 03 | 2016-06-14 16:49 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-06-14 16:49 | IFC | AFC | 100%
13408 | I491TC09-0EAAA91-001-024 | MELT SHOP MAIN BUILDING COLUMNS,FRAMING ROOF & BRACING PLAN 2 | 02 | 2013-03-04 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
13409 | I491TC09-0EAAA91-001-025 | MELT SHOP MAIN BUILDING COLUMNS,FRAMING ROOF & BRACING PLAN 3 | 02 | 2013-03-04 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
13410 | I491TC09-0EAAA91-001-026 | MELT SHOP MAIN BUILDING COLUMNS,FRAMING ROOF & BRACING PLAN 4 | 02 | 2013-03-04 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
13411 | I491TC09-0EAAA91-001-027 | MELT SHOP MAIN BUILDING COLUMNS,FRAMING ROOF & BRACING PLAN 5 | 02 | 2013-03-04 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
13412 | I491TC09-0EAAA91-001-028 | MELT SHOP MAIN BUILDING COLUMNS,FRAMING ROOF & BRACING PLAN 6 | 02 | 2013-03-04 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
13413 | I491TC09-0EAAA91-001-029 | MELT SHOP MAIN BUILDING COLUMNS,FRAMING ROOF & BRACING PLAN 7 | 02 | 2013-03-04 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
13415 | I491TC09-0EAAA91-001-030 | MELT SHOP MAIN BUILDING COLUMNS,FRAMING ROOF & BRACING PLAN 8 | 02 | 2013-03-04 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
13416 | I491TC09-0EAAA91-001-031 | MELT SHOP MAIN BUILDING COLUMNS,FRAMING ROOF & BRACING PLAN 9 | 02 | 2013-03-04 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
13417 | I491TC09-0EAAA91-001-032 | MELT SHOP MAIN BUILDING COLUMNS,FRAMING ROOF & BRACING PLAN 10 | 02 | 2013-03-04 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
13418 | I491TC09-0EAAA91-001-033 | MELT SHOP MAIN BUILDING COLUMNS,FRAMING ROOF & BRACING PLAN 11 | 02 | 2013-03-04 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
115382 | I491TC09-0EAAA91-002-261 | Melt Shop Main Building List Of Drawings (1-226) | 28 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115383 | I491TC09-0EAAA91-002-262 | Melt Shop Main Building Column Base Column & Portal Bracing Plan (Part A) (2-226) | 20 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115384 | I491TC09-0EAAA91-002-263 | Melt shop Main Building Column Base Column & Portal Bracing Plan (Part B) (3-226) | 22 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115385 | I491TC09-0EAAA91-002-264 | Meltshop Main Building-Column C-1A & C-1B (4-226) | 08 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115386 | I491TC09-0EAAA91-002-265 | Meltshop Main Building-Column C-2 (5-226) | 09 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115387 | I491TC09-0EAAA91-002-266 | Meltshop Main Building-Column C-3A,C-4 ,C-9A,C-18 (6-226) | 09 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115388 | I491TC09-0EAAA91-002-267 | Meltshop Main Building-Column C-5A & C-5B & C-5C (7-226) | 09 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115389 | I491TC09-0EAAA91-002-268 | Meltshop Main Building-Typical Girt Details (8-226) | 04 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115390 | I491TC09-0EAAA91-002-269 | Meltshop Main Building-Column C-6 & Details (9-226) | 08 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115391 | I491TC09-0EAAA91-002-270 | Meltshop Main Building-Column C-7A & C-7B & Details (10-226) | 08 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115392 | I491TC09-0EAAA91-002-271 | Meltshop Main Building-Column C-8 & Details (11-226) | 08 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115393 | I491TC09-0EAAA91-002-272 | Meltshop Main Building-Column C-12 & Details (12-226) | 09 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115394 | I491TC09-0EAAA91-002-273 | Meltshop Main Building-Column C-13 & Details (13-226) | 07 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115395 | I491TC09-0EAAA91-002-274 | Meltshop Main Building-Column C-14 & Details (14-226) | 08 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115396 | I491TC09-0EAAA91-002-275 | Meltshop Main Building-Column C-15 & Details (15-226) | 07 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115397 | I491TC09-0EAAA91-002-276 | Meltshop Main Building-Column C - 16A & C-16B & Details (16-226) | 07 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115398 | I491TC09-0EAAA91-002-277 | Meltshop Main Building-Column C-5D (17-226) | 08 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115399 | I491TC09-0EAAA91-002-278 | Meltshop Main Building-Column C-21 & Details (18-226) | 09 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115400 | I491TC09-0EAAA91-002-279 | Meltshop Main Building-Truss To Column Connection (19-226) | 10 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115401 | I491TC09-0EAAA91-002-280 | Meltshop Main Building-Bbase Plate And Shear Key Details Type B.P.1 (20-226) | 05 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115402 | I491TC09-0EAAA91-002-281 | Meltshop Main Building-Base Plate And Shear Key Details Type B.P.2 (21-226) | 03 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115403 | I491TC09-0EAAA91-002-282 | Meltshop Main Building-Base Plate And Shear Key Details Type B.P.3 & B.P.4 (22-226) | 01 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115404 | I491TC09-0EAAA91-002-283 | Meltshop Main Building Column Splice (23-226) | 03 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115405 | I491TC09-0EAAA91-002-284 | Meltshop Main Building Side Framing View At Row "A" (24-226) | 06 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115406 | I491TC09-0EAAA91-002-285 | Meltshop Main Building Side Framing Connection Detail(1/2) (25-226) | 04 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115407 | I491TC09-0EAAA91-002-286 | Meltshop Main Buildingside Framing Connection Detail(2/2) (26-226) | 04 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115408 | I491TC09-0EAAA91-002-287 | Meltshop Main Building Truss To Column Connection Detail (27-226) | 08 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115409 | I491TC09-0EAAA91-002-288 | Meltshop Main Building Main Frame At Row A (28-226) | 05 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115410 | I491TC09-0EAAA91-002-289 | Meltshop Main Building Roof And Crane Truss Type (29-226) | 04 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115411 | I491TC09-0EAAA91-002-290 | Meltshop Main Building Bracing End Connection (30-226) | 04 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115412 | I491TC09-0EAAA91-002-291 | Meltshop Main Building Beam Connection Detail (31-226) | 08 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115413 | I491TC09-0EAAA91-002-292 | Meltshop Main Building Chevron Bracing Intersection (32-226) | 03 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115414 | I491TC09-0EAAA91-002-293 | Meltshop Main Building Truss To Column Connection Detail(Crane Level) (33-226) | 02 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115415 | I491TC09-0EAAA91-002-294 | Meltshop Main Building Bracing To Beam Column Joint (34-226) | 03 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115416 | I491TC09-0EAAA91-002-295 | Meltshop Main Building Horizontal Bracing (35-226) | 02 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115417 | I491TC09-0EAAA91-002-296 | Meltshop Main Building Portal Bracing At Row "A" (36-226) | 04 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115418 | I491TC09-0EAAA91-002-297 | Meltshop Main Building Roof And Crane Truss Bracing Detail (37-226) | 02 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115419 | I491TC09-0EAAA91-002-298 | Meltshop Main Building Horizontal Truss Bracing Detail (38-226) | 03 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115420 | I491TC09-0EAAA91-002-299 | Meltshop Main Building Typical Connection Detail For Crane Girder Bottom Flange Bracing (39-226) | 02 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115421 | I491TC09-0EAAA91-002-300 | Meltshop Main Building Column Splice Details(40-226) | 03 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115422 | I491TC09-0EAAA91-002-301 | Meltshop Main Building Crane Truss Type (41-226) | 05 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115423 | I491TC09-0EAAA91-002-302 | Meltshop Main Building Base Plate And Shear Key Details Type B.P.5 (42-226) | 02 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115424 | I491TC09-0EAAA91-002-303 | Meltshop Main Building Base Plate And Shear Key Details Type B.P.6 (43-226) | 02 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115425 | I491TC09-0EAAA91-002-304 | Meltshop Main Building Main Frame At Row "B" (44-226) | 09 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115426 | I491TC09-0EAAA91-002-305 | Meltshop Main Building Crane Truss Type At Row "B" (45-226) | 03 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115427 | I491TC09-0EAAA91-002-306 | Meltshop Main Building Roof Truss Type At Row "B" (46-226) | 06 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115428 | I491TC09-0EAAA91-002-307 | Meltshop Main Building Portal Bracing At Row "B" (47-226) | 04 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115429 | I491TC09-0EAAA91-002-308 | Meltshop Main Building Truss To Column Connection At Crane Level For Special Cases (48-226) | 02 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115430 | I491TC09-0EAAA91-002-309 | Meltshop Main Building Column Splice Details (49-226) | 01 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115431 | I491TC09-0EAAA91-002-310 | Meltshop Main Building Column Splice Details(50-226) | 02 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115432 | I491TC09-0EAAA91-002-311 | Meltshop Main Building Column Splice Details (51-226) | 03 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115433 | I491TC09-0EAAA91-002-312 | Meltshop Main Building Portal Bracing At Row "C" (52-226) | 05 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115434 | I491TC09-0EAAA91-002-313 | Meltshop Main Building Main Frame At Row "C" (53-226) | 07 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115435 | I491TC09-0EAAA91-002-314 | Meltshop Main Building Main Frame At Row "C" (54-226) | 06 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115436 | I491TC09-0EAAA91-002-315 | Meltshop Main Building Base Plate And Shear Key Details Type B.P.7 (55-226) | 02 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115437 | I491TC09-0EAAA91-002-316 | Meltshop Main Building Base Plate And Shear Key Details Type B.P.8 (56-226) | 02 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115438 | I491TC09-0EAAA91-002-317 | Meltshop Main Building Base Plate And Shear Key Details Type B.P.9 (57-226) | 02 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115439 | I491TC09-0EAAA91-002-318 | Meltshop Main Building Base Plate And Shear Key Details Type B.P.10 (58-226) | 02 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115440 | I491TC09-0EAAA91-002-319 | Meltshop Main Building Base Plate And Shear Key Details Type B.P.11 (59-226) | 02 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115441 | I491TC09-0EAAA91-002-320 | Meltshop Main Building Base Plate And Shear Key Details Type B.P.12 (60-226) | 02 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115442 | I491TC09-0EAAA91-002-321 | Meltshop Main Building Base Plate And Shear Key Details Type B.P.13 (61-226) | 02 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115443 | I491TC09-0EAAA91-002-322 | Meltshop Main Building Base Plate And Shear Key Details Type B.P.14 (62-226) | 02 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115444 | I491TC09-0EAAA91-002-323 | Meltshop Main Building Base Plate And Shear Key Details Type B.P.15 (63-226) | 02 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115445 | I491TC09-0EAAA91-002-324 | Meltshop Main Building Roof Truss Top Chord Bracing Plan (Part-A) (64-226) | 12 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115446 | I491TC09-0EAAA91-002-325 | Meltshop Main Building Roof Truss Top Chord Bracing Plan (Part-B) (65-226) | 14 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115447 | I491TC09-0EAAA91-002-326 | Meltshop Main Building Roof Truss Bot Chord Bracing Plan (Part-A) (66-226) | 10 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115448 | I491TC09-0EAAA91-002-327 | Meltshop Main Building Roof Truss Bot Chord Bracing Plan (Part-B) (67-226) | 12 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115449 | I491TC09-0EAAA91-002-328 | Meltshop Main Building Truss Type - T1 & T2 (68-226) | 03 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115450 | I491TC09-0EAAA91-002-329 | Meltshop Main Building Truss Type - T3A & T3B (69-300) | 03 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115451 | I491TC09-0EAAA91-002-330 | Meltshop Main Building Truss Type - T4 & T5 (70-300) | 03 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115452 | I491TC09-0EAAA91-002-331 | Meltshop Main Building Truss Type - T6 & T7 (71-300) | 03 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115453 | I491TC09-0EAAA91-002-332 | Meltshop Main Building Truss Type - T8 & T8A (72-300) | 03 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115454 | I491TC09-0EAAA91-002-333 | Meltshop Main Building Roof Truss Connection Details(2/2) (73-300) | 04 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115455 | I491TC09-0EAAA91-002-334 | Meltshop Main Building Roof Bracing Connection Details (74-300) | 02 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115456 | I491TC09-0EAAA91-002-335 | Meltshop Main Building Beam Splice (75-300) | 02 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115457 | I491TC09-0EAAA91-002-336 | Meltshop Main Building Truss Type - T9A & T9B (76-300) | 05 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115458 | I491TC09-0EAAA91-002-337 | Meltshop Main Building Truss Type - T10A & T10B (77-300) | 04 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115459 | I491TC09-0EAAA91-002-338 | Meltshop Main Building Truss Type - T11A & T11B (78-300) | 07 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115460 | I491TC09-0EAAA91-002-339 | Meltshop Main Building Truss Type - T12A & T12B (79-300) | 04 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115461 | I491TC09-0EAAA91-002-340 | Meltshop Main Building Vertical Bracing Type V.B.1A ,V.B.1B,V.B.2A& V.B.2B (80-300) | 03 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115462 | I491TC09-0EAAA91-002-341 | Meltshop Main Building Column C-23 & Details (81-300) | 09 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115463 | I491TC09-0EAAA91-002-342 | Meltshop Main Building Column C-24 & Details (82-300) | 12 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115464 | I491TC09-0EAAA91-002-343 | Meltshop Main Building Column C-25 & Details (83-300) | 12 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115465 | I491TC09-0EAAA91-002-344 | Meltshop Main Building Column C-26 & Details (84-300) | 12 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115466 | I491TC09-0EAAA91-002-345 | Meltshop Main Building Column C-27 & Details (85-300) | 11 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115467 | I491TC09-0EAAA91-002-346 | Meltshop Main Building Column C-28 & Details (86-300) | 12 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115468 | I491TC09-0EAAA91-002-347 | Meltshop Main Building Column C-29 & Details (87-300) | 12 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115469 | I491TC09-0EAAA91-002-348 | Meltshop Main Building Column C-30 & Details (88-300) | 11 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115470 | I491TC09-0EAAA91-002-349 | Meltshop Main Building Column C-31 & Details (89-300) | 12 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115471 | I491TC09-0EAAA91-002-350 | Meltshop Main Building Base Plate And Shear Key Details Type B.P.16 (90-300) | 03 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115472 | I491TC09-0EAAA91-002-351 | Meltshop Main Building Base Plate And Shear Key Details Type B.P.17 (91-300) | 02 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115473 | I491TC09-0EAAA91-002-352 | Meltshop Main Building Base Plate And Shear Key Details Type B.P.18 (92-300) | 02 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115474 | I491TC09-0EAAA91-002-353 | Meltshop Main Building Base Plate And Shear Key Details Type B.P.19 (93-300) | 02 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115475 | I491TC09-0EAAA91-002-354 | Meltshop Main Building Base Plate And Shear Key Details Type B.P.20 (94-300) | 02 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115476 | I491TC09-0EAAA91-002-355 | Meltshop Main Building Base Plate And Shear Key Details Type B.P.21 (95-300) | 02 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115477 | I491TC09-0EAAA91-002-356 | Meltshop Main Building Base Plate And Shear Key Details Type B.P.22 (96-300) | 02 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115478 | I491TC09-0EAAA91-002-357 | Meltshop Main Building Base Plate And Shear Key Details Type B.P.23 (97-300) | 04 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115479 | I491TC09-0EAAA91-002-358 | Meltshop Main Building Column Splice Details (98-300) | 01 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115480 | I491TC09-0EAAA91-002-359 | Meltshop Main Building Column Splice Details (99-300) | 02 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115481 | I491TC09-0EAAA91-002-360 | Meltshop Main Building Base Plate And Shear Key Details Type B.P.24 (100-300) | 02 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115482 | I491TC09-0EAAA91-002-361 | Meltshop Main Building Truss Type - T13A & T13B (101-300) | 06 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115483 | I491TC09-0EAAA91-002-362 | Meltshop Main Buildingtruss Type - T14A & T14B (102-300) | 06 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115484 | I491TC09-0EAAA91-002-363 | Meltshop Main Buildingtruss Type - T15A & T15B (103-300) | 05 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115485 | I491TC09-0EAAA91-002-364 | Meltshop Main Buildingtruss Type - T16A & T16B (104-300) | 06 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115486 | I491TC09-0EAAA91-002-365 | Meltshop Main Building Truss Type - T17 & T18 (105-300) | 04 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115487 | I491TC09-0EAAA91-002-366 | Meltshop Main Building Truss Type - T19A & T19B (106-300) | 05 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115488 | I491TC09-0EAAA91-002-367 | Meltshop Main Building Purlin Arrangement (107-300) | 02 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115489 | I491TC09-0EAAA91-002-368 | Meltshop Main Building Roof Framing Plan (108-300) | 04 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115490 | I491TC09-0EAAA91-002-369 | Meltshop Main Building Typical Girt Details (109-300) | 04 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115491 | I491TC09-0EAAA91-002-370 | Meltshop Main Building Column C - 16C & Details (110-300) | 03 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115492 | I491TC09-0EAAA91-002-371 | Meltshop Main Building Truss Type - T20 (111-300) | 04 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115493 | I491TC09-0EAAA91-002-372 | Meltshop Main Building Column Splice Details (112-300) | 02 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115494 | I491TC09-0EAAA91-002-373 | Meltshop Main Building Column Splice Details (113-300) | 04 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115495 | I491TC09-0EAAA91-002-374 | Meltshop Main Building Typical Details (114-300) | 11 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115496 | I491TC09-0EAAA91-002-375 | Meltshop Main Building Main Frame At Row "D" (115-300) | 09 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115497 | I491TC09-0EAAA91-002-376 | Meltshop Main Building Crane Truss Type At Row "D" (116-300) | 06 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115498 | I491TC09-0EAAA91-002-377 | Meltshop Main Building Crane Truss Type At Row "D" (117-300) | 03 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115499 | I491TC09-0EAAA91-002-378 | Meltshop Main Building Column C-32A,32B,C-33A &C-33B (118-300) | 06 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115500 | I491TC09-0EAAA91-002-379 | Meltshop Main Building Column Column C-33C,C-33D ,C-34A (119-300) | 06 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115501 | I491TC09-0EAAA91-002-380 | Meltshop Main Building Main Frame At Row "E" (120-300) | 08 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115502 | I491TC09-0EAAA91-002-381 | Meltshop Main Building Crane Truss Type At Row "E" (121-300) | 04 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:48 | IFC | AFC | 100%
115503 | I491TC09-0EAAA91-002-382 | Meltshop Main Building Crane Truss Type At Row "E" (122-300) | 03 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115504 | I491TC09-0EAAA91-002-383 | Meltshop Main Building Roof Truss Top Chord Bracing (123-300)Plan (Part-A) | 06 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115505 | I491TC09-0EAAA91-002-384 | Meltshop Main Building Roof Truss Top Chord Bracing Plan (Part-B) (124-300) | 06 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115506 | I491TC09-0EAAA91-002-385 | Meltshop Main Building Typical Girt Details (125-300) | 03 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115507 | I491TC09-0EAAA91-002-386 | Meltshop Main Building Base Plate And Shear Key Details Type B.P.25 (126-300) | 02 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115508 | I491TC09-0EAAA91-002-387 | Meltshop Main Building Base Plate And Shear Key Details Type B.P.26 (127-300) | 02 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115509 | I491TC09-0EAAA91-002-388 | Meltshop Main Building Base Plate And Shear Key Details Type B.P.27 (128-300) | 02 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115510 | I491TC09-0EAAA91-002-389 | Meltshop Main Building Base Plate And Shear Key Details Type B.P.28 (129-300) | 02 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115511 | I491TC09-0EAAA91-002-390 | Meltshop Main Building Base Plate And Shear Key Details Type B.P.29 (130-300) | 02 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115512 | I491TC09-0EAAA91-002-391 | Meltshop Main Building Base Plate And Shear Key Details Type B.P.30 (131-300) | 02 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115513 | I491TC09-0EAAA91-002-392 | Meltshop Main Building Base Plate And Shear Key Details Type B.P.31 (132-300) | 02 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115514 | I491TC09-0EAAA91-002-393 | Meltshop Main Building Base Plate And Shear Key Details Type B.P.32 (133-300) | 02 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115515 | I491TC09-0EAAA91-002-394 | Meltshop Main Building Base Plate And Shear Key Details Type B.P.33 (134-300) | 02 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115516 | I491TC09-0EAAA91-002-395 | Meltshop Main Building Purlin Arrangement (135-300) | 02 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115517 | I491TC09-0EAAA91-002-396 | Meltshop Main Building Vertical Bracing Type V.B.3A ,V.B.3B (136-300) | 02 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115518 | I491TC09-0EAAA91-002-397 | Meltshop Main Building Roof Framing Plan (Part-B) (137-300) | 03 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115519 | I491TC09-0EAAA91-002-398 | Meltshop Main Building Side Framing View "A" & "B" (138-300) | 04 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115520 | I491TC09-0EAAA91-002-399 | Meltshop Main Building Horizontal Platform (139-300) | 05 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115521 | I491TC09-0EAAA91-002-400 | Meltshop Main Building Side View "C" & "D" (140-300) | 03 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115522 | I491TC09-0EAAA91-002-401 | Meltshop Main Building Column Splice Details (141-300) | 01 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115523 | I491TC09-0EAAA91-002-402 | Meltshop Main Building Truss Type - T21 & T22 (142-300) | 02 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115524 | I491TC09-0EAAA91-002-403 | Meltshop Main Building Column C-22 & Details (143-300) | 02 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115525 | I491TC09-0EAAA91-002-404 | Meltshop Main Building Side Framing View "E" & "F" (144-300) | 04 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115526 | I491TC09-0EAAA91-002-405 | Meltshop Main Building Beam Roof (145-300) | 01 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115527 | I491TC09-0EAAA91-002-406 | Meltshop Main Building Main Frame At Row 1.2 (146-300) | 05 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115528 | I491TC09-0EAAA91-002-407 | Meltshop Main Building Main Frame At Row 1.A (147-300) | 04 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115529 | I491TC09-0EAAA91-002-408 | Meltshop Main Building Transverse Walkway "Tw1" (148-300) | 04 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115530 | I491TC09-0EAAA91-002-409 | Meltshop Main Building Transverse Walkway "Tw2" (149-300) | 03 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115531 | I491TC09-0EAAA91-002-410 | Meltshop Main Building Portal Bracing At Row "D" (150-300) | 03 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115532 | I491TC09-0EAAA91-002-411 | Meltshop Main Building Roof Truss Connection Details (151-300) | 01 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115533 | I491TC09-0EAAA91-002-412 | Meltshop Main Building Column Splice Details (152-300) | 02 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115534 | I491TC09-0EAAA91-002-413 | Meltshop Main Building Monorail Arrangement Between Axis 2.1&2 , 15&15.1, 2&2.1 , 14.1&15 3.1&3.2 , 14.1&15 (153-300) | 04 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115535 | I491TC09-0EAAA91-002-414 | Meltshop Main Building Typical Details (154-300) | 01 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115536 | I491TC09-0EAAA91-002-415 | Meltshop Main Building Typical Details (155-300) | 01 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115537 | I491TC09-0EAAA91-002-416 | Meltshop Main Building Truss Type - T23 & T24 (156-300) | 02 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115538 | I491TC09-0EAAA91-002-417 | Meltshop Main Building Truss Type - T25 & T26 (157-300) | 03 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115539 | I491TC09-0EAAA91-002-418 | Meltshop Main Building Cable Gallery "Cg1" (158-300) | 03 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115540 | I491TC09-0EAAA91-002-419 | Meltshop Main Building Truss Type - T8C & T3C (159-300) | 02 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115541 | I491TC09-0EAAA91-002-420 | Meltshop Main Building Truss Type - T8D & T10C (160-300) | 01 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115542 | I491TC09-0EAAA91-002-421 | Meltshop Main Building Column Splice Details (161-300) | 02 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115543 | I491TC09-0EAAA91-002-422 | Meltshop Main Building Transverse Bracing & Walkway "Tb1" & "Tw4" (162-300) | 03 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115544 | I491TC09-0EAAA91-002-423 | Meltshop Main Building Main Frame At Row 16.1 Part1 (163-300) | 02 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115545 | I491TC09-0EAAA91-002-424 | Meltshop Main Building Main Frame At Row 16.1 Part2 (164-300) | 04 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115546 | I491TC09-0EAAA91-002-425 | Meltshop Main Building Truss Type - T27 (165-300) | 02 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115547 | I491TC09-0EAAA91-002-426 | Meltshop Main Building Cable Gallery "Cg2" (166-300) | 02 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115548 | I491TC09-0EAAA91-002-427 | Meltshop Main Building Cable Gallery "Cg3" (167-300) | 03 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115549 | I491TC09-0EAAA91-002-428 | Meltshop Main Building Transverse Bracing & Walkway "Tb2" & "Tw6" (168-300) | 03 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115550 | I491TC09-0EAAA91-002-429 | Meltshop Main Building Main Frame At Rows "1.2 Part2" & "16.1 Part3" (169-300) | 05 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115551 | I491TC09-0EAAA91-002-430 | Meltshop Main Building Transverse Bracing & Walkway "Tb3" & "Tw8" (170-300) | 04 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115552 | I491TC09-0EAAA91-002-431 | Meltshop Main Building Cable Gallery "Cg4" (171-300) | 03 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115553 | I491TC09-0EAAA91-002-432 | Meltshop Main Building Transverse Bracing & Walkway "Tb4" & "Tw9" (172-300) | 03 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115554 | I491TC09-0EAAA91-002-433 | Meltshop Main Building Horizontal Platform (173-300) | 04 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115555 | I491TC09-0EAAA91-002-434 | Meltshop Main Building Horizontal Platform (174-300) | 03 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115556 | I491TC09-0EAAA91-002-435 | Meltshop Main Building Main Frame At Row "D1" (175-300) | 05 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115557 | I491TC09-0EAAA91-002-436 | Meltshop Main Building Base Plate And Shear Key Details Type B.P.34 & B.P.35 (176-300) | 03 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115558 | I491TC09-0EAAA91-002-437 | Meltshop Main Building Base Plate And Shear Key Details Type B.P.36 & B.P.37 (177-300) | 01 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115559 | I491TC09-0EAAA91-002-438 | Meltshop Main Building Base Plate And Shear Key Details Type B.P.38 B.P.39 (178-300) | 01 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115560 | I491TC09-0EAAA91-002-439 | Meltshop Main Building Base Plate And Shear Key Details Type B.P.40 (179-300) | 02 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115561 | I491TC09-0EAAA91-002-440 | Meltshop Main Building Column Splice Details (180-300) | 03 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115562 | I491TC09-0EAAA91-002-441 | Meltshop Main Building Truss Type - T13C & T14C (181-300) | 03 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115563 | I491TC09-0EAAA91-002-442 | Meltshop Main Building Column C-34B,C-35,C-36A (182-300) | 04 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115564 | I491TC09-0EAAA91-002-443 | Meltshop Main Building Main Frame At Row C & B ,D1 (183-300) | 02 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115565 | I491TC09-0EAAA91-002-444 | Meltshop Main Building Canopy Hood Plan (184-300) | 04 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115566 | I491TC09-0EAAA91-002-445 | Meltshop Main Building Canopy Hood Section At Rows E, D , D1 (185-300) | 04 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115567 | I491TC09-0EAAA91-002-446 | Meltshop Main Building Canopy Hood Section At Rows D2 , D3 , D4 (186-300) | 04 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115568 | I491TC09-0EAAA91-002-447 | Meltshop Main Building Column C-36B,C-37A,C-37B (187-300) | 04 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115569 | I491TC09-0EAAA91-002-448 | Meltshop Main Building Canopy Framing Plan (188-300) | 02 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115570 | I491TC09-0EAAA91-002-449 | Meltshop Main Building Column C-39 & Details (189-300) | 04 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115571 | I491TC09-0EAAA91-002-450 | Meltshop Main Building Typical Girt Truss Assembly (190-300) | 01 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115572 | I491TC09-0EAAA91-002-451 | Meltshop Main Building Base Plate And Shear Key Details Type B.P.42 (191-300) | 01 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115573 | I491TC09-0EAAA91-002-452 | Meltshop Main Building Base Plate And Shear Key Details Type B.P.43 (192-300) | 01 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115574 | I491TC09-0EAAA91-002-453 | Meltshop Main Building Base Plate And Shear Key Details Type B.P.44 (193-300) | 01 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115575 | I491TC09-0EAAA91-002-454 | Meltshop Main Building Canopy Hood Connection Details (194-300) | 02 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115576 | I491TC09-0EAAA91-002-455 | Meltshop Main Building Crane Girder And Platform Layout Plan (Part-A) (195-300) | 03 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115577 | I491TC09-0EAAA91-002-456 | Meltshop Main Building Crane Girder And Platform Layout Plan (Part-B) (196-300) | 04 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115578 | I491TC09-0EAAA91-002-457 | Meltshop Main Building Runway Girder (C.G.21 To C.G.25) (197-300) | 02 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115579 | I491TC09-0EAAA91-002-458 | Meltshop Main Building Crane Girder Details (198-300) | 02 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115580 | I491TC09-0EAAA91-002-459 | Meltshop Main Building Canopy Hood Section At Rows 10,10.1&11 (199-300) | 01 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115581 | I491TC09-0EAAA91-002-460 | Meltshop Main Building Canopy Hood Section At Rows 10.2 &11.1 (200-300) | 01 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115582 | I491TC09-0EAAA91-002-461 | Meltshop Main Building Canopy Hood Connection Details (201-300) | 01 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115583 | I491TC09-0EAAA91-002-462 | Meltshop Main Building Truss Type - T14D & T20A (202-300) | 01 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115584 | I491TC09-0EAAA91-002-463 | Meltshop Main Building Framing Plan At El.+21.500 (203-300) | 04 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115585 | I491TC09-0EAAA91-002-464 | Meltshop Main Building Column Splice Details (204-300) | 03 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115586 | I491TC09-0EAAA91-002-465 | Meltshop Main Building Base Plate And Shear Key Details Type B.P.45 (205-300) | 01 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115587 | I491TC09-0EAAA91-002-466 | Meltshop Main Building Base Plate And Shear Key Details Type B.P.46 (206-300) | 01 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115588 | I491TC09-0EAAA91-002-467 | Meltshop Main Building Framing Plan At El.24.700 Part A & B,C (207-300) | 01 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115589 | I491TC09-0EAAA91-002-468 | Meltshop Main Building Framing Plan At El.28.100 (208-300) | 01 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115590 | I491TC09-0EAAA91-002-469 | Meltshop Main Building Stair Plan & Section (209-300) | 02 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115591 | I491TC09-0EAAA91-002-470 | Meltshop Main Building Framing Plan At El.+21.500 (210-300) | 02 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115592 | I491TC09-0EAAA91-002-471 | Meltshop Main Building Checkered Plate Plan At El. +24.700 Part A,B,C (211-300) | 02 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115593 | I491TC09-0EAAA91-002-472 | Meltshop Main Building Checkered Plate Plan At El. +28.100 (212-300) | 02 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115594 | I491TC09-0EAAA91-002-473 | Meltshop Main Building Column C-29A & Details (213-300) | 02 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115595 | I491TC09-0EAAA91-002-474 | Meltshop Main Building Typical Detail Of Checkered Plate (214-300) | 01 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115596 | I491TC09-0EAAA91-002-479 | Meltshop Main Building Typical Grating Detail (215-300) | 01 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115597 | I491TC09-0EAAA91-002-480 | Meltshop Main Building Typical Detail Of Handrail And Ladder (216-300) | 01 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115598 | I491TC09-0EAAA91-002-481 | Meltshop Main Building Grating Plan At El: 21.500 (217-300) | 01 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115599 | I491TC09-0EAAA91-002-482 | Meltshop Main Building Grating Plan At El: 21.500 (218-300) | 01 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115600 | I491TC09-0EAAA91-002-483 | Meltshop Main Building Monorail Plan And Detail (219-300) | 01 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 10:49 | IFC | AFC | 100%
115601 | I491TC09-0EAAA91-002-484 | MELT SHOP MAIN BUILDING CANOPY HOOD CONNECTION DETAILS (220-226) | 00 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 11:10 | IFC | AFC | 100%
115602 | I491TC09-0EAAA91-002-485 | MELT SHOP MAIN BUILDING GENERAL NOTE (221-226) | 00 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 11:10 | IFC | AFC | 100%
115603 | I491TC09-0EAAA91-002-486 | MELT SHOP MAIN BUILDING BASE PLATE AND SHEAR KEY DETAILS TYPE B.P.47 (222-226) | 00 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 11:10 | IFC | AFC | 100%
115604 | I491TC09-0EAAA91-002-487 | MELT SHOP MAIN BUILDING BASE PLATE AND SHEAR KEY DETAILS TYPE B.P.48 (223-226) | 00 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 11:10 | IFC | AFC | 100%
115605 | I491TC09-0EAAA91-002-488 | MELT SHOP MAIN BUILDING OTHER TYPICAL DETAILS (224-226) | 00 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 11:10 | IFC | AFC | 100%
115606 | I491TC09-0EAAA91-002-489 | MELT SHOP MAIN BUILDING CANOPY HOOD COVER SHEET SECTION AND DETAIL1 OF 2 (225-226) | 00 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 11:10 | IFC | AFC | 100%
115607 | I491TC09-0EAAA91-002-490 | MELT SHOP MAIN BUILDING CANOPY HOOD COVER SHEET SECTION AND DETAIL 2 OF 2 (226-226) | 00 | 2016-05-18 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-25 11:10 | IFC | AFC | 100%
13920 | I491TC09-0EAAA91-003-044 | Melt Shop Main Building Runway Girder And Platform Layout Plan (Part-A) | 06 | 2012-11-04 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
13921 | I491TC09-0EAAA91-003-045 | Melt Shop Main Building Runway Girder And Platform Layout Plan (Part-B) | 06 | 2012-11-04 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
13922 | I491TC09-0EAAA91-003-046 | Melt Shop Main Building Runway Girder (C.G.1 To C.G.4 ) | 06 | 2012-11-04 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
13923 | I491TC09-0EAAA91-003-047 | Melt Shop Main Building Runway Girder (C.G.5 & C.G.6 ) | 06 | 2012-11-04 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
13924 | I491TC09-0EAAA91-003-048 | Melt Shop Main Building Runway Girder (C.G.7 To C.G.11 ) | 06 | 2012-11-04 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
13925 | I491TC09-0EAAA91-003-049 | Melt Shop Main Building Runway Girder (C.G.12 To C.G.15 ) | 06 | 2012-11-04 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
13927 | I491TC09-0EAAA91-003-050 | Melt Shop Main Building Runway Girder (C.G.16 To C.G.17 ) | 06 | 2012-11-04 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
13928 | I491TC09-0EAAA91-003-051 | Melt Shop Main Building Runway Girder (C.G.18 To C.G.20 ) | 06 | 2012-11-04 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
13929 | I491TC09-0EAAA91-003-052 | Melt Shop Main Building Runway Girder General Note | 06 | 2012-11-04 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
13930 | I491TC09-0EAAA91-003-053 | Melt Shop Main Building Runway Girder Welding Specification | 06 | 2012-11-04 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
13931 | I491TC09-0EAAA91-003-054 | Melt Shop Main Building Runway Girder Type "E" , "F" & "G" Crane Grider Support | 06 | 2012-11-04 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
13932 | I491TC09-0EAAA91-003-055 | Melt Shop Main Building Runway Girder Bottom Flange Bracing Plan (Part A) | 06 | 2012-11-04 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
13933 | I491TC09-0EAAA91-003-056 | Melt Shop Main Building Runway Girder Bottom Flange Bracing Plan (Part B) | 06 | 2012-11-04 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
13934 | I491TC09-0EAAA91-003-057 | Melt Shop Main Building Runway Girder Crane Girder To Column Connection Details | 06 | 2012-11-04 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
13935 | I491TC09-0EAAA91-003-058 | Melt Shop Main Building Runway Girder Bottom Flange Bracing Plan Type P.1 To P.8 | 06 | 2012-11-04 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
13936 | I491TC09-0EAAA91-003-059 | Melt Shop Main Building Runway Girder Bottom Flange Bracing Plan Type P.9 To P.14 | 06 | 2012-11-04 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
13938 | I491TC09-0EAAA91-003-060 | Melt Shop Main Building Runway Girder Bottom Flange Bracing Plan Type P.15 To P.21 | 06 | 2012-11-04 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
133488 | I491TC09-0EAFB91-001-001 | EAF PLATFORM GENERAL NOTES & LIST OF DRAWINGS | 02 | 2018-07-10 14:52 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Civil and Steel Structure | APEC | 2018-07-10 14:52 | IFC | AC |  | 95%
133487 | I491TC09-0EAFB91-001-002 | EAF PLATFORM FOUNDATION REINFORCEMENT PLANS & SECTIONS | 02 | 2018-07-10 14:52 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Civil and Steel Structure | APEC | 2018-07-10 14:52 | IFC | AC |  | 95%
133489 | I491TC09-0EAFB91-001-003 | EAF PLATFORM AXIS 1 TO 7' | 02 | 2018-07-10 14:52 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Civil and Steel Structure | APEC | 2018-07-10 14:52 | IFC | AC |  | 95%
133490 | I491TC09-0EAFB91-001-004 | EAF PLATFORM AXIS 8 TO 12' | 02 | 2018-07-10 14:52 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Civil and Steel Structure | APEC | 2018-07-10 14:52 | IFC | AC |  | 95%
133491 | I491TC09-0EAFB91-001-005 | EAF PLATFORM AXIS 13 TO 16 | 02 | 2018-07-10 14:52 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Civil and Steel Structure | APEC | 2018-07-10 14:52 | IFC | AC |  | 95%
133492 | I491TC09-0EAFB91-001-006 | EAF PLATFORM AXIS C TO F | 02 | 2018-07-10 14:52 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Civil and Steel Structure | APEC | 2018-07-10 14:52 | IFC | AC |  | 95%
133493 | I491TC09-0EAFB91-001-007 | EAF PLATFORM AXIS F' TO H | 02 | 2018-07-10 14:53 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Civil and Steel Structure | APEC | 2018-07-10 14:53 | IFC | AC |  | 95%
133494 | I491TC09-0EAFB91-001-008 | EAF PLATFORM AXIS J TO M | 02 | 2018-07-10 14:53 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Civil and Steel Structure | APEC | 2018-07-10 14:53 | IFC | AC |  | 95%
133495 | I491TC09-0EAFB91-001-009 | EAF PLATFORM BEAM PLAN AT LEVEL +3.80 & +5.10 | 02 | 2018-07-10 14:53 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Civil and Steel Structure | APEC | 2018-07-10 14:53 | IFC | AC |  | 95%
133496 | I491TC09-0EAFB91-001-010 | EAF PLATFORM BEAM PLAN AT LEVEL +4.00 | 02 | 2018-07-10 14:53 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Civil and Steel Structure | APEC | 2018-07-10 14:53 | IFC | AC |  | 95%
133497 | I491TC09-0EAFB91-001-011 | EAF PLATFORM BEAM PLAN AT LEVEL +8.50 | 02 | 2018-07-10 14:53 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Civil and Steel Structure | APEC | 2018-07-10 14:53 | IFC | AC |  | 95%
133498 | I491TC09-0EAFB91-001-012 | EAF PLATFORM BEAM PLAN AT LEVEL +6.60 & +15.00 & +16.00 | 02 | 2018-07-10 14:53 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Civil and Steel Structure | APEC | 2018-07-10 14:53 | IFC | AC |  | 95%
133499 | I491TC09-0EAFB91-001-013 | EAF PLATFORM BEAM PLAN AT LEVEL +17.50 | 02 | 2018-07-10 14:53 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Civil and Steel Structure | APEC | 2018-07-10 14:53 | IFC | AC |  | 95%
133500 | I491TC09-0EAFB91-001-014 | EAF PLATFORM BEAM PLAN AT LEVEL +18.20 & +18.60 | 02 | 2018-07-10 14:53 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Civil and Steel Structure | APEC | 2018-07-10 14:53 | IFC | AC |  | 95%
133501 | I491TC09-0EAFB91-001-015 | EAF PLATFORM BEAM PLAN AT LEVEL +19.50 & +20.80 | 02 | 2018-07-10 14:53 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Civil and Steel Structure | APEC | 2018-07-10 14:53 | IFC | AC |  | 95%
133502 | I491TC09-0EAFB91-001-016 | EAF PLATFORM BEAM PLAN AT LEVEL +21.20 & +21.50 | 02 | 2018-07-10 14:53 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Civil and Steel Structure | APEC | 2018-07-10 14:53 | IFC | AC |  | 95%
133503 | I491TC09-0EAFB91-001-017 | EAF PLATFORM EAF PLATFORM FOUNDATION PLAN AT LEVEL +3.90 & +5.10 | 02 | 2018-07-10 14:53 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Civil and Steel Structure | APEC | 2018-07-10 14:53 | IFC | AC |  | 95%
133504 | I491TC09-0EAFB91-001-018 | EAF PLATFORM PLAN AT LEVEL +4.00 | 02 | 2018-07-10 14:53 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Civil and Steel Structure | APEC | 2018-07-10 14:53 | IFC | AC |  | 95%
133505 | I491TC09-0EAFB91-001-019 | EAF PLATFORM PLAN AT LEVEL +8.50 | 02 | 2018-07-10 14:53 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Civil and Steel Structure | APEC | 2018-07-10 14:53 | IFC | AC |  | 95%
133506 | I491TC09-0EAFB91-001-020 | EAF PLATFORM PLAN AT LEVEL +6.60 & +15.00 & +16.00 | 02 | 2018-07-10 14:53 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Civil and Steel Structure | APEC | 2018-07-10 14:53 | IFC | AC |  | 95%
133507 | I491TC09-0EAFB91-001-021 | EAF PLATFORM PLAN AT LEVEL +17.50 | 02 | 2018-07-10 14:53 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Civil and Steel Structure | APEC | 2018-07-10 14:53 | IFC | AC |  | 95%
133508 | I491TC09-0EAFB91-001-022 | EAF PLATFORM PLAN AT LEVEL +18.20 & +18.60 | 02 | 2018-07-10 14:53 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Civil and Steel Structure | APEC | 2018-07-10 14:53 | IFC | AC |  | 95%
133509 | I491TC09-0EAFB91-001-023 | EAF PLATFORM PLAN AT LEVEL +19.50 & +20.80 | 02 | 2018-07-10 14:53 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Civil and Steel Structure | APEC | 2018-07-10 14:53 | IFC | AC |  | 95%
133510 | I491TC09-0EAFB91-001-024 | EAF PLATFORM PLAN AT LEVEL +21.20 & +21.50 | 02 | 2018-07-10 14:53 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Civil and Steel Structure | APEC | 2018-07-10 14:53 | IFC | AC |  | 95%
133511 | I491TC09-0EAFB91-001-025 | EAF PLATFORM STAIR PLAN AND VIEW | 02 | 2018-07-10 14:53 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Civil and Steel Structure | APEC | 2018-07-10 14:53 | IFC | AC |  | 95%
133512 | I491TC09-0EAFB91-001-026 | EAF PLATFORM BASEPLATE LAYOUT PLAN | 02 | 2018-07-10 14:53 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Civil and Steel Structure | APEC | 2018-07-10 14:53 | IFC | AC |  | 95%
133513 | I491TC09-0EAFB91-001-027 | EAF PLATFORM BASEPLATE TYPE "1" TO "7" | 02 | 2018-07-10 14:53 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Civil and Steel Structure | APEC | 2018-07-10 14:53 | IFC | AC |  | 95%
133514 | I491TC09-0EAFB91-001-028 | EAF PLATFORM FOUNDATION BASEPLATE TYPE "8" TO "15" | 02 | 2018-07-10 14:53 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Civil and Steel Structure | APEC | 2018-07-10 14:53 | IFC | AC |  | 95%
133515 | I491TC09-0EAFB91-001-029 | EAF PLATFORM SHEAR KEY LAYOUT PLAN | 02 | 2018-07-10 14:53 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Civil and Steel Structure | APEC | 2018-07-10 14:53 | IFC | AC |  | 95%
133516 | I491TC09-0EAFB91-001-030 | EAF PLATFORM SHEAR KEY DETAILS | 02 | 2018-07-10 14:54 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Civil and Steel Structure | APEC | 2018-07-10 14:54 | IFC | AC |  | 95%
133517 | I491TC09-0EAFB91-001-031 | EAF PLATFORM TYPICAL CONNECTION DETAILS | 02 | 2018-07-10 14:54 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Civil and Steel Structure | APEC | 2018-07-10 14:54 | IFC | AC |  | 95%
133518 | I491TC09-0EAFB91-001-032 | EAF PLATFORM STAIR SECTION & VIEWS | 02 | 2018-07-10 14:54 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Civil and Steel Structure | APEC | 2018-07-10 14:54 | IFC | AC |  | 95%
133519 | I491TC09-0EAFB91-001-033 | EAF PLATFORM STAIR SECTION, VIEWS & DETAILS | 02 | 2018-07-10 14:54 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Civil and Steel Structure | APEC | 2018-07-10 14:54 | IFC | AC |  | 95%
133520 | I491TC09-0EAFB91-001-034 | EAF PLATFORM TYPICAL CONNECTION DETAILS | 02 | 2018-07-10 14:54 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Civil and Steel Structure | APEC | 2018-07-10 14:54 | IFC | AC |  | 95%
131382 | I491TC09-0EAFB91-002-001 | EAF-LF ACCESS BRIDGE 1-2 | 01 | 2017-10-14 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2017-10-16 14:20 | IFC | AFC | 100%
131383 | I491TC09-0EAFB91-002-002 | EAF-LF ACCESS BRIDGE 2-2 | 01 | 2017-10-14 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2017-10-16 14:20 | IFC | AFC | 100%
13964 | I491TC09-0EAFG02-001-001 | Center Price Roof Eaf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
13965 | I491TC09-0EAFM01-001-001 | Steel Structure Lower Shell | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | TAM |  | IFI | OB | 100%
113204 | I491TC09-0EAFM02-001-001 | Lower Shell Steel Structure | 01 | 2015-01-07 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS | 2015-01-10 14:26 | IFI | OB | 100%
113205 | I491TC09-0EAFM03-001-001 | Lower Shell-Steel Structure | 01 | 2015-01-07 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS | 2015-01-10 14:26 | IFI | OB | 100%
13968 | I491TC09-0EAFM04-001-001 | Lower Part-Steel Structure | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
13969 | I491TC09-0EAFM05-001-001 | Lower Part-Steel Structure | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
13970 | I491TC09-0EAFM06-001-001 | Lower Part-Steel Structure | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
13971 | I491TC09-0EAFM07-001-001 | Lower Part-Steel Structure | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
13972 | I491TC09-0EAFM08-001-001 | Lower Part-Steel Structure | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
115062 | I491TC09-0EAIE01-001-001 | Electrode Nippling Stand EAF WORKING PLATFORM | 00 | 2016-03-15 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS | 2016-04-02 13:52 | IFI | OB | 100%
115063 | I491TC09-0EAIE01-002-001 | Electrode Nippling Stand EAF WORKING PLATFORM | 00 | 2016-03-15 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS | 2016-04-02 13:52 | IFI | OB | 100%
115064 | I491TC09-0EAIE01-003-001 | Electrode Nippling Stand LOWER PART EAF WORKING PLATFORM 1-2 | 00 | 2016-03-15 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS | 2016-04-02 13:52 | IFI | OB | 100%
115065 | I491TC09-0EAIE01-003-002 | Electrode Nippling Stand LOWER PART EAF WORKING PLATFORM 2-2 | 00 | 2016-03-15 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS | 2016-04-02 13:52 | IFI | OB | 100%
115066 | I491TC09-0EAIE01-004-001 | Electrode Nippling Stand COVER EAF WORKING PLATFORM | 00 | 2016-03-15 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS | 2016-04-02 13:52 | IFI | OB | 100%
115067 | I491TC09-0EAIE01-005-001 | Electrode HYDRAULIC Nippling Stand LOWER PART EAF WORKING PLATFORM 1-2 | 00 | 2016-03-15 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS | 2016-04-02 13:52 | IFI | OB | 100%
115068 | I491TC09-0EAIE01-005-002 | Electrode HYDRAULIC Nippling Stand LOWER PART EAF WORKING PLATFORM 2-2 | 00 | 2016-03-15 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS | 2016-04-02 13:52 | IFI | OB | 100%
115069 | I491TC09-0EAIE01-006-001 | Clamping Pad Sheet 1 | 00 | 2016-03-15 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS | 2016-04-02 13:52 | IFI | OB | 100%
115070 | I491TC09-0EAIE01-007-001 | Clamping Base EAF WORKING PLATFORM | 00 | 2016-03-15 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS | 2016-04-02 13:52 | IFI | OB | 100%
115071 | I491TC09-0EAIE01-008-001 | Clamping Pad EAF WORKING PLATFORM | 00 | 2016-03-15 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS | 2016-04-02 13:52 | IFI | OB | 100%
130244 | I491TC09-0EAIE01-009-001 | Nippling Stand Structure Loading Sheet | 00 | 2017-01-16 | Indeterminate | Drawing | Detail | Melt Shop | Mechanical | TAM | 2017-01-21 13:41 | IFI | OB | 100%
134323 | I491TC09-0EASM03-001-001 | EAF-Slag Cooling Pit Wall Protection | 00 | 2018-10-23 | Indeterminate | Drawing | Detail | Slag Yard | Civil and Steel Structure | TAM | 2018-10-27 08:57 | IFA | AC |  | 95%
13973 | I491TC09-0LFFB01-001-001 | Lf Working Platform Platform | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Civil and Steel Structure | TAM |  | IFI | OB | 100%
116098 | I491TC09-0LFFB91-001-001 | LF PLATFORM COLUMN LAYOUT PLAN | 02 | 2016-07-13 10:52 | Indeterminate | Drawing | Detail | Ladle Furnace | Civil and Steel Structure | TAM | 2016-07-13 10:52 | IFC | AFC | 100%
116099 | I491TC09-0LFFB91-001-002 | LF PLATFORM BEAM PLAN AT LEVEL +5.97 | 02 | 2016-07-13 10:52 | Indeterminate | Drawing | Detail | Ladle Furnace | Civil and Steel Structure | TAM | 2016-07-13 10:52 | IFC | AFC | 100%
116100 | I491TC09-0LFFB91-001-003 | LF PLATFORM BEAM PLAN AT LEVEL +10.00 | 02 | 2016-07-13 10:52 | Indeterminate | Drawing | Detail | Ladle Furnace | Civil and Steel Structure | TAM | 2016-07-13 10:52 | IFC | AFC | 100%
116101 | I491TC09-0LFFB91-001-004 | LF PLATFORM AXIS 1 TO 9 | 02 | 2016-07-13 10:52 | Indeterminate | Drawing | Detail | Ladle Furnace | Civil and Steel Structure | TAM | 2016-07-13 10:52 | IFC | AFC | 100%
116102 | I491TC09-0LFFB91-001-005 | LF PLATFORM AXIS A TO G | 02 | 2016-07-13 10:52 | Indeterminate | Drawing | Detail | Ladle Furnace | Civil and Steel Structure | TAM | 2016-07-13 10:52 | IFC | AFC | 100%
116103 | I491TC09-0LFFB91-001-006 | LF PLATFORM PLAN AT LEVEL +5.97 | 02 | 2016-07-13 10:52 | Indeterminate | Drawing | Detail | Ladle Furnace | Civil and Steel Structure | TAM | 2016-07-13 10:52 | IFC | AFC | 100%
116104 | I491TC09-0LFFB91-001-007 | LF PLATFORM PLAN AT LEVEL +10.00 | 02 | 2016-07-13 10:52 | Indeterminate | Drawing | Detail | Ladle Furnace | Civil and Steel Structure | TAM | 2016-07-13 10:52 | IFC | AFC | 100%
116105 | I491TC09-0LFFB91-001-008 | LF PLATFORM BASE PLATE & CONNECTIONS DETAILS | 02 | 2016-07-13 10:52 | Indeterminate | Drawing | Detail | Ladle Furnace | Civil and Steel Structure | TAM | 2016-07-13 10:52 | IFC | AFC | 100%
116106 | I491TC09-0LFFB91-001-009 | LF PLATFORM STAIR TYPE 1 & 2 & 3 &4 | 02 | 2016-07-13 10:52 | Indeterminate | Drawing | Detail | Ladle Furnace | Civil and Steel Structure | TAM | 2016-07-13 10:52 | IFC | AFC | 100%
116107 | I491TC09-0LFFB91-001-010 | LF PLATFORM STAIR TYPE 4 & 5 | 01 | 2016-07-13 10:52 | Indeterminate | Drawing | Detail | Ladle Furnace | Civil and Steel Structure | TAM | 2016-07-13 10:52 | IFC | AFC | 100%
116097 | I491TC09-0LFFB91-001-011 | LF PLATFORM STAIR TYPE 4 & 5 | 00 | 2016-07-13 10:52 | Indeterminate | Drawing | Detail | Ladle Furnace | Civil and Steel Structure | TAM | 2016-07-13 10:52 | IFC | AFC | 100%
131362 | I491TC09-0LFFB91-002-001 | MELT SHOP - LF PLATFORM EAST STAIR AND ACCESS PLATFORM STEEL STRUCTURE AND DETAILS | 01 | 2017-10-04 | Indeterminate | Drawing | Detail | Ladle Furnace | Civil and Steel Structure | TAM | 2017-10-11 13:45 | IFC | AFC | 100%
13974 | I491TC09-0LFIE01-001-001 | Electrode Nippling Stand Lf Working Platform | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace Auxiliary | Civil and Steel Structure | APEC |  | IFI | OB | 100%
13975 | I491TC09-0LFIE02-001-001 | Electrode Nippling Stand Lf Working Platform | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace Auxiliary | Civil and Steel Structure | APEC |  | IFI | OB | 100%
13976 | I491TC09-0LFIE03-001-001 | Electrode Nippling Stand Lf Working Platform | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace Auxiliary | Civil and Steel Structure | APEC |  | IFI | OB | 100%
13977 | I491TC09-0LFIE04-001-001 | Electrode Nippling Stand Lf Working Platform | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace Auxiliary | Civil and Steel Structure | APEC |  | IFI | OB | 100%
13978 | I491TC09-0LFIE05-001-001 | Electrode Nippling Stand Lf Working Platform | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace Auxiliary | Civil and Steel Structure | APEC |  | IFI | OB | 100%
13979 | I491TC09-0LFIE06-001-001 | Electrode Nippling Stand Lf Working Platform | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace Auxiliary | Civil and Steel Structure | APEC |  | IFI | OB | 100%
13980 | I491TC09-0LFIE07-001-001 | Electrode Nippling Stand Lf Working Platform | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace Auxiliary | Civil and Steel Structure | APEC |  | IFI | OB | 100%
113068 | I491TC09-0MDAA91-001-001 | Trnsfer Tower Md-Tt-01-01 Steel Structure Column Plan,Framing,Details | 03 | 2014-11-12 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | DATIS | 2014-11-15 14:16 | IFC | AFC | 100%
113036 | I491TC09-0MDAA91-002-001 | Trnsfer Tower Md-Tt-01-01 Steel Structure Formwork & Framing Plans | 02 | 2014-10-19 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | DATIS | 2014-10-21 13:26 | IFC | AC |  | 95%
113069 | I491TC09-0MDAA91-003-001 | Trnsfer Tower Md-Tt-01-01 Steel Structure Connection Details | 03 | 2014-11-12 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | DATIS | 2014-11-15 14:16 | IFC | AFC | 100%
130535 | I491TC09-0MDCV05-001-001 | OUTDOOR FERROALLOY MHS PART - 6 GENERAL LAYOUT PLAN & SIDE VIEW 1-9 | 02 | 2017-04-29 | Indeterminate | Drawing | Detail | Material Handling | Civil and Steel Structure | IKS | 2017-04-30 15:59 | IFC | AC |  | 95%
130536 | I491TC09-0MDCV05-001-002 | OUTDOOR FERROALLOY MHS PART - 6 TRUSS " T-1 " 2-9 | 02 | 2017-04-29 | Indeterminate | Drawing | Detail | Material Handling | Civil and Steel Structure | IKS | 2017-04-30 15:59 | IFC | AC |  | 95%
130537 | I491TC09-0MDCV05-001-003 | OUTDOOR FERROALLOY MHS PART - 6 TRUSS " T-2 " 3-9 | 02 | 2017-04-29 | Indeterminate | Drawing | Detail | Material Handling | Civil and Steel Structure | IKS | 2017-04-30 15:59 | IFC | AC |  | 95%
130538 | I491TC09-0MDCV05-001-004 | OUTDOOR FERROALLOY MHS PART - 6 TRUSS " T-3 " 4-9 | 02 | 2017-04-29 | Indeterminate | Drawing | Detail | Material Handling | Civil and Steel Structure | IKS | 2017-04-30 15:59 | IFC | AC |  | 95%
130539 | I491TC09-0MDCV05-001-005 | OUTDOOR FERROALLOY MHS PART - 6 TRUSS " T-4 " 5-9 | 02 | 2017-04-30 15:59 | Indeterminate | Drawing | Detail | Material Handling | Civil and Steel Structure | IKS | 2017-04-30 15:59 | IFC | AC |  | 95%
130540 | I491TC09-0MDCV05-001-006 | OUTDOOR FERROALLOY MHS PART - 6 TAKE UP DET. 6-9 | 02 | 2017-04-29 | Indeterminate | Drawing | Detail | Material Handling | Civil and Steel Structure | IKS | 2017-04-30 16:00 | IFC | AC |  | 95%
130542 | I491TC09-0MDCV05-001-007 | OUTDOOR FERROALLOY MHS PART - 6 TAKE UP DET. 7-9 | 02 | 2017-04-29 | Indeterminate | Drawing | Detail | Material Handling | Civil and Steel Structure | IKS | 2017-04-30 16:00 | IFC | AFC | 100%
130541 | I491TC09-0MDCV05-001-008 | OUTDOOR FERROALLOY MHS PART - 6 FRAME VIEW & DET. 8-9 | 02 | 2017-04-29 | Indeterminate | Drawing | Detail | Material Handling | Civil and Steel Structure | IKS | 2017-04-30 16:00 | IFC | AFC | 100%
130543 | I491TC09-0MDCV05-001-009 | OUTDOOR FERROALLOY MHS PART - 6 FRAME VIEW & DET. 9-9 | 00 | 2017-04-29 | Indeterminate | Drawing | Detail | Material Handling | Civil and Steel Structure | IKS | 2017-04-30 16:53 | IFC | AFC | 100%
111499 | I491TC09-0MDCV09-001-001 | BIN CHARGHIMG (DRI) PART - 7 GENERAL LAYOUT PLAN | 00 | 2014-01-08 | Indeterminate | Drawing | Detail | Material Handling | Civil and Steel Structure | TAM | 2014-04-22 12:11 | IFA | AC |  | 95%
111500 | I491TC09-0MDCV09-001-002 | BIN CHARGHIMG (DRI) PART - 7 GENERAL LAYOUT PLAN & SIDE VIEW | 00 | 2014-01-08 | Indeterminate | Drawing | Detail | Material Handling | Civil and Steel Structure | TAM | 2014-04-22 12:11 | IFA | AC |  | 95%
111501 | I491TC09-0MDCV09-001-003 | BIN CHARGHIMG (DRI) PART - 7 GENERAL LAYOUT PLAN & SIDE VIEW | 00 | 2014-01-08 | Indeterminate | Drawing | Detail | Material Handling | Civil and Steel Structure | TAM | 2014-04-22 12:11 | IFA | AC |  | 95%
111502 | I491TC09-0MDCV09-001-004 | BIN CHARGHIMG (DRI) PART - 7 TRUSS " T-1 " | 00 | 2014-01-08 | Indeterminate | Drawing | Detail | Material Handling | Civil and Steel Structure | TAM | 2014-04-22 12:11 | IFA | AC |  | 95%
111503 | I491TC09-0MDCV09-001-005 | BIN CHARGHIMG (DRI) PART - 7 TRUSS " T-2 " | 00 | 2014-01-08 | Indeterminate | Drawing | Detail | Material Handling | Civil and Steel Structure | TAM | 2014-04-22 12:11 | IFA | AC |  | 95%
111504 | I491TC09-0MDCV09-001-006 | BIN CHARGHIMG (DRI) PART - 7 TRUSS " T-3 " | 00 | 2014-01-08 | Indeterminate | Drawing | Detail | Material Handling | Civil and Steel Structure | TAM | 2014-04-22 12:11 | IFA | AC |  | 95%
111506 | I491TC09-0MDCV09-001-007 | BIN CHARGHIMG (DRI) PART - 7 TRUSS " T-4 " | 00 | 2014-01-08 | Indeterminate | Drawing | Detail | Material Handling | Civil and Steel Structure | TAM | 2014-04-22 12:11 | IFA | AC |  | 95%
111505 | I491TC09-0MDCV09-001-008 | BIN CHARGHIMG (DRI) PART - 7 TRUSS " T-5 " | 00 | 2014-01-08 | Indeterminate | Drawing | Detail | Material Handling | Civil and Steel Structure | TAM | 2014-04-22 12:11 | IFA | AC |  | 95%
111507 | I491TC09-0MDCV09-001-009 | BIN CHARGHIMG (DRI) PART - 7 TRUSS " T-6 " | 00 | 2014-01-08 | Indeterminate | Drawing | Detail | Material Handling | Civil and Steel Structure | TAM | 2014-04-22 12:11 | IFA | AC |  | 95%
111508 | I491TC09-0MDCV09-001-010 | BIN CHARGHIMG (DRI) PART - 7 TRUSS " T-7 " | 00 | 2014-01-08 | Indeterminate | Drawing | Detail | Material Handling | Civil and Steel Structure | TAM | 2014-04-22 12:11 | IFA | AC |  | 95%
111510 | I491TC09-0MDCV09-001-011 | BIN CHARGHIMG (DRI) PART - 7 TRUSS " T-8 " | 00 | 2014-01-08 | Indeterminate | Drawing | Detail | Material Handling | Civil and Steel Structure | TAM | 2014-04-22 12:11 | IFA | AC |  | 95%
111511 | I491TC09-0MDCV09-001-012 | BIN CHARGHIMG (DRI) PART - 7 TRUSS " T-9 " | 00 | 2014-01-08 | Indeterminate | Drawing | Detail | Material Handling | Civil and Steel Structure | TAM | 2014-04-22 12:11 | IFA | AC |  | 95%
111509 | I491TC09-0MDCV09-001-013 | BIN CHARGHIMG (DRI) PART - 7 FRAMING PLAN & DET. TRANSFER TOWER | 00 | 2014-01-08 | Indeterminate | Drawing | Detail | Material Handling | Civil and Steel Structure | TAM | 2014-04-22 12:11 | IFA | AC |  | 95%
111513 | I491TC09-0MDCV09-001-014 | BIN CHARGHIMG (DRI) PART - 7 SIDE VIEW TRANSFER TOWER | 00 | 2014-01-08 | Indeterminate | Drawing | Detail | Material Handling | Civil and Steel Structure | TAM | 2014-04-22 12:11 | IFA | AC |  | 95%
111512 | I491TC09-0MDCV09-001-015 | BIN CHARGHIMG (DRI) PART - 7 TRANSFER TOWER DET. | 00 | 2014-01-08 | Indeterminate | Drawing | Detail | Material Handling | Civil and Steel Structure | TAM | 2014-04-22 12:11 | IFA | AC |  | 95%
111514 | I491TC09-0MDCV09-001-016 | BIN CHARGHIMG (DRI) PART - 7 FRAMING VIEW & DET. | 00 | 2014-01-08 | Indeterminate | Drawing | Detail | Material Handling | Civil and Steel Structure | TAM | 2014-04-22 12:11 | IFA | AC |  | 95%
111517 | I491TC09-0MDCV09-001-017 | BIN CHARGHIMG (DRI) PART - 7 FRAMING VIEW & DET. | 00 | 2014-01-08 | Indeterminate | Drawing | Detail | Material Handling | Civil and Steel Structure | TAM | 2014-04-22 12:11 | IFA | AC |  | 95%
111516 | I491TC09-0MDCV09-001-018 | BIN CHARGHIMG (DRI) PART - 7 FRAMING DET. | 00 | 2014-01-08 | Indeterminate | Drawing | Detail | Material Handling | Civil and Steel Structure | TAM | 2014-04-22 12:11 | IFA | AC |  | 95%
111515 | I491TC09-0MDCV09-001-019 | BIN CHARGHIMG (DRI) PART - 7 FRAMING VIEW & DET. | 00 | 2014-01-08 | Indeterminate | Drawing | Detail | Material Handling | Civil and Steel Structure | TAM | 2014-04-22 12:11 | IFA | AC |  | 95%
135189 | I491TC09-0MDSI01-001-001 | LIME & CARBONE INJ. SILOS FRAME WORK PLANS BASIC DRAWING (PHASE I) | 02 | 2019-03-18 12:38 | Indeterminate | Drawing | Detail | Material Handling | Civil and Steel Structure | TAM | 2019-03-18 12:38 | IFC | AC |  | 95%
135190 | I491TC09-0MDSI01-002-001 | LIME & CARBONE INJ. SILOS FRAME SECTIONS BASIC DRAWING (PHASE I) | 02 | 2019-03-18 12:38 | Indeterminate | Drawing | Detail | Material Handling | Civil and Steel Structure | TAM | 2019-03-18 12:38 | IFC | AC |  | 95%
135191 | I491TC09-0MDSI01-003-001 | LIME & CARBONE INJ. SILOS CONNECTION DETAILS 3-8 | 01 | 2019-03-18 12:38 | Indeterminate | Drawing | Detail | Material Handling | Civil and Steel Structure | TAM | 2019-03-18 12:38 | IFC | AC |  | 95%
135192 | I491TC09-0MDSI01-004-001 | LIME & CARBONE INJ. SILOS CONNECTION DETAILS 4-8 | 01 | 2019-03-18 12:38 | Indeterminate | Drawing | Detail | Material Handling | Civil and Steel Structure | TAM | 2019-03-18 12:38 | IFC | AC |  | 95%
135193 | I491TC09-0MDSI01-005-001 | LIME & CARBONE INJ. SILOS CONNECTION DETAILS 5-8 | 01 | 2019-03-18 12:39 | Indeterminate | Drawing | Detail | Material Handling | Civil and Steel Structure | TAM | 2019-03-18 12:39 | IFC | AC |  | 95%
135194 | I491TC09-0MDSI01-006-001 | LIME & CARBONE INJ. SILOS CONNECTION DETAILS 6-8 | 01 | 2019-03-18 12:39 | Indeterminate | Drawing | Detail | Material Handling | Civil and Steel Structure | TAM | 2019-03-18 12:39 | IFC | AC |  | 95%
135195 | I491TC09-0MDSI01-007-001 | LIME & CARBONE INJ. SILOS CONNECTION DETAILS 7-8 | 01 | 2019-03-18 12:39 | Indeterminate | Drawing | Detail | Material Handling | Civil and Steel Structure | TAM | 2019-03-18 12:39 | IFC | AC |  | 95%
135196 | I491TC09-0MDSI01-008-001 | LIME & CARBONE INJ. SILOS CONNECTION DETAILS 8-8 | 01 | 2019-03-18 12:39 | Indeterminate | Drawing | Detail | Material Handling | Civil and Steel Structure | TAM | 2019-03-18 12:39 | IFC | AC |  | 95%
115671 | I491TC09-0MDSS91-001-001 | MATERIAL HANDLING SYSTEM EAF GENERAL NOTES 1-36 | 01 | 2016-06-07 08:50 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-06-07 08:50 | IFC | AFC | 100%
115672 | I491TC09-0MDSS91-001-002 | MATERIAL HANDLING SYSTEM EAF WELDING SPECIFICATION 2-36 | 01 | 2016-06-07 08:50 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-06-07 08:50 | IFC | AFC | 100%
115674 | I491TC09-0MDSS91-001-003 | MATERIAL HANDLING SYSTEM EAF COLUMN LAYOUT PLAN 3-39 | 01 | 2016-06-07 08:50 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-06-07 08:50 | IFC | AFC | 100%
115673 | I491TC09-0MDSS91-001-004 | MATERIAL HANDLING SYSTEM EAF FRAMING PLAN AT EL. +8.70 & +11.10 4-36 | 01 | 2016-06-07 08:50 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-06-07 08:50 | IFC | AFC | 100%
115675 | I491TC09-0MDSS91-001-005 | MATERIAL HANDLING SYSTEM EAF FRAMING PLAN AT EL. +12.10 &+17.00 5-36 | 01 | 2016-06-07 08:50 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-06-07 08:50 | IFC | AFC | 100%
115676 | I491TC09-0MDSS91-001-006 | MATERIAL HANDLING SYSTEM EAF FRAMING VIEW ON AXISES A',B',D',E',F'&G' 6-36 | 01 | 2016-06-07 08:50 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-06-07 08:50 | IFC | AFC | 100%
115677 | I491TC09-0MDSS91-001-007 | MATERIAL HANDLING SYSTEM EAF FRAMING VIEW ON AXIS 1 & 2 7-36 | 01 | 2016-06-07 08:50 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-06-07 08:50 | IFC | AFC | 100%
115678 | I491TC09-0MDSS91-001-008 | MATERIAL HANDLING SYSTEM EAF BEAM & COLUMN SECTIONS 8-36 | 01 | 2016-06-07 08:50 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-06-07 08:50 | IFC | AFC | 100%
115679 | I491TC09-0MDSS91-001-009 | MATERIAL HANDLING SYSTEM EAF BASE PLATE PLAN 9-36 | 01 | 2016-06-07 08:50 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-06-07 08:50 | IFC | AFC | 100%
115680 | I491TC09-0MDSS91-001-010 | MATERIAL HANDLING SYSTEM EAF COLUMN BASE PLATE TYPE B.P.1 10-36 | 01 | 2016-06-07 08:50 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-06-07 08:50 | IFC | AFC | 100%
115681 | I491TC09-0MDSS91-001-011 | MATERIAL HANDLING SYSTEM EAF COLUMN BASE PLATE TYPE B.P.2 11-36 | 01 | 2016-06-07 08:50 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-06-07 08:50 | IFC | AFC | 100%
115682 | I491TC09-0MDSS91-001-012 | MATERIAL HANDLING SYSTEM EAF COLUMN BASE PLATE TYPE B.P.3 12-36 | 01 | 2016-06-07 08:50 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-06-07 08:50 | IFC | AFC | 100%
115683 | I491TC09-0MDSS91-001-013 | MATERIAL HANDLING SYSTEM EAF COLUMN BASE PLATE TYPE B.P.4 (1 OF 2) 13-36 | 01 | 2016-06-07 08:50 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-06-07 08:50 | IFC | AFC | 100%
115684 | I491TC09-0MDSS91-001-014 | MATERIAL HANDLING SYSTEM EAF COLUMN BASE PLATE TYPE B.P.4 (2 OF 2) 14-36 | 01 | 2016-06-07 08:50 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-06-07 08:50 | IFC | AFC | 100%
115685 | I491TC09-0MDSS91-001-015 | MATERIAL HANDLING SYSTEM EAF COLUMN BASE PLATE TYPE B.P.5 15-36 | 01 | 2016-06-07 08:50 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-06-07 08:50 | IFC | AFC | 100%
115686 | I491TC09-0MDSS91-001-016 | MATERIAL HANDLING SYSTEM EAF VERTICAL BRACING DETAILS 16-36 | 01 | 2016-06-07 08:50 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-06-07 08:50 | IFC | AFC | 100%
115687 | I491TC09-0MDSS91-001-017 | MATERIAL HANDLING SYSTEM EAF TYPICAL HORIZONTAL BRACING 17-36 | 01 | 2016-06-07 08:50 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-06-07 08:50 | IFC | AFC | 100%
115688 | I491TC09-0MDSS91-001-018 | MATERIAL HANDLING SYSTEM EAF TYPICAL STITCHES OF BRACINGS 18-36 | 01 | 2016-06-07 08:50 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-06-07 08:50 | IFC | AFC | 100%
115689 | I491TC09-0MDSS91-001-019 | MATERIAL HANDLING SYSTEM EAF BEAM B-1 CONNECTIONS 19-36 | 01 | 2016-06-07 08:50 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-06-07 08:50 | IFC | AFC | 100%
115690 | I491TC09-0MDSS91-001-020 | MATERIAL HANDLING SYSTEM EAF BEAM B-1 CONNECTION DETAILES 20-36 | 01 | 2016-06-07 08:50 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-06-07 08:50 | IFC | AFC | 100%
115691 | I491TC09-0MDSS91-001-021 | MATERIAL HANDLING SYSTEM EAF BEAM B-2, B-4 & B-5 CONNECTIONS 21-36 | 01 | 2016-06-07 08:50 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-06-07 08:50 | IFC | AFC | 100%
115692 | I491TC09-0MDSS91-001-022 | MATERIAL HANDLING SYSTEM EAF BEAM B-6 & B-9 CONNECTIONS 22-36 | 01 | 2016-06-07 08:50 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-06-07 08:50 | IFC | AFC | 100%
115693 | I491TC09-0MDSS91-001-023 | MATERIAL HANDLING SYSTEM EAF BEAM B-10 CONNECTIONS 23-36 | 01 | 2016-06-07 08:50 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-06-07 08:50 | IFC | AFC | 100%
115694 | I491TC09-0MDSS91-001-024 | MATERIAL HANDLING SYSTEM EAF BEAM SUPPORT-1 CONNECTIONS 24-36 | 01 | 2016-06-07 08:50 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-06-07 08:50 | IFC | AFC | 100%
115695 | I491TC09-0MDSS91-001-025 | MATERIAL HANDLING SYSTEM EAF BEAM SUPPORT-2 CONNECTIONS (1 OF 2) 25-36 | 01 | 2016-06-07 08:50 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-06-07 08:50 | IFC | AFC | 100%
115696 | I491TC09-0MDSS91-001-026 | MATERIAL HANDLING SYSTEM EAF BEAM SUPPORT-2 CONNECTIONS (2 OF 2) 26-36 | 01 | 2016-06-07 08:50 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-06-07 08:50 | IFC | AFC | 100%
115697 | I491TC09-0MDSS91-001-027 | MATERIAL HANDLING SYSTEM EAF BEAM SUPPORT-3 CONNECTIONS 27-36 | 01 | 2016-06-07 08:50 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-06-07 08:50 | IFC | AFC | 100%
115698 | I491TC09-0MDSS91-001-028 | MATERIAL HANDLING SYSTEM EAF BEAM TO BEAM CONNECTIONS 28-36 | 01 | 2016-06-07 08:50 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-06-07 08:50 | IFC | AFC | 100%
115699 | I491TC09-0MDSS91-001-029 | MATERIAL HANDLING SYSTEM EAF TRUSS SUPPORT OF MOVEABLE HOPPER 29-36 | 01 | 2016-06-07 08:50 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-06-07 08:50 | IFC | AFC | 100%
115700 | I491TC09-0MDSS91-001-030 | MATERIAL HANDLING SYSTEM EAFTYPICAL DETAIL OF TRUSS 30-36 | 01 | 2016-06-07 08:50 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-06-07 08:50 | IFC | AFC | 100%
115701 | I491TC09-0MDSS91-001-031 | MATERIAL HANDLING SYSTEM EAF COLUMN C-4 DETAILS AND SECTION 31-36 | 01 | 2016-06-07 08:50 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-06-07 08:50 | IFC | AFC | 100%
115702 | I491TC09-0MDSS91-001-032 | MATERIAL HANDLING SYSTEM EAF BEAM "B-1","BS-1","BS-2" & "BS-3" STIFFENERS 32-36 | 01 | 2016-06-07 08:50 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-06-07 08:50 | IFC | AFC | 100%
115703 | I491TC09-0MDSS91-001-033 | MATERIAL HANDLING SYSTEM EAF FRAMING PLAN AT EL. +8.70,+12.10 33-36 | 01 | 2016-06-07 08:50 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-06-07 08:50 | IFC | AFC | 100%
115704 | I491TC09-0MDSS91-001-034 | MATERIAL HANDLING SYSTEM EAF GRATING STRUCTURE 34-36 | 01 | 2016-06-07 08:50 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-06-07 08:50 | IFC | AFC | 100%
115705 | I491TC09-0MDSS91-001-035 | MATERIAL HANDLING SYSTEM EAF STAIR DETAIL 35-36 | 01 | 2016-06-07 08:50 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-06-07 08:50 | IFC | AFC | 100%
115706 | I491TC09-0MDSS91-001-036 | MATERIAL HANDLING SYSTEM EAF CONSTRUCTION GUIDE 36-36 | 01 | 2016-06-07 08:50 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-06-07 08:50 | IFC | AFC | 100%
112364 | I491TC09-0MDSS91-002-001 | MATERIAL HANDLING SYSTEM LF GENERAL NOTES | 01 | 2014-06-02 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2014-06-07 11:04 | IFC | AC |  | 95%
112363 | I491TC09-0MDSS91-002-002 | MATERIAL HANDLING SYSTEM LF WELDING SPECIFICATION | 01 | 2014-06-02 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2014-06-07 11:04 | IFC | AC |  | 95%
112360 | I491TC09-0MDSS91-002-003 | MATERIAL HANDLING SYSTEM LF COLUMN & BASE PLATE LAYOUT PLAN | 01 | 2014-06-02 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2014-06-07 11:04 | IFC | AC |  | 95%
112361 | I491TC09-0MDSS91-002-004 | MATERIAL HANDLING SYSTEM LF PLAN AT EL. +7.5, +12.8 , +15.8 & +19.5 | 01 | 2014-06-02 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2014-06-07 11:04 | IFC | AC |  | 95%
112362 | I491TC09-0MDSS91-002-005 | MATERIAL HANDLING SYSTEM LF SECTIONS OF ROW 1' , 2' & A' BEAM & COLUMN SECTIONS | 01 | 2014-06-02 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2014-06-07 11:04 | IFC | AC |  | 95%
112359 | I491TC09-0MDSS91-002-006 | MATERIAL HANDLING SYSTEM LF SECTIONS OF ROW B' , C' , D' ,E' & F' | 01 | 2014-06-02 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2014-06-07 11:04 | IFC | AC |  | 95%
112358 | I491TC09-0MDSS91-002-007 | MATERIAL HANDLING SYSTEM LF BASE PLATE DETAILS 1 | 01 | 2014-06-02 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2014-06-07 11:04 | IFC | AC |  | 95%
112357 | I491TC09-0MDSS91-002-008 | MATERIAL HANDLING SYSTEM LF BASE PLATE DETAILS 2 | 01 | 2014-06-02 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2014-06-07 11:04 | IFC | AC |  | 95%
112356 | I491TC09-0MDSS91-002-009 | MATERIAL HANDLING SYSTEM LF COLUMN SPLICE DETAILS 1 & 2 | 01 | 2014-06-02 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2014-06-07 11:04 | IFC | AC |  | 95%
112355 | I491TC09-0MDSS91-002-010 | MATERIAL HANDLING SYSTEM LF BEAM "B1" & "B2" CONNECTIONS | 01 | 2014-06-02 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2014-06-07 11:04 | IFC | AC |  | 95%
112354 | I491TC09-0MDSS91-002-011 | MATERIAL HANDLING SYSTEM LF BEAM "B3" & "B5" CONNECTIONS | 01 | 2014-06-02 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2014-06-07 11:04 | IFC | AC |  | 95%
112353 | I491TC09-0MDSS91-002-012 | MATERIAL HANDLING SYSTEM LF BEAM "B7" CONNECTIONS | 01 | 2014-06-02 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2014-06-07 11:04 | IFC | AC |  | 95%
112352 | I491TC09-0MDSS91-002-013 | MATERIAL HANDLING SYSTEM LF BEAM "B4" & "B5" CONNECTIONS | 01 | 2014-06-02 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2014-06-07 11:04 | IFC | AC |  | 95%
112351 | I491TC09-0MDSS91-002-014 | MATERIAL HANDLING SYSTEM LF BEAM "B5" & "B6" CONNECTIONS | 01 | 2014-06-02 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2014-06-07 11:04 | IFC | AC |  | 95%
112350 | I491TC09-0MDSS91-002-015 | MATERIAL HANDLING SYSTEM LF BEAM "B1" & "B2" STIFFENERS | 01 | 2014-06-02 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2014-06-07 11:04 | IFC | AC |  | 95%
112349 | I491TC09-0MDSS91-002-016 | MATERIAL HANDLING SYSTEM LF BEAM TO BEAM CONNECTIONS | 01 | 2014-06-02 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2014-06-07 11:04 | IFC | AC |  | 95%
112348 | I491TC09-0MDSS91-002-017 | MATERIAL HANDLING SYSTEM LF VERTICAL BRACING DETAIL | 01 | 2014-06-02 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2014-06-07 11:04 | IFC | AC |  | 95%
112347 | I491TC09-0MDSS91-002-018 | MATERIAL HANDLING SYSTEM LF TYPICAL VERTICAL BRACING CONNECTIONS & VERTICAL BRACING DETAIL | 01 | 2014-06-02 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2014-06-07 11:04 | IFC | AC |  | 95%
112346 | I491TC09-0MDSS91-002-019 | MATERIAL HANDLING SYSTEM LF TYPICAL STITCHES OF BRACINGS | 01 | 2014-06-02 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2014-06-07 11:04 | IFC | AC |  | 95%
112345 | I491TC09-0MDSS91-002-020 | MATERIAL HANDLING SYSTEM LF TYPICAL HORIZONTAL BRACING CONNECTION page 21-23 | 01 | 2014-06-02 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2014-06-07 11:04 | IFC | AC |  | 95%
112344 | I491TC09-0MDSS91-002-021 | MATERIAL HANDLING SYSTEM LF TYPICAL HORIZONTAL BRACING CONNECTION page 22-23 | 01 | 2014-06-02 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2014-06-07 11:04 | IFC | AFC | 100%
112343 | I491TC09-0MDSS91-002-022 | MATERIAL HANDLING SYSTEM LF TYPICAL HORIZONTAL BRACING CONNECTION page 23-23 | 01 | 2014-06-02 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2014-06-07 11:04 | IFC | AFC | 100%
114671 | I491TC09-0MDTK02-001-001 | OUTDOOR FERROALLOY MHS PART - 5 CANVEYOR SUPPORT 1-5 | 02 | 2015-11-10 | Indeterminate | Drawing | Detail | Material Handling | Civil and Steel Structure | TAM | 2015-11-15 09:18 | IFC | AC |  | 95%
114672 | I491TC09-0MDTK02-001-002 | OUTDOOR FERROALLOY MHS PART - 5 CANVEYOR SUPPORT 2-5 | 02 | 2015-11-10 | Indeterminate | Drawing | Detail | Material Handling | Civil and Steel Structure | TAM | 2015-11-15 09:18 | IFC | AFC | 100%
114673 | I491TC09-0MDTK02-001-003 | OUTDOOR FERROALLOY MHS PART - 5 STAIR 3-5 | 02 | 2015-11-10 | Indeterminate | Drawing | Detail | Material Handling | Civil and Steel Structure | TAM | 2015-11-15 09:18 | IFC | AFC | 100%
114674 | I491TC09-0MDTK02-001-004 | OUTDOOR FERROALLOY MHS PART - 5 STAIR 4-5 | 02 | 2015-11-10 | Indeterminate | Drawing | Detail | Material Handling | Civil and Steel Structure | TAM | 2015-11-15 09:18 | IFC | AC |  | 95%
114675 | I491TC09-0MDTK02-001-005 | OUTDOOR FERROALLOY MHS PART - 5 STAIR 5-5 | 02 | 2015-11-10 | Indeterminate | Drawing | Detail | Material Handling | Civil and Steel Structure | TAM | 2015-11-15 09:18 | IFC | AFC | 100%
14003 | I491TC09-0MEAM91-001-009 | Smp Substation(Civil & Steel Structure) Columns & Bracing Plan | 02 | 2012-10-22 | Indeterminate | Drawing | Basic | Steel Making Electrical Substation Building | Civil and Steel Structure | IKS |  | IFC | AFC | 100%
13993 | I491TC09-0MEAM91-001-010 | Smp Substation(Civil & Steel Structure) Founadtion Plan & Section | 02 | 2012-10-22 | Indeterminate | Drawing | Basic | Steel Making Electrical Substation Building | Civil and Steel Structure | IKS |  | IFC | AFC | 100%
13994 | I491TC09-0MEAM91-001-011 | Smp Substation(Civil & Steel Structure) Framing Plan On Elevation +1.20 | 02 | 2012-10-22 | Indeterminate | Drawing | Basic | Steel Making Electrical Substation Building | Civil and Steel Structure | IKS |  | IFC | AFC | 100%
13995 | I491TC09-0MEAM91-001-012 | Smp Substation(Civil & Steel Structure) Framing Plan On Elevation +7.10 | 02 | 2012-10-22 | Indeterminate | Drawing | Basic | Steel Making Electrical Substation Building | Civil and Steel Structure | IKS |  | IFC | AFC | 100%
114877 | I491TC09-0MEIR91-001-001 | SVC System Outdoor Equipments and Supports Foundation Plan | 01 | 2016-02-02 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Civil and Steel Structure | NR Electric | 2016-02-03 12:44 | IFI | OB | 100%
114878 | I491TC09-0MEIR91-002-001 | SVC System Outdoor Equipments and Supports Foundation Plan Detail | 01 | 2016-02-02 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Civil and Steel Structure | NR Electric | 2016-02-03 12:44 | IFI | OB | 100%
14058 | I491TC09-0MESS01-001-001 | Design Calculation Of Eq. Supports | 00 | 2012-03-18 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
14059 | I491TC09-0MESS02-001-001 | 400/33 Kv Substation Design Calculation Of Gantries | 00 | 2012-03-14 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFA | OB | 100%
14060 | I491TC09-0MESS03-002-001 | Steel Structure Designation | 00 | 2012-03-18 | Indeterminate | Drawing | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
14062 | I491TC09-0MESS92-001-002 | Technical Specification For Switchyard Structures | 01 | 2012-01-17 | Indeterminate | Miscellaneous(MISC) | Basic | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFC | AFC | 100%
133909 | I491TC09-0MMCT01-001-001 | Shelter Details For CT01 & CT02 Cooling Water System (43Sheet) | 01 | 2018-08-01 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | FARABARD | 2018-08-07 09:20 | IFC | AC |  | 95%
130920 | I491TC09-0MMSD91-001-001 | WTP RO SUBSTATION CIVIL & CONCRETE STRUCTURE COLUMNS PLAN | 00 | 2017-07-29 | Indeterminate | Drawing | Detail | Water Treatment System | Civil and Steel Structure | TAM | 2017-07-30 11:22 | IFA | AC |  | 95%
130921 | I491TC09-0MMSD91-001-002 | WTP RO SUBSTATION CIVIL & CONCRETE STRUCTURE FOUNDATION PLAN & SECTION | 00 | 2017-07-29 | Indeterminate | Drawing | Detail | Water Treatment System | Civil and Steel Structure | TAM | 2017-07-30 11:22 | IFA | AC |  | 95%
130922 | I491TC09-0MMSD91-001-003 | WTP RO SUBSTATION CIVIL & CONCRETE STRUCTURE FIRST & ROOF FRAMING PLAN | 00 | 2017-07-29 | Indeterminate | Drawing | Detail | Water Treatment System | Civil and Steel Structure | TAM | 2017-07-30 11:22 | IFA | AC |  | 95%
133104 | I491TC09-0MMSN01-001-001 | WCP SAND FILTER SHELTER STEEL STRUCTURE 1-3 | 02 | 2018-05-05 13:08 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | TAM | 2018-05-05 13:08 | IFC | AFC | 100%
133105 | I491TC09-0MMSN01-001-002 | WCP SAND FILTER SHELTER STEEL STRUCTURE 2-3 | 02 | 2018-05-05 13:08 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | TAM | 2018-05-05 13:08 | IFC | AFC | 100%
133030 | I491TC09-0MMSN01-001-003 | WCP SAND FILTER SHELTER STEEL STRUCTURE 3-3 | 01 | 2018-04-08 08:27 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | TAM | 2018-04-08 08:27 | IFC | AFC | 100%
129494 | I491TC09-0MMTK01-001-001 | CIVIL & STEEL STRUCTURE FOR EMERGENCY WATER TANK MAINTENACE PLATFORM AT EL. 40 m 1-16 | 02 | 2016-09-17 09:16 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | TAM | 2016-09-17 09:16 | IFC | AFC | 100%
129495 | I491TC09-0MMTK01-001-002 | CIVIL & STEEL STRUCTURE FOR EMERGENCY WATER TANK FARMING PLAN AT ELEVATIONS 2-16 | 02 | 2016-09-17 09:16 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | TAM | 2016-09-17 09:16 | IFC | AFC | 100%
129496 | I491TC09-0MMTK01-001-003 | CIVIL & STEEL STRUCTURE FOR EMERGENCY WATER TANK FARMING PLAN AT ELEVATIONS 3-16 | 02 | 2016-09-17 09:16 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | TAM | 2016-09-17 09:16 | IFC | AFC | 100%
129497 | I491TC09-0MMTK01-001-004 | CIVIL & STEEL STRUCTURE FOR EMERGENCY WATER TANK FARMING PLAN AT ELEVATIONS 4-16 | 02 | 2016-09-17 09:16 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | TAM | 2016-09-17 09:16 | IFC | AFC | 100%
129498 | I491TC09-0MMTK01-001-005 | CIVIL & STEEL STRUCTURE FOR EMERGENCY WATER TANK FARMING PLAN AT ELEVATIONS 5-16 | 02 | 2016-09-17 09:16 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | TAM | 2016-09-17 09:16 | IFC | AC |  | 95%
129499 | I491TC09-0MMTK01-001-006 | CIVIL & STEEL STRUCTURE FOR EMERGENCY WATER TANK STAIRS FRAMING PLAN AT ELEVATIONS 6-16 | 02 | 2016-09-17 09:16 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | TAM | 2016-09-17 09:16 | IFC | AFC | 100%
129500 | I491TC09-0MMTK01-001-007 | CIVIL & STEEL STRUCTURE FOR EMERGENCY WATER TANK SECTIONS A-A, B-B, C-C 7-16 | 02 | 2016-09-17 09:16 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | TAM | 2016-09-17 09:16 | IFC | AFC | 100%
129501 | I491TC09-0MMTK01-001-008 | CIVIL & STEEL STRUCTURE FOR EMERGENCY WATER TANK STAIRS WITH HANDRAIL 8-16 | 02 | 2016-09-17 09:16 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | TAM | 2016-09-17 09:16 | IFC | AFC | 100%
129502 | I491TC09-0MMTK01-001-009 | CIVIL & STEEL STRUCTURE FOR EMERGENCY WATER TANK STAIRS WITH HANDRAIL 9-16 | 02 | 2016-09-17 09:16 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | TAM | 2016-09-17 09:16 | IFC | AFC | 100%
129503 | I491TC09-0MMTK01-001-010 | CIVIL & STEEL STRUCTURE FOR EMERGENCY WATER TANK FOUNDATION DETAILS 10-16 | 02 | 2016-09-17 09:16 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | TAM | 2016-09-17 09:16 | IFC | AFC | 100%
129504 | I491TC09-0MMTK01-001-011 | CIVIL & STEEL STRUCTURE FOR EMERGENCY WATER TANK CONNECTION ELEMENTS & DETAILS 11-16 | 02 | 2016-09-17 09:16 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | TAM | 2016-09-17 09:16 | IFC | AFC | 100%
129505 | I491TC09-0MMTK01-001-012 | CIVIL & STEEL STRUCTURE FOR EMERGENCY WATER TANK CONNECTION ELEMENTS & DETAILS 12-16 | 02 | 2016-09-17 09:17 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | TAM | 2016-09-17 09:17 | IFC | AFC | 100%
129506 | I491TC09-0MMTK01-001-013 | CIVIL & STEEL STRUCTURE FOR EMERGENCY WATER TANK CONNECTION ELEMENTS & DETAILS 13-16 | 02 | 2016-09-17 09:17 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | TAM | 2016-09-17 09:17 | IFC | AFC | 100%
129507 | I491TC09-0MMTK01-001-014 | CIVIL & STEEL STRUCTURE FOR EMERGENCY WATER TANK VERTICAL BRACINGS & DETAILS 14-16 | 02 | 2016-09-17 09:17 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | TAM | 2016-09-17 09:17 | IFC | AFC | 100%
129493 | I491TC09-0MMTK01-001-015 | CIVIL & STEEL STRUCTURE FOR EMERGENCY WATER TANK VERTICAL BRACINGS & DETAILS 15-16 | 01 | 2016-09-17 09:16 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | TAM | 2016-09-17 09:16 | IFC | AFC | 100%
129492 | I491TC09-0MMTK01-001-016 | CIVIL & STEEL STRUCTURE FOR EMERGENCY WATER TANK VERTICAL BRACINGS & DETAILS 16-16 | 00 | 2016-09-17 09:16 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | TAM | 2016-09-17 09:16 | IFC | AFC | 100%
130868 | I491TC09-0MMTK01-002-001 | COOLING WATER SYSTEM EMERGENCY ELEVATED WATER TANK GELENRAL ASSEMBLY 1-10 | 01 | 2017-07-17 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | TAM | 2017-07-23 15:30 | IFC | AFC | 100%
130869 | I491TC09-0MMTK01-002-002 | COOLING WATER SYSTEM EMERGENCY ELEVATED WATER TANK OUTTER TANK DETAILS 2-10 | 01 | 2017-07-17 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | TAM | 2017-07-23 15:30 | IFC | AFC | 100%
130870 | I491TC09-0MMTK01-002-003 | COOLING WATER SYSTEM EMERGENCY ELEVATED WATER TANK NOZZLE DETAILS 3-10 | 01 | 2017-07-17 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | TAM | 2017-07-23 15:30 | IFC | AFC | 100%
130871 | I491TC09-0MMTK01-002-004 | COOLING WATER SYSTEM EMERGENCY ELEVATED WATER TANK INNER & INTERMEDIATE TANKS DETAILS 4-10 | 01 | 2017-07-17 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | TAM | 2017-07-23 15:30 | IFC | AFC | 100%
130872 | I491TC09-0MMTK01-002-005 | COOLING WATER SYSTEM EMERGENCY ELEVATED WATER TANK ROOF ASSEMBLY 5-10 | 01 | 2017-07-17 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | TAM | 2017-07-23 15:31 | IFC | AFC | 100%
130873 | I491TC09-0MMTK01-002-006 | COOLING WATER SYSTEM EMERGENCY ELEVATED WATER TANK ROOF PLATFORM DETAILS 6-10 | 01 | 2017-07-17 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | TAM | 2017-07-23 15:31 | IFC | AFC | 100%
130874 | I491TC09-0MMTK01-002-007 | COOLING WATER SYSTEM EMERGENCY ELEVATED WATER TANK LADDERS AND PLATFORMS ASSEMBLIES 7-10 | 01 | 2017-07-17 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | TAM | 2017-07-23 15:31 | IFC | AFC | 100%
130875 | I491TC09-0MMTK01-002-008 | COOLING WATER SYSTEM EMERGENCY ELEVATED WATER TANK LADDERS AND PLATFORMS DETAILS 8-10 | 01 | 2017-07-17 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | TAM | 2017-07-23 15:31 | IFC | AFC | 100%
130876 | I491TC09-0MMTK01-002-009 | COOLING COOLING WATER SYSTEM EMERGENCY ELEVATED WATER TANK MAINTENANCE DAVIT (JIB) 9-10 | 01 | 2017-07-17 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | TAM | 2017-07-23 15:31 | IFC | AFC | 100%
130877 | I491TC09-0MMTK01-002-010 | COOLING WATER SYSTEM EMERGENCY ELEVATED WATER TANK NAME PLATE 10-10 | 01 | 2017-07-17 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | TAM | 2017-07-23 15:31 | IFC | AFC | 100%
134132 | I491TC09-0MMTK01-003-001 | WTP - EMERGENCY TANK - PIPE RACK STEEL STRUCTURE DETAIL DRAWING 1-4 | 00 | 2018-09-04 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | TAM | 2018-09-09 14:26 | IFI | OB | 100%
134133 | I491TC09-0MMTK01-003-002 | WTP - EMERGENCY TANK - PIPE RACK STEEL STRUCTURE - SUPPORT @H=5.0 m 2-4 | 00 | 2018-09-04 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | TAM | 2018-09-09 14:26 | IFI | OB | 100%
134134 | I491TC09-0MMTK01-003-003 | STEEL STRUCTURE - SUPPORT - DETAIL "1" STEEL STRUCTURE - SUPPORT - DETAIL "1" 3-4 | 00 | 2018-09-04 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | TAM | 2018-09-09 14:26 | IFI | OB | 100%
134135 | I491TC09-0MMTK01-003-004 | WTP - EMERGENCY TANK - PIPE RACK SUPPORT FOR VERTICAL PIPE - STEP @5.00 m 4-4 | 00 | 2018-09-04 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | TAM | 2018-09-09 14:26 | IFI | OB | 100%
132544 | I491TC09-0MXEG01-001-001 | BASIS OF DESIGN(CIVIL & STEEL STRUCTURE) FOR DIESEL ROOM STRUCTURAL 1-5 | 01 | 2017-12-12 | Indeterminate | Drawing | Detail | General | Civil and Steel Structure | TAM | 2017-12-13 10:25 | IFC | AFC | 100%
132545 | I491TC09-0MXEG01-001-002 | BASIS OF DESIGN(CIVIL & STEEL STRUCTURE) FOR DIESEL ROOM STRUCTURAL 2-5 | 01 | 2017-12-12 | Indeterminate | Drawing | Detail | General | Civil and Steel Structure | TAM | 2017-12-13 10:25 | IFC | AFC | 100%
132546 | I491TC09-0MXEG01-001-003 | BASIS OF DESIGN(CIVIL & STEEL STRUCTURE) FOR DIESEL ROOM STRUCTURAL 3-5 | 01 | 2017-12-12 | Indeterminate | Drawing | Detail | General | Civil and Steel Structure | TAM | 2017-12-13 10:25 | IFC | AFC | 100%
132547 | I491TC09-0MXEG01-001-004 | BASIS OF DESIGN(CIVIL & STEEL STRUCTURE) FOR DIESEL ROOM STRUCTURAL 4-5 | 01 | 2017-12-12 | Indeterminate | Drawing | Detail | General | Civil and Steel Structure | TAM | 2017-12-13 10:25 | IFC | AFC | 100%
132656 | I491TC09-0MXEG01-001-005 | BASIS OF DESIGN(CIVIL & STEEL STRUCTURE) FOR DIESEL ROOM STRUCTURAL 5-5 | 01 | 2018-01-07 09:18 | Indeterminate | Drawing | Detail | General | Civil and Steel Structure | TAM | 2018-01-07 09:18 | IFC | AFC | 100%
14074 | I491TC09-0MYAA91-001-005 | Foundation And Steel Structure Workshop | 04 | 2012-02-18 | Indeterminate | Drawing | Basic | Melt Shop Maintenance Workshop | Civil and Steel Structure | IKS |  | IFC | AFC | 100%
14078 | I491TC09-0MYAA91-002-004 | Work Shop Steel Structure Detail Drawing Main Frame & Details | 03 | 2012-02-28 | Indeterminate | Drawing | Detail | Maintenance Workshop | Civil and Steel Structure | IKS |  | IFC | AFC | 100%
132978 | I491TC09-0MYAA91-003-001 | WORKSHOP SECOND FLOOR OFFICE STEEL STRUCTURE 1-8 | 01 | 2018-03-13 | Indeterminate | Drawing | Detail | Maintenance Workshop | Civil and Steel Structure | TAM | 2018-03-17 16:42 | IFC | AFC | 100%
132977 | I491TC09-0MYAA91-003-002 | WORKSHOP SECOND FLOOR OFFICE STEEL STRUCTURE 2-8 | 01 | 2018-03-13 | Indeterminate | Drawing | Detail | Maintenance Workshop | Civil and Steel Structure | TAM | 2018-03-17 16:42 | IFC | AFC | 100%
132976 | I491TC09-0MYAA91-003-003 | WORKSHOP SECOND FLOOR OFFICE STEEL STRUCTURE 3-8 | 01 | 2018-03-13 | Indeterminate | Drawing | Detail | Maintenance Workshop | Civil and Steel Structure | TAM | 2018-03-17 16:42 | IFC | AFC | 100%
132983 | I491TC09-0MYAA91-003-004 | WORKSHOP SECOND FLOOR OFFICE STEEL STRUCTURE 4-8 | 01 | 2018-03-13 | Indeterminate | Drawing | Detail | Maintenance Workshop | Civil and Steel Structure | TAM | 2018-03-17 16:42 | IFC | AFC | 100%
133058 | I491TC09-0MYAA91-003-005 | WORKSHOP SECOND FLOOR OFFICE STEEL STRUCTURE 5-8 | 02 | 2018-04-16 | Indeterminate | Drawing | Detail | Maintenance Workshop | Civil and Steel Structure | TAM | 2018-04-17 09:31 | IFC | AFC | 100%
132980 | I491TC09-0MYAA91-003-006 | WORKSHOP SECOND FLOOR OFFICE STEEL STRUCTURE 6-8 | 01 | 2018-03-13 | Indeterminate | Drawing | Detail | Maintenance Workshop | Civil and Steel Structure | TAM | 2018-03-17 16:42 | IFC | AFC | 100%
132981 | I491TC09-0MYAA91-003-007 | WORKSHOP SECOND FLOOR OFFICE STEEL STRUCTURE 7-8 | 01 | 2018-03-13 | Indeterminate | Drawing | Detail | Maintenance Workshop | Civil and Steel Structure | TAM | 2018-03-17 16:42 | IFC | AFC | 100%
132982 | I491TC09-0MYAA91-003-008 | WORKSHOP SECOND FLOOR OFFICE STEEL STRUCTURE 8-8 | 01 | 2018-03-13 | Indeterminate | Drawing | Detail | Maintenance Workshop | Civil and Steel Structure | TAM | 2018-03-17 16:42 | IFC | AFC | 100%
112142 | I491TC09-0OFFP91-001-001 | LIST OF ELECTRICAL DRAWING, LEGEND AND GENERAL NOTE | 00 | 2014-05-05 | Indeterminate | Drawing | Detail | Office - Canteen - Locker & Shower For Melt Shop | Piping & Utility | TAM | 2014-05-15 15:38 | IFA | AC |  | 95%
112141 | I491TC09-0OFFP91-001-002 | GROUND FLOOR FIRE ALARM | 00 | 2014-05-05 | Indeterminate | Drawing | Detail | Office - Canteen - Locker & Shower For Melt Shop | Piping & Utility | TAM | 2014-05-15 15:38 | IFA | AC |  | 95%
112140 | I491TC09-0OFFP91-001-003 | 1ST FLOOR FIRE ALARM | 00 | 2014-05-05 | Indeterminate | Drawing | Detail | Office - Canteen - Locker & Shower For Melt Shop | Piping & Utility | TAM | 2014-05-15 15:38 | IFA | AC |  | 95%
135147 | I491TC09-0PXAA91-001-001 | Ladle Sand Filling Station Steel Structure 1-4 | 01 | 2019-03-18 10:31 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Civil and Steel Structure | TAM | 2019-03-18 10:31 | IFC | AFC | 100%
135148 | I491TC09-0PXAA91-001-002 | Ladle Sand Filling Station Steel Structure 2-4 | 01 | 2019-03-18 10:31 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Civil and Steel Structure | TAM | 2019-03-18 10:31 | IFC | AFC | 100%
135149 | I491TC09-0PXAA91-001-003 | Ladle Sand Filling Station Steel Structure 3-4 | 01 | 2019-03-18 10:31 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Civil and Steel Structure | TAM | 2019-03-18 10:31 | IFC | AFC | 100%
135146 | I491TC09-0PXAA91-001-004 | Ladle Sand Filling Station Steel Structure 4-4 | 01 | 2019-03-18 10:31 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Civil and Steel Structure | TAM | 2019-03-18 10:31 | IFC | AFC | 100%
14087 | I491TC09-0SHAA91-001-001 | Scrap Yard Column & Vertical Bracing Plan Main Frame Vertical Bracing (Typ.1)&(Typ.2) | 00 | 2011-06-26 | Indeterminate | Drawing | Detail | Melt Shop Scrap Yard | Civil and Steel Structure | IKS |  | IFA | A | 100%
14085 | I491TC09-0SHAA91-001-002 | Scrap Yard Column & Vertical Bracing Plan Main Frame Vertical Bracing (Typ.1)&(Typ.2) | 00 | 2011-07-11 | Indeterminate | Drawing | Detail | Melt Shop Scrap Yard | Civil and Steel Structure | IKS |  | IFC | AFC | 100%
14086 | I491TC09-0SHAA91-001-004 | Scrap Yard Roof Plan Frameing & Bracing Roof Purlin Plan Crane Girders & Walkway Layout Plan | 00 | 2011-07-11 | Indeterminate | Drawing | Detail | Melt Shop Scrap Yard | Civil and Steel Structure | IKS |  | IFC | AFC | 100%
14090 | I491TC09-0SHAA91-001-006 | Scrap Yard Columns,Framing,Roof & Bracing Plan | 01 | 2011-12-19 | Indeterminate | Drawing | Detail | Melt Shop Scrap Yard | Civil and Steel Structure | IKS |  | IFC | AFC | 100%
14095 | I491TC09-0SHAA91-002-013 | Scrap Yard-Steel Structure | 04 | 2012-05-21 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop Scrap Yard | Civil and Steel Structure | IKS |  | IFC | AFC | 100%
14125 | I491TC09-0TBAA91-002-002 | Ferro Alloy Storage Steel Structure | 00 | 2011-12-19 | Indeterminate | Drawing | Detail | Melt Shop Lime And Ferroalloy Storage | Civil and Steel Structure | IKS |  | IFC | AFC | 100%
14178 | I491TC09-0TBAA91-003-057 | Ferro Alloy Storage Steel Structure Column & Vertical Bracing & Base Plate Layout Plan & Details | 06 | 2012-12-31 | Indeterminate | Drawing | Detail | Melt Shop Lime And Ferroalloy Storage | Civil and Steel Structure | IKS |  | IFC | AFC | 100%
14179 | I491TC09-0TBAA91-003-058 | Ferro Alloy Storage Steel Structure Framing View On Axis "1"To "10" & Details | 06 | 2012-12-31 | Indeterminate | Drawing | Detail | Melt Shop Lime And Ferroalloy Storage | Civil and Steel Structure | IKS |  | IFC | AFC | 100%
14180 | I491TC09-0TBAA91-003-059 | Ferro Alloy Storage Steel Structure Roof Bracings Plan & Details | 06 | 2012-12-31 | Indeterminate | Drawing | Detail | Melt Shop Lime And Ferroalloy Storage | Civil and Steel Structure | IKS |  | IFC | AFC | 100%
14182 | I491TC09-0TBAA91-003-060 | Ferro Alloy Storage Steel Structure Roof Bracings Plan & Details | 06 | 2012-12-31 | Indeterminate | Drawing | Detail | Melt Shop Lime And Ferroalloy Storage | Civil and Steel Structure | IKS |  | IFC | AFC | 100%
14183 | I491TC09-0TBAA91-003-061 | Ferro Alloy Storage Steel Structure Crane Girders Layout Plan & Details | 06 | 2012-12-31 | Indeterminate | Drawing | Detail | Melt Shop Lime And Ferroalloy Storage | Civil and Steel Structure | IKS |  | IFC | AFC | 100%
14184 | I491TC09-0TBAA91-003-062 | Ferro Alloy Storage Steel Structure Framing View On Axis "A & B " | 06 | 2012-12-31 | Indeterminate | Drawing | Detail | Melt Shop Lime And Ferroalloy Storage | Civil and Steel Structure | IKS |  | IFC | AFC | 100%
14185 | I491TC09-0TBAA91-003-063 | Ferro Alloy Storage Steel Structure Details | 06 | 2012-12-31 | Indeterminate | Drawing | Detail | Melt Shop Lime And Ferroalloy Storage | Civil and Steel Structure | IKS |  | IFC | AFC | 100%
14186 | I491TC09-0TBAA91-003-064 | Ferro Alloy Storage Steel Structure Details | 06 | 2012-12-31 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop Lime And Ferroalloy Storage | Civil and Steel Structure | IKS |  | IFC | AFC | 100%
14187 | I491TC09-0TBAA91-003-065 | Ferro Alloy Storage Steel Structure Framing View On Axis "A & B &1&10 " | 06 | 2012-12-31 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop Lime And Ferroalloy Storage | Civil and Steel Structure | IKS |  | IFC | AFC | 100%
14188 | I491TC09-0TBAA91-003-066 | Ferro Alloy Storage Steel Structure Details | 06 | 2012-12-31 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop Lime And Ferroalloy Storage | Civil and Steel Structure | IKS |  | IFC | AFC | 100%
115617 | I491TC09-0TBAM91-001-077 | Melt Shop Main Building Eaf Building (1-1 & 1-2) General Note (1-41) | 04 | 2016-05-31 10:53 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-31 10:53 | IFC | AFC | 100%
115618 | I491TC09-0TBAM91-001-078 | Melt Shop Main Building Eaf Building (1-1 & 1-2) Column And Wall Layout Plan (2-41) | 04 | 2016-05-31 10:53 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-31 10:53 | IFC | AFC | 100%
115619 | I491TC09-0TBAM91-001-079 | Melt Shop Main Building Eaf Building (1-1 & 1-2) Column C-5 To C-7 (3-41) | 04 | 2016-05-31 10:53 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-31 10:53 | IFC | AFC | 100%
14286 | I491TC09-0TBAM91-001-080 | Melt Shop Main Building Eaf Building (1-1 & 1-2) Formwork Of Conc. Wall Type W-1 To W-8 (4-41) | 03 | 2013-09-24 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
115620 | I491TC09-0TBAM91-001-081 | Melt Shop Main Building Eaf Building (1-1 & 1-2) Formwork Of Conc. Wall Type W-9 To W-18 (5-41) | 04 | 2016-05-31 10:53 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-31 10:53 | IFC | AFC | 100%
14288 | I491TC09-0TBAM91-001-082 | Melt Shop Main Building Eaf Building (1-1 & 1-2) Formwork Of Conc. Wall Type W-19 & W-25 (6-41) | 03 | 2013-09-24 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
14289 | I491TC09-0TBAM91-001-083 | Melt Shop Main Building Eaf Building (1-1 & 1-2) Reinforcement Of Walls Type W-1 T0 W-3 (7-41) | 03 | 2013-09-24 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
14290 | I491TC09-0TBAM91-001-084 | Melt Shop Main Building Eaf Building (1-1 & 1-2) Reinforcement Of Walls Type W-4 T0 W-12 (8-41) | 03 | 2013-09-24 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
115621 | I491TC09-0TBAM91-001-085 | Melt Shop Main Building Eaf Building (1-1 & 1-2) Reinforcement Of Walls Type W-13 T0 W-19 (9-41) | 04 | 2016-05-31 10:53 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-31 10:53 | IFC | AFC | 100%
115622 | I491TC09-0TBAM91-001-086 | Melt Shop Main Building Eaf Building (1-1 & 1-2 ) Reinforcement Of Walls Type W-20 & W-21 (10-41) | 04 | 2016-05-31 10:53 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-31 10:53 | IFC | AFC | 100%
14293 | I491TC09-0TBAM91-001-087 | Melt Shop Main Building Eaf Building (1-1 & 1-2) Wall Opening Reinforcement (11-41) | 03 | 2013-09-24 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
14294 | I491TC09-0TBAM91-001-088 | Melt Shop Main Building Eaf Building (1-1 & 1-2) Wall Sections (1 Of 2) (12-41) | 03 | 2013-09-24 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
14295 | I491TC09-0TBAM91-001-089 | Melt Shop Main Building Eaf Building (1-1 & 1-2) Wall Sections (2 Of 2) (13-41) | 03 | 2013-09-24 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
115623 | I491TC09-0TBAM91-001-090 | Melt Shop Main Building Eaf Building (1-1 & 1-2) Slab Formwork Plan At El -0.4,±0.0,+0.90,+1.0,+4.75 &+ 5.3 (14-41) | 04 | 2016-05-31 10:53 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-31 10:53 | IFC | AFC | 100%
115624 | I491TC09-0TBAM91-001-091 | Melt Shop Main Building Eaf Building (1-1 & 1-2) Slab Formwork Plan At El +8.20 & +12.00 (15-41) | 04 | 2016-05-31 10:53 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-31 10:53 | IFC | AFC | 100%
14299 | I491TC09-0TBAM91-001-092 | Melt Shop Main Building Eaf Building (1-1 & 1-2) Slab Formwork Plan At El +14.00,+18.00 & +22.36 (16-41) | 03 | 2013-09-24 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
115625 | I491TC09-0TBAM91-001-093 | Melt Shop Main Building Eaf Building (1-1 & 1-2) Slab Reinforcement Plan At El -0.4,±0.0,+0.90 & +1.0 (17-41) | 04 | 2016-05-31 10:53 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-31 10:53 | IFC | AFC | 100%
115626 | I491TC09-0TBAM91-001-094 | Melt Shop Main Building Eaf Building (1-1 & 1-2) Slab Reinforcement Plan At El +4.75 & +5.30 (18-41) | 04 | 2016-05-31 10:53 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-31 10:53 | IFC | AFC | 100%
14302 | I491TC09-0TBAM91-001-095 | Melt Shop Main Building Eaf Building (1-1 & 1-2)Slab Reinforcement Plan At El +8.20 (19-41) | 03 | 2013-09-24 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
14303 | I491TC09-0TBAM91-001-096 | Melt Shop Main Building Eaf Building (1-1 & 1-2) Slab Reinforcement Plan At El +12.00 (20-41) | 03 | 2013-09-24 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
14304 | I491TC09-0TBAM91-001-097 | Melt Shop Main Building Eaf Building (1-1 & 1-2) Slab Reinforcement Plan At El +14.00 (21-41) | 03 | 2013-09-24 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
14305 | I491TC09-0TBAM91-001-098 | Melt Shop Main Building Eaf Building (1-1 & 1-2) Slab Reinforcement Plan At El +18.00 & +22.36 (22-41) | 03 | 2013-09-24 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
115627 | I491TC09-0TBAM91-001-099 | Melt Shop Main Building Eaf Building Eaf Building (1-1 & 1-2) Beam Plan At El ±0.00,+1.00,+4.75 &+ 5.30 (23-41) | 04 | 2016-05-31 10:53 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-31 10:53 | IFC | AFC | 100%
14194 | I491TC09-0TBAM91-001-100 | Melt Shop Main Buildingeaf Building (1-1 & 1-2) Beam Plan At El +8.20 & +12.00 (24-41) | 03 | 2013-09-24 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
115628 | I491TC09-0TBAM91-001-101 | Melt Shop Main Building Eaf Building (1-1 & 1-2) Beam Plan At El +14.00,+18.00 & +22.36 (25-41) | 04 | 2016-05-31 10:54 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-31 10:54 | IFC | AFC | 100%
14196 | I491TC09-0TBAM91-001-102 | Melt Shop Main Building Eaf Building (1-1 & 1-2) Slab Opening Reinforcement (1 Of 2) (26-41) | 03 | 2013-09-24 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
115629 | I491TC09-0TBAM91-001-103 | Melt Shop Main Building Eaf Building (1-1 & 1-2) Slab Opening Reinforcement (2 Of 2) (27-41) | 04 | 2016-05-31 10:54 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-31 10:54 | IFC | AFC | 100%
14198 | I491TC09-0TBAM91-001-104 | Melt Shop Main Building Eaf Building (1-1 & 1-2) Beams B-1 To B-8 & Sections (28-41) | 03 | 2013-09-24 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
14199 | I491TC09-0TBAM91-001-105 | Melt Shop Main Building Eaf Building (1-1 & 1-2) Beams B-9 To B-16 & Sections (29-41) | 03 | 2013-09-24 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
14200 | I491TC09-0TBAM91-001-106 | Melt Shop Main Building Eaf Building (1-1 & 1-2) Beams B-17 To B-24 & Sections (30-41) | 03 | 2013-09-24 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
14201 | I491TC09-0TBAM91-001-107 | Melt Shop Main Building Eaf Building (1-1 & 1-2) Beams B-25 To B-31 & Sections (31-41) | 03 | 2013-09-24 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
14202 | I491TC09-0TBAM91-001-108 | Melt Shop Main Building Eaf Building (1-1 & 1-2) Beams B-32 To B-39 & Sections (32-41) | 03 | 2013-09-24 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFC | AFC | 100%
115630 | I491TC09-0TBAM91-001-109 | Melt Shop Main Building Eaf Building (1-1 & 1-2) Beams B-39A To B-46 & Sections (33-41) | 04 | 2016-05-31 10:54 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-31 10:54 | IFC | AFC | 100%
115631 | I491TC09-0TBAM91-001-110 | Melt Shop Main Building Eaf Building (1-1 & 1-2) Beams B-47 To B-60 & Sections (34-41) | 04 | 2016-05-31 10:54 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-31 10:54 | IFC | AFC | 100%
115632 | I491TC09-0TBAM91-001-111 | Melt Shop Main Building Eaf Building (1-1 & 1-2) Stair Plans & Sections (1 Of 4) (35-41) | 04 | 2016-05-31 10:54 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-31 10:54 | IFC | AFC | 100%
115633 | I491TC09-0TBAM91-001-112 | Melt Shop Main Building Eaf Building (1-1 & 1-2) Stair Plans & Sections(2 Of 4) (36-41) | 04 | 2016-05-31 10:54 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-31 10:54 | IFC | AFC | 100%
115634 | I491TC09-0TBAM91-001-113 | Melt Shop Main Building Eaf Building (1-1 & 1-2) Stair Plans & Sections(3 Of 4) (37-41) | 04 | 2016-05-31 10:54 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-31 10:54 | IFC | AFC | 100%
115635 | I491TC09-0TBAM91-001-114 | Melt Shop Main Building Eaf Building (1-1 & 1-2) Stair Plans & Sections(4 Of 4) (38-41) | 04 | 2016-05-31 10:54 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-31 10:54 | IFC | AFC | 100%
115636 | I491TC09-0TBAM91-001-115 | Melt Shop Main Building Eaf Building (1-1 & 1-2) Beams B-47 To B-60 & Sections (39-41) | 04 | 2016-05-31 10:54 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-31 10:54 | IFC | AFC | 100%
115638 | I491TC09-0TBAM91-001-116 | Melt Shop Main Building Eaf Building (1-1 & 1-2) Formwork of Transformator Type 1&2 (40-41) | 00 | 2016-05-31 11:03 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-31 11:03 | IFC | AFC | 100%
115637 | I491TC09-0TBAM91-001-117 | Melt Shop Main Building Eaf Building (1-1 & 1-2) Transformator Sections & Flooring Plan AT EL. ±0.00 (41-41) | 00 | 2016-05-31 11:03 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC | 2016-05-31 11:03 | IFC | AFC | 100%
112367 | I491TC09-0TBAM91-004-001 | EAF BUILDING ‐bar bending Report Of Listofer | 00 | 2013-06-22 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2014-06-08 11:38 | IFC | AC |  | 95%
114923 | I491TC09-0TBWD91-001-001 | FERRO ALLOY STORAGE ENTRANCE DOOR BASIS OF DESIGN | 00 | 2016-02-20 | Indeterminate | Drawing | Basic | Melt Shop Lime And Ferroalloy Storage | Civil and Steel Structure | TAM | 2016-02-21 09:59 | IFA | AC |  | 95%
14419 | I491TC10-0MXAA91-001-003 | Welding Procedure Specification (Wps) For Steel Structures | 02 | 2012-02-01 | Indeterminate | Drawing | Basic | General | Mechanical | TAM |  | IFC | AFC | 100%
14420 | I491TC11-0MEAM01-300-001 | Control Building - Mechanical Calculation | 00 | 2012-05-09 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | AFC | 100%
14421 | I491TC12-0MEAM01-301-001 | Control Building - Mechanical Drawings | 00 | 2012-05-09 | Indeterminate | Drawing | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | AFC | 100%
14422 | I491TC12-0MEAM01-302-001 | Control Building - Mechanical Drawings | 00 | 2012-05-09 | Indeterminate | Drawing | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | AFC | 100%
14423 | I491TC12-0MEAM01-303-001 | Control Building - Mechanical Drawings | 00 | 2012-05-09 | Indeterminate | Drawing | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | AFC | 100%
14424 | I491TC12-0MEAM01-304-001 | Control Building - Mechanical Drawings | 00 | 2012-05-09 | Indeterminate | Drawing | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | AFC | 100%
14425 | I491TC12-0MEAM01-305-001 | Control Building - Mechanical Drawings | 00 | 2012-05-09 | Indeterminate | Drawing | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | AFC | 100%
14426 | I491TC13-0MEAM01-200-001 | 400/33 Kv Substation Design Calculation For Control Bilding | 00 | 2012-03-18 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Civil and Steel Structure | PARSIAN |  | IFA | AC |  | 95%
14428 | I491TC14-0MEAA01-245-002 | Outdoor - Cable Channel Details Dwgs | 01 | 2012-07-29 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Civil and Steel Structure | PARSIAN |  | IFI | OB | 100%
14429 | I491TC14-0MEAM02-200-001 | 400/33 Kv Substation Foundation Plan & Section | 00 | 2012-03-18 | Indeterminate | Drawing | Detail | Main Electrical Substation And Distribution Network | Civil and Steel Structure | PARSIAN |  | IFI | OB | 100%
14430 | I491TC14-0MEAM02-201-001 | 400/33 Kv Substation Roof Plan & Sections | 00 | 2012-03-18 | Indeterminate | Drawing | Detail | Main Electrical Substation And Distribution Network | Civil and Steel Structure | PARSIAN |  | IFI | OB | 100%
14431 | I491TC14-0MEAM02-202-001 | 400/33 Kv Substation Frame Elevation | 00 | 2012-03-18 | Indeterminate | Drawing | Detail | Main Electrical Substation And Distribution Network | Civil and Steel Structure | PARSIAN |  | IFI | OB | 100%
14432 | I491TC14-0MEAM02-203-001 | 400/33 Kv Substation Beam Schdule & Sections | 00 | 2012-03-18 | Indeterminate | Drawing | Detail | Main Electrical Substation And Distribution Network | Civil and Steel Structure | PARSIAN |  | IFI | OB | 100%
14433 | I491TC14-0MEAM02-204-001 | 400/33 Kv Substation Column Schdule & Sections | 00 | 2012-03-18 | Indeterminate | Drawing | Detail | Main Electrical Substation And Distribution Network | Civil and Steel Structure | PARSIAN |  | IFI | OB | 100%
14434 | I491TC14-0MEAM02-205-001 | 400/33 Kv Substation Lintel Plan & Details | 00 | 2012-03-18 | Indeterminate | Drawing | Detail | Main Electrical Substation And Distribution Network | Civil and Steel Structure | PARSIAN |  | IFI | OB | 100%
14437 | I491TC14-0MERI01-007-002 | Site - Road Sections & Details | 01 | 2012-07-29 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Mechanical | PARSIAN |  | IFI | OB | 100%
14439 | I491TC14-0MESW01-004-002 | Site Peripheral And Entrance Gate Details | 01 | 2012-07-29 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Civil and Steel Structure | PARSIAN |  | IFI | OB | 100%
14451 | I491TC15-0MEAA01-261-001 | 400/33 Kv Substation Design Calculation Of 400 Kv Equipment Support Foundation | 00 | 2013-12-29 07:21 | Indeterminate | Miscellaneous(MISC) | Basic | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFA | OB | 100%
14457 | I491TC15-0MEAA02-252-003 | 400/33 Kv Substation Design Calculation Of Gantry Foundations | 01 | 2012-03-18 | Indeterminate | Miscellaneous(MISC) | Basic | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
14440 | I491TC15-0MEAA03-252-001 | 400/33 Kv Substation Drawing Of Equipment Foundations | 02 | 2012-03-18 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
14442 | I491TC15-0MEAA03-261-002 | 400/33 Kv Substation Drawing Of Equipment Foundations | 01 | 2012-04-03 | Indeterminate | Drawing | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFC | AFC | 100%
14443 | I491TC15-0MEAA04-252-002 | 400/33 Kv Substation Drawings Of Gantry Foundations | 01 | 2012-02-19 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
14456 | I491TC15-0MEAA05-250-001 | 400/33 Kv Substation Foundation Plan Drawings | 00 | 2011-12-12 | Indeterminate | Miscellaneous(MISC) | Basic | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
14444 | I491TC15-0METF01-283-001 | Outdoor - Design Calculation Of Aux. Trans. Foundation | 00 | 2012-03-18 | Indeterminate | Miscellaneous(MISC) | Basic | Main Electrical Substation And Distribution Network | Civil and Steel Structure | PARSIAN |  | IFI | OB | 100%
14445 | I491TC15-0METF02-280-001 | Outdoor - Design Calculation Of P. Trans. Foundation | 00 | 2012-04-29 | Indeterminate | Miscellaneous(MISC) | Basic | Main Electrical Substation And Distribution Network | Civil and Steel Structure | PARSIAN |  | IFI | OB | 100%
14446 | I491TC15-0METF03-283-001 | Outdoor - Drawings Of Aux. Trans. Foundations | 00 | 2012-03-18 | Indeterminate | Drawing | Detail | Main Electrical Substation And Distribution Network | Civil and Steel Structure | PARSIAN |  | IFI | OB | 100%
14448 | I491TC15-0METF04-281-002 | Outdoor - Drawings Of P. Trans. Foundations(T102)170Mva | 01 | 2012-07-29 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Civil and Steel Structure | PARSIAN |  | IFI | OB | 100%
14450 | I491TC15-0METF04-282-002 | Outdoor - Drawings Of P. Trans. Foundations(T101)70Mva | 01 | 2012-07-29 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Civil and Steel Structure | PARSIAN |  | IFI | OB | 100%
114584 | I491TC99-0MEAA91-001-001 | MAIN ELECTRICAL SUBSTATION EXCAVATION PLAN | 00 | 2015-10-18 17:56 | Indeterminate | Drawing | Detail | Main Electrical substation Building | Mechanical | TAM | 2015-10-18 17:56 | IFA | A | 100%
114879 | I491TC99-0MEIR91-001-001 | SVC System Cable Trench Layout | 00 | 2016-02-02 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Civil and Steel Structure | NR Electric | 2016-02-03 12:47 | IFI | OB | 100%
114880 | I491TC99-0MEIR91-002-001 | SVC System Cable Trench Layout Detail | 01 | 2016-02-02 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Civil and Steel Structure | NR Electric | 2016-02-03 12:47 | IFI | OB | 100%
14462 | I491TC99-0MVAA91-001-005 | Design Criteria For Civil & Steel Structure | 03 | 2011-07-11 | Indeterminate | Miscellaneous(MISC) | Basic | General | Mechanical | TAM |  | IFC | AFC | 100%
14464 | I491TC99-0MVAA91-002-002 | Mobilization Access Road | 01 | 2011-11-20 | Indeterminate | Miscellaneous(MISC) | Detail | General | Mechanical | TAM |  | IFI | AC |  | 95%
14469 | I491TC99-0MXAA91-001-013 | Stacking Plan Part Vi | 00 | 2011-06-14 | Indeterminate | Drawing | Basic | General | Civil and Steel Structure | TAM |  | IFA | AC |  | 95%
14470 | I491TC99-0MXAA91-001-014 | Stacking Plan Part Vii | 00 | 2011-06-14 | Indeterminate | Drawing | Basic | General | Civil and Steel Structure | TAM |  | IFA | AC |  | 95%
14504 | I491TC99-0MXAA91-001-045 | Streets Longitudinal Profile | 01 | 2012-02-01 | Indeterminate | Drawing | Basic | General | Civil and Steel Structure | TAM |  | IFA | AC |  | 95%
14505 | I491TC99-0MXAA91-001-046 | Topogeraphy Plan | 01 | 2012-05-12 | Indeterminate | Miscellaneous(MISC) | Basic | General | Civil and Steel Structure | TAM |  | IFC | AFC | 100%
14506 | I491TC99-0MXAA91-001-047 | Plot Plan | 02 | 2012-05-12 | Indeterminate | Miscellaneous(MISC) | Basic | General | Civil and Steel Structure | TAM |  | IFC | AFC | 100%
14507 | I491TC99-0MXAA91-001-048 | Plant Elevations | 01 | 2012-05-12 | Indeterminate | Miscellaneous(MISC) | Basic | General | Civil and Steel Structure | TAM |  | IFC | AFC | 100%
14508 | I491TC99-0MXAA91-001-049 | Stacking Guide Plan | 01 | 2012-05-12 | Indeterminate | Miscellaneous(MISC) | Basic | General | Civil and Steel Structure | TAM |  | IFC | AFC | 100%
14510 | I491TC99-0MXAA91-001-050 | Streets Longitudinal Profiles | 02 | 2012-05-12 | Indeterminate | Miscellaneous(MISC) | Basic | General | Civil and Steel Structure | TAM |  | IFC | AFC | 100%
14511 | I491TC99-0MXAA91-001-051 | Topogeraphic Plan Part | 02 | 2013-05-14 | Indeterminate | Drawing | Basic | General | Civil and Steel Structure | TAM |  | IFC | AC |  | 95%
14512 | I491TC99-0MXAA91-001-052 | Topogeraphic Plan Part 1 | 02 | 2013-05-14 | Indeterminate | Drawing | Basic | General | Civil and Steel Structure | TAM |  | IFC | AC |  | 95%
14513 | I491TC99-0MXAA91-001-053 | Topogeraphic Plan Part 2 | 02 | 2013-05-14 | Indeterminate | Drawing | Basic | General | Civil and Steel Structure | TAM |  | IFC | AC |  | 95%
14514 | I491TC99-0MXAA91-001-054 | Topogeraphic Plan Part 3 | 02 | 2013-05-14 | Indeterminate | Drawing | Basic | General | Civil and Steel Structure | TAM |  | IFC | AC |  | 95%
14515 | I491TC99-0MXAA91-001-055 | Topogeraphic Plan Part 4 | 02 | 2013-05-14 | Indeterminate | Drawing | Basic | General | Civil and Steel Structure | TAM |  | IFC | AC |  | 95%
14516 | I491TC99-0MXAA91-001-056 | Topogeraphic Plan Part 5 | 02 | 2013-05-14 | Indeterminate | Drawing | Basic | General | Civil and Steel Structure | TAM |  | IFC | AC |  | 95%
14517 | I491TC99-0MXAA91-001-057 | Plot Plan | 02 | 2013-05-14 | Indeterminate | Drawing | Basic | General | Civil and Steel Structure | TAM |  | IFC | AC |  | 95%
14518 | I491TC99-0MXAA91-001-058 | Plot Plan Part 1 | 02 | 2013-05-14 | Indeterminate | Drawing | Basic | General | Civil and Steel Structure | TAM |  | IFC | AC |  | 95%
14519 | I491TC99-0MXAA91-001-059 | Plot Plan Part 2 | 02 | 2013-05-14 | Indeterminate | Drawing | Basic | General | Civil and Steel Structure | TAM |  | IFC | AC |  | 95%
14521 | I491TC99-0MXAA91-001-060 | Plot Plan Part 3 | 02 | 2013-05-14 | Indeterminate | Drawing | Basic | General | Civil and Steel Structure | TAM |  | IFC | AC |  | 95%
14522 | I491TC99-0MXAA91-001-061 | Plot Plan Part 4 | 02 | 2013-05-14 | Indeterminate | Drawing | Basic | General | Civil and Steel Structure | TAM |  | IFC | AC |  | 95%
14523 | I491TC99-0MXAA91-001-062 | Plot Plan Part 5 | 02 | 2013-05-14 | Indeterminate | Drawing | Basic | General | Civil and Steel Structure | TAM |  | IFC | AC |  | 95%
114136 | I491TC99-0MXAA91-001-063 | CIVIL DRAWINGS PLANT ELEVATIONS | 03 | 2015-06-22 | Indeterminate | Drawing | Basic | General | Civil and Steel Structure | TAM | 2015-06-29 08:39 | IFC | AFC | 100%
114137 | I491TC99-0MXAA91-001-064 | Plant Elevations Part 1 | 03 | 2015-06-22 | Indeterminate | Drawing | Basic | General | Civil and Steel Structure | TAM | 2015-06-29 08:39 | IFC | AFC | 100%
117031 | I491TC99-0MXAA91-001-065 | CIVIL DRAWING PLANT ELEVATIONS STREET, DRAINAGE AND FINISHED ELEVATION PLAN PART "2" - MELT SHOP 15-33 | 04 | 2016-07-26 11:00 | Indeterminate | Drawing | Basic | General | Civil and Steel Structure | TAM | 2016-07-26 11:00 | IFC | AFC | 100%
14527 | I491TC99-0MXAA91-001-066 | Plant Elevations Part 3 | 02 | 2013-05-14 | Indeterminate | Drawing | Basic | General | Civil and Steel Structure | TAM |  | IFC | AC |  | 95%
129723 | I491TC99-0MXAA91-001-067 | SITE CIVIL DRAWING PLANT ELEVATIONS STREET, DRAINAGE AND FINISHED ELEVATION PLAN ZONE "3" - WTP & NON IND.17-33 | 04 | 2016-10-18 | Indeterminate | Drawing | Basic | General | Civil and Steel Structure | TAM | 2016-10-19 13:20 | IFC | AFC | 100%
131021 | I491TC99-0MXAA91-001-068 | SITE CIVIL DRAWING STREET, DRAINAGE AND FINISHED ELEVATION PLAN ZONE "4" - ASP & CAP 18-33 | 03 | 2017-08-08 | Indeterminate | Drawing | Basic | General | Civil and Steel Structure | TAM | 2017-08-12 09:15 | IFC | AFC | 100%
14530 | I491TC99-0MXAA91-001-069 | Stacking Plan | 02 | 2013-05-14 | Indeterminate | Drawing | Basic | General | Civil and Steel Structure | TAM |  | IFC | AC |  | 95%
14532 | I491TC99-0MXAA91-001-070 | Stacking Plan Part 1 | 02 | 2013-05-14 | Indeterminate | Drawing | Basic | General | Civil and Steel Structure | TAM |  | IFC | AC |  | 95%
14533 | I491TC99-0MXAA91-001-071 | Stacking Plan Part 2 | 02 | 2013-05-14 | Indeterminate | Drawing | Basic | General | Civil and Steel Structure | TAM |  | IFC | AC |  | 95%
14534 | I491TC99-0MXAA91-001-072 | Stacking Plan Part 3 | 02 | 2013-05-14 | Indeterminate | Drawing | Basic | General | Civil and Steel Structure | TAM |  | IFC | AC |  | 95%
14535 | I491TC99-0MXAA91-001-073 | Stacking Plan Part 4 | 02 | 2013-05-14 | Indeterminate | Drawing | Basic | General | Civil and Steel Structure | TAM |  | IFC | AC |  | 95%
14536 | I491TC99-0MXAA91-001-074 | Stacking Plan Part 5 | 02 | 2013-05-14 | Indeterminate | Drawing | Basic | General | Civil and Steel Structure | TAM |  | IFC | AC |  | 95%
14537 | I491TC99-0MXAA91-001-075 | Street Longitudinal Profile St 22-1 20-1 | 02 | 2013-05-14 | Indeterminate | Drawing | Basic | General | Civil and Steel Structure | TAM |  | IFC | AC |  | 95%
14538 | I491TC99-0MXAA91-001-076 | Street Longitudinal Profile 18-1 /10-3 /18-2 | 02 | 2013-05-14 | Indeterminate | Drawing | Basic | General | Civil and Steel Structure | TAM |  | IFC | AC |  | 95%
14539 | I491TC99-0MXAA91-001-077 | Street Longitudinal Profile St 18-3 | 02 | 2013-05-14 | Indeterminate | Drawing | Basic | General | Civil and Steel Structure | TAM |  | IFC | AC |  | 95%
14540 | I491TC99-0MXAA91-001-078 | Street Longitudinal Profile St 18-4 18-5 | 02 | 2013-05-14 | Indeterminate | Drawing | Basic | General | Civil and Steel Structure | TAM |  | IFC | AC |  | 95%
14541 | I491TC99-0MXAA91-001-079 | Street Longitudinal Profile 18-6 | 02 | 2013-05-14 | Indeterminate | Drawing | Basic | General | Civil and Steel Structure | TAM |  | IFC | AC |  | 95%
14543 | I491TC99-0MXAA91-001-080 | Street Longitudinal Profile 18-6 (Cont). 15-1 | 02 | 2013-05-14 | Indeterminate | Drawing | Basic | General | Civil and Steel Structure | TAM |  | IFC | AC |  | 95%
14544 | I491TC99-0MXAA91-001-081 | Street Longitudinal Profile St 10-1 | 02 | 2013-05-14 | Indeterminate | Drawing | Basic | General | Civil and Steel Structure | TAM |  | IFC | AC |  | 95%
14545 | I491TC99-0MXAA91-001-082 | Street Longitudinal Profile St 10-2 | 02 | 2013-05-14 | Indeterminate | Drawing | Basic | General | Civil and Steel Structure | TAM |  | IFC | AC |  | 95%
14546 | I491TC99-0MXAA91-001-083 | Street Longitudinal Profile St 10-4 | 02 | 2013-05-14 | Indeterminate | Drawing | Basic | General | Civil and Steel Structure | TAM |  | IFC | AC |  | 95%
14550 | I491TE01-0ASAA91-001-003 | Single Line Diagram For Asp 1-2 | 01 | 2013-07-11 | Indeterminate | Drawing | Basic | Air Separation Plant | Automation and Instrumentation | TAM |  | IFA | AC |  | 95%
14551 | I491TE01-0ASAA91-001-004 | Single Line Diagram For Asp 2-2 | 01 | 2013-07-11 | Indeterminate | Drawing | Basic | Air Separation Plant | Automation and Instrumentation | TAM |  | IFA | AC |  | 95%
115336 | I491TE01-0ASAA91-003-001 | Electrical Installation Material (ASP) | 00 | 2016-05-14 | Indeterminate | Drawing | Detail | Air Separation Plant | Electrical | TAM | 2016-05-25 09:36 | IFI | OB | 100%
132946 | I491TE01-0ASAM91-001-001 | ASP AND CAP SUBSTATION LAYOUT | 03 | 2018-03-05 | Indeterminate | Drawing | Detail | Air Separation Plant | Electrical | TAM | 2018-03-12 14:33 | IFC | AFC | 100%
115707 | I491TE01-0ASLT91-001-001 | ASP Street Lighting Layout (Lighting Layout) 1-2 | 03 | 2016-06-07 09:51 | Indeterminate | Drawing | Detail | Air Separation Plant | Electrical | TAM | 2016-06-07 09:51 | IFC | AFC | 100%
115708 | I491TE01-0ASLT91-001-002 | ASP Street Lighting Layout (LDP02 Single Line Daigram 2-2 | 03 | 2016-06-07 09:51 | Indeterminate | Drawing | Detail | Air Separation Plant | Electrical | TAM | 2016-06-07 09:51 | IFC | AFC | 100%
14552 | I491TE01-0DTAA91-004-001 | Powercenter Wiring Diagram And Dimension-I491Te01-0Dtaa91-004 | 00 | 2013-09-14 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Equipment | Automation and Instrumentation | HASCON |  | IFA | AC |  | 95%
130411 | I491TE01-0DTAA91-006-001 | TR5 - Transformer diagrams and dimensions | 00 | 2017-04-04 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Automation and Instrumentation | HASCON | 2017-04-09 11:38 | IFA | AC |  | 95%
113524 | I491TE01-0DTAA91-008-001 | ELECTRICAL SYSTEM FOR FUME TREATMENT PLANT VFD5 - Inverter wiring diagrams and dimensions | 00 | 2015-05-10 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Equipment | Electrical | HASCON | 2015-05-24 17:13 | IFA | A | 100%
14553 | I491TE01-0DTAA91-009-001 | Motor Control Center Wiring Diagrams And Dimensons | 00 | 2013-09-14 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Equipment | Automation and Instrumentation | HASCON |  | IFA | AC |  | 95%
113259 | I491TE01-0DTAA91-010-001 | Electrical System For Fume Treatment Plant Distribution UPS Panel | 00 | 2015-01-18 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Automation and Instrumentation | HASCON | 2015-01-20 13:29 | IFA | AC |  | 95%
129859 | I491TE01-0DTAA91-011-001 | Power cable list | 00 | 2016-12-03 14:46 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Equipment | Automation and Instrumentation | HASCON | 2016-12-03 14:46 | IFA | AC |  | 95%
115716 | I491TE01-0DTAA91-111-001 | POWER CABLE LIST FOR DRI AREA | 00 | 2016-06-07 11:34 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Equipment | Automation and Instrumentation | HASCON | 2016-06-07 11:34 | IFA | AC |  | 95%
130124 | I491TE01-0DTAA91-113-001 | FTP DRI Power Cable Data Sheet | 00 | 2017-01-10 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Equipment | Automation and Instrumentation | TAM | 2017-01-15 09:19 | IFA | AC |  | 95%
111577 | I491TE01-0DTAM91-001-001 | FTP Substation Layout | 01 | 2014-02-09 | Indeterminate | Drawing | Detail | Fume Treatment Plant Electrical Substation | Electrical | TAM | 2014-04-23 17:33 | IFC | AFC | 100%
115709 | I491TE01-0DTLT91-001-001 | FTP STREET LIGHTING LAYOUT (Lighting Layout) 1-2 | 04 | 2016-06-07 09:53 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Electrical | TAM | 2016-06-07 09:53 | IFC | AFC | 100%
115710 | I491TE01-0DTLT91-001-002 | FTP STREET LIGHTING LAYOUT (Ldp01 Single Line Diagram) 2-2 | 04 | 2016-06-07 09:53 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Electrical | TAM | 2016-06-07 09:53 | IFC | AFC | 100%
114355 | I491TE01-0DTSW91-001-001 | FTP SUBSTATION EQUIPMENT LAYOUT | 01 | 2015-09-07 09:39 | Indeterminate | Drawing | Basic | Fume Treatment Equipment | Electrical | TAM | 2015-09-07 09:39 | IFC | AFC | 100%
115610 | I491TE01-0EAAA91-002-001 | Cabinets Layout & Arrangement Drawing of EAF Building 1-2 | 01 | 2016-05-28 09:25 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Electrical | TAM | 2016-05-28 09:25 | IFC | AFC | 100%
115611 | I491TE01-0EAAA91-002-002 | Cabinets Layout & Arrangement Drawing of EAF Building 2-2 | 01 | 2016-05-28 09:25 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Electrical | TAM | 2016-05-28 09:25 | IFC | AFC | 100%
111856 | I491TE01-0EAEW01-002-001 | Technical Data Of Eaf Series Reactor | 01 | 2014-04-28 | Indeterminate | Miscellaneous(MISC) | Detail | Electric Arc Furnace | Electrical | TAMINI | 2014-05-03 11:56 | IFC | AFC | 100%
111855 | I491TE01-0EAEW01-003-001 | Rating Plate For Eaf Series Reactor | 01 | 2014-04-28 | Indeterminate | Miscellaneous(MISC) | Detail | Electric Arc Furnace | Electrical | TAMINI | 2014-05-03 11:56 | IFC | AFC | 100%
111857 | I491TE01-0EATF01-002-001 | Technical Data Of Eaf Transformer | 01 | 2014-04-28 | Indeterminate | Miscellaneous(MISC) | Detail | Electric Arc Furnace | Electrical | TAMINI | 2014-05-03 11:56 | IFC | AFC | 100%
111858 | I491TE01-0EATF01-003-001 | Rating Plate Of Eaf Furnace Transformer | 01 | 2014-04-28 | Indeterminate | Miscellaneous(MISC) | Detail | Electric Arc Furnace | Electrical | TAMINI | 2014-05-03 11:56 | IFC | AFC | 100%
115609 | I491TE01-0LFAA91-002-001 | Cabinets Layout & Aarrangement Drawing of LF Building | 01 | 2016-05-28 09:23 | Indeterminate | Drawing | Detail | Ladle Furnace | Electrical | TAM | 2016-05-28 09:23 | IFC | AFC | 100%
111859 | I491TE01-0LFTF01-002-001 | Technical Data Of Lf Transformer | 01 | 2014-04-28 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Electrical | TAMINI | 2014-05-03 11:57 | IFC | AFC | 100%
111860 | I491TE01-0LFTF01-003-001 | Rating Plate Of Lf Transformer | 01 | 2014-04-28 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Electrical | TAMINI | 2014-05-03 11:57 | IFC | AFC | 100%
112231 | I491TE01-0MDAA91-001-004 | Electrical Design Criteria For Material Handling (Conveyor) System | 03 | 2013-08-07 | Indeterminate | Miscellaneous(MISC) | Basic | Material Handling | Electrical | DATIS | 2014-05-19 16:49 | IFC | AFC | 100%
16635 | I491TE01-0MDAA91-002-001 | Cable Sizing Rules For Material Handling(Conveyor) System | 02 | 2014-02-19 09:19 | Indeterminate | Miscellaneous(MISC) | Basic | Material Handling | Electrical | DATIS | 2014-02-19 09:19 | IFC | AFC | 100%
131063 | I491TE01-0MDAA91-003-001 | Material Handling System ELECTRICAL SWITCHGEAR LAYOUT FTP SUBSTATION | 01 | 2017-08-16 | Indeterminate | Drawing | Detail | Material Handling | Automation and Instrumentation | DATIS | 2017-08-23 11:02 | IFC | AFC | 100%
16578 | I491TE01-0MDAA91-004-001 | Material Handling System Electrical Switchgear Layout Eaf Substation | 01 | 2013-12-01 | Indeterminate | Miscellaneous(MISC) | Detail | Material Handling | Electrical | DATIS | 2014-02-18 09:46 | IFC | AFC | 100%
16579 | I491TE01-0MDAA91-005-001 | Material Handling System Electrical Switchgear Layout Lf Substation | 01 | 2013-12-01 | Indeterminate | Miscellaneous(MISC) | Detail | Material Handling | Electrical | DATIS | 2014-02-18 09:47 | IFC | AFC | 100%
14572 | I491TE01-0MEGM91-001-003 | Smp Substation Layout | 02 | 2012-08-06 | Indeterminate | Miscellaneous(MISC) | Detail | Steel Making Electrical Substation | Electrical | TAM |  | IFC | AFC | 100%
114873 | I491TE01-0MEIR91-001-001 | SINGLE LINE DIGRAM FOR SVC SYSTEM | 01 | 2016-02-02 | Indeterminate | Miscellaneous(MISC) | Basic | Main Electrical Substation And Distribution Network | Electrical | NR Electric | 2016-02-03 11:55 | IFC | AFC | 100%
14575 | I491TE01-0MESW91-001-003 | Smp Substation- Mv Single Line Diagram | 00 | 2013-08-03 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | TAM |  | IFI | OB | 100%
132994 | I491TE01-0MESW91-002-001 | Electrical Overall Single Line Diagram | 02 | 2018-03-17 | Indeterminate | Drawing | Detail | Main Electrical Substation And Distribution Network | Electrical | TAM | 2018-03-18 09:15 | IFI | OB | 100%
117712 | I491TE01-0MESW91-003-001 | Electrical Power System Study | 00 | 2016-07-31 13:48 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | TAM | 2016-07-31 13:48 | IFI | AC |  | 95%
133285 | I491TE01-0MESW91-004-001 | UPS OVERALL SINGLE LINE DIAGRAM-NETWORK COMMUNICATION | 00 | 2018-06-13 | Indeterminate | Drawing | Detail | Main Electrical Substation And Distribution Network | Electrical | TAM | 2018-06-25 15:26 | IFA | AC |  | 95%
114392 | I491TE01-0MMAA91-001-001 | LV capacitor bank for Water Teratment Plant | 00 | 2015-09-19 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Automation and Instrumentation | TAM | 2015-09-21 11:42 | IFA | AC |  | 95%
135242 | I491TE01-0MMCF91-001-001 | 400V SINGLE LINE DIAGRAM (MCC) Sedimentation System of Water Cooling System 1-3 | 04 | 2019-04-14 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Electrical | TAM | 2019-04-17 13:19 | IFC | AC |  | 95%
129987 | I491TE01-0MMCF91-001-002 | 400V SINGLE LINE DIAGRAM (MCC) Sedimentation System of Water Cooling System 2-3 | 01 | 2016-12-18 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Electrical | TAM | 2016-12-20 09:54 | IFI | OB | 100%
129988 | I491TE01-0MMCF91-001-003 | 400V SINGLE LINE DIAGRAM (MCC) Sedimentation System of Water Cooling System 3-3 | 01 | 2016-12-18 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Electrical | TAM | 2016-12-20 09:54 | IFI | OB | 100%
130913 | I491TE01-0MMCF91-002-001 | Electrical Load List For Sedimentation of Water Cooling System | 02 | 2017-07-26 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Electrical | Beniz Tajhiz | 2017-07-30 11:05 | IFI | AFC | 100%
132035 | I491TE01-0MMCF91-012-001 | SEDIMENTATION CABLE ROUTING 1-2 | 03 | 2017-11-22 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Electrical | TAM | 2017-11-25 09:50 | IFC | AFC | 100%
132036 | I491TE01-0MMCF91-012-002 | SEDIMENTATION CABLE ROUTING 2-2 | 03 | 2017-11-22 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Electrical | TAM | 2017-11-25 09:50 | IFC | AFC | 100%
130667 | I491TE01-0MMCF91-014-001 | Cable Sizing Calculation For Sedimentation Of Water Cooling Plant | 01 | 2017-05-30 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Electrical | TAM | 2017-06-07 09:23 | IFC | AFC | 100%
133358 | I491TE01-0MMCF91-017-001 | WCP Sedimentation Three Line and Schematic Diagram (10 Sheet) | 03 | 2018-06-24 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Electrical | TAM | 2018-07-07 10:24 | IFI | OB | 100%
11758 | I491TE01-0MMCT01-001-001 | Electric Motor Data Sheet Ct01 | 00 | 2013-01-07 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Mechanical | FARABARD |  | IFA | AC |  | 95%
11759 | I491TE01-0MMCT02-001-001 | Electric Motor Data Sheet Ct02 | 00 | 2013-01-07 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Mechanical | FARABARD |  | IFA | AC |  | 95%
115711 | I491TE01-0MMLT91-001-001 | WTP & MELTSHOP STREET LIGHTING LAYOUT (LIGHTING LAYOUT) 1-2 | 03 | 2016-06-07 09:55 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Electrical | TAM | 2016-06-07 09:55 | IFC | AFC | 100%
135243 | I491TE01-0MMLT91-001-002 | WTP & MELTSHOP STREET LIGHTING LAYOUT (LDP04 SINGLE LINE DIAGRAM) 2-2 | 07 | 2019-04-14 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Electrical | TAM | 2019-04-17 13:19 | IFC | AC |  | 95%
114400 | I491TE01-0MXAA91-001-001 | Data sheet for Power and Instrument Cables | 00 | 2015-09-26 | Indeterminate | Miscellaneous(MISC) | Detail | General | Electrical | TAM | 2015-09-28 10:25 | IFA | OB | 100%
115151 | I491TE01-0MXAA91-002-001 | Technical Specification of Electrical Room False Floor | 01 | 2016-04-23 | Indeterminate | Miscellaneous(MISC) | Detail | General | Electrical | TAM | 2016-05-03 14:25 | IFC | AFC | 100%
132939 | I491TE01-0MXAA91-003-001 | Electrical Load List | 01 | 2018-02-25 | Indeterminate | Miscellaneous(MISC) | Detail | General | Electrical | TAM | 2018-03-12 13:49 | IFI | OB | 100%
14577 | I491TE01-0MXEG91-001-002 | Datasheet For Diesel Generator | 01 | 2013-09-04 | Indeterminate | Miscellaneous(MISC) | Detail | General | Electrical | Fortune |  | IFC | AFC | 100%
14580 | I491TE01-0MXSW91-001-003 | Technical Specification For Switchgears | 02 | 2013-10-22 | Indeterminate | Miscellaneous(MISC) | Basic | General | Electrical | Fortune |  | IFC | AFC | 100%
115760 | I491TE01-0MXTF91-002-001 | Data Sheet for LV/LV and MV/LV Transformers | 01 | 2016-06-15 | Indeterminate | Miscellaneous(MISC) | Detail | General | Electrical | TAM | 2016-06-21 13:29 | IFC | AFC | 100%
132930 | I491TE01-0MYLT91-001-001 | Workshop Under Ground Pipes | 00 | 2018-02-19 10:10 | Indeterminate | Drawing | Detail | Maintenance Workshop | Electrical | TAM | 2018-02-19 10:10 | IFI | OB | 100%
113476 | I491TE01-0SEBD91-001-001 | TECHNICAL SPECIFICATION FOR BUSDUCT | 01 | 2015-04-12 | Indeterminate | Miscellaneous(MISC) | Detail | Steel Making Electrical Substation | Electrical | TAM | 2015-04-22 09:49 | IFC | AFC | 100%
113432 | I491TE01-0SEDC91-001-001 | Technical Spcication and calculation for Smp Substation DC Charger | 01 | 2015-03-15 | Indeterminate | Miscellaneous(MISC) | Basic | Steel Making Electrical Substation | Electrical | TAM | 2015-03-17 09:30 | IFC | AFC | 100%
129271 | I491TE01-0SEDC91-002-001 | Technical Specification and calculation For Substation DC Charger(Sample For WTP.Sub) | 00 | 2016-08-14 | Indeterminate | Miscellaneous(MISC) | Detail | General | Electrical | TAM | 2016-08-15 14:33 | IFA | AFC | 100%
115713 | I491TE01-0SELT91-001-001 | WHERHOUS & SMP STREET LIGHTING LAYOUT (LIGHTING LAYOUT) 1-2 | 03 | 2016-06-07 11:31 | Indeterminate | Drawing | Detail | Steel Making Electrical Substation | Electrical | TAM | 2016-06-07 11:31 | IFC | AFC | 100%
115714 | I491TE01-0SELT91-001-002 | WHERHOUS & SMP STREET LIGHTING LAYOUT (LDP03 SINGLE LINE DIAGRAM) 2-2 | 03 | 2016-06-07 11:31 | Indeterminate | Drawing | Detail | Steel Making Electrical Substation | Electrical | TAM | 2016-06-07 11:31 | IFC | AFC | 100%
14582 | I491TE02-0EATF92-001-002 | Basic Data For Furnace Transformers | 01 | 2012-06-11 | Indeterminate | Miscellaneous(MISC) | Basic | Electric Arc Furnace | Mechanical | TAM |  | IFC | AFC | 100%
11770 | I491TE02-0METF92-001-001 | 33/0.4 Kv Earting/Auxliary Transformers 800Kva,2975&1225Amps,30S Instruction Manual | 00 | 2013-05-13 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | TAM |  | IFI | OB | 100%
11771 | I491TE02-0METF92-002-001 | 400/33Kv 70Mva Power Transformer Instruction Manual Volume Iv Of Iv | 00 | 2013-05-13 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | TAM |  | IFI | OB | 100%
11772 | I491TE02-0METF92-003-001 | 400/33Kv 170Mva Power Transformer Instruction Manual Volume Iv Of Iv | 00 | 2013-05-13 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | TAM |  | IFI | OB | 100%
11773 | I491TE02-0METF92-004-001 | 400/33Kv 70Mva Power Transformer Instruction Manual Volume Ii & Iii Of Iv | 00 | 2013-05-13 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | TAM |  | IFI | OB | 100%
11774 | I491TE02-0METF92-005-001 | 400/33Kv 170Mva Power Transformer Instruction Manual Volume Ii & Iii Of Iv | 00 | 2013-05-13 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | TAM |  | IFI | OB | 100%
11775 | I491TE02-0METF92-006-001 | 400/33Kv 70Mva Power Transformer Instruction Manual Volume I Of Iv | 00 | 2013-05-13 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | TAM |  | IFI | OB | 100%
11776 | I491TE02-0METF92-007-001 | 400/33Kv 170Mva Power Transformer Instruction Manual Volume I Of Iv | 00 | 2013-05-13 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | TAM |  | IFI | OB | 100%
14584 | I491TE02-0MNET92-001-002 | Technical Drawings Of Power (170 And 70 Mva) And Auxiliary Transformers | 01 | 2012-04-14 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | TAM |  | IFI | OB | 100%
14586 | I491TE02-0MNET92-002-002 | Technical Specification For 33/6.6 And 6.6/ 0.4 Kv Transformers | 01 | 2012-10-22 | Indeterminate | Miscellaneous(MISC) | Detail | Steel Making Electrical Substation | Electrical | TAM |  | IFC | AFC | 100%
14588 | I491TE02-0MNET92-004-002 | Data Sheet For 33/6.9 Kv Transformers | 01 | 2012-10-22 | Indeterminate | Miscellaneous(MISC) | Detail | Steel Making Electrical Substation | Electrical | TAM |  | IFC | AFC | 100%
14590 | I491TE02-0MNET92-005-002 | Data Sheet For 6.6/0.42 Kv Transformers | 01 | 2012-10-22 | Indeterminate | Miscellaneous(MISC) | Detail | Steel Making Electrical Substation | Electrical | Fortune |  | IFC | AFC | 100%
133139 | I491TE03-0ASEE91-001-001 | ASP SUBSTATION GROUNDING SYSTEM LAYOUT | 03 | 2018-05-13 | Indeterminate | Drawing | Detail | Air Separation Plant Electrical Substation | Electrical | TAM | 2018-05-15 09:33 | IFC | AFC | 100%
130447 | I491TE03-0ASEE91-002-001 | ASP GROUNDING SYSTEM LAYOUT | 03 | 2017-04-09 | Indeterminate | Drawing | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2017-04-19 09:07 | IFC | AFC | 100%
111596 | I491TE03-0ASSW91-001-001 | Asp Substation Mv Single Line Diagram | 01 | 2014-02-23 | Indeterminate | Drawing | Detail | Air Separation Plant | Electrical | TAM | 2014-04-24 13:36 | IFC | AFC | 100%
129953 | I491TE03-0ASSW91-002-001 | ASP SUBSTATION-Data Sheet for MV Switchgear | 01 | 2016-12-13 08:47 | Indeterminate | Miscellaneous(MISC) | Detail | Air Separation Plant | Electrical | TAM | 2016-12-13 08:47 | IFC | AFC | 100%
114330 | I491TE03-0CCEE91-001-001 | CCM SUBSTATION GROUNDING SYSTEM LAYOUT | 01 | 2015-09-05 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Electrical | TAM | 2015-09-07 09:07 | IFC | AFC | 100%
111580 | I491TE03-0CCSW91-001-001 | Ccm Substation Mv Single Line Diagram | 02 | 2014-02-22 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Electrical | TAM | 2014-04-23 18:05 | IFC | AFC | 100%
129954 | I491TE03-0CCSW91-002-001 | CCM SUBSTATION-Data Sheet for MV Switchgear | 01 | 2016-12-13 08:49 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Electrical | TAM | 2016-12-13 08:49 | IFC | AFC | 100%
113594 | I491TE03-0DTAA91-002-001 | Instrument List For Dedusting Systemfurnace 140Ton Eaf + Lf & Mh | 01 | 2015-05-10 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Equipment | Automation and Instrumentation | HASCON | 2015-05-27 16:21 | IFA | A | 100%
113008 | I491TE03-0DTEE91-001-001 | FTP SUBSTATION GROUNDING SYSTEM LAYOUT | 01 | 2014-09-28 16:01 | Indeterminate | Drawing | Detail | Fume Treatment Plant Electrical Substation | Electrical | TAM | 2014-09-28 16:01 | IFC | AFC | 100%
111636 | I491TE03-0DTSW91-001-001 | FTP SUBSTATION MV SINGLE LINE DIAGRAM | 01 | 2014-03-03 | Indeterminate | Drawing | Detail | Fume Treatment Plant Electrical Substation | Electrical | TAM | 2014-04-24 14:29 | IFC | AFC | 100%
129958 | I491TE03-0DTSW91-002-001 | FTP SUBSTATION-Data Sheet for MV Switchgear | 01 | 2016-12-13 08:58 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Plant Electrical Substation | Electrical | TAM | 2016-12-13 08:58 | IFC | AFC | 100%
16605 | I491TE03-0EASW91-001-001 | Meltshop Substation Mv Single Line Diagram | 01 | 2013-12-11 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop | Electrical | TAM | 2014-02-18 11:34 | IFC | AFC | 100%
14597 | I491TE03-0EASW91-002-002 | Meltshop Substation--Data Sheet For Mv Switchgear | 01 | 2013-09-29 | Indeterminate | Miscellaneous(MISC) | Detail | Steel Making Electrical Substation | Electrical | TAM |  | IFC | AFC | 100%
14599 | I491TE03-0MESW92-001-002 | Technical Specification And Data Sheet For Medium Voltage Indoor Switchgears | 01 | 2012-01-17 | Indeterminate | Miscellaneous(MISC) | Basic | General | Electrical | TAM |  | IFC | AFC | 100%
131129 | I491TE03-0MKEE91-001-001 | WTP SUBSTATION GROUNDING SYSTEM LAYOUT | 02 | 2017-08-28 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Electrical | TAM | 2017-09-06 14:06 | IFC | AFC | 100%
129956 | I491TE03-0MKSW91-002-001 | WTP SUBSTATION-Data Sheet for MV Switchgear | 01 | 2016-12-13 08:55 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Electrical | TAM | 2016-12-13 08:55 | IFC | AFC | 100%
14602 | I491TE03-0SEAA91-001-003 | Basic Data Of Smp Electrical Substation(Preliminary Overall Single Line Diagram) | 02 | 2012-01-15 | Indeterminate | Drawing | Basic | Steel Making Electrical Substation | Mechanical | TAM |  | IFC | AFC | 100%
14603 | I491TE03-0SESW91-001-001 | Data Sheet For 6.9 Kv Smp Switchgear | 00 | 2013-03-04 | Indeterminate | Miscellaneous(MISC) | Detail | Steel Making Electrical Substation Building | Electrical | TAM |  | IFA | AFC | 100%
115114 | I491TE04-0ASAA91-001-001 | LV- PMCC Schematic Diagram | 00 | 2016-04-04 | Indeterminate | Drawing | Detail | Air Separation Plant | Electrical | Fortune | 2016-04-06 14:22 | IFI | OB | 100%
115113 | I491TE04-0ASAA91-002-001 | LV- PMCC Detailed Single Line Diagram | 00 | 2016-04-04 | Indeterminate | Miscellaneous(MISC) | Detail | Air Separation Plant | Electrical | Fortune | 2016-04-06 14:21 | IFI | OB | 100%
113497 | I491TE04-0ASSW91-001-001 | ASP SUBSTATION LV SINGLE LINE DIAGRAM | 02 | 2015-04-21 | Indeterminate | Drawing | Detail | Air Separation Plant Electrical Substation | Electrical | TAM | 2015-04-22 10:50 | IFC | AFC | 100%
130007 | I491TE04-0ASSW91-002-001 | ASP DISTRIBUTION PANEL SINGLE LINE DIAGRAM 1-2 | 03 | 2016-12-25 16:51 | Indeterminate | Drawing | Detail | Air Separation Plant Main Building | Electrical | TAM | 2016-12-25 16:51 | IFC | AFC | 100%
130008 | I491TE04-0ASSW91-002-002 | ASP DISTRIBUTION PANEL SINGLE LINE DIAGRAM 2-2 | 03 | 2016-12-25 16:51 | Indeterminate | Drawing | Detail | Air Separation Plant Main Building | Electrical | TAM | 2016-12-25 16:51 | IFC | AFC | 100%
112278 | I491TE04-0ASSW91-003-001 | ASP SUBSTATION-Data Sheet for LV Switchgear | 01 | 2014-05-26 18:34 | Indeterminate | Miscellaneous(MISC) | Detail | Air Separation Plant Electrical Substation | Electrical | TAM | 2014-05-26 18:34 | IFC | AFC | 100%
114173 | I491TE04-0CCAA91-001-001 | Drives & Starters Switchboard Electrical Diagram for =HC11E0*+MCS01 | 00 | 2015-07-12 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Automation and Instrumentation | DANIELI | 2015-07-22 10:10 | IFA | A | 100%
114174 | I491TE04-0CCAA91-002-001 | Drives & Starters Switchboard Electrical Diagram for HC11E10+MCS01 | 00 | 2015-07-12 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Automation and Instrumentation | DANIELI | 2015-07-22 10:10 | IFA | A | 100%
114175 | I491TE04-0CCAA91-003-001 | Drives & Starters Switchboard Electrical Diagram For HC11E10+MCS02 | 00 | 2015-07-12 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Automation and Instrumentation | DANIELI | 2015-07-22 10:10 | IFA | A | 100%
114176 | I491TE04-0CCAA91-004-001 | Motor Protection Boxes Electrical Diagram | 00 | 2015-07-12 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Automation and Instrumentation | DANIELI | 2015-07-22 10:10 | IFA | A | 100%
115145 | I491TE04-0CCSW91-001-001 | CCM SUBSTATION LV SINGLE LINE DIAGRAM | 02 | 2016-04-17 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Electrical | TAM | 2016-04-20 11:10 | IFC | AFC | 100%
130332 | I491TE04-0CCSW91-003-001 | CCM SUBSTATION-Data Sheet for LV Switchgear | 02 | 2017-02-22 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Electrical | TAM | 2017-02-27 15:06 | IFC | AFC | 100%
113310 | I491TE04-0DTAA91-001-002 | Dedusting System Single Line Diagram | 03 | 2015-01-27 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Equipment | Automation and Instrumentation | HASCON | 2015-01-31 10:34 | IFI | AC |  | 95%
115141 | I491TE04-0DTSW91-001-001 | FTP SUBSTATION LV SINGLE LINE DIAGRAM | 03 | 2016-04-17 | Indeterminate | Drawing | Detail | Fume Treatment Plant Electrical Substation | Electrical | TAM | 2016-04-20 11:00 | IFC | AFC | 100%
130288 | I491TE04-0DTSW91-002-001 | FTP DISTRIBUTION PANEL SINGLE LINE DIAGRAM | 02 | 2017-02-04 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Electrical | TAM | 2017-02-07 10:13 | IFC | AFC | 100%
111705 | I491TE04-0DTSW91-003-001 | FTP SUBSTATION-Data Sheet for LV Switchgear | 00 | 2014-04-19 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Plant Electrical Substation | Electrical | TAM | 2014-04-27 11:36 | IFA | AFC | 100%
115154 | I491TE04-0EASW91-001-001 | MELTSHOP SUBSTATION LV SINGLE LINE DIAGRAM | 02 | 2016-04-23 | Indeterminate | Drawing | Detail | Melt Shop Electrical Substation | Electrical | TAM | 2016-05-03 14:39 | IFC | AFC | 100%
114132 | I491TE04-0EASW91-002-001 | MELTSHOP DISTRIBUTION PANEL SINGLE LINE DIAGRAM 1-2 | 00 | 2015-06-22 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Electrical | TAM | 2015-06-23 09:01 | IFA | A | 100%
114133 | I491TE04-0EASW91-002-002 | MELTSHOP DISTRIBUTION PANEL SINGLE LINE DIAGRAM 2-2 | 00 | 2015-06-22 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Electrical | TAM | 2015-06-23 09:01 | IFA | A | 100%
14607 | I491TE04-0EASW91-003-002 | Meltshop Substation-Data Sheet For Lv Switchgear | 01 | 2013-09-29 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop | Electrical | TAM |  | IFC | AFC | 100%
114656 | I491TE04-0MDAA91-001-001 | MCC Circuit Diagram for Material Handling System | 02 | 2015-11-09 09:54 | Indeterminate | Miscellaneous(MISC) | Detail | Material Handling | Electrical | TAM | 2015-11-09 09:54 | IFC | AFC | 100%
113596 | I491TE04-0MDCV91-011-001 | Lv Switchgear Sld For Lime & Ferro Alloy Mh Mcc-(Mcc-01) | 04 | 2015-05-12 | Indeterminate | Drawing | Basic | Material Handling | Electrical | DATIS | 2015-05-28 15:57 | IFC | AFC | 100%
113597 | I491TE04-0MDCV91-011-002 | Lv Switchgear Sld For Lime & Ferro Alloy Mh Mcc-(Mcc-01) | 04 | 2015-05-12 | Indeterminate | Drawing | Detail | Material Handling | Electrical | DATIS | 2015-05-28 15:57 | IFC | AFC | 100%
113598 | I491TE04-0MDCV91-012-001 | Lv Switchgear Sld For Dri To Meltshop & Eaf Charging Mh Mcc (Mcc-02) | 04 | 2015-05-12 | Indeterminate | Drawing | Basic | Material Handling | Electrical | DATIS | 2015-05-28 15:57 | IFC | AFC | 100%
113599 | I491TE04-0MDCV91-012-002 | Lv Switchgear Sld For Dri To Meltshop & Eaf Charging Mh Mcc (Mcc-02) | 04 | 2015-05-12 | Indeterminate | Drawing | Basic | Material Handling | Electrical | DATIS | 2015-05-28 15:57 | IFC | AFC | 100%
113600 | I491TE04-0MDCV91-012-003 | Lv Switchgear Sld For Dri To Meltshop & Eaf Charging Mh Mcc (Mcc-02) | 04 | 2015-05-12 | Indeterminate | Drawing | Basic | Material Handling | Electrical | DATIS | 2015-05-28 15:57 | IFC | AFC | 100%
113601 | I491TE04-0MDCV91-012-004 | Lv Switchgear Sld For Dri To Meltshop & Eaf Charging Mh Mcc (Mcc-02) | 04 | 2015-05-12 | Indeterminate | Drawing | Basic | Material Handling | Electrical | DATIS | 2015-05-28 15:57 | IFC | AFC | 100%
113602 | I491TE04-0MDCV91-012-005 | Lv Switchgear Sld For Dri To Meltshop & Eaf Charging Mh Mcc (Mcc-02) | 04 | 2015-05-12 | Indeterminate | Drawing | Detail | Material Handling | Electrical | DATIS | 2015-05-28 15:57 | IFC | AFC | 100%
113687 | I491TE04-0MDCV91-013-006 | Lv Switchgear Single Line Diagram For Mcc-3 1-3 | 04 | 2015-05-12 | Indeterminate | Drawing | Basic | Material Handling | Electrical | TAM | 2015-05-31 15:03 | IFC | AFC | 100%
113688 | I491TE04-0MDCV91-013-007 | Lv Switchgear Single Line Diagram For Mcc-3 2-3 | 04 | 2015-05-12 | Indeterminate | Drawing | Basic | Material Handling | Electrical | TAM | 2015-05-31 15:03 | IFC | AFC | 100%
113689 | I491TE04-0MDCV91-013-008 | Lv Switchgear Single Line Diagram For Mcc-3 3-3 | 04 | 2015-05-12 | Indeterminate | Drawing | Basic | Material Handling | Electrical | TAM | 2015-05-31 15:03 | IFC | AFC | 100%
114657 | I491TE04-0MDSW01-001-001 | G.A LAYOUT and EQUIPMENT LIST FOR MCC1 | 03 | 2015-11-09 09:54 | Indeterminate | Miscellaneous(MISC) | Detail | Material Handling | Electrical | TAM | 2015-11-09 09:54 | IFC | AFC | 100%
114658 | I491TE04-0MDSW02-001-001 | G.A LAYOUT and EQUIPMENT LIST FOR MCC2-E | 03 | 2015-11-09 09:54 | Indeterminate | Miscellaneous(MISC) | Detail | Material Handling | Electrical | TAM | 2015-11-09 09:54 | IFC | AFC | 100%
114659 | I491TE04-0MDSW02-002-001 | G.A LAYOUT and EQUIPMENT LIST FOR MCC2-N | 03 | 2015-11-09 09:54 | Indeterminate | Miscellaneous(MISC) | Detail | Material Handling | Electrical | TAM | 2015-11-09 09:54 | IFC | AFC | 100%
114660 | I491TE04-0MDSW03-001-001 | G.A LAYOUT and EQUIPMENT LIST FOR MCC3 | 03 | 2015-11-09 09:55 | Indeterminate | Miscellaneous(MISC) | Detail | Material Handling | Electrical | TAM | 2015-11-09 09:55 | IFC | AFC | 100%
14637 | I491TE04-0MEAA91-001-002 | Main Substation Lv Single Line Diagram | 01 | 2012-01-15 | Indeterminate | Miscellaneous(MISC) | Basic | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFC | AFC | 100%
113699 | I491TE04-0MESW91-001-001 | SMP SUBSTATION- LV SINGLE LINE DIAGRAM | 02 | 2015-06-06 08:29 | Indeterminate | Drawing | Detail | Steel Making Electrical Substation | Electrical | TAM | 2015-06-06 08:29 | IFC | AFC | 100%
130333 | I491TE04-0MESW91-002-001 | SMP SUBSTATION-Data Sheet for LV Switchgear | 02 | 2017-02-22 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Electrical | TAM | 2017-02-27 15:06 | IFC | AFC | 100%
130334 | I491TE04-0MKSW91-003-001 | WTP SUBSTATION-Data Sheet for LV Switchgear | 02 | 2017-02-22 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Electrical | TAM | 2017-02-27 15:06 | IFC | AFC | 100%
114712 | I491TE04-0MMAA91-001-001 | MCC Circuit Diagram for Water Treatment System | 02 | 2015-11-24 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Electrical | TAM | 2015-11-28 13:19 | IFC | AFC | 100%
114713 | I491TE04-0MMSW01-001-001 | G.A LAYOUT and EQUIPMENT LIST FOR WTP MCC | 03 | 2015-11-24 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Electrical | TAM | 2015-11-28 13:20 | IFC | AFC | 100%
14640 | I491TE04-0MXPA01-001-003 | Ware House-A Panels Sld | 02 | 2013-01-16 | Indeterminate | Drawing | Detail | Warehouse | Electrical | TAM |  | IFC | AFC | 100%
14643 | I491TE04-0MXPA01-002-003 | Ware House Panels Arrangement | 02 | 2013-01-16 | Indeterminate | Drawing | Detail | Warehouse | Electrical | TAM |  | IFC | AFC | 100%
129534 | I491TE04-0MZPA91-001-002 | Workshop Panels SLD (2Sheet) | 06 | 2016-09-18 09:42 | Indeterminate | Drawing | Detail | Maintenance Workshop | Electrical | TAM | 2016-09-18 09:42 | IFC | AFC | 100%
129535 | I491TE04-0MZPA91-001-003 | Workshop Panels SLD (Sheet3) | 02 | 2016-09-18 09:43 | Indeterminate | Drawing | Detail | Maintenance Workshop | Electrical | TAM | 2016-09-18 09:43 | IFC | AFC | 100%
14647 | I491TE04-0MZPA91-002-002 | Workshop Panels Arrangement | 01 | 2013-10-09 | Indeterminate | Drawing | Detail | Maintenance Workshop | Electrical | TAM |  | IFC | AFC | 100%
112124 | I491TE04-0OFAA91-001-001 | LIST OF ELECTRICAL DRAWING, LEGEND AND GENERAL NOTE | 00 | 2014-05-05 | Indeterminate | Drawing | Detail | Office - Canteen - Locker & Shower For Melt Shop | Piping & Utility | TAM | 2014-05-15 15:35 | IFA | AC |  | 95%
112123 | I491TE04-0OFAA91-001-002 | GROUND FLOOR POWER OF MECHANICAL UTILITY | 00 | 2014-05-05 | Indeterminate | Drawing | Detail | Office - Canteen - Locker & Shower For Melt Shop | Piping & Utility | TAM | 2014-05-15 15:35 | IFA | AC |  | 95%
112122 | I491TE04-0OFAA91-001-003 | 1ST FLOOR POWER OF MECHANICAL UTILITY | 00 | 2014-05-05 | Indeterminate | Drawing | Detail | Office - Canteen - Locker & Shower For Melt Shop | Piping & Utility | TAM | 2014-05-15 15:35 | IFA | AC |  | 95%
112121 | I491TE04-0OFAA91-001-004 | ROOF POWER OF MECHANICAL UTILITY | 00 | 2014-05-05 | Indeterminate | Drawing | Detail | Office - Canteen - Locker & Shower For Melt Shop | Piping & Utility | TAM | 2014-05-15 15:35 | IFA | AC |  | 95%
112120 | I491TE04-0OFAA91-001-005 | DETAIL OF ELECTRICAL | 00 | 2014-05-05 | Indeterminate | Drawing | Detail | Office - Canteen - Locker & Shower For Melt Shop | Piping & Utility | TAM | 2014-05-15 15:35 | IFA | AC |  | 95%
112130 | I491TE04-0OFPN91-001-001 | LIST OF ELECTRICAL DRAWING, LEGEND AND GENERAL NOTE | 00 | 2014-05-05 | Indeterminate | Drawing | Detail | Office - Canteen - Locker & Shower For Melt Shop | Piping & Utility | TAM | 2014-05-15 15:36 | IFA | AC |  | 95%
112129 | I491TE04-0OFPN91-001-002 | ELECTRICAL PANEL &RISER DIAGRAM | 00 | 2014-05-05 | Indeterminate | Drawing | Detail | Office - Canteen - Locker & Shower For Melt Shop | Piping & Utility | TAM | 2014-05-15 15:36 | IFA | AC |  | 95%
112128 | I491TE04-0OFPN91-001-003 | ELECTRICAL PANEL DIAGRAM | 00 | 2014-05-05 | Indeterminate | Drawing | Detail | Office - Canteen - Locker & Shower For Melt Shop | Piping & Utility | TAM | 2014-05-15 15:36 | IFA | AC |  | 95%
112127 | I491TE04-0OFPN91-001-004 | ELECTRICAL PANEL DIAGRAM | 00 | 2014-05-05 | Indeterminate | Drawing | Detail | Office - Canteen - Locker & Shower For Melt Shop | Piping & Utility | TAM | 2014-05-15 15:36 | IFA | AC |  | 95%
112126 | I491TE04-0OFPN91-001-005 | ELECTRICAL PANEL DIAGRAM | 00 | 2014-05-05 | Indeterminate | Drawing | Detail | Office - Canteen - Locker & Shower For Melt Shop | Piping & Utility | TAM | 2014-05-15 15:36 | IFA | AC |  | 95%
112125 | I491TE04-0OFPN91-001-006 | ELECTRICAL PANEL DIAGRAM | 00 | 2014-05-05 | Indeterminate | Drawing | Detail | Office - Canteen - Locker & Shower For Melt Shop | Piping & Utility | TAM | 2014-05-15 15:36 | IFA | AC |  | 95%
130042 | I491TE04-0SHPA01-001-001 | Scrap Yard Panel Sld | 03 | 2016-12-27 | Indeterminate | Drawing | Detail | Scrap Yard Equipment | Electrical | TAM | 2016-12-29 11:53 | IFC | AFC | 100%
130043 | I491TE04-0SHPA01-002-001 | Scrap Yard Panel Arrangement | 03 | 2016-12-27 | Indeterminate | Drawing | Detail | Scrap Yard Equipment | Electrical | TAM | 2016-12-29 11:53 | IFC | AFC | 100%
113698 | I491TE04-0TBSW91-001-001 | Ferro Alloy-A Panels SLD 9NDP-EDP Single line Diagram) | 02 | 2015-06-02 15:44 | Indeterminate | Drawing | Detail | Melt Shop Lime And Ferroalloy Storage | Electrical | TAM | 2015-06-02 15:44 | IFC | AFC | 100%
130006 | I491TE05-0ASLT91-001-001 | ASP- Lighting System Calculation Note | 03 | 2016-12-25 16:51 | Indeterminate | Miscellaneous(MISC) | Detail | Air Separation Plant Main Building | Electrical | TAM | 2016-12-25 16:51 | IFC | AFC | 100%
130009 | I491TE05-0ASLT91-002-001 | ASP Lighting System layout 1-2 | 03 | 2016-12-25 16:51 | Indeterminate | Drawing | Detail | Air Separation Plant Main Building | Electrical | TAM | 2016-12-25 16:51 | IFC | AFC | 100%
130010 | I491TE05-0ASLT91-002-002 | ASP Lighting System layout 2-2 | 03 | 2016-12-25 16:51 | Indeterminate | Drawing | Detail | Air Separation Plant Main Building | Electrical | TAM | 2016-12-25 16:51 | IFC | AFC | 100%
130011 | I491TE05-0ASLT91-003-001 | ASP Socket system and mechanical equipment supply layout | 03 | 2016-12-25 16:51 | Indeterminate | Drawing | Detail | Air Separation Plant Main Building | Electrical | TAM | 2016-12-25 16:51 | IFC | AFC | 100%
114281 | I491TE05-0ASLT91-004-001 | ASP SUBSTATION INDOOR LIGHTING AND SMALL POWER LAYOUT (lighting Layout) | 02 | 2015-08-29 | Indeterminate | Drawing | Detail | Air Separation Plant Electrical Substation | Electrical | TAM | 2015-08-31 09:35 | IFC | AFC | 100%
114282 | I491TE05-0ASLT91-004-002 | ASP SUBSTATION INDOOR LIGHTING AND SMALL POWER LAYOUT (Socket and fan layut cable routing) | 02 | 2015-08-29 | Indeterminate | Drawing | Detail | Air Separation Plant Electrical Substation | Electrical | TAM | 2015-08-31 09:35 | IFC | AFC | 100%
114283 | I491TE05-0ASLT91-004-003 | ASP SUBSTATION INDOOR LIGHTING AND SMALL POWER LAYOUT (Cable Routing) | 02 | 2015-08-29 | Indeterminate | Drawing | Detail | Air Separation Plant Electrical Substation | Electrical | TAM | 2015-08-31 09:35 | IFC | AFC | 100%
114284 | I491TE05-0ASLT91-004-004 | ASP SUBSTATION INDOOR LIGHTING AND SMALL POWER LAYOUT (NDP-EDP single line Diagram) | 02 | 2015-08-29 | Indeterminate | Drawing | Detail | Air Separation Plant Electrical Substation | Electrical | TAM | 2015-08-31 09:35 | IFC | AFC | 100%
114285 | I491TE05-0ASLT91-004-005 | ASP SUBSTATION INDOOR LIGHTING AND SMALL POWER LAYOUT (NDP-EDHP Single line Diagram) | 02 | 2015-08-29 | Indeterminate | Drawing | Detail | Air Separation Plant Electrical Substation | Electrical | TAM | 2015-08-31 09:35 | IFC | AFC | 100%
129994 | I491TE05-0ASPH91-002-001 | ASP-CAP SUBSTATION INDOOR TELEPHONE AND NETWORK LAYOUT | 01 | 2016-12-19 | Indeterminate | Drawing | Detail | Air Separation Plant | Electrical | TAM | 2016-12-20 10:07 | IFC | AFC | 100%
130068 | I491TE05-0ASPH91-003-001 | ASP-CAP INDOOR TELEPHONE AND PC NETWORK LAYOUT 1-3 | 00 | 2017-01-02 10:36 | Indeterminate | Drawing | Detail | Air Separation Plant | Electrical | TAM | 2017-01-02 10:36 | IFA | A | 100%
130069 | I491TE05-0ASPH91-003-002 | ASP-CAP INDOOR TELEPHONE AND PC NETWORK LAYOUT 2-3 | 00 | 2017-01-02 10:36 | Indeterminate | Drawing | Detail | Air Separation Plant | Electrical | TAM | 2017-01-02 10:36 | IFA | A | 100%
130070 | I491TE05-0ASPH91-003-003 | ASP-CAP INDOOR TELEPHONE AND PC NETWORK LAYOUT 3-3 | 00 | 2017-01-02 10:36 | Indeterminate | Drawing | Detail | Air Separation Plant | Electrical | TAM | 2017-01-02 10:36 | IFA | A | 100%
114437 | I491TE05-0CALT91-001-001 | COMPRESSED AIR PLANT- LIGHTING AND SOCKET SYSTEM LAYOUT (LIGHTING LAYOUY) | 01 | 2015-10-05 | Indeterminate | Drawing | Detail | Compressed Air Production Plant | Electrical | TAM | 2015-10-10 13:44 | IFC | AFC | 100%
114438 | I491TE05-0CALT91-001-002 | COMPRESSED AIR PLANT- LIGHTING AND SOCKET SYSTEM LAYOUT (EQUIPMENT & SOCKET LAYOUT) | 01 | 2015-10-05 | Indeterminate | Drawing | Detail | Compressed Air Production Plant | Electrical | TAM | 2015-10-10 13:44 | IFC | AFC | 100%
114439 | I491TE05-0CALT91-001-003 | COMPRESSED AIR PLANT- LIGHTING AND SOCKET SYSTEM LAYOUT (CABLE TRY LAYOUT) | 01 | 2015-10-05 | Indeterminate | Drawing | Detail | Compressed Air Production Plant | Electrical | TAM | 2015-10-10 13:44 | IFC | AFC | 100%
114440 | I491TE05-0CALT91-001-004 | COMPRESSED AIR PLANT- LIGHTING AND SOCKET SYSTEM LAYOUT (SINGLE LINE DIAGRAM) | 01 | 2015-10-05 | Indeterminate | Drawing | Detail | Compressed Air Production Plant | Electrical | TAM | 2015-10-10 13:44 | IFC | AFC | 100%
130085 | I491TE05-0CCLT91-001-001 | CCM SUBSTATION INDOOR LIGHTING AND SMALL POWER LAYOUT (LIGHTING LAYOUT) 1-4 | 03 | 2017-01-07 15:21 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Electrical | TAM | 2017-01-07 15:21 | IFC | AFC | 100%
130086 | I491TE05-0CCLT91-001-002 | CCM SUBSTATION INDOOR LIGHTING AND SMALL POWER LAYOUT (SOCKET LAYOUT) 2-4 | 03 | 2017-01-07 15:21 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Electrical | TAM | 2017-01-07 15:21 | IFC | AFC | 100%
130087 | I491TE05-0CCLT91-001-003 | CCM SUBSTATION INDOOR LIGHTING AND SMALL POWER LAYOUT (NDP-EDP SINGLE LINE DIAGRAM) 3-4 | 03 | 2017-01-07 15:21 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Electrical | TAM | 2017-01-07 15:21 | IFC | AFC | 100%
130088 | I491TE05-0CCLT91-001-004 | CCM SUBSTATION INDOOR LIGHTING AND SMALL POWER LAYOUT (NDP-EDP SINGLE LINE DIAGRAM) 4-4 | 03 | 2017-01-07 15:21 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Electrical | TAM | 2017-01-07 15:21 | IFC | AFC | 100%
135002 | I491TE05-0CCLT91-003-001 | CCM FNC MAINTENANCE ROOM INDOOR LIGHTING AND SMALL POWER LAYOUT 1-3 | 02 | 2019-01-21 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Electrical | TAM | 2019-02-03 09:00 | IFC | AC |  | 95%
135003 | I491TE05-0CCLT91-003-002 | CCM FNC MAINTENANCE ROOM INDOOR LIGHTING AND SMALL POWER LAYOUT 2-3 | 02 | 2019-01-21 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Electrical | TAM | 2019-02-03 09:01 | IFC | AC |  | 95%
135004 | I491TE05-0CCLT91-003-003 | CCM FNC MAINTENANCE ROOM INDOOR LIGHTING AND SMALL POWER LAYOUT 3-3 | 00 | 2019-01-21 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Electrical | TAM | 2019-02-03 09:01 | IFC | AC |  | 95%
129592 | I491TE05-0DTLT91-001-001 | FTP Lighting System Calculation Note | 00 | 2016-09-27 09:02 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Plant Electrical Substation | Electrical | TAM | 2016-09-27 09:02 | IFA | A | 100%
130289 | I491TE05-0DTLT91-002-001 | FTP DISTRIBUTION PANEL SINGLE LINE DIAGRAM(Air Cooler& Bag Filters) 1-5 | 02 | 2017-02-04 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Electrical | TAM | 2017-02-07 10:14 | IFC | AFC | 100%
130290 | I491TE05-0DTLT91-002-002 | FTP LIGHTING SYSTEM LAYOUT (DRI Filter & Mixing Chamber & Stack) 2-5 | 02 | 2017-02-04 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Electrical | TAM | 2017-02-07 10:14 | IFC | AFC | 100%
130291 | I491TE05-0DTLT91-002-003 | FTP LIGHTING SYSTEM LAYOUT (Material Handling System) 3-5 | 02 | 2017-02-04 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Electrical | TAM | 2017-02-07 10:14 | IFC | AFC | 100%
130292 | I491TE05-0DTLT91-002-004 | FTP LIGHTING SYSTEM LAYOUT (Outdoor Conveyor-Part1) 4-5 | 02 | 2017-02-04 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Electrical | TAM | 2017-02-07 10:14 | IFC | AFC | 100%
130293 | I491TE05-0DTLT91-002-005 | FTP LIGHTING SYSTEM LAYOUT (Outdoor Conveyor-Part1) 5-5 | 02 | 2017-02-04 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Electrical | TAM | 2017-02-07 10:14 | IFC | AFC | 100%
130294 | I491TE05-0DTLT91-003-001 | FTP-Socket system and mechanical equipment supply layout | 02 | 2017-02-04 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Electrical | TAM | 2017-02-07 10:15 | IFC | AFC | 100%
114141 | I491TE05-0DTLT91-004-001 | FTP SUBSTATION INDOOR LIGHTING AND SMALL POWER LAYOUT (lighting layout) | 02 | 2015-06-27 | Indeterminate | Drawing | Detail | Fume Treatment Plant Electrical Substation | Electrical | TAM | 2015-06-29 08:52 | IFC | AFC | 100%
114142 | I491TE05-0DTLT91-004-002 | FTP-MHS SUBSTATION INDOOR LIGHTING AND SMALL PoWER LAYOUT(SOCKET AND FAN LAYOUT) | 02 | 2015-06-27 | Indeterminate | Drawing | Detail | Fume Treatment Plant Electrical Substation | Electrical | TAM | 2015-06-29 08:52 | IFC | AFC | 100%
114143 | I491TE05-0DTLT91-004-003 | FTP-MHS SUBSTATION INDOOR LIGHTING AND SMALL PoWER LAYOUT (CABLE ROUTING) | 02 | 2015-06-27 | Indeterminate | Drawing | Detail | Fume Treatment Plant Electrical Substation | Electrical | TAM | 2015-06-29 08:52 | IFC | AFC | 100%
114144 | I491TE05-0DTLT91-004-004 | FTP-MHS SUBSTATION INDOOR LIGHTING AND SMALL PoWER LAYOUT(NDP SINGLE LINE DIAGRAM) | 02 | 2015-06-27 | Indeterminate | Drawing | Detail | Fume Treatment Plant Electrical Substation | Electrical | TAM | 2015-06-29 08:52 | IFC | AFC | 100%
114145 | I491TE05-0DTLT91-004-005 | FTP-MHS SUBSTATION INDOOR LIGHTING AND SMALL PoWER LAYOUT(EDP-EDHP SINGLE LINE DIAGRAM) | 02 | 2015-06-27 | Indeterminate | Drawing | Detail | Fume Treatment Plant Electrical Substation | Electrical | TAM | 2015-06-29 08:52 | IFC | AFC | 100%
114146 | I491TE05-0DTLT91-004-006 | FTP-MHS SUBSTATION INDOOR LIGHTING AND SMALL PoWER LAYOUT (NDHP SINGLE LINE DIAGRAM) | 02 | 2015-06-27 | Indeterminate | Drawing | Detail | Fume Treatment Plant Electrical Substation | Electrical | TAM | 2015-06-29 08:52 | IFC | AFC | 100%
114188 | I491TE05-0EALT91-002-001 | MELTSHOP- Lighting System layout ( Lighting layout) | 01 | 2015-06-22 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Electrical | TAM | 2015-07-22 16:25 | IFA | AFC | 100%
133152 | I491TE05-0EALT91-002-002 | MELTSHOP- Lighting System layout(Safty Lighting Layout) | 01 | 2015-06-22 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Electrical | TAM | 2018-05-19 11:18 | IFA | AFC | 100%
114134 | I491TE05-0EALT91-003-001 | MELTSHOP-Socket system and mechanical equipment supply layout | 00 | 2015-06-22 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Electrical | TAM | 2015-06-23 09:02 | IFA | AFC | 100%
132990 | I491TE05-0EALT91-004-001 | EAF BUILDING INDOOR LIGHTING AND SMALL POWER LAYOUT (lighting layout) 1-5 | 07 | 2018-03-17 | Indeterminate | Drawing | Detail | Melt Shop Electrical Substation | Electrical | TAM | 2018-03-18 09:10 | IFC | AFC | 100%
132991 | I491TE05-0EALT91-004-002 | EAF BUILDING INDOOR LIGHTING AND SMALL POWER LAYOUT (SOKCET layout) 2-5 | 07 | 2018-03-17 | Indeterminate | Drawing | Detail | Melt Shop Electrical Substation | Electrical | TAM | 2018-03-18 09:10 | IFC | AFC | 100%
132992 | I491TE05-0EALT91-004-003 | EAF BUILDING INDOOR LIGHTING AND SMALL POWER LAYOUT (NDP-EDP singele line diagram) 3-5 | 07 | 2018-03-17 | Indeterminate | Drawing | Detail | Melt Shop Electrical Substation | Electrical | TAM | 2018-03-18 09:10 | IFC | AFC | 100%
132993 | I491TE05-0EALT91-004-004 | EAF BUILDING INDOOR LIGHTING AND SMALL POWER LAYOUT (NDP-EDP singele line diagram) 4-5 | 07 | 2018-03-17 | Indeterminate | Drawing | Detail | Melt Shop Electrical Substation | Electrical | TAM | 2018-03-18 09:10 | IFC | AFC | 100%
132989 | I491TE05-0EALT91-004-005 | EAF BUILDING INDOOR LIGHTING AND SMALL PoWER LAYOUT (EAF Platform Lighting) 5-5 | 04 | 2018-03-17 | Indeterminate | Drawing | Detail | Melt Shop Electrical Substation | Electrical | TAM | 2018-03-18 09:10 | IFC | AFC | 100%
111650 | I491TE05-0EALT91-005-001 | LF BUILDING INDOOR LIGHTING AND SMALL PoWER LAYOUT (LIGHTING LAYOUT) | 01 | 2014-03-17 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Electrical | TAM | 2014-04-24 15:15 | IFC | AFC | 100%
111651 | I491TE05-0EALT91-005-002 | LF BUILDING INDOOR LIGHTING AND SMALL PoWER LAYOUT (SOCKET LAYOUT) | 01 | 2014-03-17 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Electrical | TAM | 2014-04-24 15:15 | IFC | AFC | 100%
111652 | I491TE05-0EALT91-005-003 | LF BUILDING INDOOR LIGHTING AND SMALL PoWER LAYOUT (NDP-EDP SINGLE DIAGRAM) | 01 | 2014-03-17 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Electrical | TAM | 2014-04-24 15:15 | IFC | AFC | 100%
134180 | I491TE05-0EALT91-006-001 | Meltshop Office 1&2 and W.c Electrical Installation (Lighting Layout) | 04 | 2018-09-17 | Indeterminate | Drawing | Detail | Melt Shop | Electrical | TAM | 2018-09-22 09:54 | IFC | AFC | 100%
134181 | I491TE05-0EALT91-006-002 | Meltshop Office 1&2 and W.c Electrical Installation (Socket Layout) | 04 | 2018-09-17 | Indeterminate | Drawing | Detail | Melt Shop | Electrical | TAM | 2018-09-22 09:54 | IFC | AFC | 100%
134182 | I491TE05-0EALT91-006-003 | Meltshop Office 1&2 and W.c Electrical Installation (Sld) | 04 | 2018-09-17 | Indeterminate | Drawing | Detail | Melt Shop | Electrical | TAM | 2018-09-22 09:54 | IFC | AFC | 100%
135239 | I491TE05-0EALT91-007-001 | MELTSHOP And CCM Diesel Generator Room ( Lighting Layout) 1-3 | 01 | 2019-04-10 | Indeterminate | Drawing | Detail | Melt Shop | Electrical | TAM | 2019-04-17 12:55 | IFC | AC |  | 95%
135240 | I491TE05-0EALT91-007-002 | MELTSHOP And CCM Diesel Generator Room (Socket Layout) 2-3 | 01 | 2019-04-10 | Indeterminate | Drawing | Detail | Melt Shop | Electrical | TAM | 2019-04-17 12:55 | IFC | AC |  | 95%
135241 | I491TE05-0EALT91-007-003 | MELTSHOP And CCM Diesel Generator Room (Single Line Diagram) 3-3 | 01 | 2019-04-10 | Indeterminate | Drawing | Detail | Melt Shop | Electrical | TAM | 2019-04-17 12:55 | IFC | AC |  | 95%
135183 | I491TE05-0EALT91-009-001 | Outdoor Lavatories and Gas Reduction Station and Stairs electrical installation (Lighting & Socket Layout) 1-3 | 01 | 2019-03-18 12:32 | Indeterminate | Drawing | Detail | Melt Shop | Electrical | TAM | 2019-03-18 12:32 | IFC | AC |  | 95%
135182 | I491TE05-0EALT91-009-002 | Outdoor Lavatories and Gas Reduction Station and Stairs electrical installation (Lighting Layout Of Stairs Type1West,Type2West,Type3South,Type4North 2-3 | 01 | 2019-03-18 12:32 | Indeterminate | Drawing | Detail | Melt Shop | Electrical | TAM | 2019-03-18 12:32 | IFC | AC |  | 95%
135181 | I491TE05-0EALT91-009-003 | Outdoor Lavatories and Gas Reduction Station and Stairs electrical installation (Lavatories Sld) 3-3 | 01 | 2019-03-18 12:32 | Indeterminate | Drawing | Detail | Melt Shop | Electrical | TAM | 2019-03-18 12:32 | IFC | AC |  | 95%
129261 | I491TE05-0LALT91-001-001 | LF & CCM LABORATORY LIGHTING AND SOCKET SYSTEM LAYOUT (NDP1 & NDP2 & EDP1 & EDP2 SINGLE LINE DIAGRAM) 1-5 | 03 | 2016-08-14 | Indeterminate | Drawing | Detail | Laboratory | Electrical | TAM | 2016-08-15 14:03 | IFC | AFC | 100%
129262 | I491TE05-0LALT91-001-002 | LF & CCM LABORATORY LIGHTING AND SMALL POWER LAYOUT ( LIGHTING LAYOUT ) 2-5 | 03 | 2016-08-14 | Indeterminate | Drawing | Detail | Laboratory | Electrical | TAM | 2016-08-15 14:03 | IFC | AFC | 100%
129263 | I491TE05-0LALT91-001-003 | LF & CCM LABORATORY LIGHTING AND SMALL POWER LAYOUT ( HVAC CABING ) 3-5 | 03 | 2016-08-14 | Indeterminate | Drawing | Detail | Laboratory | Electrical | TAM | 2016-08-15 14:03 | IFC | AFC | 100%
129264 | I491TE05-0LALT91-001-004 | LF & CCM LABORATORY LIGHTING AND SMALL POWER LAYOUT ( SOCKET LAYOUT) 4-5 | 03 | 2016-08-14 | Indeterminate | Drawing | Detail | Laboratory | Electrical | TAM | 2016-08-15 14:03 | IFC | AFC | 100%
129265 | I491TE05-0LALT91-001-005 | LF & CCM LABORATORY INDOOR LIGHTING AND SMALL POWER LAYOUT (CABLE ROUTING) 5-5 | 03 | 2016-08-14 | Indeterminate | Drawing | Detail | Laboratory | Electrical | TAM | 2016-08-15 14:03 | IFC | AFC | 100%
14650 | I491TE05-0MDAA91-001-001 | Lighting And Socket System Detail For Mhs Conveyors | 00 | 2013-05-25 | Indeterminate | Drawing | Detail | Material Handling | Automation and Instrumentation | TAM |  | IFA | AC |  | 95%
14651 | I491TE05-0MELT02-122-001 | Indoor Lighting Calculation | 00 | 2012-05-09 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
14652 | I491TE05-0MELT03-166-001 | Indoor Lighting Panel Single Line Diagram | 00 | 2012-05-09 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
14653 | I491TE05-0MELT04-130-001 | Indoor Lighting,Small Power &Tl. Layout | 00 | 2012-05-09 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
14654 | I491TE05-0MELT05-120-001 | Outdoor Lighting Calculation | 00 | 2012-04-24 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
14655 | I491TE05-0MELT06-100-001 | Outdoor Lighting Layout | 00 | 2012-04-24 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
111603 | I491TE05-0MELT91-001-001 | Smp Substation Indoor Lighting And Small Power Layout (Lighting Layout) | 02 | 2014-02-25 | Indeterminate | Drawing | Detail | Steel Making Electrical Substation Building | Electrical | TAM | 2014-04-24 14:04 | IFC | AFC | 100%
111604 | I491TE05-0MELT91-001-002 | Smp Substation Indoor Lighting And Small Power Layout (Socket And Fan Layout) | 02 | 2014-02-25 | Indeterminate | Drawing | Detail | Steel Making Electrical Substation Building | Electrical | TAM | 2014-04-24 14:04 | IFC | AFC | 100%
111605 | I491TE05-0MELT91-001-003 | Smp Substation Indoor Lighting And Small Power Layout (Cable Routing) | 02 | 2014-02-25 | Indeterminate | Drawing | Detail | Steel Making Electrical Substation Building | Electrical | TAM | 2014-04-24 14:04 | IFC | AFC | 100%
111606 | I491TE05-0MELT91-001-004 | Smp Substation Indoor Lighting And Small Power Layout (Ndp-Edp Single Line Diagram) | 02 | 2014-02-25 | Indeterminate | Drawing | Detail | Steel Making Electrical Substation Building | Electrical | TAM | 2014-04-24 14:04 | IFC | AFC | 100%
111853 | I491TE05-0MELT91-001-005 | Smp Substation Indoor Lighting And Small Power Layout (Ndp-Edp Single Line Diagram) | 02 | 2014-02-25 | Indeterminate | Drawing | Detail | Steel Making Electrical Substation Building | Electrical | TAM | 2014-05-03 09:25 | IFC | AFC | 100%
114168 | I491TE05-0MKLT91-004-001 | WTP SUBSTATION INDOOR LIGHTING AND SMALL POWER LAYOUT(Lighting Layout) | 01 | 2015-07-11 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System Substation Building | Electrical | TAM | 2015-07-22 09:07 | IFC | AFC | 100%
114169 | I491TE05-0MKLT91-004-002 | WTP SUBSTATION INDOOR LIGHTING AND SMALL POWER LAYOUT(Socket and Fan Layout) | 01 | 2015-07-11 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System Substation Building | Electrical | TAM | 2015-07-22 09:07 | IFC | AFC | 100%
114170 | I491TE05-0MKLT91-004-003 | WTP SUBSTATION INDOOR LIGHTING AND SMALL POWER LAYOUT(Cable Routing) | 01 | 2015-07-11 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System Substation Building | Electrical | TAM | 2015-07-22 09:07 | IFC | AFC | 100%
133140 | I491TE05-0MKLT91-004-004 | WTP SUBSTATION INDOOR LIGHTING AND SMALL POWER LAYOUT(NDPH Single LINE Diagram) | 02 | 2018-05-15 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System Substation Building | Electrical | TAM | 2018-05-16 09:25 | IFC | AC |  | 95%
114172 | I491TE05-0MKLT91-004-005 | WTP SUBSTATION INDOOR LIGHTING AND SMALL POWER LAYOUT(NDP Single Line Diagram) | 01 | 2015-07-11 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System Substation Building | Electrical | TAM | 2015-07-22 09:07 | IFC | AFC | 100%
134352 | I491TE05-0MKLT91-007-001 | Cooling Water System - Lighting Layout (Water Emergency Tank Tower) | 03 | 2018-11-04 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Electrical | TAM | 2018-11-06 09:18 | IFC | AFC | 100%
115747 | I491TE05-0MMLT91-001-001 | WTP LIGHTING SYSTEM CALCULATION NOTE | 01 | 2016-06-14 17:05 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Electrical | TAM | 2016-06-14 17:05 | IFC | AFC | 100%
115748 | I491TE05-0MMLT91-002-001 | WTP LIGHTING SYSTEM LAYOUT (OUTDOOR LIGHTING LAYOUT) | 01 | 2016-06-14 17:05 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Electrical | TAM | 2016-06-14 17:05 | IFC | AFC | 100%
129964 | I491TE05-0MMLT91-003-001 | Pump House Lighting And Socket System Layout (Lighting System Layout) 1-4 | 01 | 2016-12-13 09:20 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Electrical | TAM | 2016-12-13 09:20 | IFC | AFC | 100%
129963 | I491TE05-0MMLT91-003-002 | Pump House Lighting And Socket System Layout (Socket Boxes Distribution Layout) 2-4 | 01 | 2016-12-13 09:20 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Electrical | TAM | 2016-12-13 09:20 | IFC | AFC | 100%
129965 | I491TE05-0MMLT91-003-003 | Pump House Lighting And Socket System Layout (Cable Trays Layout) 3-4 | 01 | 2016-12-13 09:20 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Electrical | TAM | 2016-12-13 09:20 | IFC | AFC | 100%
129966 | I491TE05-0MMLT91-003-004 | Pump House Lighting And Socket System Layout (Panel Single Line Diagram) 4-4 | 01 | 2016-12-13 09:20 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Electrical | TAM | 2016-12-13 09:20 | IFC | AFC | 100%
133142 | I491TE05-0MMLT91-004-001 | Sedimentation Lighting And Socket System Layout ( Lighting System Layout) 1-3 | 03 | 2018-05-15 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Electrical | TAM | 2018-05-16 09:28 | IFC | AFC | 100%
133143 | I491TE05-0MMLT91-004-002 | Sedimentation Lighting And Socket System Layout (Socket Box Distribution Layout) 2-3 | 03 | 2018-05-15 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Electrical | TAM | 2018-05-16 09:28 | IFC | AFC | 100%
133144 | I491TE05-0MMLT91-004-003 | Sedimentation Lighting And Socket System Layout (Panel Single Line Diagram) 3-3 | 03 | 2018-05-15 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Electrical | TAM | 2018-05-16 09:28 | IFC | AFC | 100%
14660 | I491TE05-0MNLT91-001-001 | Melt Shop Lighting System Calculation Note | 00 | 2012-12-11 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop Main Building | Electrical | TAM |  | IFA | A | 100%
14662 | I491TE05-0MXAA91-001-002 | Basic Data For Lighting System | 01 | 2012-01-15 | Indeterminate | Miscellaneous(MISC) | Basic | General | Mechanical | TAM |  | IFC | AFC | 100%
14665 | I491TE05-0MXEF92-001-003 | Ware House Lighting System Calculation Note | 02 | 2012-12-31 | Indeterminate | Miscellaneous(MISC) | Basic | Warehouse | Electrical | TAM |  | IFC | AFC | 100%
14668 | I491TE05-0MXLT01-001-003 | Ware House-A General Lighting & Luminaires Arrangement | 02 | 2013-01-16 | Indeterminate | Drawing | Detail | Warehouse | Electrical | TAM |  | IFC | AFC | 100%
14671 | I491TE05-0MXLT01-002-003 | Ware House-A Annex Power Distribution & Lighting | 02 | 2013-01-16 | Indeterminate | Drawing | Detail | Warehouse | Electrical | TAM |  | IFC | AFC | 100%
14674 | I491TE05-0MXLT01-003-003 | Ware House Socket Boxes Distribution Layout | 02 | 2013-01-16 | Indeterminate | Drawing | Detail | Warehouse | Electrical | TAM |  | IFC | AFC | 100%
129253 | I491TE05-0MXLT91-002-001 | Plant street lighting layout | 00 | 2016-08-14 | Indeterminate | Miscellaneous(MISC) | Detail | General | Electrical | TAM | 2016-08-15 10:14 | IFI | OB | 100%
14676 | I491TE05-0MYEF91-001-002 | Workshop Lighting System Calculatiion Note | 01 | 2013-05-19 | Indeterminate | Drawing | Detail | Maintenance Workshop | Electrical | TAM |  | IFC | AFC | 100%
129536 | I491TE05-0MZLT91-001-002 | Workshop General Lighting And Luminaires Arrangement | 06 | 2016-09-18 09:43 | Indeterminate | Drawing | Detail | Maintenance Workshop | Electrical | TAM | 2016-09-18 09:43 | IFC | AFC | 100%
14680 | I491TE05-0MZLT91-002-002 | Workshop Annex Power Distribution & Lighting | 01 | 2013-10-09 | Indeterminate | Drawing | Detail | Maintenance Workshop | Electrical | TAM |  | IFC | AFC | 100%
129537 | I491TE05-0MZLT91-003-002 | Workshop Sockets Boxes Distribution Layout | 06 | 2016-09-18 09:43 | Indeterminate | Drawing | Detail | Maintenance Workshop | Electrical | TAM | 2016-09-18 09:43 | IFC | AFC | 100%
129538 | I491TE05-0MZLT91-004-001 | Electrical Drawing For Workshop Building Hvac | 03 | 2016-09-18 09:44 | Indeterminate | Drawing | Detail | Maintenance Workshop | Electrical | TAM | 2016-09-18 09:44 | IFC | AFC | 100%
135284 | I491TE05-0MZLT91-007-001 | Workshop second floor lighting and socket layout (Luminaires Arrangement) 1-5 | 03 | 2019-05-04 | Indeterminate | Drawing | Detail | Maintenance Workshop | Civil and Steel Structure | TAM | 2019-05-05 09:32 | IFC | AC |  | 95%
135285 | I491TE05-0MZLT91-007-002 | Workshop second floor lighting and socket layout (Socket Arrangement) 2-5 | 03 | 2019-05-04 | Indeterminate | Drawing | Detail | Maintenance Workshop | Civil and Steel Structure | TAM | 2019-05-05 09:32 | IFC | AC |  | 95%
135286 | I491TE05-0MZLT91-007-003 | Workshop second floor lighting and socket layout (Socket Arrangement) 3-5 | 03 | 2019-05-04 | Indeterminate | Drawing | Detail | Maintenance Workshop | Civil and Steel Structure | TAM | 2019-05-05 09:32 | IFC | AC |  | 95%
135287 | I491TE05-0MZLT91-007-004 | Workshop second floor lighting and socket layout (Cable Tray) 4-5 | 03 | 2019-05-04 | Indeterminate | Drawing | Detail | Maintenance Workshop | Civil and Steel Structure | TAM | 2019-05-05 09:32 | IFC | AC |  | 95%
135288 | I491TE05-0MZLT91-007-005 | Workshop second floor lighting and socket layout (Single Line Diagram) 5-5 | 03 | 2019-05-04 | Indeterminate | Drawing | Detail | Maintenance Workshop | Civil and Steel Structure | TAM | 2019-05-05 09:32 | IFC | AC |  | 95%
112136 | I491TE05-0OFAA91-001-001 | LIST OF ELECTRICAL DRAWING, LEGEND AND GENERAL NOTE | 00 | 2014-05-05 | Indeterminate | Drawing | Detail | Office - Canteen - Locker & Shower For Melt Shop | Piping & Utility | TAM | 2014-05-15 15:37 | IFA | AC |  | 95%
112135 | I491TE05-0OFAA91-001-002 | GROUND FLOOR LIGHTING PLAN | 00 | 2014-05-05 | Indeterminate | Drawing | Detail | Office - Canteen - Locker & Shower For Melt Shop | Piping & Utility | TAM | 2014-05-15 15:37 | IFA | AC |  | 95%
112134 | I491TE05-0OFAA91-001-003 | 1ST FLOOR LIGHTING PLAN | 00 | 2014-05-05 | Indeterminate | Drawing | Detail | Office - Canteen - Locker & Shower For Melt Shop | Piping & Utility | TAM | 2014-05-15 15:37 | IFA | AC |  | 95%
112133 | I491TE05-0OFAA91-001-004 | GROUND FLOOR POWER SOCKET | 00 | 2014-05-05 | Indeterminate | Drawing | Detail | Office - Canteen - Locker & Shower For Melt Shop | Piping & Utility | TAM | 2014-05-15 15:37 | IFA | AC |  | 95%
112132 | I491TE05-0OFAA91-001-005 | 1ST FLOOR POWER SOCKET | 00 | 2014-05-05 | Indeterminate | Drawing | Detail | Office - Canteen - Locker & Shower For Melt Shop | Piping & Utility | TAM | 2014-05-15 15:37 | IFA | AC |  | 95%
112131 | I491TE05-0OFAA91-001-006 | DETAIL OF ELECTRICAL | 00 | 2014-05-05 | Indeterminate | Drawing | Detail | Office - Canteen - Locker & Shower For Melt Shop | Piping & Utility | TAM | 2014-05-15 15:37 | IFA | AC |  | 95%
112151 | I491TE05-0OFYA91-001-001 | LIST OF ELECTRICAL DRAWING, LEGEND AND GENERAL NOTE | 00 | 2014-05-05 | Indeterminate | Drawing | Detail | Office - Canteen - Locker & Shower For Melt Shop | Piping & Utility | TAM | 2014-05-15 15:45 | IFA | AC |  | 95%
112150 | I491TE05-0OFYA91-001-002 | GROUND FLOOR UPS | 00 | 2014-05-05 | Indeterminate | Drawing | Detail | Office - Canteen - Locker & Shower For Melt Shop | Piping & Utility | TAM | 2014-05-15 15:45 | IFA | AC |  | 95%
112149 | I491TE05-0OFYA91-001-003 | 1ST FLOOR UPS | 00 | 2014-05-05 | Indeterminate | Drawing | Detail | Office - Canteen - Locker & Shower For Melt Shop | Piping & Utility | TAM | 2014-05-15 15:45 | IFA | AC |  | 95%
112139 | I491TE05-0OFYE91-001-001 | LIST OF ELECTRICAL DRAWING, LEGEND AND GENERAL NOTE | 00 | 2014-05-05 | Indeterminate | Drawing | Detail | Office - Canteen - Locker & Shower For Melt Shop | Piping & Utility | TAM | 2014-05-15 15:37 | IFA | AC |  | 95%
112138 | I491TE05-0OFYE91-001-002 | GROUND FLOOR NETWORK | 00 | 2014-05-05 | Indeterminate | Drawing | Detail | Office - Canteen - Locker & Shower For Melt Shop | Piping & Utility | TAM | 2014-05-15 15:37 | IFA | AC |  | 95%
112137 | I491TE05-0OFYE91-001-003 | 1ST FLOOR NETWORK | 00 | 2014-05-05 | Indeterminate | Drawing | Detail | Office - Canteen - Locker & Shower For Melt Shop | Piping & Utility | TAM | 2014-05-15 15:37 | IFA | AC |  | 95%
129804 | I491TE05-0SHEF91-001-003 | Scrap Yard Lighting System Calculation Note | 03 | 2016-11-13 | Indeterminate | Miscellaneous(MISC) | Detail | Scrap Yard Equipment | Electrical | TAM | 2016-11-22 09:39 | IFC | AFC | 100%
130044 | I491TE05-0SHLT01-001-001 | Scrap Yard General Lighting & Luminaires Arrangement | 03 | 2016-12-27 | Indeterminate | Drawing | Detail | Scrap Yard Equipment | Electrical | TAM | 2016-12-29 11:54 | IFC | AFC | 100%
130045 | I491TE05-0SHLT01-002-001 | Scrap Yard Socket Boxes Distribution Layout | 03 | 2016-12-27 | Indeterminate | Drawing | Detail | Scrap Yard Equipment | Electrical | TAM | 2016-12-29 11:54 | IFC | AFC | 100%
113695 | I491TE05-0TBLT91-002-001 | FERRO ALLOY-A General LIGHTING AND Luminaires Arrangement And Panel Arrangement | 02 | 2015-06-02 15:43 | Indeterminate | Drawing | Detail | Melt Shop Lime And Ferroalloy Storage | Electrical | TAM | 2015-06-02 15:43 | IFC | AFC | 100%
113696 | I491TE05-0TBLT91-003-001 | Ferro Alloy Socket Boxes Distribution Layout | 02 | 2015-06-02 15:44 | Indeterminate | Drawing | Detail | Melt Shop Lime And Ferroalloy Storage | Electrical | TAM | 2015-06-02 15:44 | IFC | AFC | 100%
14688 | I491TE06-0ASAA91-002-001 | Load List For Air Separation Plant | 00 | 2013-04-17 | Indeterminate | Miscellaneous(MISC) | Detail | Air Separation Plant | Automation and Instrumentation | Fortune |  | IFA | AC |  | 95%
129857 | I491TE06-0AUAA91-016-001 | Level2 Power Consumption list | 00 | 2016-12-03 14:41 | Indeterminate | Miscellaneous(MISC) | Detail | Automation and Control System | Automation and Instrumentation | ASM | 2016-12-03 14:41 | IFI | OB | 100%
114184 | I491TE06-0CCAA91-001-001 | motor & Component List | 00 | 2015-07-12 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Electrical | DANIELI | 2015-07-22 10:13 | IFA | A | 100%
130001 | I491TE06-0CHAA91-001-001 | Heavy Duty Cranes Power Consumption List | 00 | 2016-12-20 10:23 | Indeterminate | Miscellaneous(MISC) | Detail | Crane and Hiosts | Automation and Instrumentation | Voith | 2016-12-20 10:23 | IFA | AC |  | 95%
14691 | I491TE06-0CPAA91-001-003 | Load List For Air Plant | 02 | 2013-09-17 | Indeterminate | Miscellaneous(MISC) | Detail | Compressed Air Production Plant | Piping & Utility | HAVAYAR |  | IFC | AFC | 100%
113311 | I491TE06-0DTAA91-001-001 | ELECTRICAL SYSTEM FOR FUME TREATMENT PLANT LOAD LIST | 00 | 2015-01-27 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Equipment | Automation and Instrumentation | HASCON | 2015-01-31 10:35 | IFI | AC |  | 95%
14692 | I491TE06-0EAAA01-001-001 | Motor List Eaf | 00 | 2012-04-18 | Indeterminate | Miscellaneous(MISC) | Basic | Electric Arc Furnace | Automation and Instrumentation | FUCHS |  | IFI | OB | 100%
129999 | I491TE06-0EAAA91-002-001 | EAF Power consumption List | 00 | 2016-12-20 10:19 | Indeterminate | Miscellaneous(MISC) | Detail | Electric Arc Furnace | Automation and Instrumentation | FUCHS | 2016-12-20 10:19 | IFA | AC |  | 95%
14693 | I491TE06-0LFAA01-001-001 | Motor List Lf | 00 | 2012-04-18 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Automation and Instrumentation | FUCHS |  | IFI | OB | 100%
130000 | I491TE06-0LFAA91-002-001 | LF Power consumption List | 00 | 2016-12-20 10:22 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Automation and Instrumentation | FUCHS | 2016-12-20 10:22 | IFA | AC |  | 95%
14695 | I491TE06-0MDAA91-001-003 | Electrical Load List Material Handling (Conveyor) System | 02 | 2013-08-07 | Indeterminate | Miscellaneous(MISC) | Detail | Material Handling | Electrical | DATIS |  | IFC | AFC | 100%
14700 | I491TE06-0MMCT01-001-006 | Load List For Cooling System (Ct1) | 02 | 2013-10-08 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Electrical | FARABARD |  | IFC | AFC | 100%
14702 | I491TE06-0MMCT02-001-001 | Load List For Cooling System (Ct2) | 01 | 2013-02-19 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Piping & Utility | FARABARD |  | IFA | AC |  | 95%
130012 | I491TE07-0ASEL91-001-001 | ASP CABLE ROUTING LAYOUT | 03 | 2016-12-25 16:52 | Indeterminate | Drawing | Detail | Air Separation Plant Main Building | Electrical | TAM | 2016-12-25 16:52 | IFC | AFC | 100%
116064 | I491TE07-0CCAA91-001-001 | CABLE LIST (GP08VB-HC11-E9900-EL100_REV01_E) | 01 | 2016-07-04 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Automation and Instrumentation | TAM | 2016-07-13 09:09 | IFC | AC |  | 95%
114373 | I491TE07-0CCAA91-010-001 | Internal Cable Way Layout (GP08VB-HC11-E9900-ED201-00-E-1746939 | 00 | 2015-09-15 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Automation and Instrumentation | TAM | 2015-09-16 09:29 | IFA | AC |  | 95%
114374 | I491TE07-0CCAA91-011-001 | Internal Cable Way Layout (GP08VB-HC11-E9900-ED202-00-E-1746938 | 00 | 2015-09-15 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Automation and Instrumentation | TAM | 2015-09-16 09:29 | IFA | AC |  | 95%
114375 | I491TE07-0CCAA91-012-001 | Internal Cable Way Layout (GP08VB-HC11-E9900-ED203-00-E-1746941 | 00 | 2015-09-15 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Automation and Instrumentation | TAM | 2015-09-16 09:29 | IFA | AC |  | 95%
114376 | I491TE07-0CCAA91-013-001 | Internal Cable Way Layout (GP08VB-HC11-E9900-ED204-00-E-1746940 | 00 | 2015-09-15 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Automation and Instrumentation | TAM | 2015-09-16 09:29 | IFA | AC |  | 95%
114377 | I491TE07-0CCAA91-014-001 | Internal Cable Way Layout (GP08VB-HC11-E9900-ED205-00-E-1746942 | 00 | 2015-09-15 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Automation and Instrumentation | TAM | 2015-09-16 09:29 | IFA | AC |  | 95%
114378 | I491TE07-0CCAA91-015-001 | Internal Cable Way Layout (GP08VB-HC11-E9900-ED206-00-E-1746943 | 00 | 2015-09-15 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Automation and Instrumentation | TAM | 2015-09-16 09:29 | IFA | AC |  | 95%
114379 | I491TE07-0CCAA91-016-001 | Internal Cable Way Layout (GP08VB-HC11-E9900-ED207-00-E-1746944 | 00 | 2015-09-15 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Automation and Instrumentation | TAM | 2015-09-16 09:30 | IFA | AC |  | 95%
114380 | I491TE07-0CCAA91-017-001 | Internal Cable Way Layout (GP08VB-HC11-E9900-ED208-00-E-1746945 | 00 | 2015-09-15 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Automation and Instrumentation | TAM | 2015-09-16 09:30 | IFA | AC |  | 95%
114381 | I491TE07-0CCAA91-018-001 | Internal Cable Way Layout (GP08VB-HC11-E9900-ED209-00-E-1746946 | 00 | 2015-09-15 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Automation and Instrumentation | TAM | 2015-09-16 09:30 | IFA | AC |  | 95%
114382 | I491TE07-0CCMN01-001-001 | Internal Cable Way Layout (GP08VB-HC11-E9900-ED101-00-E-1768575 | 00 | 2015-09-15 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Automation and Instrumentation | TAM | 2015-09-16 09:30 | IFA | AC |  | 95%
114383 | I491TE07-0CCMN02-001-001 | Internal Cable Way Layout (GP08VB-HC11-E9900-ED102-00-E-1768576 | 00 | 2015-09-15 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Automation and Instrumentation | TAM | 2015-09-16 09:30 | IFA | AC |  | 95%
114384 | I491TE07-0CCMN03-001-001 | Internal Cable Way Layout (GP08VB-HC11-E9900-ED103-00-E-1768577 | 00 | 2015-09-15 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Automation and Instrumentation | TAM | 2015-09-16 09:30 | IFA | AC |  | 95%
114385 | I491TE07-0CCMN04-001-001 | Internal Cable Way Layout (GP08VB-HC11-E9900-ED151-00-E-1746937 | 00 | 2015-09-15 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Automation and Instrumentation | TAM | 2015-09-16 09:30 | IFA | AC |  | 95%
112639 | I491TE07-0CPAA91-001-001 | Cable Listfor Compressed Air Plant | 02 | 2014-07-27 | Indeterminate | Miscellaneous(MISC) | Detail | Compressed Air Production Plant | Electrical | HAVAYAR | 2014-07-28 12:05 | IFC | AFC | 100%
130724 | I491TE07-0DTEL91-001-001 | FTP CABLE ROUTING LAYOUT | 02 | 2017-06-25 09:20 | Indeterminate | Drawing | Detail | Fume Treatment Plant Electrical Substation | Electrical | TAM | 2017-06-25 09:20 | IFC | AFC | 100%
131134 | I491TE07-0DTLN91-001-001 | FUME TREATMENT GROUNDING SYSTEM LAYOUT | 03 | 2017-08-29 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Electrical | TAM | 2017-09-06 15:25 | IFC | AFC | 100%
129720 | I491TE07-0EAEL91-001-001 | Meltshop Cable Routing Layout | 02 | 2016-10-17 | Indeterminate | Drawing | Detail | Melt Shop Electrical Substation | Electrical | TAM | 2016-10-19 13:13 | IFC | AFC | 100%
129995 | I491TE07-0EAEL91-002-001 | Meltshop Power Cable Schedule | 03 | 2016-12-19 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop Electrical Substation | Electrical | TAM | 2016-12-20 10:11 | IFC | AFC | 100%
14705 | I491TE07-0EAFM01-001-001 | Upper Shell Electro | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
14706 | I491TE07-0EAFM02-001-001 | Electro Cable Channel | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
14707 | I491TE07-0EAFM03-002-001 | Electro Cable Channel | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
14708 | I491TE07-0EAFM04-003-001 | Electro Cable Box | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
14709 | I491TE07-0EALN99-001-001 | Furnaces Grounding System | 00 | 2012-11-18 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop Main Building | Automation and Instrumentation | TAM |  | IFA | AC |  | 95%
134868 | I491TE07-0LAXL01-001-001 | EAF Laboratory Penumatic Shooting System Conduits Layout Cabling1-1 1-6 | 00 | 2018-12-24 | Indeterminate | Drawing | Detail | Laboratory | Automation and Instrumentation | TAM | 2018-12-31 10:15 | IFI | OB | 100%
134867 | I491TE07-0LAXL01-001-002 | EAF Laboratory Penumatic Shooting System Conduits Layout Cabling1-1 2-6 | 00 | 2018-12-24 | Indeterminate | Drawing | Detail | Laboratory | Automation and Instrumentation | TAM | 2018-12-31 10:15 | IFI | OB | 100%
134866 | I491TE07-0LAXL01-001-003 | EAF Laboratory Penumatic Shooting System Conduits Layout Cabling1-1 3-6 | 00 | 2018-12-24 | Indeterminate | Drawing | Detail | Laboratory | Automation and Instrumentation | TAM | 2018-12-31 10:15 | IFI | OB | 100%
134865 | I491TE07-0LAXL01-001-004 | EAF Laboratory Penumatic Shooting System Conduits Layout Cabling1-1 4-6 | 00 | 2018-12-24 | Indeterminate | Drawing | Detail | Laboratory | Automation and Instrumentation | TAM | 2018-12-31 10:15 | IFI | OB | 100%
134864 | I491TE07-0LAXL01-001-005 | EAF Laboratory Penumatic Shooting System Conduits Layout Cabling1-1 5-6 | 00 | 2018-12-24 | Indeterminate | Drawing | Detail | Laboratory | Automation and Instrumentation | TAM | 2018-12-31 10:15 | IFI | OB | 100%
134863 | I491TE07-0LAXL01-001-006 | EAF Laboratory Penumatic Shooting System Conduits Layout Cabling1-1 6-6 | 00 | 2018-12-24 | Indeterminate | Drawing | Detail | Laboratory | Automation and Instrumentation | TAM | 2018-12-31 10:15 | IFI | OB | 100%
134872 | I491TE07-0LAXL01-002-001 | LF Laboratory Penumatic Shooting System Conduits Layout Cabling2-1 1-4 | 00 | 2018-12-24 | Indeterminate | Drawing | Detail | Laboratory | Automation and Instrumentation | TAM | 2018-12-31 10:15 | IFI | OB | 100%
134871 | I491TE07-0LAXL01-002-002 | LF Laboratory Penumatic Shooting System Conduits Layout Cabling2-1 2-4 | 00 | 2018-12-24 | Indeterminate | Drawing | Detail | Laboratory | Automation and Instrumentation | TAM | 2018-12-31 10:15 | IFI | OB | 100%
134870 | I491TE07-0LAXL01-002-003 | LF Laboratory Penumatic Shooting System Conduits Layout Cabling2-1 3-4 | 00 | 2018-12-24 | Indeterminate | Drawing | Detail | Laboratory | Automation and Instrumentation | TAM | 2018-12-31 10:15 | IFI | OB | 100%
134869 | I491TE07-0LAXL01-002-004 | LF Laboratory Penumatic Shooting System Conduits Layout Cabling2-1 4-4 | 00 | 2018-12-24 | Indeterminate | Drawing | Detail | Laboratory | Automation and Instrumentation | TAM | 2018-12-31 10:15 | IFI | OB | 100%
134874 | I491TE07-0LAXL01-003-001 | CCM Laboratory Penumatic Shooting System Conduits Layout Cabling3-1 | 00 | 2018-12-24 | Indeterminate | Drawing | Detail | Laboratory | Automation and Instrumentation | TAM | 2018-12-31 10:23 | IFI | OB | 100%
112607 | I491TE07-0MDAA91-001-001 | I&C TYPICAL EARTH DRAWINGS 1-14 | 00 | 2014-07-13 | Indeterminate | Drawing | Detail | Material Handling | Automation and Instrumentation | DATIS | 2014-07-16 09:18 | IFA | AC |  | 95%
112948 | I491TE07-0MDAA91-001-002 | I&C TYPICAL EARTH DRAWINGS REVISION LIST 2-14 | 00 | 2014-07-13 | Indeterminate | Drawing | Detail | Material Handling | Automation and Instrumentation | TAM | 2014-09-25 16:08 | IFA | AC |  | 95%
112949 | I491TE07-0MDAA91-001-003 | I&C TYPICAL EARTH DRAWINGS TABLE OF CONTENTS 3-14 | 00 | 2014-07-13 | Indeterminate | Drawing | Detail | Material Handling | Automation and Instrumentation | TAM | 2014-09-25 16:08 | IFA | AC |  | 95%
112950 | I491TE07-0MDAA91-001-004 | I&C TYPICAL EARTH DRAWINGS BULK SUMMARY 4-14 | 00 | 2014-07-13 | Indeterminate | Drawing | Detail | Material Handling | Automation and Instrumentation | TAM | 2014-09-25 16:08 | IFA | AC |  | 95%
112951 | I491TE07-0MDAA91-001-005 | I&C TYPICAL EARTH DRAWINGS FIELD INSTRUMENT EARTHING DETAIL (DIRECT INSTALLED) 5-14 | 00 | 2014-07-13 | Indeterminate | Drawing | Detail | Material Handling | Automation and Instrumentation | TAM | 2014-09-25 16:08 | IFA | AC |  | 95%
112952 | I491TE07-0MDAA91-001-006 | I&C TYPICAL EARTH DRAWINGS FIELD INSTRUMENT EARTHING DETAIL 6-14 | 00 | 2014-07-13 | Indeterminate | Drawing | Detail | Material Handling | Automation and Instrumentation | TAM | 2014-09-25 16:08 | IFA | AC |  | 95%
112953 | I491TE07-0MDAA91-001-007 | I&C TYPICAL EARTH DRAWINGS FIELD INSTRUMENT/JUNCTION BOX EARTHING DETAIL 7-14 | 00 | 2014-07-13 | Indeterminate | Drawing | Detail | Material Handling | Automation and Instrumentation | TAM | 2014-09-25 16:08 | IFA | AC |  | 95%
112955 | I491TE07-0MDAA91-001-008 | I&C TYPICAL EARTH DRAWINGS ANALOG JUNCTION BOX EARTHING GUIDE 8-14 | 00 | 2014-07-13 | Indeterminate | Drawing | Detail | Material Handling | Automation and Instrumentation | TAM | 2014-09-25 16:08 | IFA | AC |  | 95%
112954 | I491TE07-0MDAA91-001-009 | I&C TYPICAL EARTH DRAWINGS DIGITAL JUNCTION BOX EARTHING GUIDE 9-14 | 00 | 2014-07-13 | Indeterminate | Drawing | Detail | Material Handling | Automation and Instrumentation | TAM | 2014-09-25 16:08 | IFA | AC |  | 95%
112958 | I491TE07-0MDAA91-001-010 | I&C TYPICAL EARTH DRAWINGS JUNCTION BOX SUPPORT EARTHING GUIDE10-14 | 00 | 2014-07-13 | Indeterminate | Drawing | Detail | Material Handling | Automation and Instrumentation | TAM | 2014-09-25 16:08 | IFA | AC |  | 95%
112957 | I491TE07-0MDAA91-001-011 | I&C TYPICAL EARTH DRAWINGS CABLE TRAYS EARTHING DETAIL 11-14 | 00 | 2014-07-13 | Indeterminate | Drawing | Detail | Material Handling | Automation and Instrumentation | TAM | 2014-09-25 16:08 | IFA | AC |  | 95%
112956 | I491TE07-0MDAA91-001-012 | I&C TYPICAL EARTH DRAWINGS MARSHALLING CABINET/SYSTEM CABINET/PANEL EARTHING GUIDE 12-14 | 00 | 2014-07-13 | Indeterminate | Drawing | Detail | Material Handling | Automation and Instrumentation | TAM | 2014-09-25 16:08 | IFA | AC |  | 95%
112960 | I491TE07-0MDAA91-001-013 | I&C TYPICAL EARTH DRAWINGS INSTRUMENT EQUIPOTENTIAL NETWORK IN CONTROL ROOM13-14 | 00 | 2014-07-13 | Indeterminate | Drawing | Detail | Material Handling | Automation and Instrumentation | TAM | 2014-09-25 16:08 | IFA | AC |  | 95%
112959 | I491TE07-0MDAA91-001-014 | I&C TYPICAL EARTH DRAWINGS LOCAL CABINET /PANEL EARTHING DETAIL 14-14 | 00 | 2014-07-13 | Indeterminate | Drawing | Detail | Material Handling | Automation and Instrumentation | TAM | 2014-09-25 16:08 | IFA | AC |  | 95%
111569 | I491TE07-0MDAA91-010-002 | Cable List For Material Handling (Conveyor) System | 03 | 2014-02-09 | Indeterminate | Miscellaneous(MISC) | Detail | Material Handling | Electrical | DATIS | 2014-04-23 17:15 | IFC | AFC | 100%
114941 | I491TE07-0MDCV91-010-001 | MATERIAL HANDLING SYSTEM CABLE ROUTE LAYOUT AND SECTION OUTDOOR CONVEYORS 1-9 | 01 | 2016-02-28 09:16 | Indeterminate | Drawing | Detail | Material Handling | Electrical | DATIS | 2016-02-28 09:16 | IFC | AFC | 100%
114943 | I491TE07-0MDCV91-010-002 | MATERIAL HANDLING SYSTEM CABLE ROUTE LAYOUT AND SECTION OUTDOOR CONVEYORS 2-9 | 01 | 2016-02-28 09:16 | Indeterminate | Drawing | Detail | Material Handling | Electrical | DATIS | 2016-02-28 09:16 | IFC | AFC | 100%
114942 | I491TE07-0MDCV91-010-003 | MATERIAL HANDLING SYSTEM CABLE ROUTE LAYOUT AND SECTION OUTDOOR CONVEYORS 3-9 | 01 | 2016-02-28 09:16 | Indeterminate | Drawing | Detail | Material Handling | Electrical | DATIS | 2016-02-28 09:16 | IFC | AFC | 100%
114944 | I491TE07-0MDCV91-010-004 | MATERIAL HANDLING SYSTEM CABLE ROUTE LAYOUT AND SECTION OUTDOOR CONVEYORS 4-9 | 01 | 2016-02-28 09:16 | Indeterminate | Drawing | Detail | Material Handling | Electrical | DATIS | 2016-02-28 09:16 | IFC | AFC | 100%
114945 | I491TE07-0MDCV91-010-005 | MATERIAL HANDLING SYSTEM CABLE ROUTE LAYOUT AND SECTION OUTDOOR CONVEYORS 5-9 | 01 | 2016-02-28 09:16 | Indeterminate | Drawing | Detail | Material Handling | Electrical | DATIS | 2016-02-28 09:16 | IFC | AFC | 100%
114946 | I491TE07-0MDCV91-010-006 | MATERIAL HANDLING SYSTEM CABLE ROUTE LAYOUT AND SECTION OUTDOOR CONVEYORS 6-9 | 01 | 2016-02-28 09:16 | Indeterminate | Drawing | Detail | Material Handling | Electrical | DATIS | 2016-02-28 09:16 | IFC | AFC | 100%
114947 | I491TE07-0MDCV91-010-007 | MATERIAL HANDLING SYSTEM CABLE ROUTE LAYOUT AND SECTION OUTDOOR CONVEYORS 7-9 | 01 | 2016-02-28 09:16 | Indeterminate | Drawing | Detail | Material Handling | Electrical | DATIS | 2016-02-28 09:16 | IFC | AFC | 100%
114948 | I491TE07-0MDCV91-010-008 | MATERIAL HANDLING SYSTEM CABLE ROUTE LAYOUT AND SECTION OUTDOOR CONVEYORS 8-9 | 01 | 2016-02-28 09:16 | Indeterminate | Drawing | Detail | Material Handling | Electrical | DATIS | 2016-02-28 09:16 | IFC | AFC | 100%
114949 | I491TE07-0MDCV91-010-009 | MATERIAL HANDLING SYSTEM CABLE ROUTE LAYOUT AND SECTION OUTDOOR CONVEYORS 9-9 | 01 | 2016-02-28 09:16 | Indeterminate | Drawing | Detail | Material Handling | Electrical | DATIS | 2016-02-28 09:16 | IFC | AFC | 100%
112559 | I491TE07-0MDCV91-015-001 | Material Handling System CABLE ROUTE LAYOUT AND SECTION INDOOR CONVEYORS 1-9 | 01 | 2014-07-08 | Indeterminate | Drawing | Detail | Material Handling | Electrical | DATIS | 2014-07-12 17:08 | IFC | AFC | 100%
112560 | I491TE07-0MDCV91-015-002 | Material Handling System CABLE ROUTE LAYOUT AND SECTION INDOOR CONVEYORS 2-9 | 01 | 2014-07-08 | Indeterminate | Drawing | Detail | Material Handling | Electrical | DATIS | 2014-07-12 17:08 | IFC | AFC | 100%
112561 | I491TE07-0MDCV91-015-003 | Material Handling System CABLE ROUTE LAYOUT AND SECTION INDOOR CONVEYORS 3-9 | 01 | 2014-07-08 | Indeterminate | Drawing | Detail | Material Handling | Electrical | DATIS | 2014-07-12 17:08 | IFC | AFC | 100%
112562 | I491TE07-0MDCV91-015-004 | Material Handling System CABLE ROUTE LAYOUT AND SECTION INDOOR CONVEYORS 4-9 | 01 | 2014-07-08 | Indeterminate | Drawing | Detail | Material Handling | Electrical | DATIS | 2014-07-12 17:08 | IFC | AFC | 100%
112563 | I491TE07-0MDCV91-015-005 | Material Handling System CABLE ROUTE LAYOUT AND SECTION INDOOR CONVEYORS 5-9 | 01 | 2014-07-08 | Indeterminate | Drawing | Detail | Material Handling | Electrical | DATIS | 2014-07-12 17:08 | IFC | AFC | 100%
112564 | I491TE07-0MDCV91-015-006 | Material Handling System CABLE ROUTE LAYOUT AND SECTION INDOOR CONVEYORS 6-9 | 01 | 2014-07-08 | Indeterminate | Drawing | Detail | Material Handling | Electrical | DATIS | 2014-07-12 17:08 | IFC | AFC | 100%
112565 | I491TE07-0MDCV91-015-007 | Material Handling System CABLE ROUTE LAYOUT AND SECTION INDOOR CONVEYORS 7-9 | 01 | 2014-07-08 | Indeterminate | Drawing | Detail | Material Handling | Electrical | DATIS | 2014-07-12 17:08 | IFC | AFC | 100%
112566 | I491TE07-0MDCV91-015-008 | Material Handling System CABLE ROUTE LAYOUT AND SECTION INDOOR CONVEYORS 8-9 | 01 | 2014-07-08 | Indeterminate | Drawing | Detail | Material Handling | Electrical | DATIS | 2014-07-12 17:08 | IFC | AFC | 100%
112567 | I491TE07-0MDCV91-015-009 | Material Handling System CABLE ROUTE LAYOUT AND SECTION INDOOR CONVEYORS 9-9 | 01 | 2014-07-08 | Indeterminate | Drawing | Detail | Material Handling | Electrical | DATIS | 2014-07-12 17:08 | IFC | AFC | 100%
14713 | I491TE07-0MECH92-001-002 | Technical Specification And Data Sheet For Cable System | 01 | 2012-01-17 | Indeterminate | Miscellaneous(MISC) | Basic | Main Electrical Substation And Distribution Network | Electrical | TAM |  | IFC | AFC | 100%
14715 | I491TE07-0MEEF91-001-002 | Cable Tunnel Lighting System Calculation Note | 01 | 2012-06-30 | Indeterminate | Miscellaneous(MISC) | Detail | General | Electrical | TAM |  | IFC | AFC | 100%
14718 | I491TE07-0MEEF91-002-003 | Cable Tunnel Lighting System Layout | 02 | 2012-11-06 | Indeterminate | Drawing | Detail | Main Electrical Substation And Distribution Network | Electrical | TAM |  | IFC | AFC | 100%
14720 | I491TE07-0MEEF91-003-003 | Cable Tunnel Socket System Layout & Mechanical Equipment Supply Layout 1-2 | 01 | 2012-11-18 | Indeterminate | Drawing | Detail | Main Electrical Substation And Distribution Network | Electrical | TAM |  | IFI | OB | 100%
14721 | I491TE07-0MEEF91-003-004 | Cable Tunnel Socket System Layout & Mechanical Equipment Supply Layout 2-2 | 01 | 2012-11-18 | Indeterminate | Drawing | Detail | Main Electrical Substation And Distribution Network | Electrical | TAM |  | IFI | OB | 100%
14726 | I491TE07-0MEEF91-004-005 | Cable Tunnel Electrical Panel Single Line Diagram | 02 | 2012-12-11 | Indeterminate | Drawing | Detail | Main Electrical Substation And Distribution Network | Electrical | TAM |  | IFI | OB | 100%
14727 | I491TE07-0MEEF91-004-006 | Cable Tunnel Electrical Panel Single Line Diagram | 02 | 2012-12-11 | Indeterminate | Drawing | Detail | Main Electrical Substation And Distribution Network | Electrical | TAM |  | IFI | OB | 100%
14794 | I491TE07-0MEEH01-139-002 | 400/33 Kv Substation Mv Cable Calculation | 01 | 2012-05-29 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFC | AFC | 100%
14729 | I491TE07-0MEEH02-101-002 | Mv Cable List | 01 | 2012-05-30 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFC | AFC | 100%
14730 | I491TE07-0MEEL01-115-001 | Ac &Dc Dist. Cables Voltage Drop Calculation | 00 | 2012-06-13 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
14731 | I491TE07-0MEEL02-114-001 | 400/33 Kv Substation Ct Calculation | 00 | 2012-01-01 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
14733 | I491TE07-0MEEL03-116-002 | 400/33 Kv Substation Cvt Cables Calculation | 01 | 2012-07-29 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
14734 | I491TE07-0MEEL04-211-001 | General Instruction For Cabling &Termination | 00 | 2012-05-02 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFA | A | 100%
14735 | I491TE07-0MEEL05-201-001 | 400/33 Kv Substation Cable List | 00 | 2013-09-17 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | AFC | 100%
14736 | I491TE07-0MEEL06-201-001 | 400/33 Kv Substation Termination List | 00 | 2013-09-17 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | AFC | 100%
14796 | I491TE07-0MEEL07-117-002 | 400/33 Kv Substation Trip And Close Supply Cable Caculation | 01 | 2012-05-29 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFC | AFC | 100%
14737 | I491TE07-0MEI001-112-001 | Cable Supports Installation Guide In Gallery | 00 | 2012-05-08 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | AFC | 100%
14740 | I491TE07-0MEI002-304-004 | 400/33 Kv Substation General Document For Cable Support And Conduit Installation | 03 | 2012-05-29 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFC | OB | 100%
14741 | I491TE07-0MEI003-100-001 | Yard Area Cable Supports Installation Guide | 00 | 2012-04-29 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
114856 | I491TE07-0MEIR91-001-001 | SVC System Cables and Wires List | 00 | 2016-02-02 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | NR Electric | 2016-02-03 11:42 | IFI | OB | 100%
114871 | I491TE07-0MEIR91-002-001 | SVC System Earthing System Layout | 00 | 2016-02-02 | Indeterminate | Miscellaneous(MISC) | Basic | Main Electrical Substation And Distribution Network | Electrical | NR Electric | 2016-02-03 11:51 | IFA | AFC | 100%
114857 | I491TE07-0MEIR91-003-001 | SVC System Earthing System Layout Detail | 00 | 2016-02-02 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | NR Electric | 2016-02-03 11:43 | IFI | OB | 100%
114858 | I491TE07-0MEIR91-004-001 | SVC System Cables and Wires Technichal Specification and Data sheet | 00 | 2016-02-02 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | NR Electric | 2016-02-03 11:43 | IFI | OB | 100%
14798 | I491TE07-0MELN01-001-001 | 400/33 Kv Substation Lightning Protection Calculation | 00 | 2011-12-07 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
14744 | I491TE07-0MELN92-002-002 | Technical Specification And Data Sheet For Grounding System | 01 | 2012-01-17 | Indeterminate | Miscellaneous(MISC) | Basic | Main Electrical Substation And Distribution Network | Electrical | TAM |  | IFC | AFC | 100%
14746 | I491TE07-0MELT92-001-002 | Technical Specification And Data Sheet For Lighting And Small Power System | 01 | 2012-01-17 | Indeterminate | Miscellaneous(MISC) | Basic | Main Electrical Substation And Distribution Network | Electrical | TAM |  | IFC | AFC | 100%
14747 | I491TE07-0MEPN01-201-001 | 400/33 Kv Substation Indoor Panel Arrangement | 00 | 2012-03-18 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
14749 | I491TE07-0MEPN02-251-002 | Outdoor Panel Arrangement | 01 | 2012-05-30 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFC | AFC | 100%
133356 | I491TE07-0MMCT01-001-001 | Cooling Tower & Pump House-Earthing Calculation | 04 | 2018-06-24 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Electrical | TAM | 2018-06-26 12:41 | IFC | AFC | 100%
14751 | I491TE07-0MMCT01-002-002 | WTP Cable List | 01 | 2013-12-29 07:21 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Electrical | FARABARD |  | IFC | AFC | 100%
14753 | I491TE07-0MMCT01-005-002 | WTP CABLE SIZING CALCULATION | 01 | 2013-12-29 07:21 | Indeterminate | Miscellaneous(MISC) | Basic | Water Treatment & Cooling System | Electrical | FARABARD |  | IFC | AFC | 100%
14754 | I491TE07-0MMCT01-007-001 | Layout Of Cable Trays/Ladders & Trenches ... (Ct01 & Ct02) | 00 | 2013-07-24 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Automation and Instrumentation | FARABARD |  | IFA | AC |  | 95%
14756 | I491TE07-0MMCT02-001-001 | Earthing Calculation Ct02 | 00 | 2013-01-02 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Automation and Instrumentation | TAM |  | IFA | AC |  | 95%
129998 | I491TE07-0MMCT02-003-001 | LIGHTING LAYOUT-CT2 (WTP STAIRS AND ROOF) 1-3 | 03 | 2016-12-20 10:13 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Electrical | TAM | 2016-12-20 10:13 | IFC | AFC | 100%
129997 | I491TE07-0MMCT02-003-002 | LIGHTING LAYOUT-CT2 (WTP STAIRS AND ROOF) 2-3 | 03 | 2016-12-20 10:13 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Electrical | TAM | 2016-12-20 10:13 | IFC | AFC | 100%
129996 | I491TE07-0MMCT02-003-003 | LIGHTING LAYOUT-CT2 (WTP STAIRS AND ROOF) (WTP SUBSTATION NDP SINGLE LINE DIAGRAM) 3-3 | 01 | 2016-12-20 10:13 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Electrical | TAM | 2016-12-20 10:13 | IFC | AFC | 100%
11760 | I491TE07-0MMCT91-002-001 | Cable List For Cooling System (Ct1) | 01 | 2013-07-14 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Automation and Instrumentation | TAM |  | IFA | AC |  | 95%
132658 | I491TE07-0MMED01-001-001 | CABLE RAIL FOR SEDIMENTATION SCRAPER | 00 | 2018-01-07 09:36 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Mechanical | TAM | 2018-01-07 09:36 | IFI | OB | 100%
130326 | I491TE07-0MMEL91-001-003 | WCP Power Cable Schedule | 02 | 2017-02-18 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Electrical | TAM | 2017-02-22 13:04 | IFC | AFC | 100%
14758 | I491TE07-0MNEE91-001-002 | Warehouse Grounding System Calculation Note | 01 | 2012-03-18 | Indeterminate | Miscellaneous(MISC) | Basic | Warehouse | Electrical | TAM |  | IFC | AFC | 100%
14762 | I491TE07-0MNEE91-003-001 | Workshop Grounding System Calculation Note | 00 | 2012-04-07 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop Maintenance Workshop | Electrical | TAM |  | IFA | AFC | 100%
14766 | I491TE07-0MNEE91-005-001 | Scrap Yard Grounding System Calculation Note | 00 | 2012-04-10 | Indeterminate | Miscellaneous(MISC) | Basic | Melt Shop Scrap Yard | Electrical | TAM |  | IFA | AFC | 100%
16598 | I491TE07-0MNEE91-006-002 | Scrap Yard Grounding System Layout | 02 | 2013-12-09 | Indeterminate | Drawing | Detail | Melt Shop Scrap Yard | Electrical | TAM | 2014-02-18 11:06 | IFC | AFC | 100%
14769 | I491TE07-0MNEE91-007-001 | Ferro Alloy Grounding System Calculation Note | 01 | 2012-04-15 | Indeterminate | Miscellaneous(MISC) | Basic | Melt Shop Lime And Ferroalloy Storage | Electrical | TAM |  | IFA | AFC | 100%
16599 | I491TE07-0MNEE91-008-002 | Ferro Alloy Grounding System Layout | 02 | 2013-12-09 | Indeterminate | Drawing | Detail | Melt Shop Lime And Ferroalloy Storage | Electrical | TAM | 2014-02-18 11:07 | IFC | AFC | 100%
16600 | I491TE07-0MNEE91-009-002 | Cable Tunnel Grounding System Layout | 02 | 2013-12-09 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | TAM | 2014-02-18 11:07 | IFI | AFC | 100%
14774 | I491TE07-0MNEE91-010-001 | Melt Shop Grounding System Calculation Note | 00 | 2012-05-19 | Indeterminate | Miscellaneous(MISC) | Basic | Melt Shop Main Building | Electrical | TAM |  | IFA | AFC | 100%
16594 | I491TE07-0MNEE91-011-001 | Meltshop Grounding System Layout 1-2 | 01 | 2013-12-09 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Electrical | TAM | 2014-02-18 11:04 | IFC | AFC | 100%
16595 | I491TE07-0MNEE91-011-002 | Meltshop Grounding System Layout 2-2 | 01 | 2013-12-09 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Electrical | TAM | 2014-02-18 11:04 | IFC | AFC | 100%
14778 | I491TE07-0MNGU01-001-002 | Plant 33 Kv Cable Calculation | 01 | 2012-06-25 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | TAM |  | IFC | AFC | 100%
14780 | I491TE07-0MNGU01-002-002 | Plant 6.6 Kv Cable Calculation | 01 | 2013-04-07 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | TAM |  | IFC | AFC | 100%
14782 | I491TE07-0MXAA91-001-002 | Data Sheet For Cables | 01 | 2012-05-22 | Indeterminate | Miscellaneous(MISC) | Basic | Main Electrical Substation And Distribution Network | Electrical | TAM |  | IFC | AFC | 100%
14784 | I491TE07-0MXAA91-002-002 | Technical Specification For Cable Selection And Sizing | 01 | 2012-05-22 | Indeterminate | Miscellaneous(MISC) | Basic | Main Electrical Substation And Distribution Network | Electrical | TAM |  | IFC | AFC | 100%
14786 | I491TE07-0MXAA91-003-002 | Technical Specification For Grounding System | 01 | 2012-04-03 | Indeterminate | Miscellaneous(MISC) | Basic | General | Electrical | Fortune |  | IFC | AFC | 100%
131548 | I491TE07-0MXLN01-001-001 | Lightning Protection System Calculation Report | 02 | 2017-10-25 | Indeterminate | Drawing | Detail | General | Electrical | TAM | 2017-10-30 09:40 | IFC | AFC | 100%
14789 | I491TE07-0MXLT01-001-003 | Ware House-A Cable Trays | 02 | 2013-01-16 | Indeterminate | Drawing | Detail | Warehouse | Electrical | TAM |  | IFC | AFC | 100%
129539 | I491TE07-0MZLT91-001-002 | Workshop Cable Trays | 06 | 2016-09-18 09:44 | Indeterminate | Drawing | Detail | Maintenance Workshop | Electrical | TAM | 2016-09-18 09:44 | IFC | AFC | 100%
130046 | I491TE07-0SHLT01-001-001 | Scrap Yard Cable Trays | 03 | 2016-12-27 | Indeterminate | Drawing | Detail | Scrap Yard Equipment | Electrical | TAM | 2016-12-29 11:54 | IFC | AFC | 100%
113697 | I491TE07-0TBEL91-001-001 | Ferro Alloy Cable Trays | 02 | 2015-06-02 15:44 | Indeterminate | Drawing | Detail | Melt Shop Lime And Ferroalloy Storage | Electrical | TAM | 2015-06-02 15:44 | IFC | AFC | 100%
114527 | I491TE08-0CCDF01-001-001 | Dummy Bar Electric 8.610668.F_001_00A | 00 | 2015-10-12 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-13 08:41 | IFI | OB | 100%
16583 | I491TE08-0EASW01-001-001 | Eaf Switchgear Wiring Diagram | 01 | 2013-12-02 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Automation and Instrumentation | FUCHS | 2014-02-18 10:09 | IFC | AFC | 100%
16753 | I491TE08-0EASW01-002-001 | Eaf Mv Busbars Route | 01 | 2014-02-02 | Indeterminate | Miscellaneous(MISC) | Detail | Electric Arc Furnace | Automation and Instrumentation | TAM | 2014-02-20 15:18 | IFC | AC |  | 95%
16584 | I491TE08-0LFSW01-001-001 | Lf Mv Swithgear Wiring Diagram | 01 | 2013-12-02 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Automation and Instrumentation | FUCHS | 2014-02-18 10:09 | IFC | AFC | 100%
16754 | I491TE08-0LFSW01-002-001 | LF Mv Building Basbars Route | 01 | 2014-02-02 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Automation and Instrumentation | TAM | 2014-02-20 15:19 | IFC | AC |  | 95%
112232 | I491TE08-0MDAA91-001-001 | Material Handling System Lv Switchgear Typical Schematic Diagnam | 02 | 2013-08-07 | Indeterminate | Drawing | Basic | Material Handling | Electrical | DATIS | 2014-05-19 16:54 | IFC | AFC | 100%
112233 | I491TE08-0MDAA91-001-002 | Material Handling System Lv Switchgear Typical Schematic Diagnam | 02 | 2013-08-07 | Indeterminate | Drawing | Basic | Material Handling | Electrical | DATIS | 2014-05-19 16:54 | IFC | AFC | 100%
112234 | I491TE08-0MDAA91-001-003 | Material Handling System Lv Switchgear Typical Schematic Diagnam | 02 | 2013-08-07 | Indeterminate | Drawing | Basic | Material Handling | Electrical | DATIS | 2014-05-19 16:54 | IFC | AFC | 100%
112235 | I491TE08-0MDAA91-001-004 | Material Handling System Lv Switchgear Typical Schematic Diagnam | 02 | 2013-08-07 | Indeterminate | Drawing | Basic | Material Handling | Electrical | DATIS | 2014-05-19 16:54 | IFC | AFC | 100%
112236 | I491TE08-0MDAA91-001-005 | Material Handling System Lv Switchgear Typical Schematic Diagnam | 02 | 2013-08-07 | Indeterminate | Drawing | Basic | Material Handling | Electrical | DATIS | 2014-05-19 16:54 | IFC | AFC | 100%
112237 | I491TE08-0MDAA91-001-006 | Material Handling System Lv Switchgear Typical Schematic Diagnam | 02 | 2013-08-07 | Indeterminate | Drawing | Basic | Material Handling | Electrical | DATIS | 2014-05-19 16:54 | IFC | AFC | 100%
112238 | I491TE08-0MDAA91-001-007 | Material Handling System Lv Switchgear Typical Schematic Diagnam | 02 | 2013-08-07 | Indeterminate | Drawing | Basic | Material Handling | Electrical | DATIS | 2014-05-19 16:54 | IFC | AFC | 100%
112239 | I491TE08-0MDAA91-001-008 | Material Handling System Lv Switchgear Typical Schematic Diagnam | 02 | 2013-08-07 | Indeterminate | Drawing | Basic | Material Handling | Electrical | DATIS | 2014-05-19 16:54 | IFC | AFC | 100%
14824 | I491TE08-0MMCT01-001-013 | Schematic One Line Diagram For Cooling System(Ct01,Ct02) 1-7 | 02 | 2013-10-08 | Indeterminate | Drawing | Basic | Water Treatment & Cooling System | Electrical | FARABARD |  | IFC | AFC | 100%
14825 | I491TE08-0MMCT01-001-014 | Schematic One Line Diagram For Cooling System(Ct01,Ct02) 2-7 | 02 | 2013-10-08 | Indeterminate | Drawing | Basic | Water Treatment & Cooling System | Electrical | FARABARD |  | IFC | AFC | 100%
14826 | I491TE08-0MMCT01-001-015 | Schematic One Line Diagram For Cooling System(Ct01,Ct02) 3-7 | 02 | 2013-10-08 | Indeterminate | Drawing | Basic | Water Treatment & Cooling System | Electrical | FARABARD |  | IFC | AFC | 100%
14827 | I491TE08-0MMCT01-001-016 | Schematic One Line Diagram For Cooling System(Ct01,Ct02) 4-7 | 02 | 2013-10-08 | Indeterminate | Drawing | Basic | Water Treatment & Cooling System | Electrical | FARABARD |  | IFC | AFC | 100%
14828 | I491TE08-0MMCT01-001-017 | Schematic One Line Diagram For Cooling System(Ct01,Ct02) 5-7 | 02 | 2013-10-08 | Indeterminate | Drawing | Basic | Water Treatment & Cooling System | Electrical | FARABARD |  | IFC | AFC | 100%
14829 | I491TE08-0MMCT01-001-018 | Schematic One Line Diagram For Cooling System(Ct01,Ct02) 6-7 | 02 | 2013-10-08 | Indeterminate | Drawing | Basic | Water Treatment & Cooling System | Electrical | FARABARD |  | IFC | AFC | 100%
114714 | I491TE08-0MMCT01-005-001 | Logic and Schematic Diagram For Power center ( LV - MS - SWB) | 02 | 2015-11-24 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Electrical | CEBA | 2015-11-28 13:20 | IFC | AFC | 100%
130259 | I491TE09-0ASFP91-002-001 | ASP SUBSTATION FIRE ALARM LAYOUT | 02 | 2017-01-25 | Indeterminate | Drawing | Detail | Air Separation Plant | Electrical | TAM | 2017-01-31 15:35 | IFC | AFC | 100%
130598 | I491TE09-0ASFP91-003-001 | ASP FIRE ALARM LAYOUT | 01 | 2017-05-10 | Indeterminate | Drawing | Detail | Air Separation Plant | Electrical | TAM | 2017-05-14 15:04 | IFC | AFC | 100%
130599 | I491TE09-0ASFP91-004-001 | CAP FIRE ALARM LAYOUT | 01 | 2017-05-10 | Indeterminate | Drawing | Detail | Air Separation Plant | Electrical | TAM | 2017-05-14 15:04 | IFC | AFC | 100%
134337 | I491TE09-0ASPH91-004-001 | ASP-CAP SUBSTATION INDOOR VOIP AND PC NETWORK LAYOUT | 02 | 2018-11-04 | Indeterminate | Drawing | Detail | Air Separation Plant | Electrical | TAM | 2018-11-06 08:55 | IFI | OB | 100%
134338 | I491TE09-0ASPH91-005-001 | ASP-CAP INDOOR VOIP AND PC NETWORK LAYOUT 1-3 | 02 | 2018-11-04 | Indeterminate | Drawing | Detail | Air Separation Plant | Electrical | TAM | 2018-11-06 08:55 | IFI | OB | 100%
134339 | I491TE09-0ASPH91-005-002 | ASP-CAP INDOOR VOIP AND PC NETWORK LAYOUT 2-3 | 02 | 2018-11-04 | Indeterminate | Drawing | Detail | Air Separation Plant | Electrical | TAM | 2018-11-06 08:55 | IFI | OB | 100%
133171 | I491TE09-0ASPH91-005-003 | ASP-CAP INDOOR VOIP AND PC NETWORK LAYOUT 3-3 | 01 | 2018-05-28 15:04 | Indeterminate | Drawing | Detail | Air Separation Plant | Electrical | TAM | 2018-05-28 15:04 | IFC | AC |  | 95%
131023 | I491TE09-0ASYE91-002-001 | ASP AND ACP INTERCOM SYSTEM LAYOUT | 01 | 2017-08-10 | Indeterminate | Drawing | Detail | Air Separation Plant | Electrical | TAM | 2017-08-12 09:23 | IFC | AFC | 100%
130370 | I491TE09-0CCFP91-002-001 | CCM BUILDING FIRE ALARM SYSTEM | 01 | 2017-03-01 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Electrical | TAM | 2017-04-03 09:53 | IFC | AFC | 100%
134652 | I491TE09-0CCFP91-003-001 | FNC Building Fire Alarm System | 00 | 2018-12-12 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Electrical | TAM | 2018-12-17 10:51 | IFA | AC |  | 95%
129921 | I491TE09-0CCPH91-003-001 | CCM BUILDING TELETHONE AND NETWORK LAYOUT (2 Sheet) | 01 | 2016-12-12 14:20 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Electrical | TAM | 2016-12-12 14:20 | AFC | AFC | 100%
134340 | I491TE09-0CCPH91-004-001 | CCM BUILDING VOIP AND PC NETWORK LAYOUT | 02 | 2018-11-04 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Electrical | TAM | 2018-11-06 08:59 | IFI | OB | 100%
134342 | I491TE09-0CCPH91-005-001 | CCM FNC MAINTENANCE ROOM INDOOR NETWORK AND VOIP AND CCTV SYSTEM LAYOUT | 00 | 2018-11-04 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Electrical | TAM | 2018-11-06 09:01 | IFI | OB | 100%
131197 | I491TE09-0CCYE91-002-001 | CCM PLANT INTERCOM SYSTEM LAYOUT | 01 | 2017-09-20 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Electrical | TAM | 2017-09-27 09:54 | IFC | AFC | 100%
130260 | I491TE09-0DTFP91-002-001 | FTP-MH SUBSTATION FIRE ALARM LAYOUT | 02 | 2017-01-25 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Electrical | TAM | 2017-01-31 15:38 | IFC | AFC | 100%
130404 | I491TE09-0DTPH91-003-001 | FTP MHS TELETHONE AND NETWORK LAYOUT | 02 | 2017-03-12 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Electrical | TAM | 2017-04-04 14:01 | IFC | AFC | 100%
134343 | I491TE09-0DTPH91-004-001 | FTP-MHS VOIP AND NETWORK LAYOUT | 02 | 2018-11-04 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Electrical | TAM | 2018-11-06 09:04 | IFI | OB | 100%
131024 | I491TE09-0DTYE91-002-001 | FTP PLANT INTERCOM SYSTEM LAYOUT | 01 | 2017-08-09 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Electrical | TAM | 2017-08-12 09:25 | IFC | AFC | 100%
134958 | I491TE09-0EAFP91-002-001 | EAF TRANSFORMER ROOM FIRE ALARM SYSTEM | 00 | 2019-01-14 09:01 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Electrical | TAM | 2019-01-14 09:01 | IFA | AC |  | 95%
130403 | I491TE09-0EAFP91-004-001 | EAF BUILDING FIRE ALARM SYSTEM | 01 | 2017-03-07 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Electrical | TAM | 2017-04-04 10:20 | IFC | AFC | 100%
130119 | I491TE09-0EAFP91-008-001 | LF BUILDING FIRE ALARM SYSTEM | 03 | 2017-01-08 | Indeterminate | Drawing | Detail | Ladle Furnace | Electrical | TAM | 2017-01-09 10:21 | IFC | AFC | 100%
131028 | I491TE09-0EAFP91-011-001 | MELTSHOP PLANT FIRE ALARM SYSTEM | 02 | 2017-08-12 09:49 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Electrical | TAM | 2017-08-12 09:49 | IFC | AFC | 100%
133219 | I491TE09-0EAFP91-013-001 | MELT SHOP OFFICE FIRE ALARM SYSTEM | 01 | 2018-06-02 14:15 | Indeterminate | Drawing | Detail | Melt Shop | Electrical | TAM | 2018-06-02 14:15 | IFC | AFC | 100%
130569 | I491TE09-0EAPH91-002-001 | LF And CCM Labratory Telephone and Network System layout 1-4 | 01 | 2017-05-09 15:42 | Indeterminate | Drawing | Detail | Laboratory | Electrical | TAM | 2017-05-09 15:42 | IFC | AFC | 100%
130570 | I491TE09-0EAPH91-002-002 | LF And CCM Labratory Telephone and Network System layout 2-4 | 01 | 2017-05-09 15:42 | Indeterminate | Drawing | Detail | Laboratory | Electrical | TAM | 2017-05-09 15:42 | IFC | AFC | 100%
130571 | I491TE09-0EAPH91-002-003 | LF And CCM Labratory Telephone and Network System layout 3-4 | 01 | 2017-05-09 15:42 | Indeterminate | Drawing | Detail | Laboratory | Electrical | TAM | 2017-05-09 15:42 | IFC | AFC | 100%
130572 | I491TE09-0EAPH91-002-004 | LF And CCM Labratory Telephone and Network System layout 4-4 | 01 | 2017-05-09 15:42 | Indeterminate | Drawing | Detail | Laboratory | Electrical | TAM | 2017-05-09 15:42 | IFC | AFC | 100%
130602 | I491TE09-0EAPH91-003-001 | EAF BUILDING TELEPHONE AND NETWORK LAYOUT | 02 | 2017-05-13 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Electrical | TAM | 2017-05-20 11:16 | IFC | AFC | 100%
130629 | I491TE09-0EAPH91-004-001 | LF BUILDING TELEPHONE NETWORK LAYOUT | 02 | 2017-05-24 | Indeterminate | Drawing | Detail | Ladle Furnace | Electrical | TAM | 2017-05-27 12:01 | IFC | AFC | 100%
130765 | I491TE09-0EAPH91-006-001 | Melt Shop PLANT TELETHONE SYSTEM LAYOUT | 02 | 2017-07-08 | Indeterminate | Drawing | Detail | Melt Shop | Electrical | TAM | 2017-07-10 09:55 | IFC | AFC | 100%
134344 | I491TE09-0EAPH91-008-001 | EAF BUILDING VOIP AND PC NETWORK LAYOUT | 02 | 2018-11-04 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Electrical | TAM | 2018-11-06 09:05 | IFI | OB | 100%
134426 | I491TE09-0EAPH91-009-001 | LF BUILDING VOIP AND NETWORK LAYOUT | 02 | 2018-11-28 | Indeterminate | Drawing | Detail | Ladle Furnace | Electrical | TAM | 2018-12-01 10:16 | IFI | AC |  | 95%
134427 | I491TE09-0EAPH91-010-001 | MELTSHOP PLANT VOIP AND NETWORK SYSTEM LAYOUT | 02 | 2018-11-28 | Indeterminate | Drawing | Detail | Melt Shop | Electrical | TAM | 2018-12-01 10:17 | IFI | AC |  | 95%
134431 | I491TE09-0EAPH91-010-002 | MELTSHOP PLANT VOIP AND NETWORK AND CCTV LAYOUT 2-3 | 00 | 2018-11-28 | Indeterminate | Drawing | Detail | Melt Shop | Electrical | TAM | 2018-12-01 10:21 | IFI | AC |  | 95%
134430 | I491TE09-0EAPH91-010-003 | MELTSHOP PLANT VOIP AND NETWORK AND CCTV LAYOUT 3-3 | 00 | 2018-11-28 | Indeterminate | Drawing | Detail | Melt Shop | Electrical | TAM | 2018-12-01 10:21 | IFI | AC |  | 95%
134433 | I491TE09-0EAPH91-011-001 | MELTSHOP OFFICE NETWORK AND VOIP AND CCTV SYSTEM | 00 | 2018-11-28 | Indeterminate | Drawing | Detail | Melt Shop | Electrical | TAM | 2018-12-01 10:25 | IFI | AC |  | 95%
131025 | I491TE09-0EAYE91-002-001 | EAF BUILDING PLANT INTERCOM SYSTEM LAYOUT | 01 | 2017-08-09 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Electrical | TAM | 2017-08-12 09:42 | IFC | AFC | 100%
131032 | I491TE09-0EAYE91-004-001 | MELTSHOP INTERCOM SYSTEM LAYOUT | 01 | 2017-08-13 | Indeterminate | Drawing | Detail | Melt Shop | Electrical | TAM | 2017-08-15 11:31 | IFC | AFC | 100%
132929 | I491TE09-0LAFP91-001-001 | CCM & LF LABORATORY FIRE ALARM SYSTEM | 01 | 2018-02-19 09:48 | Indeterminate | Drawing | Detail | Laboratory | Electrical | TAM | 2018-02-19 09:48 | IFC | AFC | 100%
134345 | I491TE09-0LAPH91-007-001 | LF & CCM Labratory VOIP & Network System layout 1-2 | 02 | 2018-11-04 | Indeterminate | Drawing | Detail | General | Electrical | TAM | 2018-11-06 09:07 | IFI | OB | 100%
134346 | I491TE09-0LAPH91-007-002 | LF & CCM Labratory VOIP & Network System layout 2-2 | 02 | 2018-11-04 | Indeterminate | Drawing | Detail | General | Electrical | TAM | 2018-11-06 09:07 | IFI | OB | 100%
134960 | I491TE09-0LFFP91-001-001 | LF TRANSFORMER ROOM FIRE ALARM SYSTEM | 00 | 2019-01-14 09:06 | Indeterminate | Drawing | Detail | Ladle Furnace | Electrical | TAM | 2019-01-14 09:06 | IFA | AC |  | 95%
130603 | I491TE09-0MEPH91-005-001 | SVC-MAIN SUBSTATION TELEPHONE AND NETWORK SYSTEMS LAYOUT 1-2 | 01 | 2017-05-13 | Indeterminate | Drawing | Detail | Main Electrical Substation And Distribution Network | Electrical | TAM | 2017-05-20 11:19 | IFC | AFC | 100%
130604 | I491TE09-0MEPH91-005-002 | SVC-MAIN SUBSTATION TELEPHONE AND NETWORK SYSTEMS LAYOUT 2-2 | 01 | 2017-05-13 | Indeterminate | Drawing | Detail | Main Electrical Substation And Distribution Network | Electrical | TAM | 2017-05-20 11:19 | IFC | AFC | 100%
134434 | I491TE09-0MEPH91-006-001 | SVC - MAIN SUBSTATION VOIP AND NETWORK SYSTEMS LAYOUT 1-2 | 02 | 2018-11-28 | Indeterminate | Drawing | Detail | Main Electrical Substation And Distribution Network | Electrical | TAM | 2018-12-01 10:25 | IFI | AC |  | 95%
134435 | I491TE09-0MEPH91-006-002 | SVC - MAIN SUBSTATION VOIP AND NETWORK SYSTEMS LAYOUT 2-2 | 02 | 2018-11-28 | Indeterminate | Drawing | Detail | Main Electrical Substation And Distribution Network | Electrical | TAM | 2018-12-01 10:25 | IFI | AC |  | 95%
130369 | I491TE09-0MMFP91-002-001 | WTP SUBSTATION FIRE ALARM LAYOUT 1-2 | 03 | 2017-02-28 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Electrical | TAM | 2017-04-03 09:49 | IFC | AFC | 100%
135053 | I491TE09-0MMFP91-003-001 | SEDIMENTATION BUILDING FIRE ALARM LAYOUT | 02 | 2019-02-17 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Electrical | TAM | 2019-02-23 12:57 | IFC | AC |  | 95%
134436 | I491TE09-0MMPH91-004-001 | WTP CONTROL ROOM VOIP and PC NETWORK LAYOUT | 02 | 2018-11-28 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Electrical | TAM | 2018-12-01 10:26 | IFI | AC |  | 95%
131027 | I491TE09-0MMYE91-002-001 | WTP INTERCOM LAYOUT | 01 | 2017-08-09 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Electrical | TAM | 2017-08-12 09:47 | IFC | AFC | 100%
14847 | I491TE09-0MXAA91-002-001 | Basic Data of Fire Alarm | 00 | 2012-07-17 | Indeterminate | Miscellaneous(MISC) | Basic | Fire Fighting System | Mechanical | TAM |  | IFA | AC |  | 95%
14848 | I491TE09-0MXAA91-003-001 | Overview Of Cctv System | 00 | 2012-06-16 | Indeterminate | Drawing | Basic | Comunication | Mechanical | TAM |  | IFA | AC |  | 95%
14849 | I491TE09-0MXAA91-004-001 | Overview Of Security System | 00 | 2012-06-16 | Indeterminate | Drawing | Basic | Comunication | Mechanical | TAM |  | IFA | AC |  | 95%
133096 | I491TE09-0MXFP91-001-001 | FIRE ALARM SYSTEM BLOCK DIAGRAM | 03 | 2018-04-23 | Indeterminate | Drawing | Detail | General | Electrical | TAM | 2018-05-05 11:00 | IFC | AC |  | 95%
130460 | I491TE09-0MXFP91-002-001 | Cable Tunnel Fire alarm System Layout (DETECTION LINE) 1-4 | 01 | 2017-04-10 | Indeterminate | Drawing | Detail | Main Electrical Substation And Distribution Network | Electrical | TAM | 2017-04-24 09:28 | IFC | AFC | 100%
130461 | I491TE09-0MXFP91-002-002 | Cable Tunnel Fire alarm System Layout (ALARM LINE) 2-4 | 01 | 2017-04-10 | Indeterminate | Drawing | Detail | Main Electrical Substation And Distribution Network | Electrical | TAM | 2017-04-24 09:28 | IFC | AFC | 100%
130462 | I491TE09-0MXFP91-002-003 | Cable Tunnel Fire alarm System Layout (DETECTION LINE) 3-4 | 01 | 2017-04-10 | Indeterminate | Drawing | Detail | Main Electrical Substation And Distribution Network | Electrical | TAM | 2017-04-24 09:28 | IFC | AFC | 100%
130463 | I491TE09-0MXFP91-002-004 | Cable Tunnel Fire alarm System Layout (ALARM LINE) 4-4 | 01 | 2017-04-10 | Indeterminate | Drawing | Detail | Main Electrical Substation And Distribution Network | Electrical | TAM | 2017-04-24 09:28 | IFC | AFC | 100%
130121 | I491TE09-0MXPH91-003-001 | WAREHOUSE OFFICE TELEPHONE AND NETWORK LAYOUT | 02 | 2017-01-10 | Indeterminate | Drawing | Detail | Warehouse | Electrical | TAM | 2017-01-15 09:11 | IFC | AFC | 100%
134347 | I491TE09-0MXPH91-004-001-001 | COURTYARD NETWORK SYSTEM LAYOUT | 02 | 2018-11-04 | Indeterminate | Drawing | Detail | General | Electrical | TAM | 2018-11-06 09:12 | IFI | OB | 100%
135056 | I491TE09-0MXPH91-004-001-002 | NETWORK BLOCK DIAGRAM | 03 | 2019-02-25 | Indeterminate | Drawing | Detail | General | Electrical | TAM | 2019-03-05 14:33 | IFC | AC |  | 95%
134437 | I491TE09-0MXPH91-005-001 | WAREHOUSE VOIP AND NETWORK LAYOUT | 02 | 2018-11-28 | Indeterminate | Drawing | Detail | Warehouse | Electrical | TAM | 2018-12-01 10:26 | IFI | AC |  | 95%
132806 | I491TE09-0MXYE91-001-001 | INTERCOM SYSTEM BLOCK DIAGRAM | 04 | 2018-01-31 | Indeterminate | Drawing | Detail | General | Electrical | TAM | 2018-02-03 15:28 | IFC | AFC | 100%
134438 | I491TE09-0MYPH91-003-001 | WORKSHOP VOIP AND NETWORK SYSTEM LAYOU | 02 | 2018-11-28 | Indeterminate | Drawing | Detail | Melt Shop Maintenance Workshop | Electrical | TAM | 2018-12-01 10:26 | IFI | AC |  | 95%
130030 | I491TE09-0MZFP91-002-001 | WORKSHOP FIRE ALARM LAYOUT | 01 | 2016-12-26 10:24 | Indeterminate | Drawing | Detail | Maintenance Workshop | Electrical | TAM | 2016-12-26 10:24 | IFC | AFC | 100%
130050 | I491TE09-0MZPH91-002-001 | WORKSHOP TELETHONE AND NETWORK SYSTEM LAYOUT | 01 | 2016-12-03 | Indeterminate | Drawing | Detail | Maintenance Workshop | Electrical | TAM | 2017-01-01 09:02 | AFC | AFC | 100%
112145 | I491TE09-0OFPH91-001-001 | LIST OF ELECTRICAL DRAWING, LEGEND AND GENERAL NOTE | 00 | 2014-05-05 | Indeterminate | Drawing | Detail | Office - Canteen - Locker & Shower For Melt Shop | Piping & Utility | TAM | 2014-05-15 15:38 | IFA | AC |  | 95%
112144 | I491TE09-0OFPH91-001-002 | GROUND FLOOR TELEPHONE & ANTENNA | 00 | 2014-05-05 | Indeterminate | Drawing | Detail | Office - Canteen - Locker & Shower For Melt Shop | Piping & Utility | TAM | 2014-05-15 15:38 | IFA | AC |  | 95%
112143 | I491TE09-0OFPH91-001-003 | 1ST FLOOR TELEPHONE & ANTENNA | 00 | 2014-05-05 | Indeterminate | Drawing | Detail | Office - Canteen - Locker & Shower For Melt Shop | Piping & Utility | TAM | 2014-05-15 15:38 | IFA | AC |  | 95%
112148 | I491TE09-0OFTV91-001-001 | LIST OF ELECTRICAL DRAWING, LEGEND AND GENERAL NOTE | 00 | 2014-05-05 | Indeterminate | Drawing | Detail | Office - Canteen - Locker & Shower For Melt Shop | Piping & Utility | TAM | 2014-05-15 15:39 | IFA | AC |  | 95%
112147 | I491TE09-0OFTV91-001-002 | GROUND FLOOR CCTV&SOUND | 00 | 2014-05-05 | Indeterminate | Drawing | Detail | Office - Canteen - Locker & Shower For Melt Shop | Piping & Utility | TAM | 2014-05-15 15:39 | IFA | AC |  | 95%
112146 | I491TE09-0OFTV91-001-003 | 1ST FLOOR CCTV&SOUND | 00 | 2014-05-05 | Indeterminate | Drawing | Detail | Office - Canteen - Locker & Shower For Melt Shop | Piping & Utility | TAM | 2014-05-15 15:38 | IFA | AC |  | 95%
130273 | I491TE09-0SEFP91-004-001 | SMP SUBSTATION FIRE ALARM LAYOUT | 02 | 2017-01-29 | Indeterminate | Drawing | Detail | Steel Making Electrical Substation Building | Electrical | TAM | 2017-02-04 09:55 | IFC | AFC | 100%
129967 | I491TE09-0SEPH91-002-002 | SMP SUBSTATION TELETHONE & PC NETWORK SYSTEM LAYOUT | 01 | 2016-12-13 09:26 | Indeterminate | Drawing | Detail | Steel Making Electrical Substation | Electrical | TAM | 2016-12-13 09:26 | IFC | AFC | 100%
135057 | I491TE09-0SEPH91-003-001 | SMP SUBSTATION BUILDING SMP SUBSTATION VOIP & PC NETWORK AND CCTV LAYOUT | 03 | 2019-03-05 14:35 | Indeterminate | Drawing | Detail | Steel Making Electrical Substation Building | Electrical | TAM | 2019-03-05 14:35 | IFC | AC |  | 95%
130295 | I491TE09-0TBFP91-002-001 | WAREHOUSE FIRE ALARM LAYOUT | 01 | 2017-02-05 | Indeterminate | Drawing | Detail | Warehouse | Electrical | TAM | 2017-02-07 10:22 | IFC | AFC | 100%
130251 | I491TE09-0TBFP91-004-001 | FERRO ALLOY STORAGE FIRE ALARM SYSTEM | 01 | 2017-01-18 | Indeterminate | Drawing | Detail | Technological Building | Electrical | TAM | 2017-01-24 15:15 | IFC | AFC | 100%
134349 | I491TE09-0TBPH91-002-001 | FERRO ALLOY NETWORK SYSTEM LAYOUT PLAN | 02 | 2018-11-04 | Indeterminate | Drawing | Detail | Technological Building | Electrical | TAM | 2018-11-06 09:15 | IFI | OB | 100%
14851 | I491TE10-0EATF91-001-002 | Eaf_Furnace_Transformer Dimension_Drawings | 01 | 2013-10-08 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Electrical | FUCHS |  | IFC | AFC | 100%
14854 | I491TE10-0EATF91-002-003 | Eaf Furnace Transformer Electrical Wiring Drawings | 02 | 2013-10-09 | Indeterminate | Miscellaneous(MISC) | Detail | Electric Arc Furnace | Electrical | FUCHS |  | IFC | AFC | 100%
111702 | I491TE10-0EATF91-003-001 | "EAF Furnace Transformer Test Certificate" | 00 | 2014-04-19 | Indeterminate | Miscellaneous(MISC) | Detail | Electric Arc Furnace | Electrical | TAM | 2014-04-27 11:28 | IFI | OB | 100%
14856 | I491TE10-0EATF92-001-002 | Eaf Series Reactor Dimension Drawings | 01 | 2013-10-08 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Electrical | FUCHS |  | IFC | AFC | 100%
14859 | I491TE10-0EATF92-002-003 | Eaf Series Reactor Electrical Wiring Drawings | 02 | 2013-10-09 | Indeterminate | Miscellaneous(MISC) | Detail | Electric Arc Furnace | Electrical | FUCHS |  | IFC | AFC | 100%
111703 | I491TE10-0EATF92-003-001 | "EAF Series Reactor Test Certificate" | 00 | 2014-04-19 | Indeterminate | Miscellaneous(MISC) | Detail | Electric Arc Furnace | Electrical | TAM | 2014-04-27 11:28 | IFI | OB | 100%
14861 | I491TE10-0LFTF91-001-002 | Lf Furnance Transformer Dimension Drawings | 01 | 2013-10-08 | Indeterminate | Drawing | Detail | Ladle Furnace | Electrical | FUCHS |  | IFC | AFC | 100%
14864 | I491TE10-0LFTF91-002-003 | Lf Furnace Transformer Electrical Wiring Drawings | 02 | 2013-10-09 | Indeterminate | Miscellaneous(MISC) | Detail | Electric Arc Furnace | Electrical | FUCHS |  | IFC | AFC | 100%
111704 | I491TE10-0LFTF91-003-001 | "LF Furnace Transformer Test Certificate" | 00 | 2014-04-19 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Electrical | TAM | 2014-04-27 11:29 | IFI | OB | 100%
14867 | I491TE20-0MEDC01-081-003 | 110V Dc Battery And Charger Calculation | 01 | 2012-07-29 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
14869 | I491TE20-0MEDC02-082-002 | 48V Dc Battery & Charger Calculation | 00 | 2012-03-18 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
14870 | I491TE21-0MEDC01-128-001 | Lvdc F.V | 00 | 2013-06-12 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
14872 | I491TE21-0MEDC01-193-001 | 400/33 Kv Substation 48 V Dc Panels Sircuit Diagram | 01 | 2013-09-04 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
14893 | I491TE21-0MEDC02-160-002 | 400/33 Kv Substation 48V Dc Single Line Diagram | 02 | 2012-03-18 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
14873 | I491TE21-0MEDC03-190-001 | 400/33 Kv Substation Main Lvac Panels Sircuit Diagram | 01 | 2013-09-04 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
14874 | I491TE21-0MEDC04-150-002 | 400/33 Kv Substation Main Lvdc Single Line Diagrams | 01 | 2012-02-19 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
14876 | I491TE21-0MEHV01-001-003 | 400/33 Kv Substation Single Line Diagram | 02 | 2013-05-28 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
14877 | I491TE21-0MELT01-142-001 | 400/33 Kv Substation Outdoor Lighting Panels Sircuit Diagram | 01 | 2013-09-04 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
14878 | I491TE21-0MELT02-103-001 | Outdoor Lighting Panel Single Line Diagram | 00 | 2012-04-24 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
14897 | I491TE21-0MEPN01-101-002 | 400/33 Kv Substation Acdc Distribution Single Line Diagrams | 01 | 2012-08-01 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFC | AFC | 100%
14879 | I491TE21-0MEPR01-300-001 | 400/33 Kv Over Head Line Protection Schematic Diagram | 01 | 2013-09-04 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
14880 | I491TE21-0MEPR01-301-001 | 400/33 Kv Over Head Line Protection Schematic Diagram | 01 | 2013-09-04 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
14881 | I491TE21-0MEPR01-311-001 | 400/33 Kv Over Head Line Protection Schematic Diagram | 01 | 2013-09-04 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
14882 | I491TE21-0MEPR01-312-001 | 400/33 Kv Over Head Line Protection Schematic Diagram | 01 | 2013-09-04 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
14883 | I491TE21-0MEPR01-321-001 | 400/33 Kv Over Head Line Protection Schematic Diagram | 01 | 2013-09-04 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
14886 | I491TE21-0MEPR02-201-004 | 400/33 Kv Substation Protection Single Line Diagram | 02 | 2013-05-28 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
14900 | I491TE21-0MEPR03-201-003 | 400/33 Kv Substation Protection Trip Table | 01 | 2012-03-18 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
14903 | I491TE21-0MEYA01-101-004 | 400/33 Kv Substation Main Lvac Logic Diagram | 02 | 2012-07-29 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
14889 | I491TE21-0MEYA01-120-001 | 400/33 Kv Substation Main Lvac Panels Front View | 00 | 2013-06-12 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
14890 | I491TE21-0MEYA02-180-001 | 400/33 Kv Substation Main Lvac Panels Sircuit Diagram | 01 | 2013-09-04 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
14891 | I491TE21-0MEYA03-100-001 | 400/33 Kv Substation Main Lvac Single Line Diagram | 01 | 2012-02-19 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
14906 | I491TE22-0MEDC01-107-002 | Main Lvdc Load List | 01 | 2012-07-29 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
14908 | I491TE22-0MEPN01-110-002 | Ac/Dc Distribution Panels Load List | 01 | 2012-07-29 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFC | AFC | 100%
14909 | I491TE22-0MEPR01-201-003 | 400/33 Kv Substation Signal List | 01 | 2012-06-13 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
14916 | I491TE22-0MEXX01-001-001 | 400/33 Kv Substation List Of Document | 00 | 2011-12-11 | Indeterminate | Miscellaneous(MISC) | Basic | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
14914 | I491TE22-0MEYA01-105-003 | Main Lvac Single Line Diagram | 00 | 2013-06-12 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
14915 | I491TE22-0MEYC01-211-001 | Bardsir Steel Making Plant 400/33 Kv Substation Interface Panel I/O Configuration & Termination List | 00 | 2013-04-24 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
14919 | I491TE23-0MELN01-002-004 | 400/33 Kv Substation Earthing System Calculation | 03 | 2012-05-29 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
14921 | I491TE23-0MELN02-010-003 | 400/33 Kv Substation Earthing System Detail | 00 | 2013-06-15 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
14925 | I491TE23-0MELN04-002-003 | 400/33 Kv Substation Earthing System Plant | 00 | 2013-06-15 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
14927 | I491TE24-0MEHV02-758-001 | 400/33 Kv Substation Routine Test Report For Cb | 00 | 2012-02-07 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
14928 | I491TE24-0MEPR01-200-001 | Protection Relay Test Procedure | 00 | 2012-04-29 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
14929 | I491TE25-0MECM01-802-001 | PLC & TPS Systems Technical Specification | 00 | 2012-04-03 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Automation and Instrumentation | PARSIAN |  | IFI | OB | 100%
14930 | I491TE25-0MECM02-901-001 | 400/33 Kv Substation Rtu Technical Specification | 00 | 2012-04-03 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Automation and Instrumentation | PARSIAN |  | IFI | OB | 100%
14932 | I491TE25-0MEHV01-755-002 | 400/33 Kv Substation Technical Document Of Cb | 00 | 2012-04-09 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFC | AFC | 100%
14933 | I491TE25-0MEHV02-765-001 | Technical Document Of Ct | 00 | 2012-04-21 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
14935 | I491TE25-0MEHV03-770-002 | 400/33 Kv Substation Technical Document Of Cvt | 00 | 2013-06-15 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
14937 | I491TE25-0MEHV04-760-002 | 400/33 Kv Substation Technical Document Ds/Es | 00 | 2013-06-15 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
14942 | I491TE25-0MEHV05-780-002 | 400/33 Kv Substation Technical Document Of Line Trap | 01 | 2012-04-03 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
14939 | I491TE25-0MEHV06-775-001 | Technical Document Of Surge Arrester | 00 | 2012-02-25 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | AFC | 100%
14940 | I491TE25-0MEPR01-201-001 | 400/33 Kv Substation Protection Equipment List | 00 | 2011-12-25 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
14945 | I491TE26-0MELA01-036-001 | 400/33 Kv Substation Calculation Of Cross Section For Stranded Conductor | 00 | 2011-12-07 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
14946 | I491TE26-0MELA02-012-001 | 400/33 Kv Substation Conductor Load Calculation On Gantry Structure | 00 | 2011-12-18 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
14947 | I491TE26-0MELA03-036-001 | 400/33 Kv Substation Conductor Load Calculation On Terminal Of Equipment | 00 | 2011-12-18 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
14948 | I491TE26-0MELA05-008-001 | 400/33 Kv Substation Electrical Calculation For Tubular Conductor | 00 | 2011-12-07 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
14950 | I491TE26-0MELA06-001-003 | 400/33 Kv Substation General Layout & Sections | 02 | 2012-04-03 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
14944 | I491TE26-0MELA06-001-004 | (Design,Supply And Installation Of Bardsir Steel Making Plant 400/33Kv Substation) Instalation Documents | 00 | 2013-04-15 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFC | OB | 100%
14951 | I491TE26-0MELN01-007-001 | 400/33 Kv Substation Mechanical Calculation For Tubular Conductor | 00 | 2011-12-13 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
14952 | I491TE27-0MECM01-800-002 | 400/33 Kv Substation Plc & Tps Systems Block Diagram | 01 | 2012-03-18 | Indeterminate | Miscellaneous(MISC) | Basic | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
14954 | I491TE27-0MEPR01-201-003 | 400/33 Kv Substation Protection Panels Front View | 02 | 2012-03-18 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
15028 | I491TE99-0CPCP91-001-001 | SINGLE LINE DIAGRAM(COMPRESSOR) FOR COMPRESSED AIR PLANT | 01 | 2013-09-17 | Indeterminate | Miscellaneous(MISC) | Basic | Compressed Air Production Plant | Piping & Utility | HAVAYAR |  | IFC | AFC | 100%
15029 | I491TE99-0CPCP91-001-002 | SINGLELINEDIAGRAM (COMPRESSOR) 3-5 | 01 | 2013-09-17 | Indeterminate | Drawing | Basic | Compressed Air Production Plant | Piping & Utility | HAVAYAR |  | IFC | AFC | 100%
14958 | I491TE99-0CPCP91-001-003 | SINGLELINEDIAGRAM (COMPRESSOR) 4-5 | 01 | 2013-09-17 | Indeterminate | Drawing | Basic | Compressed Air Production Plant | Piping & Utility | HAVAYAR |  | IFC | AFC | 100%
15030 | I491TE99-0CPCP91-001-004 | SINGLELINEDIAGRAM (COMPRESSOR) 5-5 | 01 | 2013-09-17 | Indeterminate | Drawing | Basic | Compressed Air Production Plant | Piping & Utility | HAVAYAR |  | IFC | AFC | 100%
14959 | I491TE99-0EAIF01-001-001 | Suspension + Isolation -High Current System Eaf | 00 | 2012-03-10 | Indeterminate | Drawing | Basic | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
14960 | I491TE99-0EAIF02-001-001 | High Current System- Electric Arc Furnace | 00 | 2012-03-10 | Indeterminate | Drawing | Basic | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
14961 | I491TE99-0LFEB01-001-001 | Hc-Cabel Fixing Elektrode Arm Side Flexibles Hss Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Electrical | FUCHS |  | IFI | OB | 100%
14962 | I491TE99-0LFEB02-001-001 | Hc-Cabel Fixing Elektrode Arm Side Flexibles Hss Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Electrical | FUCHS |  | IFI | OB | 100%
14963 | I491TE99-0LFEH01-001-001 | High Current Cabel Flexibles Hcs Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Electrical | FUCHS |  | IFI | OB | 100%
14964 | I491TE99-0LFIF01-001-001 | High Current System Ladle Furnace | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Electrical | FUCHS |  | IFI | OB | 100%
14965 | I491TE99-0LFIF03-001-001 | High Current System Ladle Furnace | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Electrical | FUCHS |  | IFI | OB | 100%
14966 | I491TE99-0LFIH01-001-001 | Electrode Arms Ladle Furnace | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
14967 | I491TE99-0LFIH02-001-001 | Electrode Arm Ladle Furnace | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
14968 | I491TE99-0LFIH03-001-001 | Support Arm Phase 1 Electrode Arms Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
14969 | I491TE99-0LFIH04-001-001 | Support Arm Phase 1 Electrode Arm Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
14970 | I491TE99-0LFIH05-001-001 | Support Arm Phase 2 Electrode Arms Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
14971 | I491TE99-0LFIH06-001-001 | Support Arm Phase 2 Electrode Arms Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
113568 | I491TE99-0LFIH07-001-001 | Support Arm Phase 3 Electrode Arms Lf | 01 | 2015-05-06 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | TAM | 2015-05-27 16:07 | IFI | OB | 100%
14973 | I491TE99-0LFIH08-001-001 | Support Arm Phase 3 Electrode Arms Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
14974 | I491TE99-0LFLE01-001-001 | Limit Switches Arrangement Electro Roof Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Automation and Instrumentation | FUCHS |  | IFI | OB | 100%
14975 | I491TE99-0LFLE02-001-001 | Limit Switches Arrangement Electro Roof Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Automation and Instrumentation | FUCHS |  | IFI | OB | 100%
14976 | I491TE99-0LFLE03-001-001 | Limit Switches Arrangement Electro Roof Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Automation and Instrumentation | FUCHS |  | IFI | OB | 100%
14977 | I491TE99-0LFLE04-001-001 | Limit Switches Arrangement Electro Roof Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Automation and Instrumentation | FUCHS |  | IFI | OB | 100%
14978 | I491TE99-0LFLE05-001-001 | Limit Switches Arrangement Electro Roof Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Automation and Instrumentation | FUCHS |  | IFI | OB | 100%
14979 | I491TE99-0LFLE06-001-001 | Limit Switches Arrangement Electro Roof Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Automation and Instrumentation | FUCHS |  | IFI | OB | 100%
14980 | I491TE99-0LFLE07-001-001 | Limit Switches Arrangement Electro Roof Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Automation and Instrumentation | FUCHS |  | IFI | OB | 100%
14981 | I491TE99-0LFLE08-001-001 | Limit Switches Arrangement Electro Roof Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Automation and Instrumentation | FUCHS |  | IFI | OB | 100%
14982 | I491TE99-0LFLE09-001-001 | Limit Switches Arrangement Electro Roof Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Automation and Instrumentation | FUCHS |  | IFI | OB | 100%
14983 | I491TE99-0LFLE10-001-001 | Limit Switches Arrangement Electro Roof Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Automation and Instrumentation | FUCHS |  | IFI | OB | 100%
14984 | I491TE99-0LFLW01-001-001 | Electro Electrode Lifting Device Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
14985 | I491TE99-0LFRF01-001-001 | Flexible Bends Flexibles Cables Hcs Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Electrical | FUCHS |  | IFI | OB | 100%
130094 | I491TE99-0LFRL01-001-001 | D-20.00.001.504 ELECTRO - ROOF LIFTING DEVICE LF | 00 | 2017-01-09 09:01 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | FUCHS | 2017-01-09 09:01 | IFI | OB | 100%
14986 | I491TE99-0LFRL02-001-001 | Electro Roof Lifting Device Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
14989 | I491TE99-0MEAA91-001-003 | Basic Data Of Main Elc Substation(High Voltage Single Line Diagram) | 02 | 2012-01-15 | Indeterminate | Drawing | Basic | Steel Making Electrical Substation | Mechanical | TAM |  | IFC | AFC | 100%
14991 | I491TE99-0MEAA91-002-002 | Main Substation Hv Single Line Diagram | 01 | 2012-01-15 | Indeterminate | Miscellaneous(MISC) | Basic | Main Electrical Substation And Distribution Network | Electrical | TAM |  | IFC | AFC | 100%
14993 | I491TE99-0MEBD92-001-002 | Technical Specification And Data Sheet For Buswork | 01 | 2012-01-17 | Indeterminate | Miscellaneous(MISC) | Basic | Main Electrical Substation And Distribution Network | Electrical | TAM |  | IFC | AFC | 100%
14995 | I491TE99-0MECE92-001-002 | Technical Specification And Data Sheet For Capacitive Voltage Transformers | 01 | 2012-01-17 | Indeterminate | Miscellaneous(MISC) | Basic | Main Electrical Substation And Distribution Network | Electrical | TAM |  | IFC | AFC | 100%
14997 | I491TE99-0MECG92-001-002 | Technical Specification And Data Sheet For Hv Outdoor Circuit Breakers | 01 | 2012-01-17 | Indeterminate | Miscellaneous(MISC) | Basic | Main Electrical Substation And Distribution Network | Electrical | TAM |  | IFC | AFC | 100%
14999 | I491TE99-0MECX92-001-002 | Technical Specification And Data Sheet For Current Transformers | 01 | 2012-01-17 | Indeterminate | Miscellaneous(MISC) | Basic | Main Electrical Substation And Distribution Network | Electrical | TAM |  | IFC | AFC | 100%
15001 | I491TE99-0MEDC92-001-002 | Technical Specification And Data Sheet For Low Voltage Ac System | 01 | 2012-01-17 | Indeterminate | Miscellaneous(MISC) | Basic | Main Electrical Substation And Distribution Network | Electrical | TAM |  | IFC | AFC | 100%
15003 | I491TE99-0MEDK92-001-002 | Technical Specification And Data Sheet For Hv Disconnectors And | 01 | 2012-01-17 | Indeterminate | Miscellaneous(MISC) | Basic | Main Electrical Substation And Distribution Network | Electrical | TAM |  | IFC | AFC | 100%
15005 | I491TE99-0MEDO92-001-002 | Technical Specification And Data Sheet For Distributed Control System | 01 | 2012-01-17 | Indeterminate | Miscellaneous(MISC) | Basic | Main Electrical Substation And Distribution Network | Electrical | TAM |  | IFC | AFC | 100%
114874 | I491TE99-0MEIR91-001-001 | PROTECTION BLOCK DIGRAM FOR SVC SYSTEM | 01 | 2016-02-02 | Indeterminate | Miscellaneous(MISC) | Basic | Main Electrical Substation And Distribution Network | Electrical | NR Electric | 2016-02-03 11:56 | IFC | AFC | 100%
114872 | I491TE99-0MEIR91-002-001 | SVC System Cooling System Drawing | 00 | 2016-02-02 | Indeterminate | Miscellaneous(MISC) | Basic | Main Electrical Substation And Distribution Network | Electrical | NR Electric | 2016-02-03 11:52 | IFA | AFC | 100%
114859 | I491TE99-0MEIR91-003-001 | SVC System Insulators Technichal Specification and Data sheet | 00 | 2016-02-02 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | NR Electric | 2016-02-03 11:44 | IFI | OB | 100%
114860 | I491TE99-0MEIR91-004-001 | DISCONNECTORS DATASHEET FOR SVC SYSTEM | 01 | 2016-02-02 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | NR Electric | 2016-02-03 11:44 | IFI | OB | 100%
114861 | I491TE99-0MEIR91-005-001 | REACTORS DATASHEET FOR SVC SYSTEM | 01 | 2016-02-02 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | NR Electric | 2016-02-03 11:45 | IFI | OB | 100%
114862 | I491TE99-0MEIR91-006-001 | CAPACITORS DATASHEET FOR SVC SYSTEM | 01 | 2016-02-02 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | NR Electric | 2016-02-03 11:45 | IFI | OB | 100%
114863 | I491TE99-0MEIR91-007-001 | THYRISTOR VALVES DATASHEET FOR SVC SYSTEM | 01 | 2016-02-02 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | NR Electric | 2016-02-03 11:45 | IFI | OB | 100%
114864 | I491TE99-0MEIR91-008-001 | CURRENT TRANSFORMERS DATASHEET FOR SVC SYSTEM | 01 | 2016-02-02 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | NR Electric | 2016-02-03 11:45 | IFI | OB | 100%
114865 | I491TE99-0MEIR91-009-001 | SVC System Reactors Routine Test Report | 00 | 2016-02-02 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | NR Electric | 2016-02-03 11:45 | IFI | OB | 100%
114866 | I491TE99-0MEIR91-010-001 | SVC System Insulators Routine Test Report | 00 | 2016-02-02 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | NR Electric | 2016-02-03 11:45 | IFI | OB | 100%
116065 | I491TE99-0MEIR91-011-001 | SVC System Disconnector Routine Test Report | 00 | 2016-07-12 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | TAM | 2016-07-13 09:16 | IFI | OB | 100%
114867 | I491TE99-0MEIR91-012-001 | SVC System Capacitors Routine Test Report | 00 | 2016-02-02 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | NR Electric | 2016-02-03 11:45 | IFI | OB | 100%
114868 | I491TE99-0MEIR91-013-001 | SVC System CTs Routine Test Report | 00 | 2016-02-02 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | NR Electric | 2016-02-03 11:45 | IFI | OB | 100%
114869 | I491TE99-0MEIR91-014-001 | SVC System Cooling System Routine Test Report | 00 | 2016-02-02 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | NR Electric | 2016-02-03 11:45 | IFI | OB | 100%
114870 | I491TE99-0MEIR91-015-001 | SVC System Control System Factory Test Report | 00 | 2016-02-02 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | NR Electric | 2016-02-03 11:45 | IFI | OB | 100%
115192 | I491TE99-0MEIR91-016-001 | Iran Bardsir Steel SVC Proposal | 00 | 2016-05-03 | Indeterminate | Drawing | Detail | Main Electrical Substation And Distribution Network | Electrical | TAM | 2016-05-10 13:40 | IFI | OB | 100%
115191 | I491TE99-0MEIR91-017-001 | Analysis of 2 CB & 3CB Design for SVC System | 00 | 2016-05-03 | Indeterminate | Drawing | Detail | Main Electrical Substation And Distribution Network | Electrical | TAM | 2016-05-10 13:40 | IFI | OB | 100%
115190 | I491TE99-0MEIR91-018-001 | Inspection Release Note for SVC System | 00 | 2016-05-03 | Indeterminate | Drawing | Detail | Main Electrical Substation And Distribution Network | Electrical | TAM | 2016-05-10 13:40 | IFI | OB | 100%
115189 | I491TE99-0MEIR91-019-001 | Cooling System Manual for SVC System | 00 | 2016-05-03 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | TAM | 2016-05-10 13:40 | IFI | OB | 100%
115188 | I491TE99-0MEIR91-020-001 | Cooling System Datasheet for SVC System | 00 | 2016-05-03 | Indeterminate | Drawing | Detail | Main Electrical Substation And Distribution Network | Electrical | TAM | 2016-05-10 13:40 | IFI | OB | 100%
15007 | I491TE99-0MELA92-001-002 | Technical Specification And Data Sheet For Line Traps | 01 | 2012-01-17 | Indeterminate | Miscellaneous(MISC) | Basic | Main Electrical Substation And Distribution Network | Electrical | TAM |  | IFC | AFC | 100%
15009 | I491TE99-0MELN92-001-002 | Technical Specification And Data Sheet For Surge Arresters | 01 | 2012-01-17 | Indeterminate | Miscellaneous(MISC) | Basic | Main Electrical Substation And Distribution Network | Electrical | TAM |  | IFC | AFC | 100%
15011 | I491TE99-0MEOU92-001-002 | Technical Specification For Optical Access Multiplexer | 01 | 2012-01-17 | Indeterminate | Miscellaneous(MISC) | Basic | Main Electrical Substation And Distribution Network | Electrical | TAM |  | IFC | AFC | 100%
15013 | I491TE99-0MEPL92-001-002 | Technical Specification And Data Sheet For Plc | 01 | 2012-01-17 | Indeterminate | Miscellaneous(MISC) | Basic | Main Electrical Substation And Distribution Network | Electrical | TAM |  | IFC | AFC | 100%
15015 | I491TE99-0MEPS92-001-002 | Technical Specification For Dispatching System | 01 | 2012-01-17 | Indeterminate | Miscellaneous(MISC) | Basic | Main Electrical Substation And Distribution Network | Electrical | TAM |  | IFC | AFC | 100%
15017 | I491TE99-0METP92-001-002 | Technical Specification And Data Sheet For Tps | 01 | 2012-01-17 | Indeterminate | Miscellaneous(MISC) | Basic | Main Electrical Substation And Distribution Network | Electrical | TAM |  | IFC | AFC | 100%
15019 | I491TE99-0MEYC92-001-002 | Technical Specification And Data Sheet For Protection And Control System | 01 | 2012-01-17 | Indeterminate | Miscellaneous(MISC) | Basic | Main Electrical Substation And Distribution Network | Electrical | TAM |  | IFC | AFC | 100%
15021 | I491TE99-0MEYD92-001-002 | Technical Specification And Data Sheet For Low Voltage Dc System | 01 | 2012-01-17 | Indeterminate | Miscellaneous(MISC) | Basic | Main Electrical Substation And Distribution Network | Electrical | TAM |  | IFC | AFC | 100%
15022 | I491TE99-0MMCT01-002-001 | Underground & Abovground Layouts & Sections Of Control & Power Cables For Inside & Outside Of Building (Water Cooling System) (1-2) | 00 | 2013-07-24 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Automation and Instrumentation | FARABARD |  | IFA | AC |  | 95%
15023 | I491TE99-0MMCT01-002-002 | Underground & Abovground Layouts & Sections Of Control & Power Cables For Inside & Outside Of Building (Water Cooling System) (2-2) | 00 | 2013-07-24 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Automation and Instrumentation | FARABARD |  | IFA | AC |  | 95%
115205 | I491TE99-0MMCT01-002-003 | Underground & Aboveground Layouts & Sections…(Water Cooling System) 1-8 | 04 | 2016-05-04 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Electrical | TAM | 2016-05-10 15:26 | IFC | AFC | 100%
115092 | I491TE99-0MMCT01-002-004 | Underground & Aboveground Layouts & Sections…(Water Cooling System) 2-8 | 03 | 2016-03-16 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Electrical | TAM | 2016-04-02 16:14 | IFC | AFC | 100%
115093 | I491TE99-0MMCT01-002-005 | underground & abovground layouts & sections of control & power cables for inside & outside of building (Water Cooling System) 3-8 | 01 | 2016-03-16 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Electrical | TAM | 2016-04-02 16:14 | IFC | AFC | 100%
115206 | I491TE99-0MMCT01-002-006 | underground & abovground layouts & sections of control & power cables for inside & outside of building (Water Cooling System) 4-8 | 02 | 2016-05-04 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Electrical | TAM | 2016-05-10 15:27 | IFC | AFC | 100%
115095 | I491TE99-0MMCT01-002-007 | underground & abovground layouts & sections of control & power cables for inside & outside of building (Water Cooling System) 5-8 | 00 | 2016-03-16 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Electrical | TAM | 2016-04-02 16:14 | IFC | AFC | 100%
115096 | I491TE99-0MMCT01-002-008 | underground & abovground layouts & sections of control & power cables for inside & outside of building (Water Cooling System) 6-8 | 00 | 2016-03-16 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Electrical | TAM | 2016-04-02 16:14 | IFC | AFC | 100%
115097 | I491TE99-0MMCT01-002-009 | underground & abovground layouts & sections of control & power cables for inside & outside of building (Water Cooling System) 7-8 | 00 | 2016-03-16 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Electrical | TAM | 2016-04-02 16:14 | IFC | AFC | 100%
115098 | I491TE99-0MMCT01-002-010 | underground & abovground layouts & sections of control & power cables for inside & outside of building (Water Cooling System) 8-8 | 00 | 2016-03-16 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Electrical | TAM | 2016-04-02 16:14 | IFC | AFC | 100%
130247 | I491TE99-0MMCT01-004-001 | Ac UPS Sizing Calculation ( Water Treatment Plant) | 00 | 2017-01-16 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Automation and Instrumentation | TAM | 2017-01-22 09:40 | IFI | OB | 100%
133118 | I491TE99-0MMCT01-006-001 | EARTHING LAYOUT (CT01 & CT02 & Pump House ) | 04 | 2018-05-06 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Electrical | TAM | 2018-05-14 13:56 | IFC | AFC | 100%
15027 | I491TE99-0MXAA91-001-002 | Basic Engineering For Substation Monitoring | 01 | 2012-07-22 | Indeterminate | Miscellaneous(MISC) | Basic | Steel Making Electrical Substation | Automation and Instrumentation | TAM |  | IFC | AC |  | 95%
16627 | I491TG01-0MMCT01-001-003 | Plot Plan And Equipment Layout For Cooling System (Ct01 & Ct02) | 03 | 2014-02-19 08:56 | Indeterminate | Drawing | Basic | Water Treatment & Cooling System | Mechanical | TAM | 2014-02-19 08:56 | IFC | AFC | 100%
16565 | I491TG01-0MXAA91-001-001 | General Layout | 02 | 2010-12-27 | Indeterminate | Drawing | Basic | General | Mechanical | TAM |  | IFA | AC |  | 95%
129793 | I491TG02-0ASCP01-001-001 | ASP Turbo Compressor Maintenance Space | 00 | 2016-11-12 09:25 | Indeterminate | Drawing | Detail | Air Separation Plant Main Building | Mechanical | TAM | 2016-11-12 09:25 | IFI | OB | 100%
132050 | I491TG02-0CCAA91-001-001 | Sheet 1 of 4 General Layout -Plan VIEW GP08VB-HC11-G0100-BD001_001 | 05 | 2017-11-26 09:09 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Mechanical | INTECO | 2017-11-26 09:09 | IFC | AFC | 100%
132051 | I491TG02-0CCAA91-001-002 | Sheet 2 of 4 Section A-A-GP08VB-HC11-G0100-BD002_001 | 05 | 2017-11-26 09:10 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Mechanical | INTECO | 2017-11-26 09:10 | IFC | AFC | 100%
112711 | I491TG02-0CCAA91-001-003 | 6-Strand Billet Caster Layout-Topview | 01 | 2014-08-19 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Mechanical | INTECO | 2014-08-24 08:54 | IFA | AC |  | 95%
112712 | I491TG02-0CCAA91-001-004 | 6-Strand Billet Caster Layout-Sections | 01 | 2014-08-19 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Mechanical | INTECO | 2014-08-24 08:54 | IFA | AC |  | 95%
15038 | I491TG02-0CCAA91-001-005 | 6-Strand Billet Caster Layout-Sections | 00 | 2013-10-21 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Mechanical | INTECO |  | IFA | AC |  | 95%
15040 | I491TG02-0EAAA91-001-002 | Melt Shop General Layout And Sections | 01 | 2012-08-05 | Indeterminate | Drawing | Basic | Melt Shop | Mechanical | TAM |  | IFA | AC |  | 95%
15041 | I491TG02-0EAAA91-001-003 | Melt Shop General Layout Cross Section | 01 | 2012-08-05 | Indeterminate | Drawing | Basic | Melt Shop | Mechanical | TAM |  | IFA | AC |  | 95%
15042 | I491TG02-0EAAA91-001-004 | Melt Shop General Layout Cross Section | 01 | 2012-08-05 | Indeterminate | Drawing | Basic | Melt Shop | Mechanical | TAM |  | IFA | AC |  | 95%
15043 | I491TG02-0EAAA91-001-005 | Melt Shop General Layout Longitudinal Section | 01 | 2012-08-05 | Indeterminate | Drawing | Basic | Melt Shop | Mechanical | TAM |  | IFA | AC |  | 95%
15044 | I491TG02-0EAAA91-002-001 | Section Billet Storage Area (Option1) | 00 | 2011-04-24 | Indeterminate | Drawing | Basic | Melt Shop | Mechanical | TAM |  | IFA | AFC | 100%
15045 | I491TG02-0EAAA91-002-002 | Billet Storage Areasection Veiw (Option3) | 00 | 2011-04-24 | Indeterminate | Drawing | Basic | Melt Shop | Mechanical | TAM |  | IFA | AFC | 100%
15046 | I491TG02-0EAAA91-002-003 | Section Billet Storage Area (Option2) | 00 | 2011-04-24 | Indeterminate | Drawing | Basic | Melt Shop | Mechanical | TAM |  | IFA | AFC | 100%
15048 | I491TG02-0GC9101-001-002 | Location Of Boreholes And Testpit For Geotechnical Study | 01 | 2011-02-01 | Indeterminate | Drawing | Basic | General | Civil and Steel Structure | TAM |  | IFI | AC |  | 95%
15050 | I491TG02-0GCAA91-001-012 | Warehouse Foundation | 05 | 2011-07-11 | Indeterminate | Drawing | Detail | Warehouse | Civil and Steel Structure | IKS |  | IFC | AFC | 100%
15058 | I491TG02-0GCAA91-001-013 | Columns,Framing,Roof&Bracing Plan For Warehouse | 05 | 2011-07-11 | Indeterminate | Drawing | Detail | Warehouse | Civil and Steel Structure | IKS |  | IFC | AFC | 100%
113467 | I491TG02-0LAAA91-001-001 | LF laboratory layout | 00 | 2015-03-16 | Indeterminate | Drawing | Basic | Laboratory | Mechanical | TAM | 2015-04-04 13:36 | IFA | AFC | 100%
130064 | I491TG02-0LAAM91-001-001 | LF & CCM Laboratory layout 1st Floor | 02 | 2017-01-02 10:25 | Indeterminate | Drawing | Basic | Laboratory | Mechanical | TAM | 2017-01-02 10:25 | IFC | AFC | 100%
130065 | I491TG02-0LAAM91-001-002 | LF & CCM Laboratory layout 2nd Floor | 01 | 2017-01-02 10:25 | Indeterminate | Drawing | Basic | Laboratory | Mechanical | TAM | 2017-01-02 10:25 | IFC | AFC | 100%
15065 | I491TG02-0MDAA91-001-002 | Material Handling System Sections & Views | 01 | 2012-09-08 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | TAM |  | IFA | AC |  | 95%
15066 | I491TG02-0MDAA91-001-003 | Material Handling System Sections & Views(Eaf) | 01 | 2012-09-08 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | TAM |  | IFA | AC |  | 95%
15067 | I491TG02-0MDAA91-001-004 | Material Handling System Sections & Views | 01 | 2012-09-08 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | TAM |  | IFA | AC |  | 95%
15068 | I491TG02-0MDAA91-001-005 | Material Handling System Sections & Views(Lf) | 01 | 2012-09-08 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | TAM |  | IFA | AC |  | 95%
111432 | I491TG02-0MDAA91-001-006 | Material Handling System General Layout For Eaf | 01 | 2014-01-05 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | TAM | 2014-04-19 17:56 | IFC | AFC | 100%
111433 | I491TG02-0MDAA91-002-001 | Material Handling System General Layout For Eafsection A-A & B-B & C-C & D-D | 01 | 2014-01-05 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | FUCHS | 2014-04-19 17:56 | IFC | AFC | 100%
111434 | I491TG02-0MDAA91-003-001 | Material Handling System General Layout For Eaf Section E-E & F-F & G-G | 01 | 2014-01-05 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | FUCHS | 2014-04-19 17:56 | IFC | AFC | 100%
111435 | I491TG02-0MDAA91-004-001 | Material Handling System General Layout For Eaf Section H-H & J-J & K-K | 01 | 2014-01-05 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | FUCHS | 2014-04-19 17:56 | IFC | AFC | 100%
111436 | I491TG02-0MDAA91-005-001 | Material Handling System General Layout For Eaf Section L-L | 01 | 2014-01-05 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | FUCHS | 2014-04-19 17:56 | IFC | AFC | 100%
111437 | I491TG02-0MDAA91-006-001 | Material Handling System General Layout For Eaf Plan At Level +0.000 | 01 | 2014-01-05 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | FUCHS | 2014-04-19 17:56 | IFC | AFC | 100%
111438 | I491TG02-0MDAA91-007-001 | Material Handling System General Layout For Eaf Plan At Level+4.000 &+6.600 | 01 | 2014-01-05 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | FUCHS | 2014-04-19 17:56 | IFC | AFC | 100%
111439 | I491TG02-0MDAA91-008-001 | Material Handling System General Layout For Eaf Plan At Level+8.700 | 01 | 2014-01-05 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | FUCHS | 2014-04-19 17:56 | IFC | AFC | 100%
111440 | I491TG02-0MDAA91-009-001 | Material Handling System General Layout For Eaf Plan At Level+11.100 | 01 | 2014-01-05 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | FUCHS | 2014-04-19 17:56 | IFC | AFC | 100%
111441 | I491TG02-0MDAA91-010-001 | Material Handling System General Layout For Eaf Plan At Level+12.100 | 01 | 2014-01-05 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | FUCHS | 2014-04-19 17:56 | IFC | AFC | 100%
111442 | I491TG02-0MDAA91-011-001 | Material Handling System General Layout For Eaf Plan At Level+16.000 &+17.000&+17.500&+18.200 | 01 | 2014-01-05 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | FUCHS | 2014-04-19 17:56 | IFC | AFC | 100%
111443 | I491TG02-0MDAA91-012-001 | Material Handling System General Layout For Eaf Plan At Level+21.500 | 01 | 2014-01-05 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | FUCHS | 2014-04-19 17:56 | IFC | AFC | 100%
111444 | I491TG02-0MDAA91-013-001 | Material Handling System General Layout For Eaf Eaf Plan At Level+24.700 | 01 | 2014-01-05 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | FUCHS | 2014-04-19 17:56 | IFC | AFC | 100%
111445 | I491TG02-0MDAA91-014-001 | Material Handling System General Layout For Eaf Plan At Level+28.100 | 01 | 2014-01-05 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | FUCHS | 2014-04-19 17:56 | IFC | AFC | 100%
16665 | I491TG02-0MDAA91-021-001 | Material Handling System General Layout And Section For Lf Area | 01 | 2014-01-05 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | FUCHS | 2014-02-19 09:42 | IFC | AFC | 100%
16666 | I491TG02-0MDAA91-022-001 | Material Handling System General Layout For Lf Area Plan At Level +0.000,+10.27,+11.5,+12.8,+14.3 | 01 | 2014-01-05 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | FUCHS | 2014-02-19 09:42 | IFC | AFC | 100%
16667 | I491TG02-0MDAA91-023-001 | Material Handling System General Layout For Lf Area Plan At Level +15.800,21.500,24.700 | 01 | 2014-01-05 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | FUCHS | 2014-02-19 09:43 | IFC | AFC | 100%
112411 | I491TG02-0MDAA91-041-001 | Material Handling System General Layout For Ferro Alloy & Lime & Dolomite | 01 | 2014-06-25 11:18 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | TAM | 2014-06-25 11:18 | IFC | AFC | 100%
112412 | I491TG02-0MDAA91-042-001 | Material Handling System General Layout For Ferro Alloy & Lime & Dolomite | 01 | 2014-06-25 11:19 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | TAM | 2014-06-25 11:19 | IFC | AFC | 100%
15088 | I491TG02-0MDAA91-051-002 | General Arrangement For Dri Charging | 01 | 2013-07-23 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | DATIS |  | IFC | AC |  | 95%
15095 | I491TG02-0MEAA91-001-007 | Main Electrical Sub Station Layout(400 Kv Switch Yard) | 04 | 2011-10-09 | Indeterminate | Miscellaneous(MISC) | Basic | Main Electrical Substation And Distribution Network | Mechanical | TAM |  | IFC | AFC | 100%
113048 | I491TG02-0MEIR91-001-001 | GENERAL LAYOUT FOR SVC SYSTEM | 01 | 2014-10-25 | Indeterminate | Drawing | Basic | Main Electrical Substation And Distribution Network | Electrical | NR Electric | 2014-10-26 13:14 | IFI | OB | 100%
15097 | I491TG02-0MKGN91-001-002 | Water Cooling System Plant Layout | 01 | 2012-04-29 | Indeterminate | Drawing | Basic | Water Treatment & Cooling System | Mechanical | TAM |  | IFA | AC |  | 95%
15099 | I491TG02-0MVAA91-001-002 | Streets Cross Sections | 02 | 2013-05-14 | Indeterminate | Drawing | Basic | General | Civil and Steel Structure | TAM |  | IFC | AC |  | 95%
15100 | I491TG02-0MXAA91-001-002 | GENERAL LAYOUT (WTP BATTERY LIMITS) | 04 | 2011-07-23 | Indeterminate | Drawing | Basic | General | Mechanical | TAM |  | IFA | AC |  | 95%
15108 | I491TG02-0MXAA91-002-006 | General Layout (Plants Arrangments) | 01 | 2011-10-05 | Indeterminate | Drawing | Basic | General | Mechanical | TAM |  | IFA | AC |  | 95%
15109 | I491TG02-0MXAA91-002-007 | General Layout (Plants Arrangments) Option 1 | 02 | 2013-12-29 07:21 | Indeterminate | Miscellaneous(MISC) | Basic | General | Mechanical | TAM |  | IFA | AC |  | 95%
15110 | I491TG02-0MXAA91-002-008 | General Layout (Plants Arrangments) Option 2 | 02 | 2011-10-23 | Indeterminate | Miscellaneous(MISC) | Basic | General | Mechanical | TAM |  | IFA | AC |  | 95%
15111 | I491TG02-0MXAA91-002-009 | General Layout (Plants Arrangments) Option 3 | 02 | 2011-10-23 | Indeterminate | Miscellaneous(MISC) | Basic | General | Mechanical | TAM |  | IFA | AC |  | 95%
15105 | I491TG02-0MXAA91-002-015 | General Layout | 08 | 2013-06-27 | Indeterminate | Miscellaneous(MISC) | Basic | General | Mechanical | TAM |  | IFA | A | 100%
15115 | I491TG02-0MXAA91-005-002 | Long Vehicle Turning Illustration | 02 | 2013-05-14 | Indeterminate | Drawing | Basic | General | Civil and Steel Structure | TAM |  | IFC | AC |  | 95%
15116 | I491TG02-0MXAA91-005-003 | Long Vehicle Turning Illustration Part 1 | 02 | 2013-05-14 | Indeterminate | Drawing | Basic | General | Civil and Steel Structure | TAM |  | IFC | AC |  | 95%
15117 | I491TG02-0MXAA91-005-004 | Long Vehicle Turning Illustration Part 2 | 02 | 2013-05-14 | Indeterminate | Drawing | Basic | General | Civil and Steel Structure | TAM |  | IFC | AC |  | 95%
15118 | I491TG02-0MXAA91-005-005 | Long Vehicle Turning Illustration Part 3 | 02 | 2013-05-14 | Indeterminate | Drawing | Basic | General | Civil and Steel Structure | TAM |  | IFC | AC |  | 95%
15119 | I491TG02-0MXAA91-005-006 | Long Vehicle Turning Illustration Part 4 | 02 | 2013-05-14 | Indeterminate | Drawing | Basic | General | Civil and Steel Structure | TAM |  | IFC | AC |  | 95%
15120 | I491TG02-0MXAA91-005-007 | Long Vehicle Turning Illustration Part 5 | 02 | 2013-05-14 | Indeterminate | Drawing | Basic | General | Civil and Steel Structure | TAM |  | IFC | AC |  | 95%
15126 | I491TG02-0MXAA91-006-006 | Location Of Boreholes And Testpit For Geotechnical Study | 06 | 2012-01-02 | Indeterminate | Miscellaneous(MISC) | Basic | General | Civil and Steel Structure | INTECO |  | IFC | AFC | 100%
133145 | I491TG02-0MXEG01-001-001 | MELTSHOP& CCM DIESEL GENERATORS ROOM LAYOUT | 03 | 2018-05-15 | Indeterminate | Drawing | Basic | General | Electrical | TAM | 2018-05-19 09:16 | IFC | AFC | 100%
16574 | I491TG02-0PXLM02-001-001 | Ladle Debricking Area | 01 | 2013-12-03 | Indeterminate | Drawing | Basic | Melt Shop Auxiliaries | Mechanical | INTECO | 2014-02-16 11:37 | IFC | AFC | 100%
15130 | I491TG02-0PXSM02-001-003 | Ladle Slag Dumping Area | 01 | 2013-05-12 | Indeterminate | Drawing | Basic | Melt Shop Auxiliaries | Civil and Steel Structure | INTECO |  | IFC | AFC | 100%
15131 | I491TG02-0PXSM03-001-002 | Meltshop Emergency Pit | 01 | 2013-05-18 | Indeterminate | Drawing | Basic | Melt Shop Auxiliaries | Mechanical | INTECO |  | IFC | AFC | 100%
114843 | I491TG02-0PXXL15-001-001 | Pneumatic tube system layout | 00 | 2016-01-30 | Indeterminate | Drawing | Basic | Laboratory | Mechanical | TAM | 2016-02-02 09:54 | IFA | AC |  | 95%
114798 | I491TG02-0RXEA91-002-001 | Purging Station | 02 | 2016-01-12 14:52 | Indeterminate | Drawing | Basic | Melt Shop Auxiliaries | Mechanical | INTECO | 2016-01-12 14:52 | IFC | AFC | 100%
114723 | I491TG02-0RXGA91-001-001 | EMERGENCY STIRRING LANCE | 00 | 2015-11-28 | Indeterminate | Drawing | Detail | Ladle Furnace Auxiliary | Mechanical | CEBA | 2015-12-05 15:09 | IFA | AC |  | 95%
114730 | I491TG02-0RXLY01-001-001 | TEMPERATURE & SAMPLING MANIPULATOR | 00 | 2015-11-28 | Indeterminate | Drawing | Detail | Ladle Furnace Auxiliary | Mechanical | CEBA | 2015-12-07 10:05 | IFA | AC |  | 95%
114718 | I491TG02-0RXWH91-001-001 | Wire Feeder-TS Mani-emergency Lance ASSEMBLY 072-DA-11959-3 | 00 | 2015-11-28 | Indeterminate | Drawing | Detail | Ladle Furnace Auxiliary | Mechanical | TAM | 2015-12-01 10:05 | IFA | A | 100%
15164 | I491TG02-0SHAA01-002-002 | Scrap Yard Layout | 06 | 2012-04-23 | Indeterminate | Drawing | Basic | Melt Shop Scrap Yard | Civil and Steel Structure | TAM |  | IFC | AFC | 100%
15134 | I491TG02-0SHAA91-002-002 | Scrap Yard Architectural Drawing | 02 | 2011-05-25 | Indeterminate | Drawing | Detail | Melt Shop Scrap Yard | Civil and Steel Structure | TAM |  | IFA | AC |  | 95%
15138 | I491TG02-0SHAA91-002-006 | Scrap Yard Layout | 05 | 2011-11-02 | Indeterminate | Miscellaneous(MISC) | Basic | Melt Shop Scrap Yard | Mechanical | TAM |  | IFA | AC |  | 95%
15140 | I491TG02-0SXBT02-001-002 | Empty Ladle Transfer Car | 01 | 2013-01-28 | Indeterminate | Drawing | Basic | Melt Shop Auxiliaries | Mechanical | INTECO |  | IFC | AFC | 100%
114746 | I491TG02-0SXCJ91-001-001 | Sheet 1of2 Carbon Injection Line DN40 D-36.00.000.004_REV.A sheet 1 | 00 | 2015-12-06 | Indeterminate | Drawing | Basic | Eaf Auxiliaries | Mechanical | FUCHS | 2015-12-07 11:11 | IFA | AC |  | 95%
114747 | I491TG02-0SXCJ91-001-002 | Sheet 2of2 Carbon Injection Line DN40 D-36.00.000.004_REV.A sheet 2 | 00 | 2015-12-06 | Indeterminate | Drawing | Basic | Eaf Auxiliaries | Mechanical | FUCHS | 2015-12-07 11:11 | IFA | AC |  | 95%
114748 | I491TG02-0SXCJ91-002-001 | Carbon Injection D-36.00.000.005 | 00 | 2015-12-06 | Indeterminate | Drawing | Basic | Eaf Auxiliaries | Mechanical | FUCHS | 2015-12-07 11:11 | IFA | AC |  | 95%
15142 | I491TG02-0SXFD91-001-002 | Lower Shell Breakout Stand & Relining Stand | 00 | 2013-11-04 | Indeterminate | Drawing | Basic | Melt Shop Auxiliaries | Mechanical | INTECO |  | IFC | AFC | 100%
15144 | I491TG02-0SXFM03-001-002 | Lower Shell Parking Position Station | 01 | 2012-10-31 | Indeterminate | Drawing | Basic | Melt Shop Auxiliaries | Mechanical | FUCHS |  | IFC | AFC | 100%
114799 | I491TG02-0SXFM03-001-004 | Upper Shell Stand | 03 | 2016-01-12 14:54 | Indeterminate | Drawing | Basic | Melt Shop Auxiliaries | Mechanical | FUCHS | 2016-01-12 14:54 | IFC | AFC | 100%
114633 | I491TG02-0SXFM03-002-001 | EAF Roof Station | 02 | 2015-10-26 11:20 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | FUCHS | 2015-10-26 11:20 | IFC | AFC | 100%
117032 | I491TG02-0SXHB91-002-003 | ASSEMBLY HORIZONTAL LADLE PREHEATER | 05 | 2016-07-26 11:02 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | TAM | 2016-07-26 11:02 | IFC | AFC | 100%
114738 | I491TG02-0SXHB91-003-001 | ASSEMBLY VERTICAL LADLE PREHEATER | 01 | 2015-11-30 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | CEBA | 2015-12-07 10:47 | IFC | AFC | 100%
114678 | I491TG02-0SXLD91-001-001 | ASSEMBLY VERTICAL LADLE DRYER | 02 | 2015-11-22 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | TAM | 2015-11-23 11:25 | IFC | AC |  | 95%
15153 | I491TG02-0SXLI91-001-002 | Ladle Relining Station | 04 | 2012-09-18 | Indeterminate | Miscellaneous(MISC) | Basic | Melt Shop Auxiliaries | Mechanical | INTECO |  | IFA | AFC | 100%
15156 | I491TG02-0TBAA91-002-002 | Lime And Ferroalloy Storage Area Layout | 01 | 2011-07-09 | Indeterminate | Drawing | Basic | Melt Shop Lime And Ferroalloy Storage | Mechanical | TAM |  | IFA | AC |  | 95%
15160 | I491TG02-0TBAA91-003-004 | Lime And Ferroalloy Storage Area Layout 800000 | 03 | 2012-01-28 | Indeterminate | Drawing | Basic | Melt Shop Lime And Ferroalloy Storage | Mechanical | TAM |  | IFC | AFC | 100%
114686 | I491TG04-0ASCT01-001-001 | Air cooling Tower foundation Drawing | 00 | 2015-11-24 15:03 | Indeterminate | Drawing | Basic | Air Separation Plant Main Building | Mechanical | Fortune | 2015-11-24 15:03 | IFA | AFC | 100%
114853 | I491TG04-0ASCT01-002-001 | Water Cooling Tower Foundation Drawing | 00 | 2016-02-01 | Indeterminate | Drawing | Basic | Air Separation Plant | Mechanical | Fortune | 2016-02-03 11:37 | IFA | A | 100%
114687 | I491TG04-0ASIJ01-001-001 | Cold box foundation drawing 1-3 | 00 | 2015-11-24 15:03 | Indeterminate | Drawing | Basic | Air Separation Plant Main Building | Mechanical | Fortune | 2015-11-24 15:03 | IFA | AFC | 100%
114689 | I491TG04-0ASIJ01-001-002 | Cold box foundation drawing 2-3 | 00 | 2015-11-24 15:03 | Indeterminate | Drawing | Basic | Air Separation Plant Main Building | Mechanical | Fortune | 2015-11-24 15:03 | IFA | AFC | 100%
114688 | I491TG04-0ASIJ01-001-003 | Cold box foundation drawing 3-3 | 00 | 2015-11-24 15:03 | Indeterminate | Drawing | Basic | Air Separation Plant Main Building | Mechanical | Fortune | 2015-11-24 15:03 | IFA | AFC | 100%
114690 | I491TG04-0ASPS01-001-001 | PPU Skid Foundation Drawing | 00 | 2015-11-24 15:04 | Indeterminate | Drawing | Basic | Air Separation Plant Main Building | Mechanical | Fortune | 2015-11-24 15:04 | IFA | AFC | 100%
116090 | I491TG04-0ASPU01-001-001 | mould Liquid Oxygen Back up Pump foundation dwg | 00 | 2016-07-13 10:36 | Indeterminate | Drawing | Basic | Air Separation Plant | Mechanical | TAM | 2016-07-13 10:36 | IFI | OB | 100%
116091 | I491TG04-0ASPU02-001-001 | Liquid argon Back up Pump foundation dwg | 00 | 2016-07-13 10:36 | Indeterminate | Drawing | Basic | Air Separation Plant | Mechanical | TAM | 2016-07-13 10:36 | IFI | OB | 100%
116092 | I491TG04-0ASPU03-001-001 | Liquid Nitrogen Back up Pump foundation dwg | 00 | 2016-07-13 10:37 | Indeterminate | Drawing | Basic | Air Separation Plant | Mechanical | TAM | 2016-07-13 10:37 | IFI | OB | 100%
116093 | I491TG04-0ASPU04-001-001 | Liquid Nitrogen process Pump foundation dwg | 00 | 2016-07-13 10:37 | Indeterminate | Drawing | Basic | Air Separation Plant | Mechanical | TAM | 2016-07-13 10:37 | IFI | OB | 100%
114702 | I491TG04-0ASSL02-001-001 | Oxygen Silencer Foundation Drawing | 00 | 2015-11-24 15:06 | Indeterminate | Drawing | Detail | Air Separation Plant Main Building | Mechanical | Fortune | 2015-11-24 15:06 | IFA | AC |  | 95%
114703 | I491TG04-0ASSL03-001-001 | Nitrogen Silencer Foundation Drawing | 00 | 2015-11-24 15:06 | Indeterminate | Drawing | Detail | Air Separation Plant Main Building | Mechanical | Fortune | 2015-11-24 15:06 | IFA | AC |  | 95%
116094 | I491TG04-0ASSS01-001-001 | PIPE RACK FOUNDATION | 00 | 2016-07-13 10:37 | Indeterminate | Drawing | Basic | Air Separation Plant | Mechanical | TAM | 2016-07-13 10:37 | IFI | OB | 100%
114691 | I491TG04-0ASTK01-001-001 | Liquid Oxygen Tank foundation drawing | 00 | 2015-11-24 15:04 | Indeterminate | Drawing | Basic | Air Separation Plant Main Building | Mechanical | Fortune | 2015-11-24 15:04 | IFA | AFC | 100%
114692 | I491TG04-0ASTK03-001-001 | Liquid Argon Tank Foundation Drawing | 00 | 2015-11-24 15:04 | Indeterminate | Drawing | Basic | Air Separation Plant Main Building | Mechanical | Fortune | 2015-11-24 15:04 | IFA | AFC | 100%
114693 | I491TG04-0ASTK04-001-001 | Oxygen buffer tank foundation drawing | 00 | 2015-11-24 15:04 | Indeterminate | Drawing | Basic | Air Separation Plant Main Building | Mechanical | Fortune | 2015-11-24 15:04 | IFA | AFC | 100%
114694 | I491TG04-0ASTK05-001-001 | Nitrogen buffer tank foundation drawing | 00 | 2015-11-24 15:04 | Indeterminate | Drawing | Basic | Air Separation Plant Main Building | Mechanical | Fortune | 2015-11-24 15:04 | IFA | AFC | 100%
115732 | I491TG04-0ASTK06-001-001 | Argon buffer tank foundation drawing | 00 | 2016-06-13 | Indeterminate | Drawing | Basic | Air Separation Plant Main Building | Mechanical | Fortune | 2016-06-14 14:10 | IFI | OB | 100%
114695 | I491TG04-0ASVS01-001-001 | Waste Liquid Vaporizer foundation drawing | 00 | 2015-11-24 15:05 | Indeterminate | Drawing | Basic | Air Separation Plant | Mechanical | Fortune | 2015-11-24 15:05 | IFA | AFC | 100%
114696 | I491TG04-0ASVS02-001-001 | Liquid oxygen vaporizer foundation drawing | 00 | 2015-11-24 15:05 | Indeterminate | Drawing | Basic | Air Separation Plant | Mechanical | Fortune | 2015-11-24 15:05 | IFA | AFC | 100%
114854 | I491TG04-0ASVS03-001-001 | Liquid Nitrogen Vaporizer Foundation Drawing | 00 | 2016-02-01 | Indeterminate | Drawing | Basic | Air Separation Plant | Mechanical | Fortune | 2016-02-03 11:38 | IFA | A | 100%
114855 | I491TG04-0ASVS04-001-001 | Liquid Argon Vaporizer Foundation Drawing | 00 | 2016-02-01 | Indeterminate | Drawing | Basic | Air Separation Plant | Mechanical | Fortune | 2016-02-03 11:38 | IFA | A | 100%
129630 | I491TG04-0ASVS05-001-001 | WASTER NITROGEN SILENCER FOUNDATION DRAWING(SL1201) | 00 | 2016-10-03 | Indeterminate | Drawing | Detail | Air Separation Plant | Mechanical | Fortune | 2016-10-04 10:48 | IFI | OB | 100%
114697 | I491TG04-0ASXX01-001-001 | DCAC Skid Foundation Drawing | 00 | 2015-11-24 15:05 | Indeterminate | Drawing | Basic | Air Separation Plant Main Building | Mechanical | Fortune | 2015-11-24 15:05 | IFA | AFC | 100%
114698 | I491TG04-0ASXX02-001-001 | Nitrogen Pressure Reducer Foundation Drawing | 00 | 2015-11-24 15:06 | Indeterminate | Drawing | Basic | Air Separation Plant Main Building | Mechanical | Fortune | 2015-11-24 15:06 | IFA | AFC | 100%
114699 | I491TG04-0ASXX03-001-001 | Argon Pressure Reducer Foundation Drawing | 00 | 2015-11-24 15:06 | Indeterminate | Drawing | Basic | Air Separation Plant Main Building | Mechanical | Fortune | 2015-11-24 15:06 | IFA | AFC | 100%
114700 | I491TG04-0ASXX04-001-001 | After Cooler Foundation Drawing | 00 | 2015-11-24 15:06 | Indeterminate | Drawing | Basic | Air Separation Plant Main Building | Mechanical | Fortune | 2015-11-24 15:06 | IFA | AFC | 100%
129469 | I491TG04-0ASXX05-002-001 | Oxygen Blast Wall Foundation | 00 | 2016-09-10 | Indeterminate | Drawing | Detail | Air Separation Plant | Mechanical | TAM | 2016-09-11 09:46 | IFI | OB | 100%
133222 | I491TG05-0ASAA91-001-001 | CABLE TRENCH LAYOUT AIR SEPARATION PLANT | 05 | 2018-05-30 | Indeterminate | Drawing | Detail | Air Separation Plant | Electrical | TAM | 2018-06-11 10:26 | IFC | AFC | 100%
130409 | I491TG05-0ASAA91-001-002 | CABLE TRENCH LAYOUT AIR SEPARATION PLANT CIVIL AND STRUCTURAL DETAILS | 02 | 2017-04-04 | Indeterminate | Drawing | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2017-04-09 11:31 | IFC | AC |  | 95%
115248 | I491TG05-0ASAA91-002-001 | CABLE CONDUIT LAYOUT Air Separation Plant | 00 | 2016-05-07 | Indeterminate | Drawing | Detail | Air Separation Plant | Electrical | Fortune | 2016-05-14 16:25 | IFI | OB | 100%
115249 | I491TG05-0ASAA91-003-001 | ELECTRICAL CABLE TRAY LAYOUT Air Separation Plant | 00 | 2016-05-07 | Indeterminate | Drawing | Detail | Air Separation Plant | Electrical | Fortune | 2016-05-14 16:25 | IFI | OB | 100%
115250 | I491TG05-0ASAA91-004-001 | CABLE ROUTE LAYOUT Air Separation Plant | 00 | 2016-05-07 | Indeterminate | Drawing | Detail | Air Separation Plant | Electrical | Fortune | 2016-05-14 16:25 | IFI | OB | 100%
114911 | I491TG05-0AUAA91-001-001 | Steel making plant underground routing layout for Automation 1-4 | 01 | 2016-02-13 | Indeterminate | Drawing | Basic | Automation and Control System | Automation and Instrumentation | TAM | 2016-02-14 15:52 | IFC | AC |  | 95%
114912 | I491TG05-0AUAA91-001-002 | Steel making plant underground routing layout for Automation 2-4 | 01 | 2016-02-13 | Indeterminate | Drawing | Basic | Automation and Control System | Automation and Instrumentation | TAM | 2016-02-14 15:52 | IFC | AC |  | 95%
114913 | I491TG05-0AUAA91-001-003 | Steel making plant underground routing layout for Automation 3-4 | 01 | 2016-02-13 | Indeterminate | Drawing | Basic | Automation and Control System | Automation and Instrumentation | TAM | 2016-02-14 15:52 | IFC | AC |  | 95%
114914 | I491TG05-0AUAA91-001-004 | Steel making plant underground routing layout for Automation 4-4 | 00 | 2016-02-13 | Indeterminate | Drawing | Basic | Automation and Control System | Automation and Instrumentation | TAM | 2016-02-14 15:52 | IFC | AC |  | 95%
15170 | I491TG05-0EAAA91-001-006 | Steel Making Plant Under Ground Main Cable Routing Layout | 04 | 2012-08-15 | Indeterminate | Drawing | Basic | General | Mechanical | TAM |  | IFC | AFC | 100%
15173 | I491TG05-0EAAA91-002-003 | Steel Making Plant Under Ground Power Cable Routing Layout | 01 | 2012-09-08 | Indeterminate | Drawing | Detail | Main Electrical Substation And Distribution Network | Electrical | TAM |  | IFC | AFC | 100%
15174 | I491TG05-0EAAA91-002-004 | Steel Making Plant Under Ground Power Cable Routing Layout | 01 | 2012-09-08 | Indeterminate | Drawing | Detail | Main Electrical Substation And Distribution Network | Electrical | TAM |  | IFC | AFC | 100%
15175 | I491TG05-0EAAA91-002-005 | Steel Making Plant Under Ground Power Cable Routing Layout | 01 | 2012-09-08 | Indeterminate | Drawing | Detail | Main Electrical Substation And Distribution Network | Electrical | TAM |  | IFC | AFC | 100%
15176 | I491TG05-0EAAA91-002-006 | Steel Making Plant Under Ground Power Cable Routing Layout | 01 | 2012-09-08 | Indeterminate | Drawing | Detail | Main Electrical Substation And Distribution Network | Electrical | TAM |  | IFC | AFC | 100%
112644 | I491TG05-0MBAA91-001-003 | Under Ground Pipes For Make Up Water Roots | 01 | 2013-07-24 | Indeterminate | Drawing | Detail | Media Distribution System | Piping & Utility | TAM | 2014-08-11 09:02 | IFC | AFC | 100%
112645 | I491TG05-0MBAA91-001-004 | Under Ground Pipes For Make Up Water Sections | 01 | 2013-07-24 | Indeterminate | Drawing | Detail | Media Distribution System | Piping & Utility | TAM | 2014-08-11 09:02 | IFC | AFC | 100%
115349 | I491TG05-0MDAA91-001-001 | Instrument Cable Route Layout (25 sheet) | 01 | 2016-05-17 | Indeterminate | Drawing | Detail | Material Handling | Automation and Instrumentation | DATIS | 2016-05-25 09:56 | IFC | AFC | 100%
15183 | I491TG05-0MSAA91-001-001 | Fire Water System Route | 01 | 2012-08-27 | Indeterminate | Drawing | Basic | General | Piping & Utility | TAM |  | IFC | AFC | 100%
15184 | I491TG05-0MSAA91-001-002 | Fire Water System Route | 01 | 2012-08-27 | Indeterminate | Drawing | Basic | General | Piping & Utility | TAM |  | IFC | AFC | 100%
114149 | I491TG05-0MSAA91-001-003 | Fire Water System Route | 02 | 2015-06-30 14:22 | Indeterminate | Drawing | Detail | Fire Fighting System | Piping & Utility | TAM | 2015-06-30 14:22 | IFC | AC |  | 95%
114150 | I491TG05-0MSAA91-001-004 | Fire Water System Route | 02 | 2015-06-30 14:22 | Indeterminate | Drawing | Detail | Fire Fighting System | Piping & Utility | TAM | 2015-06-30 14:22 | IFC | AC |  | 95%
115805 | I491TG05-0MSAA91-002-001 | FIRE WATER NETWORK 1-2 | 02 | 2016-06-29 | Indeterminate | Drawing | Detail | Fire Fighting System | Piping & Utility | TAM | 2016-07-03 10:57 | IFC | AFC | 100%
115806 | I491TG05-0MSAA91-002-002 | FIRE WATER NETWORK 2-2 | 01 | 2016-06-29 | Indeterminate | Drawing | Detail | Fire Fighting System | Piping & Utility | TAM | 2016-07-03 10:57 | IFC | AFC | 100%
15188 | I491TG05-0MXAA91-001-003 | (Underground Pipes) Longitudinal Section | 01 | 2013-08-01 | Indeterminate | Drawing | Basic | General | Civil and Steel Structure | IKS |  | IFC | AFC | 100%
111578 | I491TG05-0MXAA91-001-004 | (Underground Pipes) Domestic Sewage Network | 02 | 2014-02-10 | Indeterminate | Drawing | Basic | General | Civil and Steel Structure | IKS | 2014-04-23 17:42 | IFC | AFC | 100%
15191 | I491TG05-0MXAA91-003-002 | جدول ترازیابی و مشخصات ارتفاعی محورها | 01 | 2013-08-01 | Indeterminate | Miscellaneous(MISC) | Basic | General | Civil and Steel Structure | IKS |  | IFC | AFC | 100%
15194 | I491TG05-0NGAA91-001-003 | Natural Gas Distribution Plan1-2 | 01 | 2012-08-27 | Indeterminate | Drawing | Basic | Natural Gas Reducing Station | Piping & Utility | TAM |  | IFC | AFC | 100%
15195 | I491TG05-0NGAA91-001-004 | Natural Gas Distribution Plan2-2 | 01 | 2012-08-27 | Indeterminate | Drawing | Basic | Natural Gas Reducing Station | Piping & Utility | TAM |  | IFC | AFC | 100%
15196 | I491TG05-0NGAA91-002-001 | Main Natural Gas Distribution Network | 00 | 2012-11-18 | Indeterminate | Drawing | Detail | Natural Gas Reducing Station | Piping & Utility | TAM |  | IFA | AC |  | 95%
112504 | I491TG05-0NGAA91-003-001 | Route of Gas line for Medical Center | 00 | 2014-07-07 | Indeterminate | Drawing | Basic | Media Distribution System | Piping & Utility | TAM | 2014-07-09 11:08 | IFA | A | 100%
114797 | I491TG07-0ASAA91-001-001 | P&Id For Air Seperation Plant | 01 | 2016-01-11 | Indeterminate | Drawing | Detail | Air Separation Plant | Piping & Utility | Fortune | 2016-01-12 14:49 | IFC | AC |  | 95%
129795 | I491TG07-0ASCP01-001-001 | Turbo Compressor Outline and PID 1~6 | 00 | 2016-11-12 09:31 | Indeterminate | Drawing | Detail | Air Separation Plant Main Building | Piping & Utility | TAM | 2016-11-12 09:31 | IFI | OB | 100%
134086 | I491TG07-0ASCP02-001-001 | Booster Air Compressor 02_PID_24319469 | 00 | 2018-08-15 | Indeterminate | Drawing | Detail | Air Separation Plant | Mechanical | TAM | 2018-08-21 13:05 | IFI | OB | 100%
134087 | I491TG07-0ASCP02-002-001 | Booster Air Compressor PID Instrument List 03_IST_2431966 (5 sheet) | 00 | 2018-08-15 | Indeterminate | Miscellaneous(MISC) | Detail | Air Separation Plant Main Building | Mechanical | TAM | 2018-08-21 13:06 | IFI | OB | 100%
112574 | I491TG07-0CPAA91-001-003 | Piping And Instrument Diagram (P&Id) For Air Compressor Plant | 02 | 2014-07-08 | Indeterminate | Drawing | Detail | Compressed Air Production Plant | Piping & Utility | HAVAYAR | 2014-07-13 13:53 | IFC | AC |  | 95%
112575 | I491TG07-0CPAA91-001-004 | Piping And Instrument Diagram (P&Id) For Air Compressor Plant | 02 | 2014-07-08 | Indeterminate | Drawing | Detail | Compressed Air Production Plant | Piping & Utility | HAVAYAR | 2014-07-13 13:53 | IFC | AFC | 100%
112576 | I491TG07-0CPAA91-001-005 | Piping And Instrument Diagram (P&Id) For Air Compressor Plant | 02 | 2014-07-08 | Indeterminate | Drawing | Detail | Compressed Air Production Plant | Piping & Utility | HAVAYAR | 2014-07-13 13:53 | IFC | AC |  | 95%
112577 | I491TG07-0CPAA91-001-006 | Piping And Instrument Diagram (P&Id) For Air Compressor Plant | 02 | 2014-07-08 | Indeterminate | Drawing | Detail | Compressed Air Production Plant | Piping & Utility | HAVAYAR | 2014-07-13 13:53 | IFC | AFC | 100%
15204 | I491TG07-0DTAA91-001-001 | Dedusting System Fournace 140 Ton Eaf+Lf&Mh P&Id-Suction Net | 00 | 2013-03-12 | Indeterminate | Miscellaneous(MISC) | Basic | Fume Treatment Equipment | Automation and Instrumentation | HASCON |  | IFA | AFC | 100%
15205 | I491TG07-0DTAA91-002-001 | Dedusting System Fournace 140 Ton Eaf+Lf&Mh P&Id-Wcd | 00 | 2013-03-12 | Indeterminate | Miscellaneous(MISC) | Basic | Fume Treatment Equipment | Automation and Instrumentation | HASCON |  | IFA | AFC | 100%
15206 | I491TG07-0DTAA91-003-001 | Dedusting System Fournace 140 Ton Eaf+Lf&Mh P&Id-Bag Filter A-B | 00 | 2013-03-12 | Indeterminate | Miscellaneous(MISC) | Basic | Fume Treatment Equipment | Automation and Instrumentation | HASCON |  | IFA | AFC | 100%
15207 | I491TG07-0DTAA91-004-001 | Dedusting System Fournace 140 Ton Eaf+Lf&Mh P&Id-Bag Filter C-D | 00 | 2013-03-12 | Indeterminate | Miscellaneous(MISC) | Basic | Fume Treatment Equipment | Automation and Instrumentation | HASCON |  | IFA | AFC | 100%
15208 | I491TG07-0DTAA91-005-001 | Dedusting System Fournace 140 Ton Eaf+Lf&Mh P&Id-Dust Storage | 00 | 2013-03-12 | Indeterminate | Miscellaneous(MISC) | Basic | Fume Treatment Equipment | Automation and Instrumentation | HASCON |  | IFA | AFC | 100%
15209 | I491TG07-0DTAA91-006-001 | Dedusting System Fournace 140 Ton Eaf+Lf&Mh P&Id-Main Suction Fan | 00 | 2013-03-12 | Indeterminate | Miscellaneous(MISC) | Basic | Fume Treatment Equipment | Automation and Instrumentation | HASCON |  | IFA | AFC | 100%
15210 | I491TG07-0DTAA91-007-001 | Dedusting System Fournace 140 Ton Eaf+Lf&Mh P&Id-Compressed Air | 00 | 2013-03-12 | Indeterminate | Miscellaneous(MISC) | Basic | Fume Treatment Equipment | Automation and Instrumentation | HASCON |  | IFA | AFC | 100%
15211 | I491TG07-0DTAA91-008-001 | Dedusting System Fournace 140 Ton Eaf+Lf&Mh P&Id-Dri | 00 | 2013-03-12 | Indeterminate | Miscellaneous(MISC) | Basic | Fume Treatment Equipment | Automation and Instrumentation | HASCON |  | IFA | AFC | 100%
130031 | I491TG07-0DTAA91-103-001 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH DRI EQUIPMENT LAYOUT | 00 | 2016-12-26 10:40 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | TAM | 2016-12-26 10:40 | IFA | AC |  | 95%
130033 | I491TG07-0DTAA91-105-001 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH DRI CABLE TRAY AND CABLE TRUNKING LAYOUT | 00 | 2016-12-27 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Automation and Instrumentation | TAM | 2016-12-29 11:32 | IFA | AC |  | 95%
15212 | I491TG07-0EAAA91-001-001 | Hydraulic Eaf | 00 | 2012-09-18 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | TAM |  | IFA | A | 100%
15223 | I491TG07-0EAAA91-001-002 | Eaf Main Water Flowsheet | 01 | 2012-09-18 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | TAM |  | IFA | A | 100%
15226 | I491TG07-0EAAA91-001-003 | Roof-Water Eaf | 00 | 2012-09-18 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | TAM |  | IFA | A | 100%
15227 | I491TG07-0EAAA91-001-004 | Water-Eaf Upper Shell | 01 | 2012-09-18 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | TAM |  | IFA | A | 100%
15228 | I491TG07-0EAAA91-001-005 | Gases-Eaf | 01 | 2012-09-18 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | TAM |  | IFA | A | 100%
15229 | I491TG07-0EAAA91-001-006 | Flowsheet, Pressure Measuring Compressed Air Eaf | 00 | 2012-09-18 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | TAM |  | IFA | A | 100%
15230 | I491TG07-0EAAA91-001-007 | Pressure Measuring - Pipeing-Compressed Air Eaf | 00 | 2012-09-18 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | TAM |  | IFA | A | 100%
15231 | I491TG07-0EAAA91-001-008 | Slide Gate Flowsheet-Compressed Air | 01 | 2012-09-18 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | TAM |  | IFA | A | 100%
15232 | I491TG07-0EAAA91-001-009 | Flowsheet Tap Hole Filling-Compressed Air Eaf | 01 | 2012-09-18 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | TAM |  | IFA | A | 100%
15213 | I491TG07-0EAAA91-001-010 | Eaf - Spray Cooling-Compressed Air | 01 | 2012-09-18 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | TAM |  | IFA | A | 100%
15214 | I491TG07-0EAAA91-001-011 | Mooving Sleeve Valve Stand-Compressed Air Eaf | 03 | 2012-09-18 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | TAM |  | IFA | A | 100%
15215 | I491TG07-0EAAA91-001-012 | Lubrication Eaf-Media & Fluide | 01 | 2012-09-18 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | TAM |  | IFA | A | 100%
15216 | I491TG07-0EAAA91-001-013 | Lubrication Eaf-Media & Fluide | 00 | 2012-09-18 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | TAM |  | IFA | A | 100%
15217 | I491TG07-0EAAA91-001-014 | Gases-Eaf | 01 | 2012-09-18 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | TAM |  | IFA | A | 100%
15218 | I491TG07-0EAAA91-001-015 | Flowsheet_Natural Gas Eaf | 00 | 2012-09-18 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | TAM |  | IFA | A | 100%
15219 | I491TG07-0EAAA91-001-016 | Flowsheet-Oxygen Eaf | 00 | 2012-09-18 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | TAM |  | IFA | A | 100%
15220 | I491TG07-0EAAA91-001-017 | Bottom Stirring-Inert Gas Eaf | 04 | 2012-09-18 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | TAM |  | IFA | A | 100%
15221 | I491TG07-0EAAA91-001-018 | Eaf- Ladle Stirring-Inert Gas Eaf | 00 | 2012-09-18 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | TAM |  | IFA | A | 100%
15222 | I491TG07-0EAAA91-001-019 | Carbon Injection Line- Carbon Injection Installation | 00 | 2012-09-18 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | TAM |  | IFA | A | 100%
15224 | I491TG07-0EAAA91-001-020 | Flow Sheet-Unidos 3,0 Triple-Carbon Injection Installation | 01 | 2012-09-18 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | TAM |  | IFA | A | 100%
15225 | I491TG07-0EAAA91-001-021 | Flow Sheet-Unidos 3,0 Triple-Carbon Injection Installation-Bom | 00 | 2012-09-18 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | TAM |  | IFA | A | 100%
114803 | I491TG07-0EAEW01-001-001 | EAF Series Reactor 27/32.4MV Ar | 00 | 2016-01-17 | Indeterminate | Drawing | Basic | Electric Arc Furnace | Automation and Instrumentation | TAM | 2016-01-18 09:10 | IFI | OB | 100%
114804 | I491TG07-0EATF01-001-001 | EAF Transformer PID 140+20 MVA | 00 | 2016-01-17 | Indeterminate | Drawing | Basic | Electric Arc Furnace | Automation and Instrumentation | TAM | 2016-01-18 09:11 | IFI | OB | 100%
15233 | I491TG07-0LFAA91-001-001 | Hydraulic System Pid-Hydraulic Lf | 00 | 2012-09-18 | Indeterminate | Miscellaneous(MISC) | Basic | Ladle Furnace | Mechanical | TAM |  | IFA | A | 100%
15238 | I491TG07-0LFAA91-001-002 | Water Lf | 03 | 2012-09-18 | Indeterminate | Drawing | Basic | Ladle Furnace | Mechanical | TAM |  | IFA | A | 100%
15239 | I491TG07-0LFAA91-001-003 | High Current System-Water Lf | 01 | 2012-09-18 | Indeterminate | Drawing | Basic | Ladle Furnace | Mechanical | TAM |  | IFA | A | 100%
15240 | I491TG07-0LFAA91-001-004 | Lf Roof-Water Lf | 01 | 2012-09-18 | Indeterminate | Drawing | Basic | Ladle Furnace | Mechanical | TAM |  | IFA | A | 100%
15241 | I491TG07-0LFAA91-001-005 | Compressed Air Flowsheet-Lf | 01 | 2012-09-18 | Indeterminate | Drawing | Basic | Ladle Furnace | Mechanical | TAM |  | IFA | A | 100%
15242 | I491TG07-0LFAA91-001-006 | Compressed Air-Lf | 00 | 2012-09-18 | Indeterminate | Drawing | Basic | Ladle Furnace | Mechanical | TAM |  | IFA | A | 100%
15243 | I491TG07-0LFAA91-001-007 | Lubrication Lf-Media & Fluide | 00 | 2012-09-18 | Indeterminate | Drawing | Basic | Ladle Furnace | Mechanical | TAM |  | IFA | A | 100%
15244 | I491TG07-0LFAA91-001-008 | Lubrication Lf-Media & Fluide-Bom | 00 | 2012-09-18 | Indeterminate | Drawing | Basic | Ladle Furnace | Mechanical | TAM |  | IFA | A | 100%
15245 | I491TG07-0LFAA91-001-009 | Lf- Ladle Stirring-Inert Gas Lf | 02 | 2012-09-18 | Indeterminate | Drawing | Basic | Ladle Furnace | Mechanical | TAM |  | IFA | A | 100%
15234 | I491TG07-0LFAA91-001-010 | Pneumatic-Piping Roof Lf | 00 | 2012-09-18 | Indeterminate | Drawing | Basic | Ladle Furnace | Mechanical | TAM |  | IFA | A | 100%
15235 | I491TG07-0LFAA91-001-011 | Pneumatic-Piping Roof Lf- Bom | 00 | 2012-09-18 | Indeterminate | Drawing | Basic | Ladle Furnace | Mechanical | TAM |  | IFA | A | 100%
15236 | I491TG07-0LFAA91-001-012 | Pneumatic-Piping Roof Lf | 00 | 2012-09-18 | Indeterminate | Drawing | Basic | Ladle Furnace | Mechanical | TAM |  | IFA | A | 100%
15237 | I491TG07-0LFAA91-001-013 | Pneumatic-Piping Roof Lf-Bom | 00 | 2012-09-18 | Indeterminate | Drawing | Basic | Ladle Furnace | Mechanical | TAM |  | IFA | A | 100%
114805 | I491TG07-0LFTF01-001-001 | LF Transformer PID | 00 | 2016-01-17 | Indeterminate | Drawing | Basic | Ladle Furnace | Automation and Instrumentation | TAM | 2016-01-18 09:15 | IFI | OB | 100%
116072 | I491TG07-0MDAA91-001-010 | Material Handling System Process And Instrument Diagram Cover | 02 | 2016-07-12 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | DATIS | 2016-07-13 09:53 | IFC | AC |  | 95%
116073 | I491TG07-0MDAA91-001-011 | Material Handling System Process And Instrument Diagram Index | 02 | 2016-07-12 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | DATIS | 2016-07-13 09:53 | IFC | AC |  | 95%
116074 | I491TG07-0MDAA91-001-012 | Material Handling System Process And Instrument Diagram Legend (1/2) | 02 | 2016-07-12 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | DATIS | 2016-07-13 09:53 | IFC | AC |  | 95%
116075 | I491TG07-0MDAA91-001-013 | Material Handling System Process And Instrument Diagram Legend (2/2) | 02 | 2016-07-12 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | DATIS | 2016-07-13 09:53 | IFC | AC |  | 95%
116076 | I491TG07-0MDAA91-001-014 | Material Handling System Process And Instrument Diagram (1/4) | 02 | 2016-07-12 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | DATIS | 2016-07-13 09:53 | IFC | AC |  | 95%
116077 | I491TG07-0MDAA91-001-015 | Material Handling System Process And Instrument Diagram (2/4) | 02 | 2016-07-12 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | DATIS | 2016-07-13 09:53 | IFC | AC |  | 95%
116078 | I491TG07-0MDAA91-001-016 | Material Handling System Process And Instrument Diagram (3/4) | 02 | 2016-07-12 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | DATIS | 2016-07-13 09:53 | IFC | AC |  | 95%
116079 | I491TG07-0MDAA91-001-017 | Material Handling System Process And Instrument Diagram (4/4) | 02 | 2016-07-12 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | DATIS | 2016-07-13 09:53 | IFC | AC |  | 95%
130699 | I491TG07-0MMAA91-001-001 | WTP PROCESS AND INSTRUMENT DIAGRAM(P&ID) 1-4 | 00 | 2017-06-19 | Indeterminate | Drawing | Detail | Water Treatment System | Mechanical | TAM | 2017-06-21 11:16 | IFA | AC |  | 95%
130702 | I491TG07-0MMAA91-001-002 | WTP PROCESS AND INSTRUMENT DIAGRAM(P&ID) 2-4 | 00 | 2017-06-19 | Indeterminate | Drawing | Detail | Water Treatment System | Mechanical | TAM | 2017-06-21 11:16 | IFA | AC |  | 95%
130700 | I491TG07-0MMAA91-001-003 | WTP PROCESS AND INSTRUMENT DIAGRAM(P&ID) 3-4 | 00 | 2017-06-19 | Indeterminate | Drawing | Detail | Water Treatment System | Mechanical | TAM | 2017-06-21 11:16 | IFA | AC |  | 95%
130701 | I491TG07-0MMAA91-001-004 | WTP PROCESS AND INSTRUMENT DIAGRAM(P&ID) 4-4 | 00 | 2017-06-19 | Indeterminate | Drawing | Detail | Water Treatment System | Mechanical | TAM | 2017-06-21 11:16 | IFA | AC |  | 95%
135251 | I491TG07-0MMCF91-001-004 | WTP PROCESS AND INSTRUMENT DIAGRAM(P&ID) SEDIMENTATION 1-6 | 03 | 2019-04-28 | Indeterminate | Drawing | Basic | Water Treatment & Cooling System | Automation and Instrumentation | FARABARD | 2019-04-29 10:26 | IFC | AC |  | 95%
135252 | I491TG07-0MMCF91-001-005 | WTP PROCESS AND INSTRUMENT DIAGRAM(P&ID) SEDIMENTATION 2-6 | 03 | 2019-04-28 | Indeterminate | Drawing | Basic | Water Treatment & Cooling System | Automation and Instrumentation | FARABARD | 2019-04-29 10:26 | IFC | AC |  | 95%
135253 | I491TG07-0MMCF91-001-006 | WTP PROCESS AND INSTRUMENT DIAGRAM(P&ID) SEDIMENTATION 3-6 | 03 | 2019-04-28 | Indeterminate | Drawing | Basic | Water Treatment & Cooling System | Automation and Instrumentation | FARABARD | 2019-04-29 10:26 | IFC | AC |  | 95%
135254 | I491TG07-0MMCF91-001-007 | WTP PROCESS AND INSTRUMENT DIAGRAM(P&ID) SEDIMENTATION 4-6 | 03 | 2019-04-28 | Indeterminate | Drawing | Basic | Water Treatment & Cooling System | Automation and Instrumentation | FARABARD | 2019-04-29 10:26 | IFC | AC |  | 95%
135256 | I491TG07-0MMCF91-001-008 | WTP PROCESS AND INSTRUMENT DIAGRAM(P&ID) SEDIMENTATION 5-6 | 00 | 2019-04-28 | Indeterminate | Drawing | Basic | Water Treatment & Cooling System | Automation and Instrumentation | FARABARD | 2019-04-29 10:30 | IFC | AC |  | 95%
135250 | I491TG07-0MMCF91-003-001 | Control philosophy For Sedimentation System | 03 | 2019-04-28 | Indeterminate | Miscellaneous(MISC) | Basic | Water Treatment & Cooling System | Automation and Instrumentation | TAM | 2019-04-29 10:25 | IFC | AC |  | 95%
135204 | I491TG07-0MMCT01-001-003 | PIPING AND INSTRUMENT DIAGRAM FOR COOLING SYSTEM CT01 1-4 | 05 | 2019-04-08 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Piping & Utility | TAM | 2019-04-14 15:02 | IFC | AC |  | 95%
135207 | I491TG07-0MMCT01-001-004 | PIPING AND INSTRUMENT DIAGRAM FOR COOLING SYSTEM CT01 2-4 | 06 | 2019-04-08 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Piping & Utility | TAM | 2019-04-14 15:03 | IFC | AC |  | 95%
135205 | I491TG07-0MMCT01-001-005 | PIPING AND INSTRUMENT DIAGRAM FOR COOLING SYSTEM CT01 3-4 | 05 | 2019-04-08 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Piping & Utility | TAM | 2019-04-14 15:02 | IFC | AC |  | 95%
135206 | I491TG07-0MMCT01-001-006 | PIPING AND INSTRUMENT DIAGRAM FOR COOLING SYSTEM CT01 4-4 | 01 | 2019-04-08 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Piping & Utility | TAM | 2019-04-14 15:02 | IFC | AC |  | 95%
15275 | I491TG07-0MMCT01-002-001 | Chemical Dosing Package P&Id (Ct01) | 00 | 2013-03-11 | Indeterminate | Drawing | Basic | Water Treatment & Cooling System | Automation and Instrumentation | TAM |  | IFA | A | 100%
15276 | I491TG07-0MMCT01-002-002 | Chemical Dosing Package P&Id (Ct01) | 00 | 2013-03-11 | Indeterminate | Drawing | Basic | Water Treatment & Cooling System | Automation and Instrumentation | TAM |  | IFA | A | 100%
130690 | I491TG07-0MMCT01-003-002 | PIPING AND INSTRUMENT DIAGRAM FOR SAND FILTER | 03 | 2017-06-13 | Indeterminate | Drawing | Basic | Water Treatment & Cooling System | Piping & Utility | TAM | 2017-06-14 15:00 | IFC | AC |  | 95%
135208 | I491TG07-0MMCT02-001-002 | PIPING AND INSTRUMENT DIAGRAM FOR COOLING SYSTEM CT02 | 04 | 2019-04-08 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Piping & Utility | TAM | 2019-04-14 15:03 | IFC | AC |  | 95%
15281 | I491TG07-0MMCT02-002-001 | Chemical Dosing Package P&Id (Ct02) | 00 | 2013-03-11 | Indeterminate | Drawing | Basic | Water Treatment & Cooling System | Automation and Instrumentation | TAM |  | IFA | A | 100%
15282 | I491TG07-0MMCT02-002-002 | Chemical Dosing Package P&Id (Ct02) | 00 | 2013-03-11 | Indeterminate | Drawing | Basic | Water Treatment & Cooling System | Automation and Instrumentation | TAM |  | IFA | A | 100%
130692 | I491TG07-0MMCT02-003-002 | PIPING AND INSTRUMENT DIAGRAM FOR SAND FILTER | 03 | 2017-06-13 | Indeterminate | Drawing | Basic | Water Treatment & Cooling System | Piping & Utility | TAM | 2017-06-14 15:01 | IFC | AC |  | 95%
15285 | I491TG07-0NGAA91-001-001 | Natural Gas Pressure Reducing Station Piping And Instrumentation Diagram (P&Id) | 00 | 2012-12-16 | Indeterminate | Drawing | Detail | Natural Gas Reducing Station | Piping & Utility | TAM |  | IFA | AC |  | 95%
114749 | I491TG07-0SXCJ91-001-001 | Carbon Injection Flow Sheet D-36.00.000.000_REV.D | 00 | 2015-12-06 | Indeterminate | Drawing | Basic | Eaf Auxiliaries | Mechanical | FUCHS | 2015-12-07 11:11 | IFA | AC |  | 95%
115246 | I491TG08-0ASAA91-001-001 | ELECTRICAL EQUIPMENT LAYOUT | 00 | 2016-05-07 | Indeterminate | Drawing | Detail | Air Separation Plant | Electrical | Fortune | 2016-05-14 16:22 | IFI | OB | 100%
113521 | I491TG08-0MDCV91-001-001 | Material Handling System Electrical Device Location Layout Outdoor Conveyors (1-4) | 02 | 2015-05-09 | Indeterminate | Drawing | Detail | Material Handling | Electrical | DATIS | 2015-05-24 16:40 | IFC | AFC | 100%
113522 | I491TG08-0MDCV91-001-002 | Material Handling System Electrical Device Location Layout Outdoor Conveyors (2-4) | 02 | 2015-05-09 | Indeterminate | Drawing | Detail | Material Handling | Electrical | DATIS | 2015-05-24 16:40 | IFC | AFC | 100%
113523 | I491TG08-0MDCV91-001-003 | Material Handling System Electrical Device Location Layout Outdoor Conveyors (3-4) | 02 | 2015-05-09 | Indeterminate | Drawing | Detail | Material Handling | Electrical | DATIS | 2015-05-24 16:40 | IFC | AFC | 100%
111585 | I491TG08-0MDCV91-006-001 | Material Handling System ELECTRICAL DEVICE LOCATION LAYOUT INDOOR CONVEYORS 1-11 | 01 | 2014-02-22 | Indeterminate | Drawing | Detail | Material Handling | Electrical | DATIS | 2014-04-23 19:11 | IFC | AFC | 100%
111586 | I491TG08-0MDCV91-006-002 | Material Handling System ELECTRICAL DEVICE LOCATION LAYOUT INDOOR CONVEYORS 2-11 | 01 | 2014-02-22 | Indeterminate | Drawing | Detail | Material Handling | Electrical | DATIS | 2014-04-23 19:11 | IFC | AFC | 100%
111587 | I491TG08-0MDCV91-006-003 | Material Handling System ELECTRICAL DEVICE LOCATION LAYOUT INDOOR CONVEYORS 3-11 | 01 | 2014-02-22 | Indeterminate | Drawing | Detail | Material Handling | Electrical | DATIS | 2014-04-23 19:11 | IFC | AFC | 100%
111588 | I491TG08-0MDCV91-006-004 | Material Handling System ELECTRICAL DEVICE LOCATION LAYOUT INDOOR CONVEYORS 4-11 | 01 | 2014-02-22 | Indeterminate | Drawing | Detail | Material Handling | Electrical | DATIS | 2014-04-23 19:11 | IFC | AFC | 100%
111589 | I491TG08-0MDCV91-006-005 | Material Handling System ELECTRICAL DEVICE LOCATION LAYOUT INDOOR CONVEYORS 5-11 | 01 | 2014-02-22 | Indeterminate | Drawing | Detail | Material Handling | Electrical | DATIS | 2014-04-23 19:11 | IFC | AFC | 100%
111590 | I491TG08-0MDCV91-006-006 | Material Handling System ELECTRICAL DEVICE LOCATION LAYOUT INDOOR CONVEYORS 6-11 | 01 | 2014-02-22 | Indeterminate | Drawing | Detail | Material Handling | Electrical | DATIS | 2014-04-23 19:11 | IFC | AFC | 100%
111591 | I491TG08-0MDCV91-006-007 | Material Handling System ELECTRICAL DEVICE LOCATION LAYOUT INDOOR CONVEYORS 7-11 | 01 | 2014-02-22 | Indeterminate | Drawing | Detail | Material Handling | Electrical | DATIS | 2014-04-23 19:11 | IFC | AFC | 100%
111592 | I491TG08-0MDCV91-006-008 | Material Handling System ELECTRICAL DEVICE LOCATION LAYOUT INDOOR CONVEYORS 8-11 | 00 | 2014-02-22 | Indeterminate | Drawing | Detail | Material Handling | Electrical | DATIS | 2014-04-23 19:11 | IFC | AFC | 100%
111593 | I491TG08-0MDCV91-006-009 | Material Handling System ELECTRICAL DEVICE LOCATION LAYOUT INDOOR CONVEYORS 9-11 | 00 | 2014-02-22 | Indeterminate | Drawing | Detail | Material Handling | Electrical | DATIS | 2014-04-23 19:11 | IFC | AFC | 100%
111594 | I491TG08-0MDCV91-006-010 | Material Handling System ELECTRICAL DEVICE LOCATION LAYOUT INDOOR CONVEYORS 10-11 | 00 | 2014-02-22 | Indeterminate | Drawing | Detail | Material Handling | Electrical | DATIS | 2014-04-23 19:11 | IFC | AFC | 100%
111595 | I491TG08-0MDCV91-006-011 | Material Handling System ELECTRICAL DEVICE LOCATION LAYOUT INDOOR CONVEYORS 11-11 | 00 | 2014-02-22 | Indeterminate | Drawing | Detail | Material Handling | Electrical | DATIS | 2014-04-23 19:11 | IFC | AFC | 100%
129900 | I491TG10-0CCAA91-001-001 | 2.1.073 CCM Danieli Standard (Document Numbering) | 00 | 2016-12-04 14:58 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2016-12-04 14:58 | IFI | OB | 100%
129901 | I491TG10-0CCAA91-001-002 | 3.210.001 CCM Danieli Standard (Bolt and Screw) | 00 | 2016-12-04 14:58 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2016-12-04 14:58 | IFI | OB | 100%
129902 | I491TG10-0CCAA91-001-003 | 3.220.001 CCM Danieli Standard (NUTS) | 00 | 2016-12-04 14:58 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2016-12-04 14:58 | IFI | OB | 100%
129903 | I491TG10-0CCAA91-001-004 | 6.200.001 CCM Danieli Standard (Steel Bars) | 00 | 2016-12-04 14:58 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2016-12-04 14:58 | IFI | OB | 100%
129904 | I491TG10-0CCAA91-001-005 | 24103-R06 CCM Danieli Standard (Tolerances) | 00 | 2016-12-04 14:58 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2016-12-04 14:58 | IFI | OB | 100%
129905 | I491TG10-0CCAA91-001-006 | 24603-R05 CCM Danieli Standard (Preload Forces and Tightening) | 00 | 2016-12-04 14:58 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2016-12-04 14:58 | IFI | OB | 100%
129906 | I491TG10-0CCAA91-001-007 | 24701-R04 CCM Danieli Standard (Safety Prescriptions) | 00 | 2016-12-04 14:58 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2016-12-04 14:58 | IFI | OB | 100%
129907 | I491TG10-0CCAA91-001-008 | 28006-R10 CCM Danieli Standard (Structures And piping Manufacturing) | 00 | 2016-12-04 14:58 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2016-12-04 14:58 | IFI | OB | 100%
129908 | I491TG10-0CCAA91-001-009 | 28032-R00 CCM Danieli Standard (Rolled Steel- Supply Spcification) | 00 | 2016-12-04 14:58 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2016-12-04 14:58 | IFI | OB | 100%
129909 | I491TG10-0CCAA91-001-010 | 28043-R03 CCM Danieli Standard (Precision Classes For Machining) | 00 | 2016-12-04 14:58 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2016-12-04 14:58 | IFI | OB | 100%
129910 | I491TG10-0CCAA91-001-011 | 28102-R03 CCM Danieli Standard (NDT For Leak Testing) | 00 | 2016-12-04 14:58 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2016-12-04 14:58 | IFI | OB | 100%
129911 | I491TG10-0CCAA91-001-012 | 28115-R06 CCM Danieli Standard (NDT On Welded Structures) | 00 | 2016-12-04 14:58 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2016-12-04 14:58 | IFI | OB | 100%
129912 | I491TG10-0CCAA91-001-013 | 28300-R06 CCM Danieli Standard (Steel Heat Treatments) | 00 | 2016-12-04 14:58 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2016-12-04 14:58 | IFI | OB | 100%
129913 | I491TG10-0CCAA91-001-014 | 28300-R07 CCM Danieli Standard (Heat Treatments Terminology) | 00 | 2016-12-04 14:58 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2016-12-04 14:58 | IFI | OB | 100%
129914 | I491TG10-0CCAA91-001-015 | 28302-R08 CCM Danieli Standard (Protective Coating Of Metal Surfaces) | 00 | 2016-12-04 14:58 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2016-12-04 14:58 | IFI | OB | 100%
129915 | I491TG10-0CCAA91-001-016 | 28307-R01 CCM Danieli Standard (Vibratory Stress Relieving) | 00 | 2016-12-04 14:58 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2016-12-04 14:58 | IFI | OB | 100%
129916 | I491TG10-0CCAA91-001-017 | 28900-R16 CCM Danieli Standard (Test And Inspection Codes List) | 00 | 2016-12-04 14:58 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2016-12-04 14:58 | IFI | OB | 100%
130323 | I491TG10-0CCAA91-018-001 | Danieli Standard For Oils,Fire Resistant Hydraulic Fluids And Greases | 00 | 2017-02-15 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2017-02-16 12:46 | IFI | OB | 100%
113021 | I491TG10-0EAAA91-001-001 | CCM DANIELLI Civil Standards | 00 | 2014-10-19 09:17 | Indeterminate | Miscellaneous(MISC) | Basic | Continuous Casting Machine (CCM) | Civil and Steel Structure | TAM | 2014-10-19 09:17 | IFI | OB | 100%
15292 | I491TG99-0ASAA91-001-003 | Basic Data For Air Separation Plant | 01 | 2011-10-23 | Indeterminate | Miscellaneous(MISC) | Basic | Air Separation Plant | Mechanical | TAM |  | IFC | AFC | 100%
15295 | I491TG99-0CAAA91-001-003 | Basic Data Of Compressed Air Plant | 01 | 2011-07-11 | Indeterminate | Miscellaneous(MISC) | Basic | Compressed Air Production Plant | Mechanical | TAM |  | IFC | AFC | 100%
15398 | I491TG99-0CCAA91-001-001 | Basic Data Of Ccm & Auxilaries | 02 | 2012-01-17 | Indeterminate | Miscellaneous(MISC) | Basic | Continuous Casting Machine (CCM) | Mechanical | TAM |  | IFC | AFC | 100%
16560 | I491TG99-0CCAA91-001-002 | Basic Data Of Ccm & Auxilaries | 00 | 2011-07-11 | Indeterminate | Miscellaneous(MISC) | Basic | Continuous Casting Machine (CCM) | Mechanical | TAM |  | IFC | AC |  | 95%
113683 | I491TG99-0CCTK91-001-001 | basis of design for Scale Pit | 01 | 2015-05-30 13:33 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Mechanical | TAM | 2015-05-30 13:33 | IFC | AC |  | 95%
15298 | I491TG99-0CHAA91-001-003 | Time Analysis For Teeming And Charging Crane | 02 | 2013-01-26 | Indeterminate | Miscellaneous(MISC) | Basic | Crane and Hiosts | Mechanical | TAM |  | IFC | AFC | 100%
15302 | I491TG99-0CHAA91-002-004 | Basic Data Of Heavy Duty Cranes | 03 | 2012-08-06 | Indeterminate | Miscellaneous(MISC) | Basic | Crane and Hiosts | Mechanical | TAM |  | IFC | AFC | 100%
15304 | I491TG99-0CHAA91-003-002 | Basic Data For Cranes Of Maintenance Workshop, Ferro-Alloy Storage Area And Warehouse | 01 | 2012-04-23 | Indeterminate | Miscellaneous(MISC) | Basic | Crane and Hiosts | Mechanical | TAM |  | IFC | AFC | 100%
129943 | I491TG99-0CHAA91-004-001 | Basic Data For Jib Cranes | 02 | 2016-12-10 | Indeterminate | Miscellaneous(MISC) | Basic | Crane and Hiosts | Mechanical | TAM | 2016-12-12 16:48 | IFC | AFC | 100%
15307 | I491TG99-0CHAA91-005-002 | Basic Engineering For Cranes Of Maintenance Workshop, Ferroalloy Storage Area And Warehouse | 01 | 2013-03-17 | Indeterminate | Miscellaneous(MISC) | Basic | Crane and Hiosts | Mechanical | FIROUZA |  | IFC | AFC | 100%
112889 | I491TG99-0CHAA91-011-001 | Basic Engineering for Heavy Duty Crane Part1 | 01 | 2014-09-17 | Indeterminate | Miscellaneous(MISC) | Basic | Crane and Hiosts | Mechanical | TAM | 2014-09-18 15:31 | IFC | AFC | 100%
15312 | I491TG99-0DTAA91-001-005 | Basic Data For Fume Treatment Plant | 03 | 2012-04-09 | Indeterminate | Miscellaneous(MISC) | Basic | Fume Treatment Equipment | Mechanical | TAM |  | IFC | AFC | 100%
15321 | I491TG99-0EAAA91-001-004 | Basic Data Of Electric Arc Furnace | 02 | 2011-11-27 | Indeterminate | Miscellaneous(MISC) | Basic | Electric Arc Furnace | Mechanical | TAM |  | IFC | AFC | 100%
15313 | I491TG99-0EAAA91-002-001 | Technical Report For Arrsngement Plant Extension | 00 | 2011-04-24 | Indeterminate | Drawing | Basic | Melt Shop | Mechanical | TAM |  | IFA | AFC | 100%
15315 | I491TG99-0EAAA91-003-002 | Technical Report For Melt Shop Billet Storage Area | 02 | 2013-12-29 07:21 | Indeterminate | Miscellaneous(MISC) | Basic | Melt Shop | Mechanical | TAM |  | IFC | AFC | 100%
15316 | I491TG99-0EAAA91-004-001 | Melt Shop Basis Of Design (Mechanical And Electrical Utilities) | 00 | 2012-03-07 | Indeterminate | Miscellaneous(MISC) | Basic | General Civil | Civil and Steel Structure | TAM |  | IFA | AC |  | 95%
15324 | I491TG99-0LAXL91-001-002 | Technical Report For Meltshop Billet Storage | 00 | 2011-04-24 | Indeterminate | Drawing | Basic | Melt Shop | Mechanical | TAM |  | IFA | AFC | 100%
15327 | I491TG99-0LAXL91-001-006 | Basic Data Of Laboratory | 03 | 2012-02-13 | Indeterminate | Miscellaneous(MISC) | Basic | Laboratory | Mechanical | TAM |  | IFC | AFC | 100%
15330 | I491TG99-0LFAA91-001-005 | Basic Data For Ladle Furnace | 03 | 2011-11-27 | Indeterminate | Miscellaneous(MISC) | Basic | Ladle Furnace | Mechanical | TAM |  | IFC | AFC | 100%
15333 | I491TG99-0MCAA91-001-003 | Basic Data Of Meltshop Auxiliaries | 02 | 2012-04-07 | Indeterminate | Miscellaneous(MISC) | Basic | Melt Shop Auxiliaries | Mechanical | TAM |  | IFC | AFC | 100%
112462 | I491TG99-0MDAA91-001-006 | Basic Data Of Material Handling | 07 | 2014-06-29 | Indeterminate | Miscellaneous(MISC) | Basic | Material Handling | Mechanical | TAM | 2014-07-01 14:51 | IFC | AFC | 100%
15342 | I491TG99-0MDAA91-002-001 | Basic Engineering Of Material Handling | 00 | 2011-07-25 | Indeterminate | Miscellaneous(MISC) | Basic | Material Handling | Mechanical | TAM |  | IFA | AC |  | 95%
15344 | I491TG99-0MDAA91-003-002 | Basic Data Of Media Distribution System | 01 | 2012-07-28 | Indeterminate | Miscellaneous(MISC) | Basic | Media Distribution System | Mechanical | TAM |  | IFC | AFC | 100%
15346 | I491TG99-0MEET92-001-002 | Technical Specications Of Power And Auxilliary Transformers | 01 | 2012-01-17 | Indeterminate | Miscellaneous(MISC) | Basic | Main Electrical Substation And Distribution Network | Electrical | TAM |  | IFC | AFC | 100%
15349 | I491TG99-0MKAA91-001-003 | Basic Data Of Water Treatment Plant&Cooling Systems | 01 | 2011-07-11 | Indeterminate | Miscellaneous(MISC) | Basic | Water Treatment & Cooling System | Mechanical | TAM |  | IFC | AFC | 100%
15350 | I491TG99-0MKAA91-002-001 | Water Treatment & Cooling Systems(Bfd) | 00 | 2011-04-26 | Indeterminate | Drawing | Basic | Water Treatment & Cooling System | Mechanical | TAM |  | IFA | AC |  | 95%
15352 | I491TG99-0MKGN91-001-002 | Basis Of Design Of Water Treatment Plant & Cooling System | 01 | 2012-04-28 | Indeterminate | Miscellaneous(MISC) | Basic | Water Treatment & Cooling System | Piping & Utility | TAM |  | IFC | AC |  | 95%
15354 | I491TG99-0MRAA91-001-002 | Basic Data Of Hvac System | 01 | 2012-01-03 | Indeterminate | Miscellaneous(MISC) | Basic | Air Conditioning and Ventilation | Mechanical | TAM |  | IFC | AFC | 100%
15356 | I491TG99-0MSAA91-001-002 | Basic Data Of Fire Fighting Systems | 01 | 2012-06-13 | Indeterminate | Miscellaneous(MISC) | Basic | Fire Fighting System | Mechanical | TAM |  | IFC | AFC | 100%
15358 | I491TG99-0MSAA91-002-002 | Basic Engineering For Fire Fighting Systems | 01 | 2012-08-27 | Indeterminate | Miscellaneous(MISC) | Basic | General | Piping & Utility | TAM |  | IFC | AFC | 100%
133059 | I491TG99-0MSAA91-004-001 | Fire Box Piping Plan for Meltshop | 03 | 2018-04-16 | Indeterminate | Drawing | Detail | Melt Shop | Mechanical | TAM | 2018-04-17 09:34 | IFI | OB | 100%
15360 | I491TG99-0MSAA91-010-002 | Fire Fighting For Warehouse | 01 | 2012-12-16 | Indeterminate | Drawing | Detail | Warehouse | Piping & Utility | TAM |  | IFC | AFC | 100%
15361 | I491TG99-0MSAA91-011-001 | Fire Fighting For Work Shop | 00 | 2012-11-21 | Indeterminate | Drawing | Detail | Maintenance Workshop | Piping & Utility | TAM |  | IFA | AC |  | 95%
132749 | I491TG99-0MSAA91-014-001 | P&ID OF AUTOMATIC FIRE FIGHTING CO2 SYSTEM FOR SMP 1-11 | 04 | 2018-02-01 11:41 | Indeterminate | Drawing | Detail | Fire Fighting System | Piping & Utility | TAM | 2018-02-01 11:41 | IFC | AFC | 100%
132750 | I491TG99-0MSAA91-014-002 | P&ID OF AUTOMATIC FIRE FIGHTING CO2 SYSTEM FOR EAF 2-11 | 04 | 2018-02-01 11:41 | Indeterminate | Drawing | Detail | Fire Fighting System | Piping & Utility | TAM | 2018-02-01 11:41 | IFC | AFC | 100%
132751 | I491TG99-0MSAA91-014-003 | P&ID OF AUTOMATIC FIRE FIGHTING CO2 SYSTEM FOR LF 3-11 | 04 | 2018-02-01 11:41 | Indeterminate | Drawing | Detail | Fire Fighting System | Piping & Utility | TAM | 2018-02-01 11:41 | IFC | AFC | 100%
132752 | I491TG99-0MSAA91-014-004 | P&ID OF AUTOMATIC FIRE FIGHTING CO2 SYSTEM FOR WTP 4-11 | 04 | 2018-02-01 11:41 | Indeterminate | Drawing | Detail | Fire Fighting System | Piping & Utility | TAM | 2018-02-01 11:41 | IFC | AFC | 100%
132753 | I491TG99-0MSAA91-014-005 | P&ID OF AUTOMATIC FIRE FIGHTING CO2 SYSTEM FOR ASP 5-11 | 04 | 2018-02-01 11:41 | Indeterminate | Drawing | Detail | Fire Fighting System | Piping & Utility | TAM | 2018-02-01 11:41 | IFC | AFC | 100%
132754 | I491TG99-0MSAA91-014-006 | P&ID OF AUTOMATIC FIRE FIGHTING CO2 SYSTEM FOR FTP 6-11 | 04 | 2018-02-01 11:41 | Indeterminate | Drawing | Detail | Fire Fighting System | Piping & Utility | TAM | 2018-02-01 11:41 | IFC | AFC | 100%
132755 | I491TG99-0MSAA91-014-007 | P&ID OF AUTOMATIC FIRE FIGHTING CO2 SYSTEM FOR CCM 7-11 | 04 | 2018-02-01 11:41 | Indeterminate | Drawing | Detail | Fire Fighting System | Piping & Utility | TAM | 2018-02-01 11:41 | IFC | AFC | 100%
132756 | I491TG99-0MSAA91-014-008 | P&ID OF AUTOMATIC FIRE FIGHTING CO2 SYSTEM FOR CCM 8-11 | 03 | 2018-02-01 11:41 | Indeterminate | Drawing | Detail | Fire Fighting System | Piping & Utility | TAM | 2018-02-01 11:41 | IFC | AFC | 100%
133861 | I491TG99-0MSAA91-014-009 | P&ID OF AUTOMATIC FIRE FIGHTING CO2 SYSTEM FOR RO SUBSTAITION 9-11 | 00 | 2018-07-22 | Indeterminate | Drawing | Detail | Fire Fighting System | Piping & Utility | TAM | 2018-07-23 08:37 | IFA | A | 100%
133862 | I491TG99-0MSAA91-014-010 | P&ID OF AUTOMATIC FIRE FIGHTING CO2 SYSTEM FOR EAF TRANSFORMER 10-11 | 00 | 2018-07-22 | Indeterminate | Drawing | Detail | Fire Fighting System | Piping & Utility | TAM | 2018-07-23 08:37 | IFA | A | 100%
133863 | I491TG99-0MSAA91-014-011 | P&ID OF AUTOMATIC FIRE FIGHTING CO2 SYSTEM FOR LF TRANSFORMER 11-11 | 00 | 2018-07-22 | Indeterminate | Drawing | Detail | Fire Fighting System | Piping & Utility | TAM | 2018-07-23 08:37 | IFA | A | 100%
130632 | I491TG99-0MSAA91-015-001 | Automatic Fire Fighting For Transformer Rooms | 00 | 2017-05-27 12:11 | Indeterminate | Drawing | Detail | Fire Fighting System | Mechanical | TAM | 2017-05-27 12:11 | IFI | OB | 100%
132761 | I491TG99-0MSAA91-016-001 | P&ID OF AUTOMATIC FIRE FIGHTING FM200 SYSTEM FOR SMP 1-18 | 04 | 2018-02-01 11:42 | Indeterminate | Drawing | Detail | Fire Fighting System | Piping & Utility | TAM | 2018-02-01 11:42 | IFC | AFC | 100%
132762 | I491TG99-0MSAA91-016-002 | P&ID OF AUTOMATIC FIRE FIGHTING FM200 SYSTEM FOR EAF 2-18 | 04 | 2018-02-01 11:42 | Indeterminate | Drawing | Detail | Fire Fighting System | Piping & Utility | TAM | 2018-02-01 11:42 | IFC | AFC | 100%
132763 | I491TG99-0MSAA91-016-003 | P&ID OF AUTOMATIC FIRE FIGHTING FM200 SYSTEM FOR LF 3-18 | 04 | 2018-02-01 11:42 | Indeterminate | Drawing | Detail | Fire Fighting System | Piping & Utility | TAM | 2018-02-01 11:42 | IFC | AFC | 100%
132764 | I491TG99-0MSAA91-016-004 | P&ID OF AUTOMATIC FIRE FIGHTING FM200 SYSTEM FOR WTP 4-18 | 04 | 2018-02-01 11:42 | Indeterminate | Drawing | Detail | Fire Fighting System | Piping & Utility | TAM | 2018-02-01 11:42 | IFC | AFC | 100%
132765 | I491TG99-0MSAA91-016-005 | P&ID OF AUTOMATIC FIRE FIGHTING FM200 SYSTEM FOR ASP 5-18 | 04 | 2018-02-01 11:42 | Indeterminate | Drawing | Detail | Fire Fighting System | Piping & Utility | TAM | 2018-02-01 11:42 | IFC | AFC | 100%
132766 | I491TG99-0MSAA91-016-006 | P&ID OF AUTOMATIC FIRE FIGHTING FM200 SYSTEM FOR FTP 6-18 | 04 | 2018-02-01 11:42 | Indeterminate | Drawing | Detail | Fire Fighting System | Piping & Utility | TAM | 2018-02-01 11:42 | IFC | AFC | 100%
132767 | I491TG99-0MSAA91-016-007 | P&ID OF AUTOMATIC FIRE FIGHTING FM200 SYSTEM FOR CCM 7-18 | 04 | 2018-02-01 11:42 | Indeterminate | Drawing | Detail | Fire Fighting System | Piping & Utility | TAM | 2018-02-01 11:42 | IFC | AFC | 100%
132768 | I491TG99-0MSAA91-016-008 | DATA FOR AUTOMATIC FIRE FIGHTING FM200 SYSTEM 8-18 | 03 | 2018-02-01 11:42 | Indeterminate | Drawing | Detail | Fire Fighting System | Piping & Utility | TAM | 2018-02-01 11:42 | IFC | AFC | 100%
132757 | I491TG99-0MSAA91-016-009 | P&ID OF AUTOMATIC FIRE FIGHTING FM200 SYSTEM FOR ASP 9-18 | 01 | 2018-02-01 11:41 | Indeterminate | Drawing | Detail | Fire Fighting System | Piping & Utility | TAM | 2018-02-01 11:41 | IFC | AFC | 100%
132758 | I491TG99-0MSAA91-016-010 | P&ID OF AUTOMATIC FIRE FIGHTING FM200 SYSTEM FOR ASP 10-18 | 01 | 2018-02-01 11:42 | Indeterminate | Drawing | Detail | Fire Fighting System | Piping & Utility | TAM | 2018-02-01 11:42 | IFC | AFC | 100%
132759 | I491TG99-0MSAA91-016-011 | P&ID OF AUTOMATIC FIRE FIGHTING FM200 SYSTEM FOR ASP 11-18 | 01 | 2018-02-01 11:42 | Indeterminate | Drawing | Detail | Fire Fighting System | Piping & Utility | TAM | 2018-02-01 11:42 | IFC | AFC | 100%
132760 | I491TG99-0MSAA91-016-012 | P&ID OF AUTOMATIC FIRE FIGHTING FM200 SYSTEM FOR CCM 12-18 | 01 | 2018-02-01 11:42 | Indeterminate | Drawing | Detail | Fire Fighting System | Piping & Utility | TAM | 2018-02-01 11:42 | IFC | AFC | 100%
133864 | I491TG99-0MSAA91-016-013 | P&ID OF AUTOMATIC FIRE FIGHTING FM200 SYSTEM FOR ASP POWER ROOM 13-18 | 00 | 2018-07-22 | Indeterminate | Drawing | Detail | Fire Fighting System | Piping & Utility | TAM | 2018-07-23 08:37 | IFA | A | 100%
133865 | I491TG99-0MSAA91-016-014 | P&ID OF AUTOMATIC FIRE FIGHTING FM200 SYSTEM FOR ASP CONTROL ROOM 14-18 | 00 | 2018-07-22 | Indeterminate | Drawing | Detail | Fire Fighting System | Piping & Utility | TAM | 2018-07-23 08:38 | IFA | A | 100%
133866 | I491TG99-0MSAA91-016-015 | P&ID OF AUTOMATIC FIRE FIGHTING FM200 SYSTEM FOR WTP RO CONTROL ROOM 15-18 | 00 | 2018-07-22 | Indeterminate | Drawing | Detail | Fire Fighting System | Piping & Utility | TAM | 2018-07-23 08:38 | IFA | A | 100%
133867 | I491TG99-0MSAA91-016-016 | P&ID OF AUTOMATIC FIRE FIGHTING FM200 SYSTEM FOR WTP SUPERVISORY ROOM 16-18 | 00 | 2018-07-22 | Indeterminate | Drawing | Detail | Fire Fighting System | Piping & Utility | TAM | 2018-07-23 08:38 | IFA | A | 100%
133868 | I491TG99-0MSAA91-016-017 | P&ID OF AUTOMATIC FIRE FIGHTING FM200 SYSTEM FOR WTP SEDIMENTATION BLOWER MCC PANEL ROOM 17-18 | 00 | 2018-07-22 | Indeterminate | Drawing | Detail | Fire Fighting System | Piping & Utility | TAM | 2018-07-23 08:38 | IFA | A | 100%
133869 | I491TG99-0MSAA91-016-018 | P&ID OF AUTOMATIC FIRE FIGHTING FM200 SYSTEM FOR WTP RUN OUT 18-18 | 00 | 2018-07-22 | Indeterminate | Drawing | Detail | Fire Fighting System | Piping & Utility | TAM | 2018-07-23 08:38 | IFA | A | 100%
114992 | I491TG99-0MSAA91-017-001 | PIPING PLAN - CO2 SYSTEM EAF BUILDING /SWITCHGEAR ROOM 2 1-2 | 00 | 2016-03-01 | Indeterminate | Drawing | Basic | Fire Fighting System | Piping & Utility | TAM | 2016-03-07 09:40 | IFA | AC |  | 95%
114993 | I491TG99-0MSAA91-017-002 | PIPING PLAN - CO2 SYSTEM EAF BUILDING /SWITCHGEAR ROOM 2 2-2 | 00 | 2016-03-01 | Indeterminate | Drawing | Basic | Fire Fighting System | Piping & Utility | TAM | 2016-03-07 09:40 | IFA | AC |  | 95%
114994 | I491TG99-0MSAA91-018-001 | PIPING PLAN - CO2 SYSTEM LF BUILDING /SWITCHGEAR ROOM | 00 | 2016-03-01 | Indeterminate | Drawing | Basic | Fire Fighting System | Piping & Utility | TAM | 2016-03-07 09:40 | IFA | AC |  | 95%
114995 | I491TG99-0MSAA91-019-001 | PIPING PLAN - CO2 SYSTEM WTP BUILDING /SWITCHGEAR ROOM | 00 | 2016-03-01 | Indeterminate | Drawing | Basic | Fire Fighting System | Piping & Utility | TAM | 2016-03-07 09:41 | IFA | AC |  | 95%
130908 | I491TG99-0MSAA91-023-001 | PIPING PLAN - CO2 SYSTEM CCM BUILDING /SWITCHGEAR ROOM | 00 | 2017-07-26 | Indeterminate | Drawing | Detail | Fire Fighting System | Mechanical | TAM | 2017-07-30 10:54 | IFI | OB | 100%
115201 | I491TG99-0MSAA91-025-001 | PIPING PLAN - FM200 SYSTEM EAF BUILDING ROOM 1-3 | 00 | 2016-05-03 | Indeterminate | Drawing | Detail | Fire Fighting System | Piping & Utility | TAM | 2016-05-10 14:59 | IFI | OB | 100%
115200 | I491TG99-0MSAA91-025-002 | PIPING PLAN - FM200 SYSTEM EAF BUILDING ROOM 2-3 | 00 | 2016-05-03 | Indeterminate | Drawing | Detail | Fire Fighting System | Piping & Utility | TAM | 2016-05-10 14:59 | IFI | OB | 100%
115199 | I491TG99-0MSAA91-025-003 | PIPING PLAN - FM200 SYSTEM EAF BUILDING ROOM 3-3 | 00 | 2016-05-03 | Indeterminate | Drawing | Detail | Fire Fighting System | Piping & Utility | TAM | 2016-05-10 14:59 | IFI | OB | 100%
115193 | I491TG99-0MSAA91-026-001 | PIPING PLAN - FM200 SYSTEM WTP BUILDING ROOM 1-1 | 00 | 2016-05-03 | Indeterminate | Drawing | Detail | Fire Fighting System | Piping & Utility | TAM | 2016-05-10 14:59 | IFI | OB | 100%
115194 | I491TG99-0MSAA91-027-001 | PIPING PLAN - FM200 SYSTEM ASP BUILDING ROOM 1-1 | 00 | 2016-05-03 | Indeterminate | Drawing | Detail | Fire Fighting System | Piping & Utility | TAM | 2016-05-10 14:59 | IFI | OB | 100%
115195 | I491TG99-0MSAA91-028-001 | PIPING PLAN - FM200 SYSTEM SMP BUILDING ROOM 1-1 | 00 | 2016-05-03 | Indeterminate | Drawing | Detail | Fire Fighting System | Piping & Utility | TAM | 2016-05-10 14:59 | IFI | OB | 100%
115196 | I491TG99-0MSAA91-029-001 | PIPING PLAN - FM200 SYSTEM LF BUILDING ROOM 1-3 | 00 | 2016-05-03 | Indeterminate | Drawing | Detail | Fire Fighting System | Piping & Utility | TAM | 2016-05-10 14:59 | IFI | OB | 100%
115197 | I491TG99-0MSAA91-029-002 | PIPING PLAN - FM200 SYSTEM LF BUILDING ROOM 2-3 | 00 | 2016-05-03 | Indeterminate | Drawing | Detail | Fire Fighting System | Piping & Utility | TAM | 2016-05-10 14:59 | IFI | OB | 100%
115198 | I491TG99-0MSAA91-029-003 | PIPING PLAN - FM200 SYSTEM LF BUILDING ROOM 3-3 | 00 | 2016-05-03 | Indeterminate | Drawing | Detail | Fire Fighting System | Piping & Utility | TAM | 2016-05-10 14:59 | IFI | OB | 100%
115202 | I491TG99-0MSAA91-030-001 | PIPING PLAN - FM200 SYSTEM FTP BUILDING ROOM 1-2 | 00 | 2016-05-03 | Indeterminate | Drawing | Detail | Fire Fighting System | Piping & Utility | TAM | 2016-05-10 14:59 | IFI | OB | 100%
115203 | I491TG99-0MSAA91-030-002 | PIPING PLAN - FM200 SYSTEM FTP BUILDING ROOM 2-2 | 00 | 2016-05-03 | Indeterminate | Drawing | Detail | Fire Fighting System | Piping & Utility | TAM | 2016-05-10 14:59 | IFI | OB | 100%
130909 | I491TG99-0MSAA91-031-001 | PIPING PLAN - FM200 SYSTEM CCM BUILDING ROOM 1-2 | 00 | 2017-07-26 | Indeterminate | Drawing | Detail | Fire Fighting System | Mechanical | TAM | 2017-07-30 10:56 | IFI | OB | 100%
130910 | I491TG99-0MSAA91-031-002 | PIPING PLAN - FM200 SYSTEM CCM BUILDING ROOM 2-2 | 00 | 2017-07-26 | Indeterminate | Drawing | Detail | Fire Fighting System | Mechanical | TAM | 2017-07-30 10:56 | IFI | OB | 100%
15365 | I491TG99-0MXAA91-001-003 | Streets And Traffic Report | 02 | 2013-01-07 | Indeterminate | Miscellaneous(MISC) | Basic | General | Mechanical | TAM |  | IFC | AFC | 100%
15400 | I491TG99-0MXAA91-001-006 | Basic Data Of Warehouse | 03 | 2013-12-29 07:21 | Indeterminate | Miscellaneous(MISC) | Basic | Warehouse | Mechanical | TAM |  | IFC | AFC | 100%
15364 | I491TG99-0MXAA91-001-007 | Overview Of Paging System | 01 | 2012-06-19 | Indeterminate | Drawing | Basic | Comunication | Mechanical | TAM |  | IFA | AC |  | 95%
16567 | I491TG99-0MXAA91-002-001 | Basic Data Of Mobile Equipment | 00 | 2011-05-23 | Indeterminate | Miscellaneous(MISC) | Basic | Mobile Equipment | Mechanical | TAM |  | IFA | AC |  | 95%
15367 | I491TG99-0MXAA91-002-003 | Basis Of Design (Mechanical And Electrical Utilities) For Warehouse | 01 | 2012-02-13 | Indeterminate | Miscellaneous(MISC) | Basic | Warehouse | Mechanical | TAM |  | IFC | AC |  | 95%
15371 | I491TG99-0MXAA91-003-004 | Overview Of Telephone System | 01 | 2012-06-19 | Indeterminate | Drawing | Basic | Comunication | Mechanical | TAM |  | IFA | AC |  | 95%
15372 | I491TG99-0MXAA91-003-005 | Basis Of Design For The Complete Plant | 02 | 2012-06-30 | Indeterminate | Miscellaneous(MISC) | Basic | General | Mechanical | TAM |  | IFC | AFC | 100%
15374 | I491TG99-0MXAA91-004-002 | Overview Of Intercom System | 01 | 2012-06-19 | Indeterminate | Drawing | Basic | Comunication | Mechanical | TAM |  | IFA | AC |  | 95%
15375 | I491TG99-0MXAA91-005-001 | Overview Of Paging System | 00 | 2011-07-10 | Indeterminate | Drawing | Basic | Comunication | Mechanical | TAM |  | IFA | AC |  | 95%
15377 | I491TG99-0MXAA91-005-003 | Basic Data Of Slag Yard | 01 | 2012-04-22 | Indeterminate | Miscellaneous(MISC) | Basic | Slag Yard | Mechanical | TAM |  | IFC | AFC | 100%
15379 | I491TG99-0MXAA91-006-002 | Basic Data Of Mobile Equipment | 02 | 2012-11-13 | Indeterminate | Miscellaneous(MISC) | Detail | Mobile Equipment | Mechanical | TAM |  | IFC | AFC | 100%
115668 | I491TG99-0MYAA91-001-003 | Basic Data For Maintenance Workshop | 05 | 2016-06-06 11:15 | Indeterminate | Miscellaneous(MISC) | Basic | Maintenance Workshop | Mechanical | TAM | 2016-06-06 11:15 | IFC | AFC | 100%
15380 | I491TG99-0MYAA91-002-001 | Workshop Basis Of Design (Mechanical And Electrical Utilities) | 00 | 2012-02-20 | Indeterminate | Miscellaneous(MISC) | Basic | Maintenance Workshop | Mechanical | TAM |  | IFA | AC |  | 95%
15383 | I491TG99-0NGAA91-001-003 | Basic Data Of Natural Gas Pressure Reduction Station | 02 | 2011-11-02 | Indeterminate | Miscellaneous(MISC) | Basic | Natural Gas Reducing Station | Mechanical | TAM |  | IFC | AFC | 100%
15384 | I491TG99-0NGAA91-002-001 | Basic Engineering For Natural Gas Distribution System | 00 | 2012-07-17 | Indeterminate | Miscellaneous(MISC) | Basic | Natural Gas Reducing Station | Piping & Utility | TAM |  | IFA | AC |  | 95%
15386 | I491TG99-0SHAA91-001-006 | Basic Data Of Scrap Yard Equipment | 05 | 2012-12-31 | Indeterminate | Miscellaneous(MISC) | Basic | Scrap Yard Equipment | Mechanical | TAM |  | IFC | AFC | 100%
15387 | I491TG99-0SHAA91-002-001 | Scrap Yard Basis Of Design (Mechanical And Electrical Utilities) | 00 | 2012-03-07 | Indeterminate | Miscellaneous(MISC) | Basic | General Civil | Civil and Steel Structure | TAM |  | IFA | AC |  | 95%
15393 | I491TG99-0TBAA91-001-004 | Basic Data Of Ferroalloy Storage | 02 | 2012-07-04 | Indeterminate | Miscellaneous(MISC) | Basic | Melt Shop Lime And Ferroalloy Storage | Mechanical | TAM |  | IFC | AFC | 100%
15397 | I491TG99-0TBAA91-002-001 | Basic Data Of Ferroalloy Storage(Base On 800,000 Ton Production) | 00 | 2013-12-29 07:21 | Indeterminate | Miscellaneous(MISC) | Basic | Melt Shop Lime And Ferroalloy Storage | Mechanical | TAM |  | IFA | AC |  | 95%
15394 | I491TG99-0TBAA91-002-005 | Ferroalloy Storage Basis Of Design(Mechanical And Electrical Utilities) | 00 | 2012-03-06 | Indeterminate | Miscellaneous(MISC) | Basic | General Civil | Civil and Steel Structure | TAM |  | IFA | AC |  | 95%
15403 | I491TH02-0ASAA91-001-001 | Material Requisition For Air Separation Plant | 00 | 2011-11-20 | Indeterminate | Miscellaneous(MISC) | Detail | Air Separation Plant | Piping & Utility | Fortune |  | IFI | OB | 100%
132576 | I491TH02-0ASDR01-002-001 | MATERIAL REQUISITION FOR AIR SEPARATION PLANT PERLITE OF COLDBOX | 00 | 2017-12-19 | Indeterminate | Miscellaneous(MISC) | Detail | Air Separation Plant | Mechanical | TAM | 2017-12-27 09:50 | IFI | OB | 100%
15404 | I491TH02-0CCAA91-001-001 | Material Requisition For Continuous Casting Machine | 00 | 2011-11-20 | Indeterminate | Material Requisition(MR) | Basic | Continuous Casting Machine (CCM) | Mechanical | INTECO |  | IFI | OB | 100%
130442 | I491TH02-0CCFF91-001-001 | Material requisition for CCM Castable Dense Refractory | 00 | 2017-04-08 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2017-04-17 10:51 | IFI | OB | 100%
15405 | I491TH02-0CHAA91-001-001 | Material Requisition For Heavy Duty Cranes | 00 | 2011-11-22 | Indeterminate | Material Requisition(MR) | Basic | Crane and Hiosts | Mechanical | TAM |  | IFI | OB | 100%
15406 | I491TH02-0DTAA91-001-001 | Material Requisition For Fume Treatment Plant | 00 | 2011-11-20 | Indeterminate | Material Requisition(MR) | Basic | Fume Treatment Equipment | Mechanical | HASCON |  | IFI | OB | 100%
131360 | I491TH02-0DTFF91-001-001 | Material Requisition for Insulation of settling chamber | 02 | 2017-10-04 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Equipment | Mechanical | TAM | 2017-10-11 09:27 | IFI | OB | 100%
15407 | I491TH02-0EAAA91-001-001 | Material Requisition For Eaf & Lf | 00 | 2011-11-20 | Indeterminate | Miscellaneous(MISC) | Detail | Electric Arc Furnace | Mechanical | TAM |  | IFI | OB | 100%
131117 | I491TH02-0EAEC01-002-001 | Material Requisition For Electrode Recovery Tong | 01 | 2017-08-26 | Indeterminate | Miscellaneous(MISC) | Detail | Eaf Auxiliaries | Mechanical | TAM | 2017-08-30 13:38 | IFI | OB | 100%
130548 | I491TH02-0LAXL91-001-001 | Material Requisition For Equipment Of Laboratory | 01 | 2017-05-03 | Indeterminate | Miscellaneous(MISC) | Detail | Laboratory | Mechanical | TAM | 2017-05-06 14:12 | IFI | AC |  | 95%
15408 | I491TH02-0MEAA91-001-001 | Material Requisition For 400/33 Kv Substation | 00 | 2011-10-10 | Indeterminate | Material Requisition(MR) | Basic | Main Electrical Substation And Distribution Network | Mechanical | TAM |  | IFI | OB | 100%
130713 | I491TH02-0MSAA91-001-001 | Material Requisition For Fire Fighting Total Flooding System | 00 | 2017-06-19 | Indeterminate | Miscellaneous(MISC) | Detail | Fire Fighting System | Mechanical | TAM | 2017-06-21 13:41 | IFI | OB | 100%
130638 | I491TH02-0MYAA91-001-001 | Material Requisition For workshop Equipment | 02 | 2017-05-28 11:30 | Indeterminate | Miscellaneous(MISC) | Detail | Maintenance Workshop | Mechanical | TAM | 2017-05-28 11:30 | IFI | OB | 100%
129783 | I491TH02-0PXFF91-001-001 | Material Requisition for General Refractories of Melt shop | 00 | 2016-11-08 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop | Mechanical | TAM | 2016-11-12 09:08 | IFI | AC |  | 95%
129344 | I491TH02-0PXGA01-001-001 | Material Requisition For Gas Coupling And Connections | 00 | 2016-08-27 08:54 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop Auxiliaries | Mechanical | TAM | 2016-08-27 08:54 | IFI | OB | 100%
134400 | I491TH02-0PXLV01-001-001 | REQUST FOR QOUTATION OF SMP ELEVATOR | 00 | 2018-11-13 | Indeterminate | Miscellaneous(MISC) | Detail | Eaf Auxiliaries | Mechanical | TAM | 2018-11-15 10:34 | IFI | OB | 100%
129766 | I491TH02-0RXGA01-001-001 | Technical Specification for Emergency stirring lance | 01 | 2016-10-29 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace Auxiliary | Mechanical | TAM | 2016-11-02 09:25 | IFC | AC |  | 95%
130249 | I491TH02-0SXLX01-001-001 | Material Requisition For Lime Injection system | 00 | 2017-01-16 | Indeterminate | Miscellaneous(MISC) | Detail | Eaf Auxiliaries | Mechanical | TAM | 2017-01-24 14:59 | IFI | OB | 100%
132773 | I491TH02-0WAAA91-001-001 | Material Requisition For Warehouse Auxilliary Equipment | 01 | 2018-01-23 | Indeterminate | Miscellaneous(MISC) | Detail | Warehouse | Mechanical | TAM | 2018-02-03 13:07 | IFI | OB | 100%
129601 | I491TH02-0WAXT91-001-001 | Material Requisition For Warehouses Rack Shelf System | 00 | 2016-09-27 | Indeterminate | Miscellaneous(MISC) | Detail | Warehouse | Mechanical | TAM | 2016-09-29 09:53 | IFI | OB | 100%
15410 | I491TH03-0MXAA91-001-002 | General Technical Specifications For Painting & Colour Coding | 01 | 2011-12-26 | Indeterminate | Miscellaneous(MISC) | Detail | General | Mechanical | TAM |  | IFC | AFC | 100%
134636 | I491TH05-0PXFD91-001-001 | Melt Shop Debricking Machine Transport Prescription-1080049110010081 | 00 | 2018-12-12 | Indeterminate | Drawing | Detail | Mobile Equipment | Mechanical | TAM | 2018-12-17 09:25 | IFI | OB | 100%
114711 | I491TH06-0MDAA91-002-002 | Lv Switchgear Inquiry Document For Material Handling ((Conveyor)) System | 02 | 2015-11-24 | Indeterminate | Miscellaneous(MISC) | Detail | Material Handling | Electrical | DATIS | 2015-11-25 10:53 | IFC | AFC | 100%
15416 | I491TH06-0MDCB91-001-004 | Local Control Box Inquiry Document For Material Handling (Conveyor) System | 02 | 2013-08-17 | Indeterminate | Miscellaneous(MISC) | Detail | Material Handling | Electrical | DATIS |  | IFC | AFC | 100%
113138 | I491TH06-0MMCT01-001-001 | Material Requisition for Plate Heat exchainger | 00 | 2014-12-17 13:53 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Mechanical | TAM | 2014-12-17 13:53 | IFI | AC |  | 95%
129952 | I491TI01-0ASAA91-001-001 | PLC Instrument Earthing Diagram Air Separation Plant | 00 | 2016-12-12 | Indeterminate | Drawing | Detail | Air Separation Plant | Automation and Instrumentation | Fortune | 2016-12-13 08:46 | IFA | A | 100%
115116 | I491TI01-0ASAA91-002-001 | PLC system Diagram | 00 | 2016-04-04 | Indeterminate | Drawing | Detail | Air Separation Plant | Automation and Instrumentation | Fortune | 2016-04-06 14:27 | IFA | OB | 100%
115344 | I491TI01-0ASAA91-003-001 | Support Diagram for Tray | 00 | 2016-05-16 | Indeterminate | Miscellaneous(MISC) | Detail | Air Separation Plant | Automation and Instrumentation | Fortune | 2016-05-25 09:50 | IFA | A | 100%
115110 | I491TI01-0ASAA91-004-001 | ASP Instrument HOOKUP 20160205 | 00 | 2016-04-04 | Indeterminate | Miscellaneous(MISC) | Detail | Air Separation Plant | Automation and Instrumentation | Fortune | 2016-04-06 13:58 | IFA | AC |  | 95%
134088 | I491TI01-0ASCP02-001-001 | Electrical Schematic NEMA12 06_2_ES_24646879 (4Sheet) | 00 | 2018-08-15 | Indeterminate | Miscellaneous(MISC) | Detail | Air Separation Plant Main Building | Mechanical | TAM | 2018-08-21 13:06 | IFI | OB | 100%
112642 | I491TI01-0CCAA91-001-001 | AUTOMATION BLOCK DIAGRAM | 00 | 2014-08-09 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Automation and Instrumentation | TAM | 2014-08-10 08:53 | IFA | AC |  | 95%
134234 | I491TI01-0CCHB01-001-001 | Tundish Preheater PID COMBUSTIONE 001-DS-17000-1_P&ID COMBUSTIONE | 01 | 2018-09-23 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2018-10-02 08:58 | IFC | AFC | 100%
134235 | I491TI01-0CCHB01-002-001 | Tundish Preheater PID IDRAULICA 001-DH-17001-0 | 01 | 2018-09-23 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2018-10-02 08:58 | IFC | AFC | 100%
134236 | I491TI01-0CCHB02-001-001 | Preheating Stove PI COMBUSTIONE 020-DS-16943-1 | 01 | 2018-09-23 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2018-10-02 08:58 | IFC | AFC | 100%
134237 | I491TI01-0CCHB03-001-001 | Sen and Nozzel Preheater 051-DS-16937-2_P&ID COMBUSTIONE | 01 | 2018-09-23 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2018-10-02 08:58 | IFC | AFC | 100%
134238 | I491TI01-0CCTD10-001-001 | Tundish Drying Station 001-DH-17003-0_PID_IDRAULICA | 01 | 2018-09-23 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2018-10-02 08:59 | IFC | AFC | 100%
134239 | I491TI01-0CCTD10-002-001 | Tundish Drying Station 001-DH-17003-0_PID_IDRAULICA | 01 | 2018-09-23 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2018-10-02 08:59 | IFC | AFC | 100%
115765 | I491TI01-0CHEU01-001-001 | AUTOMATION BLOCK DIAGRAM FOR TEEMING CRANE | 00 | 2016-06-15 | Indeterminate | Drawing | Detail | Crane and Hiosts | Automation and Instrumentation | TAM | 2016-06-21 14:23 | IFA | AC |  | 95%
15417 | I491TI01-0CPAA91-001-001 | Instrument Hook Up (Field ) | 00 | 2013-03-03 | Indeterminate | Miscellaneous(MISC) | Detail | Compressed Air Production Plant | Automation and Instrumentation | HAVAYAR |  | IFA | OB | 100%
113023 | I491TI01-0CPAA91-002-001 | CAP Local Control Panel Drawing & Dimensio | 01 | 2014-10-14 | Indeterminate | Drawing | Detail | Compressed Air Production Plant | Electrical | TAM | 2014-10-20 16:26 | IFI | OB | 100%
113024 | I491TI01-0CPAA91-003-001 | CAP UNIT CONTROL PANEL DRAWING & DIMENSION | 01 | 2014-10-14 | Indeterminate | Drawing | Detail | Compressed Air Production Plant | Electrical | TAM | 2014-10-20 16:26 | IFI | OB | 100%
130878 | I491TI01-0DTAA91-001-001 | FTP Automation Block Diagram | 02 | 2017-07-17 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Automation and Instrumentation | HASCON | 2017-07-24 12:43 | IFC | AFC | 100%
113256 | I491TI01-0DTAA91-003-001 | Electrical And Instruments Typical Detail Chook-Up For Fume Treatment Plant | 00 | 2015-01-18 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Automation and Instrumentation | HASCON | 2015-01-20 13:10 | IFA | AC |  | 95%
129941 | I491TI01-0DTAA91-103-001 | DRI - Typical Hook-up connection diagram | 00 | 2016-12-07 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Automation and Instrumentation | HASCON | 2016-12-12 16:45 | IFA | AC |  | 95%
135388 | I491TI01-0MDAA91-001-003 | Automation Block Diagram For Materail Handling Plant | 03 | 2019-05-20 | Indeterminate | Miscellaneous(MISC) | Basic | Material Handling | Automation and Instrumentation | DATIS | 2019-05-21 11:32 | IFC | AC |  | 95%
15422 | I491TI01-0MDAA91-002-001 | Cover Sheet 1/14 | 00 | 2013-05-28 | Indeterminate | Drawing | Detail | Material Handling | Automation and Instrumentation | DATIS |  | IFA | A | 100%
15428 | I491TI01-0MDAA91-002-002 | Revision Index 2/14 | 00 | 2013-05-28 | Indeterminate | Drawing | Detail | Material Handling | Automation and Instrumentation | DATIS |  | IFA | A | 100%
15429 | I491TI01-0MDAA91-002-003 | General Note And References 3/14 | 00 | 2013-05-28 | Indeterminate | Drawing | Detail | Material Handling | Automation and Instrumentation | DATIS |  | IFA | A | 100%
15430 | I491TI01-0MDAA91-002-004 | Code Number 4/14 | 00 | 2013-05-28 | Indeterminate | Drawing | Detail | Material Handling | Automation and Instrumentation | DATIS |  | IFA | A | 100%
15431 | I491TI01-0MDAA91-002-005 | Pr01: Pull Rope Switch 5/14 | 00 | 2013-05-28 | Indeterminate | Drawing | Detail | Material Handling | Automation and Instrumentation | DATIS |  | IFA | A | 100%
15432 | I491TI01-0MDAA91-002-006 | Ms01: Skew Switch 6/14 | 00 | 2013-05-28 | Indeterminate | Drawing | Detail | Material Handling | Automation and Instrumentation | DATIS |  | IFA | A | 100%
15433 | I491TI01-0MDAA91-002-007 | Ms01: Skew Switch 7/14 | 00 | 2013-05-28 | Indeterminate | Drawing | Detail | Material Handling | Automation and Instrumentation | DATIS |  | IFA | A | 100%
15434 | I491TI01-0MDAA91-002-008 | Ss01: Speed Switch (Proximity) 8/14 | 00 | 2013-05-28 | Indeterminate | Drawing | Detail | Material Handling | Automation and Instrumentation | DATIS |  | IFA | A | 100%
15435 | I491TI01-0MDAA91-002-009 | Hl01: Horn-Light (Low Distance) 9/14 | 00 | 2013-05-28 | Indeterminate | Drawing | Detail | Material Handling | Automation and Instrumentation | DATIS |  | IFA | A | 100%
15423 | I491TI01-0MDAA91-002-010 | Hl02: Horn-Light (Local) 10/14 | 00 | 2013-05-28 | Indeterminate | Drawing | Detail | Material Handling | Automation and Instrumentation | DATIS |  | IFA | A | 100%
15424 | I491TI01-0MDAA91-002-011 | Tp01: Position Switch (Tilt) 11/14 | 00 | 2013-05-28 | Indeterminate | Drawing | Detail | Material Handling | Automation and Instrumentation | DATIS |  | IFA | A | 100%
15425 | I491TI01-0MDAA91-002-012 | Tp02: Position Switch (Tilt) 12/14 | 00 | 2013-05-28 | Indeterminate | Drawing | Detail | Material Handling | Automation and Instrumentation | DATIS |  | IFA | A | 100%
15426 | I491TI01-0MDAA91-002-013 | Jb01: Junction Box Stand On Structure 13/14 | 00 | 2013-05-28 | Indeterminate | Drawing | Detail | Material Handling | Automation and Instrumentation | DATIS |  | IFA | A | 100%
15427 | I491TI01-0MDAA91-002-014 | Sh01: Sunshade 14/14 | 00 | 2013-05-28 | Indeterminate | Drawing | Detail | Material Handling | Automation and Instrumentation | DATIS |  | IFA | A | 100%
114922 | I491TI01-0MDAA91-005-001 | MHS Control Logic Diagram | 01 | 2016-02-16 | Indeterminate | Drawing | Detail | Material Handling | Automation and Instrumentation | DATIS | 2016-02-21 09:55 | IFC | AC |  | 95%
15436 | I491TI01-0MEYC02-301-002 | Avr Control & Interlocking Logic Diagram | 01 | 2012-06-13 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
15437 | I491TI01-0MEYC03-501-001 | 400/33 Kv Substation Control Sircuit Diagram | 01 | 2013-09-04 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
15438 | I491TI01-0MEYC03-511-001 | 400/33 Kv Substation Control Sircuit Diagram | 01 | 2013-09-04 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
15439 | I491TI01-0MEYC03-512-001 | 400/33 Kv Substation Control Sircuit Diagram | 01 | 2013-09-04 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
15440 | I491TI01-0MEYC03-531-001 | 400/33 Kv Substation Control Sircuit Diagram | 01 | 2013-09-04 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
15456 | I491TI01-0MEYC03-532-001 | 400/33 Kv Substation Control Sircuit Diagram | 01 | 2013-09-04 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
15457 | I491TI01-0MEYC03-533-001 | 400/33 Kv Substation Control Sircuit Diagram | 01 | 2013-09-04 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
15441 | I491TI01-0MEYC03-801-001 | 400/33 Kv Substation Measuring Panels Sircuit Diagram | 01 | 2013-09-04 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
15442 | I491TI01-0MEYC03-901-001 | 400/33 Kv Substation Avr Panels Sircuit Diagram | 01 | 2013-09-04 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
15443 | I491TI01-0MEYC03-902-001 | 400/33 Kv Substation Avr Panels Sircuit Diagram | 01 | 2013-09-04 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
15444 | I491TI01-0MEYC04-801-001 | Measuring Panel Circuit Diagrams | 00 | 2012-09-04 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
15455 | I491TI01-0MEYC05-300-002 | 400/33 Kv Substation Measuring Single Line Digram | 02 | 2013-05-28 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
15445 | I491TI01-0MKGN91-001-001 | Water Cooling System Automation Block Diagram | 00 | 2012-05-02 | Indeterminate | Drawing | Basic | Water Treatment & Cooling System | Automation and Instrumentation | FARABARD |  | IFA | AC |  | 95%
15446 | I491TI01-0MKGN91-001-002 | Automation Block Diagram For Water Cooling System | 00 | 2013-12-29 07:21 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Electrical | FARABARD |  | IFC | AFC | 100%
113211 | I491TI01-0MMCT01-002-001 | WTP LOGIC DIAGRAM | 03 | 2015-01-07 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Automation and Instrumentation | FARABARD | 2015-01-10 14:30 | IFC | AFC | 100%
130410 | I491TI01-0MMCT01-003-001 | INSTRUMENT HOOK UP AND Drawing | 03 | 2017-04-09 11:35 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Automation and Instrumentation | FARABARD | 2017-04-09 11:35 | IFC | AFC | 100%
15450 | I491TI01-0MXAA91-001-004 | Automation Block Diagram | 01 | 2013-05-26 | Indeterminate | Drawing | Basic | Automation and Control System | Mechanical | TAM |  | IFC | AFC | 100%
134637 | I491TI01-0PXFD91-001-001 | Melt Shop Debricking Machine Hydraulic Drawings 10711074a | 00 | 2018-12-12 | Indeterminate | Drawing | Detail | Mobile Equipment | Mechanical | TAM | 2018-12-17 09:25 | IFI | OB | 100%
114734 | I491TI01-0PXHB01-002-001 | Horizontal Ladle Preheater Pneumatic Diagram | 00 | 2015-11-28 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Automation and Instrumentation | CEBA | 2015-12-07 10:38 | IFA | AC |  | 95%
114735 | I491TI01-0PXPC01-001-001 | Horizontal Ladle Preheater Combustion Diagram | 01 | 2015-11-28 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Automation and Instrumentation | CEBA | 2015-12-07 10:41 | IFC | AFC | 100%
114729 | I491TI01-0RXGA91-001-001 | EMERGENCY STIRRING LANCE HYDRAULIC DIAGRAM | 00 | 2015-12-05 15:18 | Indeterminate | Drawing | Detail | Ladle Furnace Auxiliary | Mechanical | CEBA | 2015-12-05 15:18 | IFI | OB | 100%
114722 | I491TI01-0RXWH91-001-001 | Wire Feeder PNEUMATIC DIAGRAM 090-DA-13703 | 00 | 2015-11-28 | Indeterminate | Drawing | Detail | Ladle Furnace Auxiliary | Mechanical | CEBA | 2015-12-01 11:20 | IFI | A | 100%
15452 | I491TI01-0SHAA91-001-002 | Scrap Car Automation Diagram | 01 | 2012-12-08 | Indeterminate | Drawing | Detail | Scrap Yard Equipment | Automation and Instrumentation | TAM |  | IFC | AC |  | 95%
114709 | I491TI01-0SXHB91-003-001 | VERTICAL LADLE PREHEATER COMBUSTION DIAGRAM | 01 | 2015-11-24 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Automation and Instrumentation | CEBA | 2015-11-25 10:49 | IFC | AFC | 100%
114710 | I491TI01-0SXHB91-004-001 | VERTICAL LADLE PREHEATER HYDRAULIC DIAGRAM | 00 | 2015-11-24 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Automation and Instrumentation | CEBA | 2015-11-25 10:50 | IFA | AFC | 100%
114680 | I491TI01-0SXLD91-001-001 | VERTICAL LADLE DRYER COMBUSTION DIAGRAM | 01 | 2015-11-23 11:32 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Automation and Instrumentation | CEBA | 2015-11-23 11:32 | IFC | AFC | 100%
114681 | I491TI01-0SXLD91-002-001 | VERTICAL LADLE DRYER HYDRAULIC DIAGRAM | 00 | 2015-11-23 11:35 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Automation and Instrumentation | CEBA | 2015-11-23 11:35 | IFA | AFC | 100%
115146 | I491TI02-0ASAA91-001-001 | ASP Control Room Layout Diagram 1-4 | 00 | 2016-04-18 | Indeterminate | Drawing | Detail | Air Separation Plant | Automation and Instrumentation | Fortune | 2016-04-20 11:15 | IFA | AC |  | 95%
115147 | I491TI02-0ASAA91-001-002 | ASP Control Room Layout Diagram 2-4 | 00 | 2016-04-18 | Indeterminate | Drawing | Detail | Air Separation Plant | Automation and Instrumentation | Fortune | 2016-04-20 11:15 | IFA | AC |  | 95%
115148 | I491TI02-0ASAA91-001-003 | ASP Control Room Layout Diagram 3-4 | 00 | 2016-04-18 | Indeterminate | Drawing | Detail | Air Separation Plant | Automation and Instrumentation | Fortune | 2016-04-20 11:15 | IFA | AC |  | 95%
115149 | I491TI02-0ASAA91-001-004 | ASP Control Room Layout Diagram 4-4 | 00 | 2016-04-18 | Indeterminate | Drawing | Detail | Air Separation Plant | Automation and Instrumentation | Fortune | 2016-04-20 11:15 | IFA | AC |  | 95%
115345 | I491TI02-0ASAA91-002-001 | Instrument Cable and Tray Layout | 00 | 2016-05-16 | Indeterminate | Miscellaneous(MISC) | Detail | Air Separation Plant | Automation and Instrumentation | Fortune | 2016-05-25 09:50 | IFA | A | 100%
115107 | I491TI02-0ASAA91-003-001 | Instruments Point Layout 1-3 | 00 | 2016-04-03 | Indeterminate | Drawing | Detail | Air Separation Plant | Automation and Instrumentation | Fortune | 2016-04-06 10:24 | IFI | OB | 100%
115108 | I491TI02-0ASAA91-003-002 | Instruments Point Layout 2-3 | 00 | 2016-04-03 | Indeterminate | Drawing | Detail | Air Separation Plant | Automation and Instrumentation | Fortune | 2016-04-06 10:24 | IFI | OB | 100%
115109 | I491TI02-0ASAA91-003-003 | Instruments Point Layout 3-3 | 00 | 2016-04-03 | Indeterminate | Drawing | Detail | Air Separation Plant | Automation and Instrumentation | Fortune | 2016-04-06 10:24 | IFI | OB | 100%
134089 | I491TI02-0ASCP02-001-001 | Booster Air Compressor Control Panel Outline DWG 07_PANEL OL_24646887 | 00 | 2018-08-15 | Indeterminate | Drawing | Detail | Air Separation Plant Main Building | Mechanical | TAM | 2018-08-21 13:07 | IFI | OB | 100%
134090 | I491TI02-0ASCP02-002-001 | Booster Air Compressor Control Panel Specification 06_PANEL SPEC_24633463 (4 Sheet) | 00 | 2018-08-15 | Indeterminate | Miscellaneous(MISC) | Detail | Air Separation Plant Main Building | Mechanical | TAM | 2018-08-21 13:07 | IFI | OB | 100%
130407 | I491TI02-0AUAA91-001-001 | Level2 Control Room Layout & arrangement | 00 | 2017-03-12 | Indeterminate | Drawing | Detail | Automation and Control System | Automation and Instrumentation | ASM | 2017-04-05 14:07 | IFA | AC |  | 95%
114372 | I491TI02-0CCAA91-005-001 | Internal Electrical Equipment Layout GP08VB-HC11-E9000-ED201 | 01 | 2015-09-14 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Automation and Instrumentation | TAM | 2015-09-16 09:07 | IFC | AC |  | 95%
113194 | I491TI02-0CCAA91-005-002 | Internal Electrical Equipment Layout GP08VB-HC11-E9000-ED301 | 00 | 2015-01-04 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Automation and Instrumentation | TAM | 2015-01-07 17:31 | IFA | AC |  | 95%
113195 | I491TI02-0CCAA91-005-003 | Internal Electrical Equipment Layout GP08VB-HC11-E9000-ED302 | 00 | 2015-01-04 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Automation and Instrumentation | TAM | 2015-01-07 17:31 | IFA | AC |  | 95%
114386 | I491TI02-0CCAA91-006-001 | Internal Cable Way Layout (GP08VB-HC11-E9000-ED151-01-E-1700056 | 01 | 2015-09-15 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Automation and Instrumentation | TAM | 2015-09-16 09:30 | IFC | AC |  | 95%
114387 | I491TI02-0CCAA91-007-001 | Internal Cable Way Layout (GP08VB-HC11-E9000-ED152-01-E-1700541 | 01 | 2015-09-15 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Automation and Instrumentation | TAM | 2015-09-16 09:30 | IFC | AC |  | 95%
114388 | I491TI02-0CCAA91-008-001 | Internal Cable Way Layout (GP08VB-HC11-E9000-ED153-00-E-1740519 | 00 | 2015-09-15 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Automation and Instrumentation | TAM | 2015-09-16 09:30 | IFA | AC |  | 95%
114389 | I491TI02-0CCAA91-009-001 | Internal Cable Way Layout (GP08VB-HC11-T8700-ED040-00-E-1700547 | 00 | 2015-09-15 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Automation and Instrumentation | TAM | 2015-09-16 09:30 | IFA | AC |  | 95%
114390 | I491TI02-0CCAA91-010-001 | Internal Cable Way Layout (GP08VB-HC11-E9000-ED301-01-E-1700057 | 00 | 2015-09-15 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Automation and Instrumentation | TAM | 2015-09-16 09:30 | IFA | AC |  | 95%
114391 | I491TI02-0CCAA91-011-001 | Internal Cable Way Layout (GP08VB-HC11-E9000-ED302-01-E-1700059 | 00 | 2015-09-15 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Automation and Instrumentation | TAM | 2015-09-16 09:30 | IFA | AC |  | 95%
114402 | I491TI02-0CCAA91-021-001 | CCM MACHINE T.O.P FIELD ELECTRICAL DEVICE LAYOUT GP08VB-HC11-E9000-BD101 | 00 | 2015-09-27 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Automation and Instrumentation | DANIELI | 2015-09-28 10:44 | IFA | AC |  | 95%
114403 | I491TI02-0CCAA91-022-001 | CCM MACHINE T.O.P FIELD ELECTRICAL DEVICE LAYOUT GP08VB-HC11-E9000-BD102 | 00 | 2015-09-27 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Automation and Instrumentation | DANIELI | 2015-09-28 10:44 | IFA | AC |  | 95%
114404 | I491TI02-0CCAA91-023-001 | CCM MACHINE T.O.P FIELD ELECTRICAL DEVICE LAYOUT GP08VB-HC11-E9000-BD103 | 00 | 2015-09-27 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Automation and Instrumentation | DANIELI | 2015-09-28 10:44 | IFA | AC |  | 95%
114405 | I491TI02-0CCAA91-024-001 | CCM MACHINE T.O.P FIELD ELECTRICAL DEVICE LAYOUT GP08VB-HC11-E9000-BD104 | 00 | 2015-09-27 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Automation and Instrumentation | DANIELI | 2015-09-28 10:44 | IFA | AC |  | 95%
114406 | I491TI02-0CCAA91-025-001 | CCM MACHINE T.O.P FIELD ELECTRICAL DEVICE LAYOUT GP08VB-HC11-E9000-BD105 | 00 | 2015-09-27 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Automation and Instrumentation | DANIELI | 2015-09-28 10:44 | IFA | AC |  | 95%
114407 | I491TI02-0CCAA91-026-001 | CCM MACHINE T.O.P FIELD ELECTRICAL DEVICE LAYOUT GP08VB-HC11-E9000-BD106 | 00 | 2015-09-27 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Automation and Instrumentation | DANIELI | 2015-09-28 10:44 | IFA | AC |  | 95%
114408 | I491TI02-0CCAA91-027-001 | CCM MACHINE T.O.P FIELD ELECTRICAL DEVICE LAYOUT GP08VB-HC11-E9000-BD107 | 00 | 2015-09-27 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Automation and Instrumentation | DANIELI | 2015-09-28 10:44 | IFA | AC |  | 95%
114409 | I491TI02-0CCAA91-028-001 | CCM MACHINE T.O.P FIELD ELECTRICAL DEVICE LAYOUT GP08VB-HC11-E9000-BD108 | 00 | 2015-09-27 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Automation and Instrumentation | DANIELI | 2015-09-28 10:44 | IFA | AC |  | 95%
114410 | I491TI02-0CCAA91-029-001 | CCM MACHINE T.O.P FIELD ELECTRICAL DEVICE LAYOUT GP08VB-HC11-E9000-BD109 | 00 | 2015-09-27 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Automation and Instrumentation | DANIELI | 2015-09-28 10:44 | IFA | AC |  | 95%
114411 | I491TI02-0CCAA91-030-001 | CCM MACHINE T.O.P FIELD ELECTRICAL DEVICE LAYOUT GP08VB-HC11-E9000-BD110 | 00 | 2015-09-27 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Automation and Instrumentation | DANIELI | 2015-09-28 10:44 | IFA | AC |  | 95%
114412 | I491TI02-0CCAA91-031-001 | CCM MACHINE T.O.P FIELD ELECTRICAL DEVICE LAYOUT GP08VB-HC11-E9000-BD111 | 00 | 2015-09-27 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Automation and Instrumentation | DANIELI | 2015-09-28 10:44 | IFA | AC |  | 95%
114413 | I491TI02-0CCAA91-032-001 | CCM MACHINE T.O.P FIELD ELECTRICAL DEVICE LAYOUT GP08VB-HC11-E9000-BD101 | 00 | 2015-09-27 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Automation and Instrumentation | DANIELI | 2015-09-28 10:44 | IFA | AC |  | 95%
114414 | I491TI02-0CCAA91-033-001 | CCM MACHINE T.O.P FIELD ELECTRICAL DEVICE LAYOUT GP08VB-HC11-E9000-BD113 | 00 | 2015-09-27 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Automation and Instrumentation | DANIELI | 2015-09-28 10:44 | IFA | AC |  | 95%
113060 | I491TI02-0CCAM91-001-001 | CONTINUOUS CASTING MACHINE INTERNAL ELECTRICAL EQUIPMENTS LAYOUT HC11+E01 ELECTRICAL CABIN | 00 | 2014-10-07 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Automation and Instrumentation | TAM | 2014-11-06 11:56 | IFA | AC |  | 95%
15458 | I491TI02-0CCCW91-001-001 | Overview Cooling Water Systems Ccm | 00 | 2013-10-29 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Mechanical | TAM |  | IFA | AFC | 100%
15459 | I491TI02-0CCDF91-001-001 | Dummy Bar Withdrawal Unit | 00 | 2013-10-29 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Mechanical | TAM |  | IFA | AFC | 100%
15460 | I491TI02-0CCDF91-001-002 | Pneumatic Dummy Bar Movement | 00 | 2013-10-29 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Mechanical | TAM |  | IFA | AFC | 100%
133783 | I491TI02-0CCHY91-001-001 | CCM Ladle Turret and Tundish Car Hydraulic 6.374961.D_001_02 | 03 | 2018-07-18 14:37 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2018-07-18 14:37 | IFI | OB | 100%
15462 | I491TI02-0CCHY91-001-002 | Hydraulic Unit 1 | 00 | 2013-10-29 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Mechanical | TAM |  | IFA | AFC | 100%
133784 | I491TI02-0CCHY91-002-001 | CCM Ladle Turret Hydraulic 6374963F_002 | 03 | 2018-07-18 14:37 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2018-07-18 14:37 | IFI | OB | 100%
114586 | I491TI02-0CCHY91-002-002 | Sheet 2of3 CCM Ladle Turret Hydraulic 6.374963.F_002_02 | 00 | 2015-10-26 10:40 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-26 10:40 | IFI | OB | 100%
114588 | I491TI02-0CCHY91-002-003 | Sheet 3of3 CCM Ladle Turret Hydraulic 6.374963.F_003_02 | 00 | 2015-10-26 10:40 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-26 10:40 | IFI | OB | 100%
133782 | I491TI02-0CCHY91-003-001 | CCM Tundish Car Valve Stand 6374965A_001 | 02 | 2018-07-18 14:37 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Mechanical | TAM | 2018-07-18 14:37 | IFI | OB | 100%
133781 | I491TI02-0CCHY91-004-001 | CCM Ladle Turret Hydraulic 6374963F_003 | 02 | 2018-07-18 14:37 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Mechanical | TAM | 2018-07-18 14:37 | IFI | OB | 100%
133780 | I491TI02-0CCHY91-005-001 | CCM Ladle Turret 6374963F_001 | 01 | 2018-07-18 14:37 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Mechanical | TAM | 2018-07-18 14:37 | IFI | OB | 100%
133785 | I491TI02-0CCHY91-006-001 | CCM Extraction Straightening Unit 6.374999.C_001_01 | 03 | 2018-07-18 14:37 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2018-07-18 14:37 | IFI | OB | 100%
133786 | I491TI02-0CCHY91-007-001 | CCM Strand Cutting Device 6.374998.B_001_01A | 03 | 2018-07-18 14:37 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2018-07-18 14:37 | IFI | OB | 100%
133787 | I491TI02-0CCHY91-008-001 | CCM Slide Gate Unit 6.374996.S_001_01 | 03 | 2018-07-18 14:37 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2018-07-18 14:37 | IFI | OB | 100%
133788 | I491TI02-0CCHY91-009-001 | CCM Ladle Slide Gate Test 6.374995.Z_001_01A | 03 | 2018-07-18 14:37 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2018-07-18 14:37 | IFI | OB | 100%
130551 | I491TI02-0CCHY91-010-001 | CCM Valve Stand 6.374993.W_001_01 | 00 | 2017-05-07 14:19 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2017-05-07 14:19 | IFI | OB | 100%
133975 | I491TI02-0CCHY91-010-002 | CCM Slide Gates Valves Stand 6374993W_002 | 01 | 2018-07-18 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2018-08-11 13:15 | IFI | OB | 100%
133789 | I491TI02-0CCHY91-011-001 | CCM Valve Stand 6.374993.W_002_01 | 03 | 2018-07-18 14:37 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2018-07-18 14:37 | IFI | OB | 100%
133779 | I491TI02-0CCHY91-012-001 | CCM Moulds Lubrication 6 Strands 6374992V_001 | 01 | 2018-07-18 14:37 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Mechanical | TAM | 2018-07-18 14:37 | IFI | OB | 100%
133790 | I491TI02-0CCHY91-013-001 | CCM Tundish Tilting Hydraulic Unit 6.374990.F_001_01 | 02 | 2018-07-18 14:37 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2018-07-18 14:37 | IFI | OB | 100%
133791 | I491TI02-0CCHY91-014-001 | CCM Run Out Valves Stand 6.374985.W_006_01 | 02 | 2018-07-18 14:37 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2018-07-18 14:37 | IFI | OB | 100%
133792 | I491TI02-0CCHY91-015-001 | CCM Run Out Valves Stand 6.374985.W_005_01 | 02 | 2018-07-18 14:37 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2018-07-18 14:37 | IFI | OB | 100%
133793 | I491TI02-0CCHY91-016-001 | CCM Run Out Valves Stand 6.374985.W_004_01 | 02 | 2018-07-18 14:37 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2018-07-18 14:37 | IFI | OB | 100%
133794 | I491TI02-0CCHY91-017-001 | CCM Run Out Valves Stand 6.374985.W_003_01 | 02 | 2018-07-18 14:37 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2018-07-18 14:37 | IFI | OB | 100%
133795 | I491TI02-0CCHY91-018-001 | CCM Run Out Valves Stand 6.374985.W_002_01 | 02 | 2018-07-18 14:37 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2018-07-18 14:37 | IFI | OB | 100%
133796 | I491TI02-0CCHY91-019-001 | CCM Run Out Valves Stand 6.374985.W_001_01 | 02 | 2018-07-18 14:37 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2018-07-18 14:37 | IFI | OB | 100%
133797 | I491TI02-0CCHY91-020-001 | CCM Run Out Unit 6.374983.R_001_01 | 02 | 2018-07-18 14:37 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2018-07-18 14:37 | IFI | OB | 100%
133798 | I491TI02-0CCHY91-021-001 | CCM Valves Stand 6.374975.C_006_04 | 02 | 2018-07-18 14:37 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2018-07-18 14:37 | IFI | OB | 100%
133799 | I491TI02-0CCHY91-022-001 | CCM Valves Stand 6.374975.C_005_04 | 02 | 2018-07-18 14:37 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2018-07-18 14:37 | IFI | OB | 100%
133800 | I491TI02-0CCHY91-023-001 | CCM Valves Stand 6.374975.C_004_04 | 02 | 2018-07-18 14:37 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2018-07-18 14:37 | IFI | OB | 100%
133801 | I491TI02-0CCHY91-024-001 | CCM Valves Stand 6.374975.C_003_04 | 02 | 2018-07-18 14:37 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2018-07-18 14:37 | IFI | OB | 100%
133802 | I491TI02-0CCHY91-025-001 | CCM Valves Stand 6.374975.C_002_04 | 02 | 2018-07-18 14:37 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2018-07-18 14:37 | IFI | OB | 100%
133803 | I491TI02-0CCHY91-026-001 | CCM Valves Stand 6.374975.C_001_04 | 02 | 2018-07-18 14:37 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2018-07-18 14:37 | IFI | OB | 100%
133804 | I491TI02-0CCHY91-027-001 | CCM Acumulators Stand 6.374974.B_001_00A | 02 | 2018-07-18 14:37 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2018-07-18 14:37 | IFI | OB | 100%
133778 | I491TI02-0CCHY91-028-001 | CCM Mould Oscillation 6374973A_001 | 01 | 2018-07-18 14:36 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Mechanical | TAM | 2018-07-18 14:36 | IFI | OB | 100%
133805 | I491TI02-0CCHY91-029-001 | CCM Oscill Benches Accumulators 6.374972.G_001_00A | 02 | 2018-07-18 14:37 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2018-07-18 14:37 | IFI | OB | 100%
133806 | I491TI02-0CCHY91-030-001 | Mould Oscillatores Unit 6.374968.L_001_01 | 02 | 2018-07-18 14:37 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2018-07-18 14:37 | IFI | OB | 100%
133807 | I491TI02-0CCHY91-031-001 | CCM Strand Cut 6.374966.B_001_02 | 02 | 2018-07-18 14:37 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2018-07-18 14:37 | IFI | OB | 100%
133808 | I491TI02-0CCHY91-032-001 | CCM Out Accumulator 6.375001.F_001_00 | 02 | 2018-07-18 14:37 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2018-07-18 14:37 | IFI | OB | 100%
15471 | I491TI02-0CCLK91-001-001 | Turret | 00 | 2013-10-29 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Mechanical | TAM |  | IFA | AFC | 100%
15472 | I491TI02-0CCMJ91-001-001 | Mould | 00 | 2013-10-29 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Mechanical | TAM |  | IFA | AFC | 100%
15473 | I491TI02-0CCRL91-001-001 | Runout Area Part 1 | 00 | 2013-10-29 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Mechanical | TAM |  | IFA | AFC | 100%
15474 | I491TI02-0CCTB91-001-001 | Runout Area Part 2 | 00 | 2013-10-29 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Mechanical | TAM |  | IFA | AFC | 100%
15475 | I491TI02-0CCTD91-003-001 | Tundish Car | 00 | 2013-10-29 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Mechanical | TAM |  | IFA | AFC | 100%
130672 | I491TI02-0DTAA91-001-001 | ELECTRICAL EQUIPMENT LIST FOR FTP AREA | 01 | 2017-06-07 10:34 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Equipment | Automation and Instrumentation | HASCON | 2017-06-07 10:34 | IFC | AFC | 100%
130879 | I491TI02-0DTAA91-002-001 | ELECTRICAL & CONTROL ROOM LAYOUT FOR FUME TREATMENT PLANT | 02 | 2017-07-17 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Automation and Instrumentation | HASCON | 2017-07-24 12:45 | IFC | AFC | 100%
130028 | I491TI02-0DTAA91-004-001 | INSTRUMENT AND JUNCTION BOXES LOCATION LAYOUT FOR FTP 1-6 | 02 | 2016-12-26 09:37 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Automation and Instrumentation | HASCON | 2016-12-26 09:37 | IFC | AFC | 100%
130023 | I491TI02-0DTAA91-004-002 | INSTRUMENT AND JUNCTION BOXES LOCATION LAYOUT FOR FTP 2-6 | 02 | 2016-12-26 09:37 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Automation and Instrumentation | HASCON | 2016-12-26 09:37 | IFC | AFC | 100%
130024 | I491TI02-0DTAA91-004-003 | INSTRUMENT AND JUNCTION BOXES LOCATION LAYOUT FOR FTP 3-6 | 02 | 2016-12-26 09:37 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Automation and Instrumentation | HASCON | 2016-12-26 09:37 | IFC | AFC | 100%
130025 | I491TI02-0DTAA91-004-004 | INSTRUMENT AND JUNCTION BOXES LOCATION LAYOUT FOR FTP 4-6 | 02 | 2016-12-26 09:37 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Automation and Instrumentation | HASCON | 2016-12-26 09:37 | IFC | AFC | 100%
130026 | I491TI02-0DTAA91-004-005 | INSTRUMENT AND JUNCTION BOXES LOCATION LAYOUT FOR FTP 5-6 | 02 | 2016-12-26 09:37 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Automation and Instrumentation | HASCON | 2016-12-26 09:37 | IFC | AFC | 100%
130027 | I491TI02-0DTAA91-004-006 | INSTRUMENT AND JUNCTION BOXES LOCATION LAYOUT FOR FTP 6-6 | 02 | 2016-12-26 09:37 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Automation and Instrumentation | HASCON | 2016-12-26 09:37 | IFC | AFC | 100%
131051 | I491TI02-0DTAA91-005-001 | CABLE TRAY AND CABLE TRUNKING LAYOUT 1-20 | 02 | 2017-08-14 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Automation and Instrumentation | TAM | 2017-08-15 12:28 | IFC | AFC | 100%
131039 | I491TI02-0DTAA91-005-002 | CABLE TRAY AND CABLE TRUNKING LAYOUT 2-20 | 02 | 2017-08-14 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Automation and Instrumentation | TAM | 2017-08-15 12:28 | IFC | AFC | 100%
131040 | I491TI02-0DTAA91-005-003 | CABLE TRAY AND CABLE TRUNKING LAYOUT 3-20 | 02 | 2017-08-14 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Automation and Instrumentation | TAM | 2017-08-15 12:28 | IFC | AFC | 100%
131041 | I491TI02-0DTAA91-005-004 | CABLE TRAY AND CABLE TRUNKING LAYOUT 4-20 | 02 | 2017-08-14 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Automation and Instrumentation | TAM | 2017-08-15 12:28 | IFC | AFC | 100%
131035 | I491TI02-0DTAA91-005-005 | CABLE TRAY AND CABLE TRUNKING LAYOUT 5-20 | 02 | 2017-08-14 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Automation and Instrumentation | TAM | 2017-08-15 12:28 | IFC | AFC | 100%
131036 | I491TI02-0DTAA91-005-006 | CABLE TRAY AND CABLE TRUNKING LAYOUT 6-20 | 02 | 2017-08-14 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Automation and Instrumentation | TAM | 2017-08-15 12:28 | IFC | AFC | 100%
131037 | I491TI02-0DTAA91-005-007 | CABLE TRAY AND CABLE TRUNKING LAYOUT 7-20 | 02 | 2017-08-14 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Automation and Instrumentation | TAM | 2017-08-15 12:28 | IFC | AFC | 100%
131038 | I491TI02-0DTAA91-005-008 | CABLE TRAY AND CABLE TRUNKING LAYOUT 8-20 | 02 | 2017-08-14 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Automation and Instrumentation | TAM | 2017-08-15 12:28 | IFC | AFC | 100%
131042 | I491TI02-0DTAA91-005-009 | CABLE TRAY AND CABLE TRUNKING LAYOUT 9-20 | 02 | 2017-08-14 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Automation and Instrumentation | TAM | 2017-08-15 12:28 | IFC | AFC | 100%
131043 | I491TI02-0DTAA91-005-010 | CABLE TRAY AND CABLE TRUNKING LAYOUT 10-20 | 02 | 2017-08-14 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Automation and Instrumentation | TAM | 2017-08-15 12:28 | IFC | AFC | 100%
131044 | I491TI02-0DTAA91-005-011 | CABLE TRAY AND CABLE TRUNKING LAYOUT 11-20 | 02 | 2017-08-14 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Automation and Instrumentation | TAM | 2017-08-15 12:28 | IFC | AFC | 100%
131045 | I491TI02-0DTAA91-005-012 | CABLE TRAY AND CABLE TRUNKING LAYOUT 12-20 | 02 | 2017-08-14 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Automation and Instrumentation | TAM | 2017-08-15 12:28 | IFC | AFC | 100%
131046 | I491TI02-0DTAA91-005-013 | CABLE TRAY AND CABLE TRUNKING LAYOUT 13-20 | 02 | 2017-08-14 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Automation and Instrumentation | TAM | 2017-08-15 12:28 | IFC | AFC | 100%
131047 | I491TI02-0DTAA91-005-014 | CABLE TRAY AND CABLE TRUNKING LAYOUT 14-20 | 02 | 2017-08-14 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Automation and Instrumentation | TAM | 2017-08-15 12:28 | IFC | AFC | 100%
131048 | I491TI02-0DTAA91-005-015 | CABLE TRAY AND CABLE TRUNKING LAYOUT 15-20 | 02 | 2017-08-14 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Automation and Instrumentation | TAM | 2017-08-15 12:28 | IFC | AFC | 100%
131049 | I491TI02-0DTAA91-005-016 | CABLE TRAY AND CABLE TRUNKING LAYOUT 16-20 | 02 | 2017-08-14 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Automation and Instrumentation | TAM | 2017-08-15 12:28 | IFC | AFC | 100%
131050 | I491TI02-0DTAA91-005-017 | CABLE TRAY AND CABLE TRUNKING LAYOUT 17-20 | 02 | 2017-08-14 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Automation and Instrumentation | TAM | 2017-08-15 12:28 | IFC | AFC | 100%
130022 | I491TI02-0DTAA91-101-001 | DRI - Electical equipment list | 00 | 2016-12-26 09:18 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Automation and Instrumentation | HASCON | 2016-12-26 09:18 | IFA | AC |  | 95%
129949 | I491TI02-0DTAA91-103-001 | DRI EQUIPMENT LAYOUT FOR FUME TREATMENT PLANT | 01 | 2016-12-10 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Automation and Instrumentation | HASCON | 2016-12-13 08:40 | IFC | AC |  | 95%
129877 | I491TI02-0DTAA91-104-001 | DRI INSTRUMENT AND JUNCTION BOXES LOCATION LAYOUT | 00 | 2016-12-04 09:22 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Automation and Instrumentation | HASCON | 2016-12-04 09:22 | IFA | AC |  | 95%
113266 | I491TI02-0DTAA91-105-001 | DRI CABLE TRAY AND CABLE TRUNKING LAYOUT FOR FUME TREATMENT PLANT | 00 | 2015-01-18 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Automation and Instrumentation | HASCON | 2015-01-28 10:56 | IFA | AC |  | 95%
115060 | I491TI02-0DTPC01-001-001 | In Field FTP Control Panel Layout | 01 | 2016-03-08 | Indeterminate | Drawing | Basic | Fume Treatment Equipment | Automation and Instrumentation | TAM | 2016-03-14 14:05 | IFC | AFC | 100%
133417 | I491TI02-0EAAA91-001-001 | EAF MAIN CABLE TRAY AND LADDER ROUTE 1-11 | 01 | 2018-07-03 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Automation and Instrumentation | TAM | 2018-07-08 16:55 | IFC | AC |  | 95%
133418 | I491TI02-0EAAA91-001-002 | EAF MAIN CABLE TRAY AND LADDER ROUTE 2-11 | 01 | 2018-07-03 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Automation and Instrumentation | TAM | 2018-07-08 16:55 | IFC | AC |  | 95%
133419 | I491TI02-0EAAA91-001-003 | EAF MAIN CABLE TRAY AND LADDER ROUTE 3-11 | 01 | 2018-07-03 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Automation and Instrumentation | TAM | 2018-07-08 16:55 | IFC | AC |  | 95%
133420 | I491TI02-0EAAA91-001-004 | EAF MAIN CABLE TRAY AND LADDER ROUTE 4-11 | 01 | 2018-07-03 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Automation and Instrumentation | TAM | 2018-07-08 16:55 | IFC | AC |  | 95%
133421 | I491TI02-0EAAA91-001-005 | EAF MAIN CABLE TRAY AND LADDER ROUTE 5-11 | 01 | 2018-07-03 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Automation and Instrumentation | TAM | 2018-07-08 16:55 | IFC | AC |  | 95%
133422 | I491TI02-0EAAA91-001-006 | EAF MAIN CABLE TRAY AND LADDER ROUTE 6-11 | 01 | 2018-07-03 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Automation and Instrumentation | TAM | 2018-07-08 16:55 | IFC | AC |  | 95%
133423 | I491TI02-0EAAA91-001-007 | EAF MAIN CABLE TRAY AND LADDER ROUTE 7-11 | 01 | 2018-07-03 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Automation and Instrumentation | TAM | 2018-07-08 16:55 | IFC | AC |  | 95%
133424 | I491TI02-0EAAA91-001-008 | EAF MAIN CABLE TRAY AND LADDER ROUTE 8-11 | 01 | 2018-07-03 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Automation and Instrumentation | TAM | 2018-07-08 16:55 | IFC | AC |  | 95%
133429 | I491TI02-0EAAA91-001-009 | EAF MAIN CABLE TRAY AND LADDER ROUTE 9-11 | 00 | 2018-07-03 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Automation and Instrumentation | TAM | 2018-07-08 17:01 | IFC | AC |  | 95%
133430 | I491TI02-0EAAA91-001-010 | EAF MAIN CABLE TRAY AND LADDER ROUTE 10-11 | 00 | 2018-07-03 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Automation and Instrumentation | TAM | 2018-07-08 17:01 | IFC | AC |  | 95%
133428 | I491TI02-0EAAA91-001-011 | EAF MAIN CABLE TRAY AND LADDER ROUTE 11-11 | 00 | 2018-07-03 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Automation and Instrumentation | TAM | 2018-07-08 17:01 | IFC | AC |  | 95%
133436 | I491TI02-0LFAA91-001-001 | LF MAIN CABLE TRAY AND LADDER ROUTE 1-6 | 01 | 2018-07-04 | Indeterminate | Drawing | Detail | Ladle Furnace | Automation and Instrumentation | TAM | 2018-07-10 09:14 | IFC | AC |  | 95%
133437 | I491TI02-0LFAA91-001-002 | LF MAIN CABLE TRAY AND LADDER ROUTE 2-6 | 01 | 2018-07-04 | Indeterminate | Drawing | Detail | Ladle Furnace | Automation and Instrumentation | TAM | 2018-07-10 09:14 | IFC | AC |  | 95%
133438 | I491TI02-0LFAA91-001-003 | LF MAIN CABLE TRAY AND LADDER ROUTE 3-6 | 01 | 2018-07-04 | Indeterminate | Drawing | Detail | Ladle Furnace | Automation and Instrumentation | TAM | 2018-07-10 09:14 | IFC | AC |  | 95%
133439 | I491TI02-0LFAA91-001-004 | LF MAIN CABLE TRAY AND LADDER ROUTE 4-6 | 00 | 2018-07-04 | Indeterminate | Drawing | Detail | Ladle Furnace | Automation and Instrumentation | TAM | 2018-07-10 09:14 | IFC | AC |  | 95%
133440 | I491TI02-0LFAA91-001-005 | LF MAIN CABLE TRAY AND LADDER ROUTE 5-6 | 00 | 2018-07-04 | Indeterminate | Drawing | Detail | Ladle Furnace | Automation and Instrumentation | TAM | 2018-07-10 09:14 | IFC | AC |  | 95%
133441 | I491TI02-0LFAA91-001-006 | LF MAIN CABLE TRAY AND LADDER ROUTE 6-6 | 00 | 2018-07-04 | Indeterminate | Drawing | Detail | Ladle Furnace | Automation and Instrumentation | TAM | 2018-07-10 09:14 | IFC | AC |  | 95%
114883 | I491TI02-0MDAA91-001-001 | INSTRUMENT LOCATION LAYOUT BELT CONVEYOR MD-CV-01-01 1-25 | 01 | 2016-02-06 09:00 | Indeterminate | Drawing | Detail | Material Handling | Automation and Instrumentation | DATIS | 2016-02-06 09:00 | IFC | AC |  | 95%
114884 | I491TI02-0MDAA91-001-002 | INSTRUMENT LOCATION LAYOUT BELT CONVEYOR MD-CV-02-01 2-25 | 01 | 2016-02-06 09:00 | Indeterminate | Drawing | Detail | Material Handling | Automation and Instrumentation | DATIS | 2016-02-06 09:00 | IFC | AC |  | 95%
114885 | I491TI02-0MDAA91-001-003 | INSTRUMENT LOCATION LAYOUT LIME+DOL BINS MD-TK-02~04-01 3-25 | 01 | 2016-02-06 09:00 | Indeterminate | Drawing | Detail | Material Handling | Automation and Instrumentation | DATIS | 2016-02-06 09:00 | IFC | AC |  | 95%
114886 | I491TI02-0MDAA91-001-004 | INSTRUMENT LOCATION LAYOUT LIME+DOL BINS MD-TK-02~04-01 4-25 | 01 | 2016-02-06 09:00 | Indeterminate | Drawing | Detail | Material Handling | Automation and Instrumentation | DATIS | 2016-02-06 09:00 | IFC | AC |  | 95%
114887 | I491TI02-0MDAA91-001-005 | INSTRUMENT LOCATION LAYOUT BELT CONVEYOR MD-CV-03-01 5-25 | 01 | 2016-02-06 09:00 | Indeterminate | Drawing | Detail | Material Handling | Automation and Instrumentation | DATIS | 2016-02-06 09:00 | IFC | AC |  | 95%
114888 | I491TI02-0MDAA91-001-006 | INSTRUMENT LOCATION LAYOUT BELT CONVEYOR MD-CV-04-01 6-25 | 01 | 2016-02-06 09:00 | Indeterminate | Drawing | Detail | Material Handling | Automation and Instrumentation | DATIS | 2016-02-06 09:00 | IFC | AC |  | 95%
114889 | I491TI02-0MDAA91-001-007 | INSTRUMENT LOCATION LAYOUT SHUTTLE BELT CONVEYOR MD-CV-05-01 7-25 | 01 | 2016-02-06 09:00 | Indeterminate | Drawing | Detail | Material Handling | Automation and Instrumentation | DATIS | 2016-02-06 09:00 | IFC | AC |  | 95%
114890 | I491TI02-0MDAA91-001-008 | INSTRUMENT LOCATION LAYOUTSHUTTLE BELT CONVEYOR MD-CV-06-01 8-25 | 01 | 2016-02-06 09:00 | Indeterminate | Drawing | Detail | Material Handling | Automation and Instrumentation | DATIS | 2016-02-06 09:00 | IFC | AC |  | 95%
114891 | I491TI02-0MDAA91-001-009 | INSTRUMENT LOCATION LAYOUT SHUTTLE BELT CONVEYOR MD-CV-09-01 9-25 | 01 | 2016-02-06 09:00 | Indeterminate | Drawing | Detail | Material Handling | Automation and Instrumentation | DATIS | 2016-02-06 09:00 | IFC | AC |  | 95%
114892 | I491TI02-0MDAA91-001-010 | INSTRUMENT LOCATION LAYOUT EAF DRI & FERRO ALLOY BINS MD-TK-06~16+ 29~32 (SHEET1/2) 10-25 | 01 | 2016-02-06 09:00 | Indeterminate | Drawing | Detail | Material Handling | Automation and Instrumentation | DATIS | 2016-02-06 09:00 | IFC | AC |  | 95%
114893 | I491TI02-0MDAA91-001-011 | INSTRUMENT LOCATION LAYOUT EAF DRI & FERRO ALLOY BINS MD-TK-06~16+ 29~32 (SHEET1/2) 11-25 | 01 | 2016-02-06 09:00 | Indeterminate | Drawing | Detail | Material Handling | Automation and Instrumentation | DATIS | 2016-02-06 09:00 | IFC | AC |  | 95%
114894 | I491TI02-0MDAA91-001-012 | INSTRUMENT LOCATION LAYOUT LF FERRO ALLOYS BINS MD-TK-17~28-01 12-25 | 01 | 2016-02-06 09:00 | Indeterminate | Drawing | Detail | Material Handling | Automation and Instrumentation | DATIS | 2016-02-06 09:00 | IFC | AC |  | 95%
114895 | I491TI02-0MDAA91-001-013 | INSTRUMENT LOCATION LAYOUT LF FERRO ALLOYS FIXED HOPPER MD-TK-36~38-01 13-25 | 01 | 2016-02-06 09:00 | Indeterminate | Drawing | Detail | Material Handling | Automation and Instrumentation | DATIS | 2016-02-06 09:00 | IFC | AC |  | 95%
114896 | I491TI02-0MDAA91-001-014 | INSTRUMENT LOCATION LAYOUT BELT CONVEYOR MD-CV-07-01 14-25 | 01 | 2016-02-06 09:00 | Indeterminate | Drawing | Detail | Material Handling | Automation and Instrumentation | DATIS | 2016-02-06 09:00 | IFC | AC |  | 95%
114897 | I491TI02-0MDAA91-001-015 | INSTRUMENT LOCATION LAYOUT BELT CONVEYOR MD-CV-08-01 15-25 | 01 | 2016-02-06 09:00 | Indeterminate | Drawing | Detail | Material Handling | Automation and Instrumentation | DATIS | 2016-02-06 09:00 | IFC | AC |  | 95%
114898 | I491TI02-0MDAA91-001-016 | INSTRUMENT LOCATION LAYOUT BELT CONVEYOR MD-CV-12-01 16-25 | 01 | 2016-02-06 09:00 | Indeterminate | Drawing | Detail | Material Handling | Automation and Instrumentation | DATIS | 2016-02-06 09:00 | IFC | AC |  | 95%
114899 | I491TI02-0MDAA91-001-017 | INSTRUMENT LOCATION LAYOUT BELT CONVEYOR MD-CV-13-01 17-25 | 01 | 2016-02-06 09:00 | Indeterminate | Drawing | Detail | Material Handling | Automation and Instrumentation | DATIS | 2016-02-06 09:00 | IFC | AC |  | 95%
114900 | I491TI02-0MDAA91-001-018 | INSTRUMENT LOCATION LAYOUT BELT CONVEYOR MD-CV-14-01 18-25 | 01 | 2016-02-06 09:00 | Indeterminate | Drawing | Detail | Material Handling | Automation and Instrumentation | DATIS | 2016-02-06 09:00 | IFC | AC |  | 95%
114901 | I491TI02-0MDAA91-001-019 | INSTRUMENT LOCATION LAYOUT BELT CONVEYOR MD-CV-15-01 19-25 | 01 | 2016-02-06 09:00 | Indeterminate | Drawing | Detail | Material Handling | Automation and Instrumentation | DATIS | 2016-02-06 09:00 | IFC | AC |  | 95%
114902 | I491TI02-0MDAA91-001-020 | INSTRUMENT LOCATION LAYOUT BELT CONVEYOR MD-CV-16-01 20-25 | 01 | 2016-02-06 09:00 | Indeterminate | Drawing | Detail | Material Handling | Automation and Instrumentation | DATIS | 2016-02-06 09:00 | IFC | AC |  | 95%
114903 | I491TI02-0MDAA91-001-021 | INSTRUMENT LOCATION LAYOUT BELT CONVEYOR MD-CV-17-01 21-25 | 01 | 2016-02-06 09:00 | Indeterminate | Drawing | Detail | Material Handling | Automation and Instrumentation | DATIS | 2016-02-06 09:00 | IFC | AC |  | 95%
114904 | I491TI02-0MDAA91-001-022 | INSTRUMENT LOCATION LAYOUT BELT CONVEYOR MD-CV-18-01 22-25 | 01 | 2016-02-06 09:00 | Indeterminate | Drawing | Detail | Material Handling | Automation and Instrumentation | DATIS | 2016-02-06 09:00 | IFC | AC |  | 95%
114905 | I491TI02-0MDAA91-001-023 | INSTRUMENT LOCATION LAYOUT BELT CONVEYOR MD-CV-19-01 23-25 | 01 | 2016-02-06 09:00 | Indeterminate | Drawing | Detail | Material Handling | Automation and Instrumentation | DATIS | 2016-02-06 09:00 | IFC | AC |  | 95%
114906 | I491TI02-0MDAA91-001-024 | INSTRUMENT LOCATION LAYOUT EAF SURGE HOPPERS MD-TK-34~35-01 24-25 | 01 | 2016-02-06 09:00 | Indeterminate | Drawing | Detail | Material Handling | Automation and Instrumentation | DATIS | 2016-02-06 09:00 | IFC | AC |  | 95%
114907 | I491TI02-0MDAA91-001-025 | INSTRUMENT LOCATION LAYOUT MOVABLE WEIGHING HOPPERS MD-TK-33 25-25 | 01 | 2016-02-06 09:00 | Indeterminate | Drawing | Detail | Material Handling | Automation and Instrumentation | DATIS | 2016-02-06 09:00 | IFC | AC |  | 95%
15476 | I491TI02-0MEYC01-310-002 | 400/33 Kv Substation Avr Panel Front View | 01 | 2012-06-13 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
15480 | I491TI02-0MEYC02-301-001 | 400/33 Kv Substation Control Panel Front View | 00 | 2011-12-13 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
15479 | I491TI02-0MEYC03-303-002 | Measuring Panel Front View | 01 | 2012-03-18 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
134183 | I491TI02-0MMCF91-009-001 | Sedimentation Layout For All Electrical Equipment Electrical Room Electrical Equipment Fields | 02 | 2018-09-17 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Electrical | TAM | 2018-09-22 10:22 | IFC | AFC | 100%
130911 | I491TI02-0MMCT01-001-001 | INSTRUMENT LOCATION DRAWING FOR WATER COOLING PLANT | 03 | 2017-07-26 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Automation and Instrumentation | FARABARD | 2017-07-30 11:00 | IFC | AFC | 100%
115379 | I491TI02-0MMCT01-002-001 | Instrument Cable Tray and Conduit Route | 00 | 2016-05-25 10:33 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Automation and Instrumentation | FARABARD | 2016-05-25 10:33 | IFA | AC |  | 95%
133166 | I491TI02-0MMCT01-004-001 | SYMBOL & LEGEND FOR INSTRUMENT LOCATION | 00 | 2018-05-20 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Mechanical | TAM | 2018-05-28 14:59 | IFI | OB | 100%
115346 | I491TI03-0ASAA91-003-001 | IO List (ASP) | 00 | 2016-05-16 | Indeterminate | Miscellaneous(MISC) | Detail | Air Separation Plant | Automation and Instrumentation | Fortune | 2016-05-25 09:51 | IFA | A | 100%
115347 | I491TI03-0ASAA91-004-001 | Instrument Cable List (ASP) | 00 | 2016-05-16 | Indeterminate | Miscellaneous(MISC) | Detail | Air Separation Plant | Automation and Instrumentation | Fortune | 2016-05-25 09:52 | IFA | A | 100%
115115 | I491TI03-0ASAA91-005-001 | Instrument Installation Material (ASP) | 00 | 2016-04-04 | Indeterminate | Miscellaneous(MISC) | Detail | Air Separation Plant | Automation and Instrumentation | Fortune | 2016-04-06 14:24 | IFI | OB | 100%
129844 | I491TI03-0AUAA91-002-001 | Level2 Operators Stations (HMI) | 00 | 2016-11-23 | Indeterminate | Miscellaneous(MISC) | Detail | Automation and Control System | Automation and Instrumentation | ASM | 2016-11-24 11:14 | IFI | A | 100%
114806 | I491TI03-0AUAA91-003-001 | LEVEL 2 OPERATOR MANUAL FOR CCM | 00 | 2016-01-17 | Indeterminate | Miscellaneous(MISC) | Basic | Continuous Casting Machine (CCM) | Automation and Instrumentation | DANIELI | 2016-01-18 09:24 | IFA | A | 100%
114807 | I491TI03-0AUAA91-004-001 | LEVEL 2 SYSTEM ADMINISTRATIVE MANUAL FOR CCM | 00 | 2016-01-17 | Indeterminate | Miscellaneous(MISC) | Basic | Continuous Casting Machine (CCM) | Automation and Instrumentation | DANIELI | 2016-01-18 09:24 | IFA | A | 100%
114808 | I491TI03-0AUAA91-009-001 | LEVEL 2 FUNCTION DESCRIPTION FOR CCM | 00 | 2016-01-17 | Indeterminate | Miscellaneous(MISC) | Basic | Continuous Casting Machine (CCM) | Automation and Instrumentation | TAM | 2016-01-18 09:25 | IFA | A | 100%
116969 | I491TI03-0AUAA91-010-001 | Level 2 Function Description for EAF Plant | 00 | 2016-07-25 15:46 | Indeterminate | Miscellaneous(MISC) | Basic | Automation and Control System | Automation and Instrumentation | TAM | 2016-07-25 15:46 | IFA | AC |  | 95%
116970 | I491TI03-0AUAA91-011-001 | Level 2 Function Description for LF Plant | 00 | 2016-07-25 15:46 | Indeterminate | Miscellaneous(MISC) | Basic | Automation and Control System | Automation and Instrumentation | TAM | 2016-07-25 15:46 | IFA | AC |  | 95%
130350 | I491TI03-0AUAA91-014-001 | Level2 Installation Manual | 01 | 2017-02-28 13:19 | Indeterminate | Miscellaneous(MISC) | Detail | Automation and Control System | Automation and Instrumentation | ASM | 2017-02-28 13:19 | IFI | OB | 100%
135238 | I491TI03-0CCAA91-001-001 | Catalogues for CCM Instrument for The Caster | 00 | 2019-04-14 16:03 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2019-04-14 16:03 | IFI | OB | 100%
115715 | I491TI03-0CCAA91-002-001 | Instrument List for CCM | 01 | 2016-06-07 11:33 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Automation and Instrumentation | TAM | 2016-06-07 11:33 | IFC | AC |  | 95%
113200 | I491TI03-0CCAA91-010-001 | CCM General Electrical Data GP08VB-HC11-E9000-ES121 | 00 | 2015-01-07 18:21 | Indeterminate | Miscellaneous(MISC) | Basic | Continuous Casting Machine (CCM) | Automation and Instrumentation | TAM | 2015-01-07 18:21 | IFA | AC |  | 95%
114815 | I491TI03-0CCAA91-013-001 | Level1 Operation Manual for CCM | 00 | 2016-01-18 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Automation and Instrumentation | DANIELI | 2016-01-18 09:59 | IFA | A | 100%
15481 | I491TI03-0CCHY91-010-001 | Hydraulic Unit Slide Gates Car 1 | 00 | 2013-10-29 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Mechanical | TAM |  | IFA | AFC | 100%
115333 | I491TI03-0CHAA91-001-001 | Manual Instructions For Heavy Duty Cranes | 00 | 2016-05-10 | Indeterminate | Miscellaneous(MISC) | Detail | Crane and Hiosts | Automation and Instrumentation | Voith | 2016-05-25 09:28 | IFI | OB | 100%
130316 | I491TI03-0DTAA91-001-001 | Functional Description Fume Treatment Equipment | 00 | 2017-02-15 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Equipment | Automation and Instrumentation | HASCON | 2017-02-16 10:40 | IFA | AC |  | 95%
130125 | I491TI03-0DTAA91-003-001 | IO LIST FOR AUTOMATION | 00 | 2017-01-10 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Equipment | Automation and Instrumentation | HASCON | 2017-01-15 09:30 | IFA | AC |  | 95%
130126 | I491TI03-0DTAA91-004-001 | FTP INTERFACE IO LIST FROM_TO EAF | 00 | 2017-01-10 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Equipment | Automation and Instrumentation | HASCON | 2017-01-15 09:32 | IFA | AC |  | 95%
113565 | I491TI03-0DTAA91-005-001 | INSTRUMENT CABLE LIST Fume Treatment Plant | 00 | 2015-05-10 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Equipment | Automation and Instrumentation | HASCON | 2015-05-27 16:03 | IFA | AFC | 100%
129856 | I491TI03-0DTAA91-008-001 | FTP CONTROL CABLE LIST | 00 | 2016-12-03 10:58 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Equipment | Automation and Instrumentation | HASCON | 2016-12-03 10:58 | IFA | AC |  | 95%
130317 | I491TI03-0DTAA91-101-001 | DRI-Functional Description | 00 | 2017-02-15 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Equipment | Automation and Instrumentation | HASCON | 2017-02-16 10:41 | IFA | AC |  | 95%
115667 | I491TI03-0DTAA91-102-001 | DRI Instrument list Fume Treatment Plant | 00 | 2016-06-06 11:13 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Equipment | Automation and Instrumentation | HASCON | 2016-06-06 11:13 | IFA | AC |  | 95%
130120 | I491TI03-0DTAA91-103-001 | FTP DRI IO List and Addressing | 00 | 2017-01-09 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Equipment | Automation and Instrumentation | HASCON | 2017-01-15 09:08 | IFA | AC |  | 95%
115717 | I491TI03-0DTAA91-105-001 | INSTRUMENT CABLE LIST FOR DRI AREA | 00 | 2016-06-07 11:35 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Equipment | Automation and Instrumentation | HASCON | 2016-06-07 11:35 | IFA | AC |  | 95%
15482 | I491TI03-0EAAA91-001-001 | Eaf Function Description | 00 | 2012-09-26 | Indeterminate | Miscellaneous(MISC) | Detail | Electric Arc Furnace | Automation and Instrumentation | FUCHS |  | IFA | AC |  | 95%
15483 | I491TI03-0EAAA91-002-001 | Eaf Ladle Car Functional Description | 00 | 2013-01-16 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop Auxiliaries | Automation and Instrumentation | FUCHS |  | IFA | AC |  | 95%
115342 | I491TI03-0EAAA91-003-001 | Eaf Emergency Function Description | 01 | 2016-05-16 | Indeterminate | Miscellaneous(MISC) | Detail | Electric Arc Furnace | Automation and Instrumentation | FUCHS | 2016-05-25 09:47 | IFC | AFC | 100%
115262 | I491TI03-0EAAA91-006-001 | EAF Operation Manual | 00 | 2016-05-09 | Indeterminate | Miscellaneous(MISC) | Detail | Electric Arc Furnace | Automation and Instrumentation | FUCHS | 2016-05-24 16:46 | IFI | OB | 100%
111643 | I491TI03-0EAAA91-007-001 | ELECTRIIC ARC FURNACE ERECTION,, OPERATIIONAND MAIINTENANCE MANUAL | 00 | 2014-03-08 | Indeterminate | Miscellaneous(MISC) | Detail | Electric Arc Furnace | Mechanical | FUCHS | 2014-04-24 14:56 | IFI | OB | 100%
129775 | I491TI03-0EAAA91-009-001 | EAF Cable List | 00 | 2016-11-05 | Indeterminate | Miscellaneous(MISC) | Detail | Electric Arc Furnace | Automation and Instrumentation | TAM | 2016-11-12 08:51 | IFI | OB | 100%
15485 | I491TI03-0EAFG01-001-001 | Furnace Pressure Control Roof Eaf | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
15486 | I491TI03-0LFAA91-001-001 | Lf Function Description | 00 | 2012-09-26 | Indeterminate | Miscellaneous(MISC) | Basic | Ladle Furnace | Automation and Instrumentation | FUCHS |  | IFA | AC |  | 95%
15487 | I491TI03-0LFAA91-002-001 | Lf Ladle Car Functional Description | 00 | 2013-01-16 | Indeterminate | Miscellaneous(MISC) | Basic | Melt Shop Auxiliaries | Automation and Instrumentation | FUCHS |  | IFA | AC |  | 95%
115343 | I491TI03-0LFAA91-003-001 | Lf Emergency Function Description | 01 | 2016-05-16 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Automation and Instrumentation | TAM | 2016-05-25 09:48 | IFC | AFC | 100%
115255 | I491TI03-0LFAA91-005-001 | LF Operation Manual | 00 | 2016-05-09 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Automation and Instrumentation | FUCHS | 2016-05-15 08:55 | IFI | OB | 100%
112268 | I491TI03-0MDAA91-001-001 | Belt Scale Data Sheet For CV03 | 01 | 2014-02-15 | Indeterminate | Miscellaneous(MISC) | Basic | Material Handling | Mechanical | DATIS | 2014-05-26 11:27 | IFC | AFC | 100%
15489 | I491TI03-0MDAA91-002-001 | Instrument Index | 00 | 2013-05-18 | Indeterminate | Miscellaneous(MISC) | Detail | Material Handling | Automation and Instrumentation | DATIS |  | IFA | A | 100%
116942 | I491TI03-0MDAA91-003-001 | Material Handling I/O Signal List | 02 | 2016-07-18 | Indeterminate | Miscellaneous(MISC) | Detail | Material Handling | Automation and Instrumentation | DATIS | 2016-07-25 10:20 | IFC | AC |  | 95%
114509 | I491TI03-0MDAA91-005-001 | Alarm and Set point List | 00 | 2015-10-11 14:18 | Indeterminate | Miscellaneous(MISC) | Detail | Material Handling | Automation and Instrumentation | DATIS | 2015-10-11 14:18 | IFA | AC |  | 95%
114655 | I491TI03-0MDAA91-006-001 | INSTRUMENT AND CONTROL CABLE SCHEDULE | 00 | 2015-11-09 09:52 | Indeterminate | Miscellaneous(MISC) | Detail | Material Handling | Automation and Instrumentation | DATIS | 2015-11-09 09:52 | IFA | AC |  | 95%
114582 | I491TI03-0MDAA91-010-001 | Process Control Philosophy For Matrial Handling System | 02 | 2015-10-18 11:25 | Indeterminate | Miscellaneous(MISC) | Basic | Material Handling | Automation and Instrumentation | TAM | 2015-10-18 11:25 | IFC | AFC | 100%
114436 | I491TI03-0MDCV10-002-001 | Belt Weigh Feeder Operation Manual For cv.10& cv.11 | 00 | 2015-10-05 | Indeterminate | Miscellaneous(MISC) | Detail | Material Handling | Automation and Instrumentation | VIDMAR | 2015-10-10 13:37 | IFI | OB | 100%
130931 | I491TI03-0MMCT01-001-001 | BARDSIR STEEL COMPLEX INSTRUMENT INDEX FOR WTP | 01 | 2017-07-31 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Automation and Instrumentation | FARABARD | 2017-08-02 08:52 | IFC | AFC | 100%
129950 | I491TI03-0MMCT01-002-001 | Vendor Document For WTP | 00 | 2016-12-12 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Automation and Instrumentation | FARABARD | 2016-12-13 08:42 | IFI | OB | 100%
115378 | I491TI03-0MMCT01-003-001 | Bardsir Steel Complex INSTRUMENT CABLE LIST WTP | 00 | 2016-05-25 10:32 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Automation and Instrumentation | FARABARD | 2016-05-25 10:32 | IFA | AC |  | 95%
112181 | I491TI03-0MMCT01-004-001 | WTP IO List | 01 | 2014-05-17 10:38 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Automation and Instrumentation | FARABARD | 2014-05-17 10:38 | IFC | AFC | 100%
15491 | I491TI03-0MMCT01-005-002 | Vibration Switch Data Sheet For Cooling System (Ct01) | 01 | 2013-08-08 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Automation and Instrumentation | FARABARD |  | IFC | AFC | 100%
15494 | I491TI03-0MMCT01-006-002 | Ultrasonic Flow Transmitter Data Sheet For Cooling System (Ct01) | 01 | 2013-08-08 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Automation and Instrumentation | FARABARD |  | IFC | AFC | 100%
15495 | I491TI03-0MMCT01-007-002 | Dp Transmitter Data Sheet For Cooling System (Ct01) | 01 | 2013-08-08 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Automation and Instrumentation | FARABARD |  | IFC | AFC | 100%
129816 | I491TI03-0MMCT01-008-002 | Ultrasonic Level Transmitter Data Sheet For Cooling System(CT01) | 02 | 2016-11-16 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Automation and Instrumentation | FARABARD | 2016-11-22 11:00 | IFC | AFC | 100%
15501 | I491TI03-0MMCT01-009-002 | Conductivity Analyzer Data Sheet For Cooling System (Ct01) | 01 | 2013-08-08 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Automation and Instrumentation | FARABARD |  | IFC | AFC | 100%
15504 | I491TI03-0MMCT01-010-002 | Ph Analyzer Data Sheet For Cooling System (Ct01) | 01 | 2013-08-08 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Automation and Instrumentation | FARABARD |  | IFC | AFC | 100%
15505 | I491TI03-0MMCT01-011-003 | Temperature Transmitter Data Sheet For Cooling System (Ct01) | 01 | 2013-08-08 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Automation and Instrumentation | FARABARD |  | IFC | AFC | 100%
15511 | I491TI03-0MMCT01-012-003 | Pressure Transmitter Data Sheet For Cooling System (Ct01) | 01 | 2013-08-08 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Automation and Instrumentation | FARABARD |  | IFC | AFC | 100%
129822 | I491TI03-0MMCT01-013-001 | Pressure Indicator Data Sheet For Cooling System(Ct01) | 02 | 2016-11-21 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Automation and Instrumentation | FARABARD | 2016-11-23 11:09 | IFC | AFC | 100%
15516 | I491TI03-0MMCT01-014-003 | Temperature Indicator Data Sheet For Cooling System (Ct01) | 01 | 2013-08-08 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Automation and Instrumentation | FARABARD |  | IFC | AFC | 100%
113360 | I491TI03-0MMCT01-015-001 | Control Valve Data Sheet For Cooling System Ct01 | 01 | 2013-05-19 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Automation and Instrumentation | FARABARD | 2015-02-18 10:51 | IFA | A | 100%
15517 | I491TI03-0MMCT01-015-002 | Penumatic Valve Data Sheet For Cooling System Ct01 | 01 | 2013-08-08 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Automation and Instrumentation | FARABARD |  | IFC | AFC | 100%
113361 | I491TI03-0MMCT01-016-001 | Chemical Level Switch Data Sheet For Cooling System Ct01 | 01 | 2013-05-19 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Automation and Instrumentation | FARABARD | 2015-02-18 10:51 | IFA | A | 100%
113363 | I491TI03-0MMCT01-018-001 | Differential Pressure Switch Data Sheet For Cooling System Ct01 | 01 | 2013-05-19 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Automation and Instrumentation | FARABARD | 2015-02-18 10:51 | IFA | A | 100%
15522 | I491TI03-0MMCT01-018-002 | Differential Pressure Indicator Switch Data Sheet For Cooling System Ct01 | 01 | 2013-08-08 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Automation and Instrumentation | FARABARD |  | IFC | AFC | 100%
133411 | I491TI03-0MMCT01-020-002 | Orifice Plate Data Sheet For Cooling System Ct01 | 03 | 2018-07-02 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Automation and Instrumentation | FARABARD | 2018-07-08 16:27 | IFC | AFC | 100%
111308 | I491TI03-0MMCT01-021-001 | PRESSURE SWITCH DATA SHEET FOR COOLING SYSTEM | 01 | 2014-04-16 09:31 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Automation and Instrumentation | FARABARD | 2014-04-16 09:31 | IFC | AFC | 100%
129951 | I491TI03-0MMCT01-022-001 | Operation Manual for WTP | 00 | 2016-12-12 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Mechanical | FARABARD | 2016-12-13 08:42 | IFI | OB | 100%
15528 | I491TI03-0MMCT02-005-003 | Vibration Switch Data Sheet For Cooling System Ct02 | 01 | 2013-08-08 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Automation and Instrumentation | FARABARD |  | IFC | AFC | 100%
15531 | I491TI03-0MMCT02-006-003 | Ultrasonic Flow Transmitter Data Sheet For Cooling System (Ct02) | 01 | 2013-08-08 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Automation and Instrumentation | FARABARD |  | IFC | AFC | 100%
15532 | I491TI03-0MMCT02-007-002 | Dp Transmitter Data Sheet For Cooling System (Ct02) | 01 | 2013-08-08 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Automation and Instrumentation | FARABARD |  | IFC | AFC | 100%
129813 | I491TI03-0MMCT02-008-002 | Ultrasonic Level Transmitter Data Sheet For Cooling System(Ct02) | 01 | 2016-11-16 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Automation and Instrumentation | FARABARD | 2016-11-22 10:37 | IFC | AFC | 100%
15538 | I491TI03-0MMCT02-009-003 | Conductivity Analyzer Data Sheet For Cooling System (Ct02) | 01 | 2013-08-08 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Automation and Instrumentation | FARABARD |  | IFC | AFC | 100%
15541 | I491TI03-0MMCT02-010-003 | Ph Analyzer Data Sheet For Cooling System (Ct02) | 01 | 2013-08-08 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Automation and Instrumentation | FARABARD |  | IFC | AFC | 100%
15542 | I491TI03-0MMCT02-011-003 | Temperature Transmitter Data Sheet For Cooling System (Ct02) | 01 | 2013-08-08 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Automation and Instrumentation | FARABARD |  | IFC | AFC | 100%
15547 | I491TI03-0MMCT02-012-002 | Pressure Transmitter Data Sheet For Cooling System Ct02 | 01 | 2013-08-08 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Automation and Instrumentation | FARABARD |  | IFC | AFC | 100%
15548 | I491TI03-0MMCT02-012-003 | Pressure Transmitter Data Sheet For Cooling System Ct02 | 01 | 2013-08-08 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Automation and Instrumentation | FARABARD |  | IFC | AFC | 100%
129823 | I491TI03-0MMCT02-013-002 | Pressure Indicator Data Sheet For Cooling System Ct02 | 01 | 2016-11-21 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Automation and Instrumentation | FARABARD | 2016-11-23 11:09 | IFC | AFC | 100%
15553 | I491TI03-0MMCT02-014-003 | Temperature Indicator Data Sheet For Cooling System Ct02 | 01 | 2013-08-08 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Automation and Instrumentation | FARABARD |  | IFC | AFC | 100%
15555 | I491TI03-0MMCT02-015-001 | Control Valve Data Sheet For Cooling System Ct02 | 00 | 2013-05-19 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Automation and Instrumentation | FARABARD |  | IFA | A | 100%
15554 | I491TI03-0MMCT02-015-002 | Penumatic Valve Data Sheet For Cooling System Ct02 | 01 | 2013-08-08 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Automation and Instrumentation | FARABARD |  | IFC | AFC | 100%
15556 | I491TI03-0MMCT02-016-001 | Chemical Level Switch Data Sheet For Cooling System Ct02 | 00 | 2013-05-19 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Automation and Instrumentation | FARABARD |  | IFA | A | 100%
15557 | I491TI03-0MMCT02-017-001 | Solenoid Valve Data Sheet For Cooling System Ct02 | 00 | 2013-05-19 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Automation and Instrumentation | TAM |  | IFA | A | 100%
15559 | I491TI03-0MMCT02-018-001 | Differential Pressure Switch Data Sheet For Cooling System Ct02 | 00 | 2013-05-19 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Automation and Instrumentation | FARABARD |  | IFA | A | 100%
15558 | I491TI03-0MMCT02-018-002 | Differential Pressure Indicator Switchdata Sheet For Cooling System Ct02 | 01 | 2013-08-08 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Automation and Instrumentation | FARABARD |  | IFC | AFC | 100%
15560 | I491TI03-0MMCT02-019-001 | Flowindicator Data Sheet For Cooling System Ct02 | 00 | 2013-05-19 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Automation and Instrumentation | TAM |  | IFA | A | 100%
15561 | I491TI03-0MMCT02-020-002 | Orifice Plate Data Sheet For Cooling System Ct02 | 01 | 2013-08-08 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Automation and Instrumentation | FARABARD |  | IFC | AFC | 100%
15564 | I491TI03-0MXAA91-001-002 | Basic Data Of Level 2 System | 01 | 2011-05-30 | Indeterminate | Miscellaneous(MISC) | Basic | Automation and Control System | Mechanical | TAM |  | IFA | AC |  | 95%
15567 | I491TI03-0SHAA91-001-003 | Scrap Car Function Description | 02 | 2013-03-18 | Indeterminate | Miscellaneous(MISC) | Detail | Scrap Yard Equipment | Automation and Instrumentation | TAM |  | IFC | AFC | 100%
115111 | I491TI04-0ASAA91-001-001 | Instrument Data Sheet (ASP) | 00 | 2016-04-04 | Indeterminate | Miscellaneous(MISC) | Detail | Air Separation Plant | Automation and Instrumentation | Fortune | 2016-04-06 14:07 | IFA | A | 100%
113132 | I491TI04-0AUAA91-001-001 | Level 2 IPC Hardware Specification | 01 | 2014-12-14 | Indeterminate | Miscellaneous(MISC) | Detail | Automation and Control System | Automation and Instrumentation | TAM | 2014-12-15 09:32 | IFC | AFC | 100%
114177 | I491TI04-0CCAA91-004-001 | Emergency panel technical specification | 00 | 2015-07-12 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Automation and Instrumentation | DANIELI | 2015-07-22 10:10 | IFA | A | 100%
15569 | I491TI04-0CPAA91-001-002 | Instrument List | 01 | 2013-05-06 | Indeterminate | Miscellaneous(MISC) | Detail | Compressed Air Production Plant | Automation and Instrumentation | HAVAYAR |  | IFC | AFC | 100%
115204 | I491TI04-0DTAA91-001-001 | Instrument Data sheets For Fume Treatment Plant | 00 | 2016-05-04 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Equipment | Automation and Instrumentation | HASCON | 2016-05-10 15:12 | IFA | AC |  | 95%
130133 | I491TI04-0DTAA91-002-001 | FTP-CONTROL AND SPECIAL CABLES DATASHEET | 00 | 2017-01-15 09:45 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Equipment | Automation and Instrumentation | HASCON | 2017-01-15 09:45 | IFA | AC |  | 95%
129858 | I491TI04-0DTAA91-101-001 | DRI - Instrument data sheets | 00 | 2016-12-03 14:44 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Equipment | Automation and Instrumentation | HASCON | 2016-12-03 14:44 | IFA | AC |  | 95%
130122 | I491TI04-0DTAA91-102-001 | DRI-Control and Special Cable Data Sheet | 01 | 2017-01-10 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Equipment | Automation and Instrumentation | HASCON | 2017-01-15 09:14 | IFA | AC |  | 95%
15570 | I491TI04-0EAAA91-001-001 | EAF Pc Hardware Specification | 00 | 2012-07-28 | Indeterminate | Miscellaneous(MISC) | Detail | Electric Arc Furnace | Automation and Instrumentation | FUCHS |  | IFI | OB | 100%
15571 | I491TI04-0LFAA91-001-001 | LF Pc Hardware Specification | 00 | 2012-07-28 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Automation and Instrumentation | FUCHS |  | IFI | OB | 100%
15572 | I491TI04-0MDAA91-001-001 | Technical Specification For Material Handling Instrument | 00 | 2013-05-18 | Indeterminate | Miscellaneous(MISC) | Basic | Material Handling | Automation and Instrumentation | DATIS |  | IFA | A | 100%
15573 | I491TI04-0MDAA91-002-001 | Technical Specification For I&C Junction Box | 00 | 2013-05-18 | Indeterminate | Miscellaneous(MISC) | Basic | Material Handling | Automation and Instrumentation | DATIS |  | IFA | A | 100%
15574 | I491TI04-0MDAA91-004-001 | Technical Specification For I&C Cable | 00 | 2013-05-18 | Indeterminate | Miscellaneous(MISC) | Basic | Material Handling | Automation and Instrumentation | DATIS |  | IFA | A | 100%
15575 | I491TI04-0MDAA91-007-001 | Datasheet For Conveyor Instrument | 00 | 2013-05-18 | Indeterminate | Miscellaneous(MISC) | Detail | Material Handling | Automation and Instrumentation | DATIS |  | IFA | A | 100%
15576 | I491TI04-0MDAA91-008-001 | Datasheet For Position Instrument | 00 | 2013-05-18 | Indeterminate | Miscellaneous(MISC) | Detail | Material Handling | Automation and Instrumentation | DATIS |  | IFA | A | 100%
15577 | I491TI04-0MDAA91-009-001 | Datasheet for Temperature Instruments | 00 | 2013-05-18 | Indeterminate | Miscellaneous(MISC) | Detail | Material Handling | Automation and Instrumentation | DATIS |  | IFA | A | 100%
15578 | I491TI04-0MDAA91-011-001 | Datasheet For Level Instrument | 00 | 2013-05-18 | Indeterminate | Miscellaneous(MISC) | Detail | Material Handling | Automation and Instrumentation | DATIS |  | IFA | A | 100%
15579 | I491TI04-0MDAA91-012-001 | Datasheet For Weighing Instrument | 00 | 2013-05-18 | Indeterminate | Miscellaneous(MISC) | Detail | Material Handling | Automation and Instrumentation | DATIS |  | IFA | A | 100%
111598 | I491TI04-0MDAA91-016-001 | MHS NITROGEN DATA SHEET | 00 | 2014-02-23 | Indeterminate | Miscellaneous(MISC) | Basic | Material Handling | Mechanical | TAM | 2014-04-24 13:45 | IFA | AC |  | 95%
15580 | I491TI04-0MEYC01-301-001 | Metering Apparatus Technical Specification | 00 | 2012-05-29 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | PARSIAN |  | IFI | OB | 100%
129940 | I491TI04-0MMAA91-001-001 | Technical Specification For Instrumentation Of Cooling Water System | 01 | 2016-12-07 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Automation and Instrumentation | TAM | 2016-12-12 16:43 | IFC | AFC | 100%
129831 | I491TI04-0MMCF91-012-001 | Control system & HMI Specification | 00 | 2016-11-21 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Automation and Instrumentation | TAM | 2016-11-23 11:22 | IFI | OB | 100%
11762 | I491TI04-0MMCT01-003-001 | Flow Element Calculation Sheet For Cooling System | 01 | 2013-08-08 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Piping & Utility | TAM |  | IFC | AFC | 100%
11763 | I491TI04-0MMCT02-003-001 | Flow Element Calculation Sheet For Cooling System | 01 | 2013-08-08 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Piping & Utility | TAM |  | IFC | AFC | 100%
115348 | I491TI05-0ASAA91-001-001 | Junction Box Wiring Drawings | 00 | 2016-05-16 | Unchecked | Miscellaneous(MISC) | Detail | Air Separation Plant | Automation and Instrumentation | Fortune | 2016-05-25 09:52 | IFA | A | 100%
115335 | I491TI05-0ASAA91-004-001 | Control Panel Wiring Diagram (ASP) | 00 | 2016-05-14 | Indeterminate | Drawing | Detail | Air Separation Plant | Automation and Instrumentation | TAM | 2016-05-25 09:35 | IFA | AC |  | 95%
113381 | I491TI05-0AUAA91-001-001 | I-O list for substation monitoring | 01 | 2015-02-21 14:50 | Indeterminate | Miscellaneous(MISC) | Detail | Steel Making Electrical Substation | Automation and Instrumentation | TAM | 2015-02-21 14:50 | IFC | AFC | 100%
113478 | I491TI05-0AUAA91-002-001 | SUBSTATION MONITORING WIRING DIAGRAM for All Plants | 01 | 2015-04-19 | Indeterminate | Miscellaneous(MISC) | Basic | GENERAL PLANT | Automation and Instrumentation | TAM | 2015-04-22 09:52 | IFC | AFC | 100%
113137 | I491TI05-0AUAA91-003-001 | Level 2 Electrical Drawing | 00 | 2014-12-16 | Indeterminate | Miscellaneous(MISC) | Detail | Automation and Control System | Automation and Instrumentation | TAM | 2014-12-17 08:54 | IFA | A | 100%
114178 | I491TI05-0CCAA91-005-001 | Emergency panel electrical diagram | 00 | 2015-07-12 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Automation and Instrumentation | DANIELI | 2015-07-22 10:11 | IFA | A | 100%
114179 | I491TI05-0CCAA91-006-001 | Local control station electrical diagram MOULD TILTING DEVICE | 00 | 2015-07-12 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Automation and Instrumentation | DANIELI | 2015-07-22 10:11 | IFA | A | 100%
114180 | I491TI05-0CCAA91-007-001 | Local control station electrical diagram for TUNDISH TILTING | 00 | 2015-07-12 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Automation and Instrumentation | DANIELI | 2015-07-22 10:11 | IFA | A | 100%
114181 | I491TI05-0CCAA91-008-001 | Local control station electrical diagram for TUNDISH STOPPER ROD | 00 | 2015-07-12 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Automation and Instrumentation | DANIELI | 2015-07-22 10:11 | IFA | A | 100%
114182 | I491TI05-0CCAA91-009-001 | AUTOMATION SYSTEM ELECTRICAL DIAGRAM for Gen-Services | 00 | 2015-07-12 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Automation and Instrumentation | DANIELI | 2015-07-22 10:11 | IFA | A | 100%
114183 | I491TI05-0CCAA91-010-001 | AUTOMATION SYSTEM ELECTRICAL DIAGRAM for Strands | 00 | 2015-07-12 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Automation and Instrumentation | DANIELI | 2015-07-22 10:11 | IFA | A | 100%
134212 | I491TI05-0CCHB01-001-001 | Instruction Manual For Tundish Preheating System | 00 | 2018-09-22 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | CEBA | 2018-09-30 11:37 | IFI | OB | 100%
134211 | I491TI05-0CCHB02-001-001 | Instruction Manual For Sen Preheating Stove | 00 | 2018-09-22 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | CEBA | 2018-09-30 11:37 | IFI | OB | 100%
134213 | I491TI05-0CCTD10-001-001 | Instruction Manual For Tundish Drying Station | 00 | 2018-09-22 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | CEBA | 2018-09-30 11:37 | IFI | OB | 100%
113322 | I491TI05-0CHEU01-001-001 | Electrical drawings for teeming crane | 00 | 2015-02-04 | Indeterminate | Miscellaneous(MISC) | Detail | Crane and Hiosts | Automation and Instrumentation | TAM | 2015-02-10 15:50 | IFA | A | 100%
113382 | I491TI05-0CHEU02-001-001 | Electrical Drawings For SCRAP CHARGING CRANE | 00 | 2015-02-21 14:53 | Indeterminate | Miscellaneous(MISC) | Detail | Crane and Hiosts | Electrical | TAM | 2015-02-21 14:53 | IFA | A | 100%
15603 | I491TI05-0CPCP01-001-001 | Wiring diagram compressor for compressed air plant 5-10 | 02 | 2013-09-17 | Indeterminate | Drawing | Detail | Compressed Air Production Plant | Piping & Utility | HAVAYAR |  | IFC | AFC | 100%
15583 | I491TI05-0CPCP01-001-002 | Wiring Diagram Compressor Compressed Air Plant | 02 | 2013-09-17 | Indeterminate | Miscellaneous(MISC) | Detail | Compressed Air Production Plant | Piping & Utility | HAVAYAR |  | IFC | AFC | 100%
15604 | I491TI05-0CPCP01-001-002 | Wiring diagram compressor for compressed air plant 6-10 | 02 | 2013-09-17 | Indeterminate | Drawing | Detail | Compressed Air Production Plant | Piping & Utility | HAVAYAR |  | IFC | AFC | 100%
15605 | I491TI05-0CPCP01-001-003 | Wiring diagram compressor for compressed air plant 7-10 | 02 | 2013-09-17 | Indeterminate | Drawing | Detail | Compressed Air Production Plant | Piping & Utility | HAVAYAR |  | IFC | AFC | 100%
15606 | I491TI05-0CPCP01-001-004 | Wiring diagram compressor for compressed air plant 8-10 | 02 | 2013-09-17 | Indeterminate | Drawing | Detail | Compressed Air Production Plant | Piping & Utility | HAVAYAR |  | IFC | AFC | 100%
15607 | I491TI05-0CPCP01-001-005 | Wiring diagram compressor for compressed air plant9-10 | 02 | 2013-09-17 | Indeterminate | Drawing | Detail | Compressed Air Production Plant | Piping & Utility | HAVAYAR |  | IFC | AFC | 100%
15608 | I491TI05-0CPCP01-001-006 | Wiring diagram compressor for compressed air plant10-10 | 02 | 2013-09-17 | Indeterminate | Drawing | Detail | Compressed Air Production Plant | Piping & Utility | HAVAYAR |  | IFC | AFC | 100%
15585 | I491TI05-0CPDR01-001-002 | Wiring Diagram Dryer Hdt90 For Compressed Air Plant | 01 | 2013-09-17 | Indeterminate | Miscellaneous(MISC) | Detail | Compressed Air Production Plant | Piping & Utility | HAVAYAR |  | IFC | AFC | 100%
15587 | I491TI05-0CPDR02-001-002 | Wiring Diagram Dryer Act900 For Compressed Air Plant | 01 | 2013-09-17 | Indeterminate | Miscellaneous(MISC) | Detail | Compressed Air Production Plant | Piping & Utility | HAVAYAR |  | IFC | AFC | 100%
113025 | I491TI05-0CPYC01-001-001 | CAP Unit Control Panel Internal Wiring Diagram | 01 | 2014-10-14 | Indeterminate | Drawing | Detail | Compressed Air Production Plant | Electrical | HAVAYAR | 2014-10-20 16:27 | IFI | OB | 100%
113026 | I491TI05-0CPYC01-002-001 | CAP Unit Control Panel Termination Diagram | 01 | 2014-10-14 | Indeterminate | Drawing | Detail | Compressed Air Production Plant | Electrical | HAVAYAR | 2014-10-20 16:27 | IFI | OB | 100%
15609 | I491TI05-0CPYC01-003-001 | IO List For Compressed Air Plant | 02 | 2013-07-02 | Indeterminate | Miscellaneous(MISC) | Detail | Compressed Air Production Plant | Automation and Instrumentation | HAVAYAR |  | IFA | AC |  | 95%
113027 | I491TI05-0CPYC01-004-001 | CAP LOCAL CONTROL PANEL WIRING DIAGRAM | 01 | 2014-10-14 | Indeterminate | Drawing | Detail | Compressed Air Production Plant | Electrical | TAM | 2014-10-20 16:27 | IFI | OB | 100%
113257 | I491TI05-0DTAA91-001-001 | Electrical System For fume Treatment Plant Control Panel PLC1 | 00 | 2015-01-18 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Automation and Instrumentation | HASCON | 2015-01-20 13:10 | IFA | AC |  | 95%
15588 | I491TI05-0DTAA91-002-001 | Power And Control Panel Lf Booster “Pcp1” Electrical System For Fume Treatment Plant | 00 | 2013-09-08 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Equipment | Automation and Instrumentation | HASCON |  | IFA | AC |  | 95%
15589 | I491TI05-0DTAA91-003-001 | Electrical System For Fume Treatment Plantpower And Control Panel Rmhs Booster "Pcp2" | 00 | 2013-09-08 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Equipment | Automation and Instrumentation | HASCON |  | IFA | AC |  | 95%
15590 | I491TI05-0DTAA91-004-001 | Electrical System For Fume Treatment Plant Power And Control Panel Mhs Booster Reciving Area "Pcp3" | 00 | 2013-09-08 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Equipment | Automation and Instrumentation | HASCON |  | IFA | AC |  | 95%
114189 | I491TI05-0DTAA91-005-001 | ELECTRICAL SYSTEM FOR FUME TREATMENT PLANT POWER AND CONTROL PANEL EAF DAMPER AND INSTRUMENTS "PCP4" | 00 | 2015-07-22 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Equipment | Automation and Instrumentation | HASCON | 2015-07-27 12:02 | IFA | AFC | 100%
15591 | I491TI05-0DTAA91-006-001 | Electrical System For Fume Treatment Plant Remote I/O Panel Bag Filter Compt. A & B Area | 00 | 2013-09-28 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Equipment | Automation and Instrumentation | HASCON |  | IFA | AC |  | 95%
15592 | I491TI05-0DTAA91-007-001 | Electrical System For Fume Treatment Plant Remote I/O Panel Bag Filter Compt. C & D Area | 00 | 2013-09-28 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Equipment | Automation and Instrumentation | HASCON |  | IFA | AC |  | 95%
15593 | I491TI05-0DTAA91-008-001 | Electrical System For Fume Treatment Plant Remote I/O Panel Dust Silo And Transport Area | 00 | 2013-09-28 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Equipment | Automation and Instrumentation | HASCON |  | IFA | AC |  | 95%
15594 | I491TI05-0DTAA91-011-001 | MHS Booster Fan Panel Wiring Diagram And Dimension | 00 | 2013-09-14 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Equipment | Automation and Instrumentation | TAM |  | IFA | AC |  | 95%
15595 | I491TI05-0DTAA91-011-002 | Electrical System For Fume Treatment Plant Remote I/O Panel Main Fan Area | 00 | 2013-09-28 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Equipment | Automation and Instrumentation | TAM |  | IFA | AC |  | 95%
113258 | I491TI05-0DTAA91-012-001 | Electrical System For Fume Treatment plant Remote I/O Panel Main Fan Area | 00 | 2015-01-18 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Automation and Instrumentation | TAM | 2015-01-20 13:10 | IFA | AC |  | 95%
129600 | I491TI05-0DTAA91-111-001 | PCP6- DRI Power and Control Panel Wiring Diagram and Dimensions | 00 | 2016-09-27 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Automation and Instrumentation | HASCON | 2016-09-29 09:46 | IFA | AC |  | 95%
135006 | I491TI05-0DTDE05-001-001 | MHS Dampers Wiring Diagram | 00 | 2019-01-21 | Indeterminate | Miscellaneous(MISC) | Detail | Material Handling | Automation and Instrumentation | TAM | 2019-02-03 09:05 | IFA | A | 100%
15596 | I491TI05-0EAAA91-001-001 | Eaf Automation Cableing Diagram | 00 | 2012-08-06 | Indeterminate | Miscellaneous(MISC) | Detail | Electric Arc Furnace | Automation and Instrumentation | FUCHS |  | IFI | OB | 100%
130287 | I491TI05-0EAEL91-001-001 | EAF Automation Level1Drawings | 01 | 2017-02-04 | Indeterminate | Miscellaneous(MISC) | Detail | Electric Arc Furnace | Automation and Instrumentation | FUCHS | 2017-02-07 10:10 | IFI | OB | 100%
15598 | I491TI05-0EAEL91-002-001 | Eaf Automation Drawing Terminal Diagram | 00 | 2012-07-28 | Indeterminate | Miscellaneous(MISC) | Detail | Electric Arc Furnace | Automation and Instrumentation | FUCHS |  | IFI | OB | 100%
15599 | I491TI05-0EAFM01-001-001 | Lower Shell -Bottom Temperature Measurement | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
15600 | I491TI05-0EAFM02-001-001 | Bottom Temp.Measurem. Lower Shell Heat Protection Switch-Box | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
15601 | I491TI05-0LFAA91-001-001 | Lf Automation Cableing Diagram | 00 | 2012-08-06 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Automation and Instrumentation | FUCHS |  | IFI | OB | 100%
15610 | I491TI05-0LFEL91-001-001 | Lf Automation Level1 Drawings | 00 | 2012-05-05 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Automation and Instrumentation | FUCHS |  | IFI | OB | 100%
15602 | I491TI05-0LFEL91-002-001 | Lf Automation Drawing Terminal Diagram | 00 | 2012-07-28 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Automation and Instrumentation | TAM |  | IFI | OB | 100%
114715 | I491TI05-0MDCV10-001-001 | DRI Weigh Feedrs wiring diagram | 02 | 2015-11-24 | Indeterminate | Drawing | Detail | Material Handling | Automation and Instrumentation | TAM | 2015-11-28 13:23 | IFC | AFC | 100%
114654 | I491TI05-0MDCV11-001-001 | Weigh Feeders wiring diagram | 02 | 2015-10-06 | Indeterminate | Drawing | Detail | Material Handling | Automation and Instrumentation | TAM | 2015-10-26 14:28 | IFC | AFC | 100%
114100 | I491TI05-0MDFE91-001-001 | WIRING DIAGRAM for MHS FEEDERS FE01,2&3 | 01 | 2015-06-20 | Indeterminate | Drawing | Detail | Material Handling | Automation and Instrumentation | TAM | 2015-06-22 09:48 | IFI | OB | 100%
114101 | I491TI05-0MDFE91-002-001 | WIRING DIAGRAM for MHS FEEDERS FE04.01-09 | 01 | 2015-06-20 | Indeterminate | Drawing | Detail | Material Handling | Automation and Instrumentation | TAM | 2015-06-22 09:48 | IFI | OB | 100%
114102 | I491TI05-0MDFE91-003-001 | WIRING DIAGRAM for MHS FEEDERS FE05.01-15 | 01 | 2015-06-20 | Indeterminate | Drawing | Detail | Material Handling | Automation and Instrumentation | TAM | 2015-06-22 09:48 | IFI | OB | 100%
132884 | I491TI05-0MMCF91-001-001 | WCP SEDIMENTATION LOCAL CONTROL PANELS 1-3 | 00 | 2018-02-12 10:28 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | TAM | 2018-02-12 10:28 | IFI | OB | 100%
132885 | I491TI05-0MMCF91-001-002 | WCP SEDIMENTATION LOCAL CONTROL PANELS 2-3 | 00 | 2018-02-12 10:28 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | TAM | 2018-02-12 10:28 | IFI | OB | 100%
132886 | I491TI05-0MMCF91-001-003 | WCP SEDIMENTATION LOCAL CONTROL PANELS 3-3 | 00 | 2018-02-12 10:28 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | TAM | 2018-02-12 10:28 | IFI | OB | 100%
134638 | I491TI05-0PXFD91-001-001 | Melt Shop Debricking Machine Wiring Diagram 16010513_EN | 00 | 2018-12-12 | Indeterminate | Drawing | Detail | Mobile Equipment | Mechanical | TAM | 2018-12-17 09:25 | IFI | OB | 100%
116961 | I491TI05-0PXPC01-001-001 | Electrical Drawing For Empty Ladle Car | 01 | 2016-07-25 15:34 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop Auxiliaries | Automation and Instrumentation | TAM | 2016-07-25 15:34 | IFC | AC |  | 95%
115340 | I491TI05-0PXPC01-002-001 | Horizontal Ladle Preheater Electrical drawings for Meltshop Auxiliaries | 00 | 2016-05-15 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop Auxiliaries | Automation and Instrumentation | CEBA | 2016-05-25 09:45 | IFI | OB | 100%
115341 | I491TI05-0PXPC01-004-001 | Vertical Dryer Electrical drawings for Meltshop Auxiliaries | 00 | 2016-05-15 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop Auxiliaries | Automation and Instrumentation | CEBA | 2016-05-25 09:45 | IFI | OB | 100%
113064 | I491TI05-0RX0A01-001-001 | LF Tempreature and Sampling Lance Electrical drawig | 00 | 2014-11-10 10:28 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace Auxiliary | Automation and Instrumentation | TAM | 2014-11-10 10:28 | IFA | AC |  | 95%
113065 | I491TI05-0RXGA01-001-001 | LF Emergency Stirring Lance Electrical drawig | 00 | 2014-11-10 10:29 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace Auxiliary | Automation and Instrumentation | TAM | 2014-11-10 10:29 | IFA | AC |  | 95%
114816 | I491TI05-0RXHB01-001-001 | Horizontal Ladle Pre Heater Automation Drawings | 00 | 2016-01-23 | Indeterminate | Miscellaneous(MISC) | Basic | Ladle Furnace Auxiliary | Automation and Instrumentation | TAM | 2016-01-24 09:39 | IFI | OB | 100%
113066 | I491TI05-0RXOA01-001-001 | 2Strands Wire Feeder Machine Electrical drawig | 00 | 2014-11-10 10:29 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace Auxiliary | Automation and Instrumentation | TAM | 2014-11-10 10:29 | IFA | AC |  | 95%
112922 | I491TI05-0SEAA91-001-001 | SUBSTATION MONITORING WIRING DIAGRAM for SMP | 00 | 2014-09-21 | Indeterminate | Drawing | Detail | Steel Making Electrical Substation | Automation and Instrumentation | TAM | 2014-09-22 10:23 | IFI | OB | 100%
114778 | I491TI05-0SHAA91-001-001 | ELECTRICAL DRAWING FOR SCRAP CAR ( SCRAP YARD EQUIPMENT) | 01 | 2015-12-15 | Indeterminate | Drawing | Detail | Scrap Yard Equipment | Electrical | TAM | 2015-12-26 14:17 | IFC | AFC | 100%
115112 | I491TI06-0ASAA91-001-001 | Orifice Calculation Result Datasheet (ASP) | 00 | 2016-04-04 | Indeterminate | Miscellaneous(MISC) | Detail | Air Separation Plant | Automation and Instrumentation | Fortune | 2016-04-06 14:19 | IFI | OB | 100%
130252 | I491TI06-0ASAA91-002-001 | ASP Local Control Panel Test Report | 00 | 2017-01-21 | Indeterminate | Miscellaneous(MISC) | Detail | Air Separation Plant | Automation and Instrumentation | Fortune | 2017-01-24 15:26 | IFI | OB | 100%
15611 | I491TI07-0EAAA91-001-001 | Eaf Automation Level1 Hmi Screens | 00 | 2012-08-07 | Indeterminate | Miscellaneous(MISC) | Detail | Electric Arc Furnace | Automation and Instrumentation | FUCHS |  | IFI | OB | 100%
15612 | I491TI07-0EAAC01-001-001 | Interface List Eaf | 00 | 2012-04-18 | Indeterminate | Miscellaneous(MISC) | Basic | Electric Arc Furnace | Automation and Instrumentation | FUCHS |  | IFI | OB | 100%
15613 | I491TI07-0EAAC01-002-001 | Eaf Instrument List | 00 | 2012-04-18 | Indeterminate | Miscellaneous(MISC) | Basic | Electric Arc Furnace | Automation and Instrumentation | FUCHS |  | IFI | OB | 100%
15614 | I491TI07-0EAAC01-003-001 | Instrument List For Eaf Ladle Transfer Car | 00 | 2013-03-12 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop Auxiliaries | Automation and Instrumentation | FUCHS |  | IFA | AC |  | 95%
15615 | I491TI07-0EAFM05-004-001 | Electro Limit Switch Slagdoor | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
15616 | I491TI07-0LFAA91-001-001 | Lf Automation Level1 Hmi Screens | 00 | 2012-08-07 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Automation and Instrumentation | FUCHS |  | IFI | OB | 100%
15617 | I491TI07-0LFAC01-001-001 | Interface List Lf | 00 | 2012-04-18 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Automation and Instrumentation | FUCHS |  | IFI | OB | 100%
15618 | I491TI07-0LFAC01-002-001 | Lf Instrument List | 00 | 2012-04-18 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Automation and Instrumentation | FUCHS |  | IFI | OB | 100%
15619 | I491TI07-0LFAC01-003-001 | Instrument List For Lf Ladle Transfer Car | 00 | 2013-03-12 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop Auxiliaries | Automation and Instrumentation | FUCHS |  | IFA | AC |  | 95%
114507 | I491TI07-0MMCT01-004-001 | WTP Control System Drawing(LCP1) | 01 | 2015-10-10 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Automation and Instrumentation | FARABARD | 2015-10-11 14:11 | IFC | AFC | 100%
112611 | I491TI07-0MMCT01-004-002 | WTP Control System Drawing(LCP2) | 00 | 2014-07-13 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Automation and Instrumentation | TAM | 2014-07-16 09:23 | IFA | A | 100%
112612 | I491TI07-0MMCT01-004-003 | WTP Control System Drawing(PC01) | 00 | 2014-07-13 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Automation and Instrumentation | TAM | 2014-07-16 09:23 | IFA | A | 100%
15620 | I491TI07-0SHAC01-001-001 | Sensor List Scrap Car | 00 | 2012-10-01 | Indeterminate | Miscellaneous(MISC) | Detail | Scrap Yard Equipment | Automation and Instrumentation | TAM |  | IFA | AC |  | 95%
129776 | I491TI10-0MMCT01-001-001 | MATERIAL TAKE OFF LIST | 00 | 2016-11-06 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Automation and Instrumentation | TAM | 2016-11-12 08:56 | IFI | OB | 100%
15622 | I491TI99-0CPAA91-001-002 | Process Control Philosophy For Air Compressor Plant | 01 | 2013-05-25 | Indeterminate | Miscellaneous(MISC) | Detail | Compressed Air Production Plant | Piping & Utility | HAVAYAR |  | IFC | AFC | 100%
15624 | I491TI99-0CPAA91-002-002 | Instrument Data Sheet (Field) For Compressed Air Plant | 01 | 2013-09-28 | Indeterminate | Miscellaneous(MISC) | Detail | Compressed Air Production Plant | Automation and Instrumentation | HAVAYAR |  | IFC | AFC | 100%
132741 | I491TI99-0MMCF91-028-001 | WCP Software and Wtpn_mpV0 | 00 | 2018-01-17 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Automation and Instrumentation | TAM | 2018-02-01 10:48 | IFI | OB | 100%
114840 | I491TM01-0ASAA91-001-001 | Design & Construction Specification For Air Separation Plant | 00 | 2016-01-25 | Indeterminate | Miscellaneous(MISC) | Detail | Air Separation Plant | Piping & Utility | TAM | 2016-02-02 09:43 | IFA | AC |  | 95%
133221 | I491TM01-0CCFF91-001-001 | Bardsir SteelMaking Plant TUNDISH REFRACTORY | 00 | 2018-05-30 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2018-06-02 14:27 | IFI | OB | 100%
134220 | I491TM01-0CCHB01-001-001 | Combustion Components Data Sheet For Tundish Preheating Station | 00 | 2018-09-22 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | CEBA | 2018-09-30 11:38 | IFI | OB | 100%
134219 | I491TM01-0CCHB01-002-001 | lining Components Data Sheet For Tundish Preheating Station | 00 | 2018-09-22 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | CEBA | 2018-09-30 11:38 | IFI | OB | 100%
134218 | I491TM01-0CCHB01-003-001 | Hydraulic Components Data Sheet For Tundish Preheating Station | 00 | 2018-09-22 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | CEBA | 2018-09-30 11:38 | IFI | OB | 100%
134217 | I491TM01-0CCHB02-001-001 | Combustion Components Data Sheet For Sen Preheating Stove | 00 | 2018-09-22 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | CEBA | 2018-09-30 11:38 | IFI | OB | 100%
134216 | I491TM01-0CCHB02-002-001 | lining Components Date Sheet For Sen Preheating Station (Venturi Type) | 00 | 2018-09-22 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | CEBA | 2018-09-30 11:38 | IFI | OB | 100%
134215 | I491TM01-0CCHB03-001-001 | Combustion Components Date Sheet For Sen Preheating Station (Venturi Type) | 00 | 2018-09-22 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | CEBA | 2018-09-30 11:38 | IFI | OB | 100%
134214 | I491TM01-0CCHB03-002-001 | lining Components Date Sheet For Sen Preheating Staton (Venturi Type) | 00 | 2018-09-22 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | CEBA | 2018-09-30 11:38 | IFI | OB | 100%
133409 | I491TM01-0CCPU01-001-001 | CCM Scale Pit Pump Data Sheet Pumpiran PV4-200-40 | 01 | 2018-07-07 16:23 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2018-07-07 16:23 | IFI | OB | 100%
114519 | I491TM01-0CCSQ02-001-001 | CCM Steam Exhust Fan 6.181176.H_001_03 | 00 | 2015-10-11 15:06 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-11 15:06 | IFI | OB | 100%
134223 | I491TM01-0CCTD10-001-001 | Combustion Components Datte Sheet For Tundish Drying Station | 00 | 2018-09-22 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | CEBA | 2018-09-30 11:38 | IFI | OB | 100%
134222 | I491TM01-0CCTD10-002-001 | lining Components Data Sheet For Tandish Drying Station | 00 | 2018-09-22 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | CEBA | 2018-09-30 11:38 | IFI | OB | 100%
134221 | I491TM01-0CCTD10-003-001 | Hydraulic Components Data Sheet For Tundish Drying Station | 00 | 2018-09-22 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | CEBA | 2018-09-30 11:38 | IFI | OB | 100%
15626 | I491TM01-0CPCP01-001-002 | Data Sheet For Air Compressor (Hy-45000) For Compressed Air Plant | 01 | 2013-05-25 | Indeterminate | Miscellaneous(MISC) | Detail | Compressed Air Production Plant | Piping & Utility | HAVAYAR |  | IFC | AFC | 100%
113469 | I491TM01-0CPDR01-001-002 | Data Sheet For Desiccant Dryer(Hdt-90) For Compressed Air Plant | 02 | 2013-08-20 | Indeterminate | Miscellaneous(MISC) | Detail | Compressed Air Production Plant | Piping & Utility | HAVAYAR | 2015-04-06 11:48 | IFC | AFC | 100%
16035 | I491TM01-0CPDR02-001-002 | Data Sheet For Dryer (Act-900) For Compressed Air Plant | 01 | 2013-05-25 | Indeterminate | Miscellaneous(MISC) | Basic | Compressed Air Production Plant | Piping & Utility | TAM |  | IFC | AFC | 100%
133873 | I491TM01-0CPDR03-001-001 | Specification and Data Sheet For Fume Treatment Plant Compressed Air Receiver Vessel | 01 | 2018-07-24 08:20 | Indeterminate | Miscellaneous(MISC) | Detail | Compressed Air Production Plant | Mechanical | TAM | 2018-07-24 08:20 | IFI | OB | 100%
132690 | I491TM01-0CPDR04-001-001 | Specification and Data Sheet For Fume Treatment Plant Compressed Air Dryer | 00 | 2018-01-15 | Indeterminate | Miscellaneous(MISC) | Detail | Compressed Air Production Plant | Mechanical | TAM | 2018-01-20 09:59 | IFI | OB | 100%
15631 | I491TM01-0CPFL01-001-001 | Data Sheet For Micro Filter (Afs 0706) For Compressed Air Plant | 00 | 2013-03-03 | Indeterminate | Miscellaneous(MISC) | Detail | Compressed Air Production Plant | Piping & Utility | HAVAYAR |  | IFA | AC |  | 95%
112568 | I491TM01-0CPFL02-001-001 | Data Sheet For Pre Filter (Afm 0706) For Compressed Air Plant | 01 | 2014-07-08 | Indeterminate | Miscellaneous(MISC) | Detail | Compressed Air Production Plant | Piping & Utility | HAVAYAR | 2014-07-13 13:39 | IFC | AFC | 100%
112569 | I491TM01-0CPFL03-001-001 | Data Sheet For Micro Filter (Hy-1200) For Compressed Air Plant | 01 | 2014-07-08 | Indeterminate | Miscellaneous(MISC) | Detail | Compressed Air Production Plant | Piping & Utility | HAVAYAR | 2014-07-13 13:39 | IFC | AFC | 100%
112570 | I491TM01-0CPFL04-001-001 | Data Sheet For Pre Filter (Hy-1200) For Compressed Air Plant | 01 | 2014-07-08 | Indeterminate | Miscellaneous(MISC) | Detail | Compressed Air Production Plant | Piping & Utility | HAVAYAR | 2014-07-13 13:40 | IFC | AFC | 100%
112571 | I491TM01-0CPFL05-001-001 | Data Sheet Pre Filter (Afs 0706) For Compressed Air Plant | 02 | 2014-07-08 | Indeterminate | Miscellaneous(MISC) | Detail | Compressed Air Production Plant | Piping & Utility | TAM | 2014-07-13 13:40 | IFC | AFC | 100%
112573 | I491TM01-0CPFL06-001-001 | Data Sheet Micro Filter (AFM0706) For Compressed Air Plant | 00 | 2014-07-08 | Indeterminate | Miscellaneous(MISC) | Detail | Compressed Air Production Plant | Piping & Utility | TAM | 2014-07-13 13:42 | IFC | AFC | 100%
15636 | I491TM01-0CPTK01-001-002 | Data Sheet For Air Receiver (Hy-10000) For Compressed Air Plant | 01 | 2013-05-25 | Indeterminate | Miscellaneous(MISC) | Detail | Compressed Air Production Plant | Piping & Utility | HAVAYAR |  | IFC | AFC | 100%
129926 | I491TM01-0DTAA91-006-001 | Air tank-main Filters For Fume Treatment Plant | 00 | 2016-12-12 15:16 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2016-12-12 15:16 | IFI | OB | 100%
129927 | I491TM01-0DTAA91-007-001 | Air tanks DRI Filter For Fume Treatment Plant | 00 | 2016-12-12 15:16 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2016-12-12 15:16 | IFI | OB | 100%
15637 | I491TM01-0DTAA91-008-001 | Cages For Main Filters | 00 | 2013-09-11 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Equipment | Mechanical | HASCON |  | IFI | OB | 100%
15639 | I491TM01-0DTAA91-009-001 | Cages For Dri Filter | 00 | 2013-09-11 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Equipment | Mechanical | HASCON |  | IFI | OB | 100%
134367 | I491TM01-0DTAA91-010-001 | Datta Sheet For Bags main filter 6519-M10 | 00 | 2018-11-13 10:17 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Equipment | Mechanical | TAM | 2018-11-13 10:17 | IFI | OB | 100%
134368 | I491TM01-0DTAA91-011-001 | Datta Sheet For Bags DRI filter 6519-M11 | 00 | 2018-11-13 10:17 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Equipment | Mechanical | TAM | 2018-11-13 10:17 | IFI | OB | 100%
134369 | I491TM01-0DTAA91-012-001 | Datta Sheet For Rotary feeder for main filter 6519-M12 | 00 | 2018-11-13 10:17 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Equipment | Mechanical | TAM | 2018-11-13 10:17 | IFI | OB | 100%
129928 | I491TM01-0DTAA91-013-001 | FTP CONTROL ROOM FIRE ALARM - DETECTION LINE LAYOUT | 00 | 2016-12-12 15:20 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2016-12-12 15:20 | IFI | OB | 100%
15641 | I491TM01-0DTAA91-014-001 | Rotary Feeders Mixing Chamber | 00 | 2013-09-11 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Equipment | Mechanical | HASCON |  | IFI | OB | 100%
129929 | I491TM01-0DTAA91-015-001 | FTP CONTROL ROOM FIRE ALARM - ALARM LINE LAYOUT | 00 | 2016-12-12 16:12 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2016-12-12 16:12 | IFI | OB | 100%
15643 | I491TM01-0DTAA91-016-001 | Rotary Feeders Airpin Cooler | 00 | 2013-09-11 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Equipment | Mechanical | HASCON |  | IFI | OB | 100%
15645 | I491TM01-0DTAA91-017-001 | Rotary Feeder Horizontal Cyclone | 00 | 2013-09-11 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Equipment | Mechanical | HASCON |  | IFI | OB | 100%
15647 | I491TM01-0DTAA91-020-001 | Chain Conveyor Mixing Chamber | 00 | 2013-09-11 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Equipment | Mechanical | HASCON |  | IFI | OB | 100%
15650 | I491TM01-0DTAA91-021-001 | Traversal Chain Conveyors For Airpin Cooler Discharge | 00 | 2013-09-11 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Equipment | Mechanical | HASCON |  | IFI | OB | 100%
134370 | I491TM01-0DTAA91-022-001 | Datta Sheet For Bucket elevator 6519-M22 | 01 | 2018-11-13 10:17 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2018-11-13 10:17 | IFI | OB | 100%
113384 | I491TM01-0DTAA91-023-001 | Screw conveyor roof Silo | 00 | 2015-02-21 14:54 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2015-02-21 14:54 | IFI | OB | 100%
15652 | I491TM01-0DTAA91-024-001 | Chain Conveyors For Hopper Airpin Cooler | 00 | 2013-09-11 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Equipment | Mechanical | HASCON |  | IFI | OB | 100%
129930 | I491TM01-0DTAA91-025-001 | Screw conveyor for DRI filter For Fume Treatment Equipment | 00 | 2016-12-12 16:31 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2016-12-12 16:31 | IFI | OB | 100%
129931 | I491TM01-0DTAA91-026-001 | Main Fans For Fume Treatment Equipment | 00 | 2016-12-12 16:32 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2016-12-12 16:32 | IFI | OB | 100%
129932 | I491TM01-0DTAA91-027-001 | Main Booster For Fume Treatment Equipment | 00 | 2016-12-12 16:32 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2016-12-12 16:32 | IFI | OB | 100%
129933 | I491TM01-0DTAA91-028-001 | LF Booster fan For Fume Treatment Equipment | 00 | 2016-12-12 16:32 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2016-12-12 16:32 | IFI | OB | 100%
129934 | I491TM01-0DTAA91-029-001 | MHS Fan Reciving Area For Fume Treatment Equipment | 00 | 2016-12-12 16:32 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2016-12-12 16:32 | IFI | OB | 100%
129935 | I491TM01-0DTAA91-030-001 | RMHS fan For Fume Treatment Equipment | 00 | 2016-12-12 16:32 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2016-12-12 16:32 | IFI | OB | 100%
129936 | I491TM01-0DTAA91-031-001 | DRI fan For Fume Treatment Equipment | 00 | 2016-12-12 16:33 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2016-12-12 16:33 | IFI | OB | 100%
130531 | I491TM01-0DTAA91-032-001 | Motors Main Fans Data Sheet Fume Treatment Equipment | 00 | 2017-04-29 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2017-04-30 15:50 | IFI | OB | 100%
130532 | I491TM01-0DTAA91-033-001 | Motor for primary booster Data Sheet Fume Treatment Equipment | 00 | 2017-04-29 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2017-04-30 15:51 | IFI | OB | 100%
130533 | I491TM01-0DTAA91-034-001 | Motor for LF Fan Data Sheet Fume Treatment Equipment | 00 | 2017-04-29 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2017-04-30 15:52 | IFI | OB | 100%
129937 | I491TM01-0DTAA91-035-001 | Motor Mhs fan For Fume Treatment Equipment | 00 | 2016-12-12 16:33 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2016-12-12 16:33 | IFI | OB | 100%
129938 | I491TM01-0DTAA91-037-001 | Motor DRI fan For Fume Treatment Equipment | 00 | 2016-12-12 16:33 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2016-12-12 16:33 | IFI | OB | 100%
134371 | I491TM01-0DTAA91-039-001 | Datta Sheet For Cilindri Poppet filtri principali 6519-M39 | 00 | 2018-11-13 10:17 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Equipment | Mechanical | TAM | 2018-11-13 10:17 | IFI | OB | 100%
134372 | I491TM01-0DTAA91-041-001 | Data Sheet For Telescopic bellow silo 6519-M41 | 00 | 2018-11-13 10:18 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Equipment | Mechanical | TAM | 2018-11-13 10:18 | IFI | OB | 100%
113385 | I491TM01-0DTAA91-045-001 | Mixing Chamber Expansion Joint | 00 | 2015-02-21 14:55 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2015-02-21 14:55 | IFI | OB | 100%
113386 | I491TM01-0DTAA91-046-001 | Airpin Cooler Expansion Joint | 00 | 2015-02-21 14:55 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2015-02-21 14:55 | IFI | OB | 100%
113387 | I491TM01-0DTAA91-047-001 | Silo Expansion Joint | 00 | 2015-02-21 14:55 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2015-02-21 14:55 | IFI | OB | 100%
113388 | I491TM01-0DTAA91-048-001 | Expansion Joint ø 1400 | 00 | 2015-02-21 14:55 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2015-02-21 14:55 | IFI | OB | 100%
129939 | I491TM01-0DTAA91-061-001 | Expansion joint Hairpin collector For Fume Treatment Equipment | 00 | 2016-12-12 16:33 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2016-12-12 16:33 | IFI | OB | 100%
134373 | I491TM01-0DTAA91-063-001 | Datta Sheet For Hydraulic cylinder for sliding elbow 6519-M63 | 00 | 2018-11-13 10:18 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Equipment | Mechanical | TAM | 2018-11-13 10:18 | IFI | OB | 100%
134374 | I491TM01-0DTAA91-069-001 | Datta Sheet For Ventilatore MHS_LF_EAF_REC area 6519-M69 | 00 | 2018-11-13 10:18 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Equipment | Mechanical | TAM | 2018-11-13 10:18 | IFI | OB | 100%
15653 | I491TM01-0DTEJ01-005-001 | Dedusting System Duct Fournace 140 Ton Eaf+Lf & Mh & Sliding Expansion Joint By-Pass Diam. 2700 | 01 | 2013-08-18 | Indeterminate | Drawing | Basic | Fume Treatment Equipment | Mechanical | HASCON |  | IFA | A | 100%
15654 | I491TM01-0DTEJ01-006-001 | Dedusting System Duct Fournace 140 Ton Eaf+Lf & Mh & Sliding Expansion Joint Canopy Hood Diam. 3300 | 01 | 2013-08-18 | Indeterminate | Drawing | Basic | Fume Treatment Equipment | Mechanical | HASCON |  | IFA | A | 100%
112913 | I491TM01-0DTEJ01-008-001 | Dedusting System Duct Fournace 140 Ton Eaf+Lf & Mh & Sliding Expansion Joint For Mixing Inletdiam. 5000 | 02 | 2014-09-21 | Indeterminate | Drawing | Basic | Fume Treatment Equipment | Mechanical | HASCON | 2014-09-22 09:49 | IFI | OB | 100%
15656 | I491TM01-0DTEJ01-009-001 | Dedusting System Duct Fournace 140 Ton Eaf+Lf & Mh & Sliding Expansion Joint For Filter 5000X3250 | 01 | 2013-08-18 | Indeterminate | Drawing | Basic | Fume Treatment Equipment | Mechanical | HASCON |  | IFA | A | 100%
15657 | I491TM01-0DTEJ01-010-001 | Dedusting System Duct Fournace 140 Ton Eaf+Lf & Mh & Sliding Expansion Joint For Mixing Outlet 6500X5000 | 01 | 2013-08-18 | Indeterminate | Drawing | Basic | Fume Treatment Equipment | Mechanical | HASCON |  | IFA | A | 100%
15658 | I491TM01-0DTEJ01-011-001 | Dedusting System Duct Fournace 140 Ton Eaf+Lf & Mh & Sliding Expansion Joint For Hairpin Outlet 3200X1900 | 01 | 2013-08-18 | Indeterminate | Drawing | Basic | Fume Treatment Equipment | Mechanical | HASCON |  | IFA | A | 100%
15659 | I491TM01-0DTEJ01-012-001 | Dedusting System Duct Fournace 140 Ton Eaf+Lf & Mh & Sliding Expansion Joint For Chimney 3500X2000 | 00 | 2013-08-18 | Indeterminate | Drawing | Basic | Fume Treatment Equipment | Mechanical | HASCON |  | IFA | A | 100%
15660 | I491TM01-0DTEJ01-013-001 | Dedusting System Duct Fournace 140 Ton Eaf+Lf & Mh & Sliding Expansion Joint For Ducts Diam. 3100 | 00 | 2013-08-18 | Indeterminate | Drawing | Basic | Fume Treatment Equipment | Mechanical | HASCON |  | IFA | A | 100%
112914 | I491TM01-0DTEJ01-014-001 | DEDUSTING SYSTEM FOURNACE 140Ton EAF+LF & MH EXPANSION JOINT CYCLON DUCT Ø1400 | 00 | 2014-09-21 | Indeterminate | Drawing | Basic | Fume Treatment Equipment | Mechanical | HASCON | 2014-09-22 09:49 | IFI | OB | 100%
15661 | I491TM01-0DTEJ01-015-001 | Dedusting System Duct Fournace 140 Ton Eaf+Lf & Mh & Sliding Expansion Joint For Ducts Diam. 3100 | 00 | 2013-08-18 | Indeterminate | Drawing | Basic | Fume Treatment Equipment | Mechanical | HASCON |  | IFA | A | 100%
15662 | I491TM01-0DTEJ01-016-001 | Dedusting System Duct Fournace 140 Ton Eaf+Lf & Mh & Sliding Expansion Joint For Ducts Diam. 3100 | 00 | 2013-08-18 | Indeterminate | Drawing | Basic | Fume Treatment Equipment | Mechanical | HASCON |  | IFA | A | 100%
113073 | I491TM01-0EAEC01-001-001 | Material Requisition for Electrode for EAF and LF | 01 | 2014-11-17 | Indeterminate | Miscellaneous(MISC) | Detail | Electric Arc Furnace | Mechanical | TAM | 2014-11-22 08:28 | IFI | OB | 100%
112465 | I491TM01-0EAFF91-001-001 | Inquiry for Refractory for EAF and Ladle | 00 | 2014-07-02 | Indeterminate | Miscellaneous(MISC) | Detail | Electric Arc Furnace | Mechanical | TAM | 2014-07-03 10:44 | IFI | AC |  | 95%
115129 | I491TM01-0EAFF91-002-001 | Bardsir Steel Making Plant EAF Refractory | 00 | 2016-04-06 | Indeterminate | Miscellaneous(MISC) | Detail | Electric Arc Furnace | Mechanical | TAM | 2016-04-10 10:02 | IFI | OB | 100%
130549 | I491TM01-0EAOF91-001-001 | Data sheet for oil and grease of EAF LF and Auxiliaries | 01 | 2017-05-03 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop Auxiliaries | Mechanical | TAM | 2017-05-06 14:14 | IFI | AC |  | 95%
15663 | I491TM01-0MDCV10-001-001 | Eaf 5Th Hole Charging Belt Weigh Feeder Under Dri Bins Md-Cv-10.01~04 | 00 | 2013-07-10 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | DATIS |  | IFI | OB | 100%
15664 | I491TM01-0MDCV10-001-002 | Eaf 5Th Hole Charging Belt Weigh Feeder Under Dri Bins Md-Cv-10.01~04 | 00 | 2013-07-10 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | DATIS |  | IFI | OB | 100%
15665 | I491TM01-0MDCV10-001-003 | Eaf 5Th Hole Charging Belt Weigh Feeder Md-Cv-11.01~03 | 00 | 2013-07-10 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | DATIS |  | IFI | OB | 100%
15666 | I491TM01-0MDCV10-001-004 | Eaf 5Th Hole Charging Belt Weigh Feeder Md-Cv-11.01~03 | 00 | 2013-07-10 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | DATIS |  | IFI | OB | 100%
15667 | I491TM01-0MDFE01-001-001 | Dolomite And Lime Electro-Mechanic Vibrating Feeder Md-Fe-01.01 | 00 | 2013-07-10 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | DATIS |  | IFI | OB | 100%
15668 | I491TM01-0MDFE01-001-002 | Dolomite And Lime Electro-Mechanic Vibrating Feedermd-Fe-01.01 | 00 | 2013-07-10 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | DATIS |  | IFI | OB | 100%
15669 | I491TM01-0MDFE02-001-001 | Dolomite And Lime Electro-Mechanic Vibrating Feeder Md-Fe-02.01~03 | 00 | 2013-07-10 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | DATIS |  | IFI | OB | 100%
15670 | I491TM01-0MDFE02-001-002 | Dolomite And Lime Electro-Mechanic Vibrating Feedermd-Fe-02.01~03 | 00 | 2013-07-10 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | DATIS |  | IFI | OB | 100%
15671 | I491TM01-0MDFE02-002-001 | Dolomite And Lime Electro-Mechanic Vibrating Feeder Md-Fe-02.04 | 00 | 2013-07-10 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | DATIS |  | IFI | OB | 100%
15672 | I491TM01-0MDFE02-002-002 | Dolomite And Lime Electro-Mechanic Vibrating Feeder Md-Fe-02.04 | 00 | 2013-07-10 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | DATIS |  | IFI | OB | 100%
15673 | I491TM01-0MDFE03-001-001 | Dolomite And Lime Electro-Mechanic Vibrating Feeder Md-Fe-03.01~09 | 00 | 2013-07-10 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | DATIS |  | IFI | OB | 100%
15674 | I491TM01-0MDFE03-001-002 | Dolomite And Lime Electro-Mechanic Vibrating Feeder Md-Fe-03.01~09 | 00 | 2013-07-10 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | DATIS |  | IFI | OB | 100%
15676 | I491TM01-0MDFE04-001-001 | Dolomite And Lime Electro-Mechanic Vibrating Feeder Md-Fe-04.01~15 | 00 | 2013-07-10 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | DATIS |  | IFI | OB | 100%
15675 | I491TM01-0MDFE04-001-002 | Dolomite And Lime Electro-Mechanic Vibrating Feeder Md-Fe-03.01~09 | 00 | 2013-07-10 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | DATIS |  | IFI | OB | 100%
112468 | I491TM01-0MLXL91-001-001 | Inquiry for pneumatic post system | 00 | 2014-07-03 | Indeterminate | Miscellaneous(MISC) | Detail | Laboratory | Mechanical | TAM | 2014-07-05 09:47 | IFI | OB | 100%
15677 | I491TM01-0MMCT01-001-001 | Cooling Tower Data Sheet Ct01 | 00 | 2013-01-02 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Piping & Utility | TAM |  | IFA | AC |  | 95%
15678 | I491TM01-0MMCT01-002-001 | Fan Package Data Sheet Ct01 | 00 | 2013-01-02 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Piping & Utility | TAM |  | IFA | AC |  | 95%
112617 | I491TM01-0MMCT01-003-001 | Gear Reducer Data Sheet for cooling System CT01 | 01 | 2014-07-15 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Piping & Utility | TAM | 2014-07-16 09:33 | IFC | AFC | 100%
15680 | I491TM01-0MMCT01-004-001 | Drive Shaft Data Sheet Ct01 | 00 | 2013-01-02 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Piping & Utility | TAM |  | IFA | AC |  | 95%
15681 | I491TM01-0MMCT01-005-001 | Internal Data Sheet Ct01 | 00 | 2013-01-02 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Piping & Utility | TAM |  | IFA | AC |  | 95%
114928 | I491TM01-0MMCT01-006-001 | DATA SHEET FOR CT01 CORROSION INHIBITOR & SCALE DOSING PUMP | 00 | 2016-02-24 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Piping & Utility | TAM | 2016-02-28 08:48 | IFI | OB | 100%
114929 | I491TM01-0MMCT01-008-001 | DATA SHEET FOR CT01 BIOCIDE DOSING PUMP | 00 | 2016-02-24 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Piping & Utility | TAM | 2016-02-28 08:48 | IFI | OB | 100%
15683 | I491TM01-0MMCT01-012-002 | Pump Process Data Sheet Of Cooling Water System | 01 | 2013-03-09 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Piping & Utility | TAM |  | IFC | AFC | 100%
15684 | I491TM01-0MMCT02-001-001 | Cooling Tower Data Sheet Ct02 | 00 | 2013-01-02 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Piping & Utility | TAM |  | IFA | AC |  | 95%
15685 | I491TM01-0MMCT02-002-001 | Fan Package Data Sheet Ct02 | 00 | 2013-01-02 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Piping & Utility | TAM |  | IFA | AC |  | 95%
113012 | I491TM01-0MMCT02-003-001 | Gear Reducer Data Sheet for cooling System CT02 | 02 | 2014-10-01 10:02 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Piping & Utility | TAM | 2014-10-01 10:02 | IFC | AFC | 100%
15687 | I491TM01-0MMCT02-004-001 | Drive Shaft Data Sheet Ct02 | 00 | 2013-01-02 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Piping & Utility | TAM |  | IFA | AC |  | 95%
15688 | I491TM01-0MMCT02-005-001 | Internal Data Sheet Ct02 | 00 | 2013-01-02 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Piping & Utility | TAM |  | IFA | AC |  | 95%
114930 | I491TM01-0MMCT02-009-001 | Data Sheet For CT2 Scale Dosing Pump | 00 | 2016-02-24 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Piping & Utility | TAM | 2016-02-28 08:48 | IFI | OB | 100%
114931 | I491TM01-0MMCT02-011-001 | DATA SHEET FOR CT02 BIOCIDE DOSING PUMP | 00 | 2016-02-24 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Piping & Utility | TAM | 2016-02-28 08:48 | IFI | OB | 100%
130002 | I491TM01-0MMHE01-001-001 | Specification and Data Sheet For plate heat exchanger | 01 | 2016-12-20 10:25 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Piping & Utility | TAM | 2016-12-20 10:25 | IFI | OB | 100%
132657 | I491TM01-0MMOS02-001-001 | Specification and Data Sheet for sedimentation oil Collection System | 00 | 2018-01-07 09:36 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Mechanical | TAM | 2018-01-07 09:36 | IFI | OB | 100%
131356 | I491TM01-0MXEG01-001-001 | Data Sheet For Meltshop and ccm Diesel Generator | 00 | 2017-10-02 | Indeterminate | Miscellaneous(MISC) | Detail | General | Electrical | TAM | 2017-10-11 09:06 | IFI | OB | 100%
115131 | I491TM01-0PXFF91-001-001 | Bardsir Steel Making Plant Ladle Refractory | 01 | 2016-04-06 | Indeterminate | Miscellaneous(MISC) | Detail | Electric Arc Furnace | Mechanical | TAM | 2016-04-11 10:32 | IFI | OB | 100%
130550 | I491TM01-0PXOT91-001-001 | Meltshop And Eaf Auxiliary Equipment Hydraulic And Lubricant Consumable Oil | 00 | 2017-05-03 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop Auxiliaries | Mechanical | TAM | 2017-05-06 14:18 | IFI | AC |  | 95%
114781 | I491TM02-0ASAA91-001-001 | Plot Plan For Air Separation Plant | 01 | 2015-12-20 | Indeterminate | Drawing | Basic | Air Separation Plant | Piping & Utility | TAM | 2015-12-27 10:04 | IFC | AFC | 100%
113097 | I491TM02-0CCAA91-002-001 | CCM Equipment Layout 6329589B_001 | 00 | 2014-12-09 10:02 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Mechanical | TAM | 2014-12-09 10:02 | IFA | AC |  | 95%
113098 | I491TM02-0CCAA91-002-002 | CCM Equipment Layout 6329589B_002 | 00 | 2014-12-09 10:02 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Mechanical | TAM | 2014-12-09 10:02 | IFA | AC |  | 95%
113099 | I491TM02-0CCAA91-002-003 | CCM Equipment Layout 6329589B_003 | 00 | 2014-12-09 10:02 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Mechanical | TAM | 2014-12-09 10:02 | IFA | AC |  | 95%
113100 | I491TM02-0CCAA91-002-004 | CCM Equipment Layout 6329589B_004 | 00 | 2014-12-09 10:02 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Mechanical | TAM | 2014-12-09 10:02 | IFA | AC |  | 95%
113101 | I491TM02-0CCAA91-002-005 | CCM Equipment Layout 6329589B_005 | 00 | 2014-12-09 10:02 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Mechanical | TAM | 2014-12-09 10:02 | IFA | AC |  | 95%
114513 | I491TM02-0CCCC01-001-001 | CCM Fix Curved Sector 8.650296.R_001_00 | 00 | 2015-10-11 15:05 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-11 15:05 | IFI | OB | 100%
114514 | I491TM02-0CCCC02-001-001 | CCM Fix Curved Sector Adaptor 8.680057.N_001_00 | 00 | 2015-10-11 15:05 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-11 15:05 | IFI | OB | 100%
114530 | I491TM02-0CCDF01-002-001 | Dummy Bar Location 6.068057.E_001_01 | 00 | 2015-10-12 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-13 08:41 | IFI | OB | 100%
15694 | I491TM02-0CCDF02-002-001 | Ccm Roller Unit 200-390-2006-1000 | 00 | 2013-10-29 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Mechanical | TAM |  | IFA | AFC | 100%
114525 | I491TM02-0CCDF04-001-001 | Dummy Bar Head 130x130 8.650404.Z_001_00 | 00 | 2015-10-12 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-13 08:40 | IFI | OB | 100%
114523 | I491TM02-0CCDF05-001-001 | Dummy Bar Head 150x150 8.650403.X_001_00 | 00 | 2015-10-12 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-13 08:40 | IFI | OB | 100%
114524 | I491TM02-0CCDF06-001-001 | Dummy Bar Head 200x200 8.650411.N_001_00 | 00 | 2015-10-12 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-13 08:40 | IFI | OB | 100%
114415 | I491TM02-0CCHB01-001-002 | CCM Tundish Preheating Station 6.267235.A_001_01 | 02 | 2015-10-03 11:30 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-03 11:30 | IFA | A | 100%
114416 | I491TM02-0CCHB02-001-001 | CCM Nozzle Preheating Oven 6.147321.X_001_00 | 01 | 2015-10-03 11:30 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-03 11:30 | IFA | A | 100%
114417 | I491TM02-0CCHB03-001-001 | Sheet 1of2 CCM Shroud Preheating Station 6.267312.E_001_02 | 00 | 2015-10-03 12:01 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-03 12:01 | IFA | A | 100%
114418 | I491TM02-0CCHB03-001-002 | Sheet 1of3 Nozzle Heater on Tundish Car 8.664191.D_001_00A | 00 | 2015-10-03 12:01 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-03 12:01 | IFA | A | 100%
114419 | I491TM02-0CCHB03-001-003 | Sheet 2of2 CCM Shroud Preheating Station 6.267312.E_002_02 | 00 | 2015-10-03 12:01 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-03 12:01 | IFA | A | 100%
114420 | I491TM02-0CCHB03-001-004 | Sheet 2of3 Nozzle Heater on Tundish Car 8.664191.D_002_00A | 00 | 2015-10-03 12:01 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-03 12:01 | IFA | A | 100%
114421 | I491TM02-0CCHB03-001-005 | Sheet 3of3 Nozzle Heater on Tundish Car 8.664191.D_003_00A | 00 | 2015-10-03 12:01 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-03 12:01 | IFA | A | 100%
114445 | I491TM02-0CCLK01-001-005 | Sheet 5of6 Ladle Turret 8.566931.S_005_02 | 00 | 2015-10-05 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-10 13:48 | IFI | OB | 100%
114446 | I491TM02-0CCLK01-001-006 | Sheet 6of6 Ladle Turret 8.566931.S_006_02 | 00 | 2015-10-05 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-10 13:48 | IFI | OB | 100%
114447 | I491TM02-0CCLK02-001-001 | Turret Cylinder Arm 8.567059.K_001_00 | 00 | 2015-10-05 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-10 13:49 | IFI | OB | 100%
114448 | I491TM02-0CCLK06-001-001 | Ladle Turret Transport 6.343509.Q_001_01 | 00 | 2015-10-05 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-10 13:49 | IFI | OB | 100%
114449 | I491TM02-0CCLK07-001-001 | Cover Lifting Crane 8.680168.S_001_00 | 00 | 2015-10-05 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-10 13:49 | IFI | OB | 100%
114453 | I491TM02-0CCMJ01-001-001 | CCM Mould 8.494930.V_001_02 | 00 | 2015-10-06 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-10 14:22 | IFI | OB | 100%
114458 | I491TM02-0CCMJ02-002-001 | Mould Oscilator 6.147011.L_001_00A | 00 | 2015-10-06 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-10 14:23 | IFI | OB | 100%
114459 | I491TM02-0CCMJ02-003-001 | Mould Oscilator 6.362023.X_001_00 | 00 | 2015-10-06 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-10 14:24 | IFI | OB | 100%
114454 | I491TM02-0CCMJ03-001-001 | Mould Level Calibrator 8.360596.P_001_03E | 00 | 2015-10-06 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-10 14:23 | IFI | OB | 100%
114558 | I491TM02-0CCMM01-001-001 | CCM Marking Machine 6.329650.T_001_00 | 00 | 2015-10-18 11:09 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-18 11:09 | IFI | OB | 100%
114516 | I491TM02-0CCMS02-001-002 | Sheet 2of2 CCM Spray Cage 8.687876.C_002_01 | 00 | 2015-10-11 15:06 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-11 15:06 | IFI | OB | 100%
114520 | I491TM02-0CCMS03-001-001 | CCM Zone 2 Spray 130x130 8.687877.D_001_00 | 00 | 2015-10-11 15:06 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-11 15:06 | IFI | OB | 100%
114521 | I491TM02-0CCMS04-001-001 | CCM Zone 2 Spray 150x150 8.687875.B_001_00 | 00 | 2015-10-11 15:06 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-11 15:06 | IFI | OB | 100%
114522 | I491TM02-0CCMS05-001-001 | CCM Zone 2 Spray 200x200 8.687874.A_001_00 | 00 | 2015-10-11 15:07 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-11 15:07 | IFI | OB | 100%
114562 | I491TM02-0CCPW02-002-001 | Lateral Comb Transfer Support 8.691504.B_001_00 | 00 | 2015-10-18 11:09 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-18 11:09 | IFI | OB | 100%
114563 | I491TM02-0CCPW02-003-001 | Lateral Comb Transfer Location 6.372147.B_001_00 | 00 | 2015-10-18 11:09 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-18 11:09 | IFI | OB | 100%
114564 | I491TM02-0CCPW02-004-001 | Sheet 1of2 Lateral Comb Transfer Transport 6.372146 (1) | 00 | 2015-10-18 11:09 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-18 11:09 | IFI | OB | 100%
114565 | I491TM02-0CCPW02-004-002 | Sheet 2of2 Lateral Comb Transfer Transport 6.372146 (2) | 00 | 2015-10-18 11:09 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-18 11:09 | IFI | OB | 100%
114540 | I491TM02-0CCRL01-001-002 | Sheet 2of2 CCM DRT 8.610604.Z_002_01 | 00 | 2015-10-13 11:32 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-13 11:32 | IFI | OB | 100%
114541 | I491TM02-0CCRL02-005-001 | Sheet 1of2 CCM TRT 8.610587.G_001_00 | 00 | 2015-10-13 11:32 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-13 11:32 | IFI | OB | 100%
114542 | I491TM02-0CCRL02-005-002 | Sheet 2of2 CCM TRT 8.610587.G_002_00 | 00 | 2015-10-13 11:32 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-13 11:32 | IFI | OB | 100%
114543 | I491TM02-0CCRL02-006-001 | CCM TRT Frame 8.610593.E_001_00 Layou | 00 | 2015-10-13 11:33 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-13 11:33 | IFI | OB | 100%
114544 | I491TM02-0CCRL02-007-001 | CCM TRT Assy 6.343530.A_001_00 | 00 | 2015-10-13 11:33 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-13 11:33 | IFI | OB | 100%
114547 | I491TM02-0CCRL07-002-001 | CCM IRT Frame 8.610579.X_001_00 | 00 | 2015-10-13 11:33 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-13 11:33 | IFI | OB | 100%
114548 | I491TM02-0CCRL10-001-001 | CCM ART 8.680005.K_001_02 | 00 | 2015-10-13 11:33 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-13 11:33 | IFI | OB | 100%
114549 | I491TM02-0CCRL10-003-001 | CCM ART Device 6.372153.G_001_01 | 00 | 2015-10-13 11:34 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-13 11:34 | IFI | OB | 100%
114550 | I491TM02-0CCRL10-004-001 | CCM ART Transport 6.372154.A_001_00 | 00 | 2015-10-13 11:34 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-13 11:34 | IFI | OB | 100%
15728 | I491TM02-0CCSG01-001-001 | 6-Strand Billet Caster Emergrency Slide Gate | 00 | 2013-11-23 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM |  | IFA | A | 100%
15729 | I491TM02-0CCSG02-001-001 | 6-Strand Billet Caster Noozle Changer | 00 | 2013-11-23 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM |  | IFA | A | 100%
114470 | I491TM02-0CCSO02-001-001 | Sheet 1of3 Stopper Rod 8.680017.E_001_00 | 01 | 2015-10-07 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-11 11:48 | IFI | OB | 100%
114471 | I491TM02-0CCSO02-001-002 | Sheet 2of3 Stopper Rod 8.680017.E_002_00 | 00 | 2015-10-07 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-11 11:48 | IFI | OB | 100%
114472 | I491TM02-0CCSO02-001-003 | Sheet 3of3 Stopper Rod 8.680017.E_003_00 | 00 | 2015-10-07 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-11 11:48 | IFI | OB | 100%
114473 | I491TM02-0CCSO02-002-001 | Sheet 1of3 Stopper Rod Transport 6.267062.F_001_00 | 00 | 2015-10-07 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-11 11:48 | IFI | OB | 100%
114532 | I491TM02-0CCSX01-001-002 | Sheet 1of2 CCM WS Unit 8.680106.M_001_00 | 00 | 2015-10-13 10:14 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-13 10:14 | IFI | OB | 100%
114534 | I491TM02-0CCSX01-001-003 | Sheet 2of2 CCM WS Unit 8.680106.M_002_00 | 00 | 2015-10-13 10:14 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-13 10:14 | IFI | OB | 100%
15733 | I491TM02-0CCSX01-003-001 | Ccm Withdrawal Unit 1 200-390-2008-1100 | 00 | 2013-10-29 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Mechanical | TAM |  | IFA | AFC | 100%
114570 | I491TM02-0CCTB01-001-003 | Sheet 3 of 2 CCM Cooling Bed 8.680134.G_003_00A. | 00 | 2015-10-18 11:11 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-18 11:11 | IFI | OB | 100%
114573 | I491TM02-0CCTB01-002-001 | CCM Cooling Bed Fender 8.680103.H_001_00 | 00 | 2015-10-18 11:11 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-18 11:11 | IFI | OB | 100%
114574 | I491TM02-0CCTB01-003-001 | Sheet 1 of 2 Cooling Bed Grease 8.680162.L_001_00 | 00 | 2015-10-18 11:11 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-18 11:11 | IFI | OB | 100%
114575 | I491TM02-0CCTB01-003-002 | Sheet 2of 2 Cooling Bed Grease 8.680162.L_002_00 | 00 | 2015-10-18 11:11 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-18 11:11 | IFI | OB | 100%
114576 | I491TM02-0CCTB01-004-001 | Cooling Bed Hydraulic 8.680161.K_001_00 | 00 | 2015-10-18 11:11 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-18 11:11 | IFI | OB | 100%
114577 | I491TM02-0CCTB01-005-001 | Cooling Bed Hydraulic 8.491642.B_001_00A | 00 | 2015-10-18 11:11 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-18 11:11 | IFI | OB | 100%
114578 | I491TM02-0CCTB01-006-001 | Cooling Bed Limit Switch 8.146980.A_001_00T | 00 | 2015-10-18 11:11 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-18 11:11 | IFI | OB | 100%
114579 | I491TM02-0CCTB01-007-001 | Cooling Bed Limit Encoder 8.097517.Q_001_01A | 00 | 2015-10-18 11:11 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-18 11:11 | IFI | OB | 100%
114580 | I491TM02-0CCTB01-007-002 | Cooling Bed Limit Switch 8.146967.G_001_01U | 00 | 2015-10-18 11:11 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-18 11:11 | IFI | OB | 100%
114477 | I491TM02-0CCTD01-002-001 | CCM Tundish 8.566950.Q_001_00 | 00 | 2015-10-07 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-11 11:49 | IFI | OB | 100%
114478 | I491TM02-0CCTD03-001-003 | Sheet 1of3 Tundish Car 8.566938.G_001_00A | 01 | 2015-10-07 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-11 11:50 | IFI | OB | 100%
114479 | I491TM02-0CCTD03-001-004 | Sheet 2of3 Tundish Car 8.566938.G_002_00A | 00 | 2015-10-07 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-11 11:50 | IFI | OB | 100%
114480 | I491TM02-0CCTD03-001-005 | Sheet 3of3 Tundish Car 8.566938.G_003_00A | 00 | 2015-10-07 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-11 11:50 | IFI | OB | 100%
16620 | I491TM02-0CCTD03-002-001 | 6-Strand Billet Caster Foundation Tract 1+2 Tundish Car | 01 | 2013-12-18 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | TAM | 2014-02-18 13:15 | IFC | AFC | 100%
114481 | I491TM02-0CCTD03-003-001 | Sheet 1of3 Tundish Car1 Transport 6.343533.Z_001_00 | 00 | 2015-10-07 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-11 11:50 | IFI | OB | 100%
114482 | I491TM02-0CCTD03-003-002 | Sheet 2of3 Tundish Car1 Transport 6.343533.Z_002_00 | 00 | 2015-10-07 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-11 11:50 | IFI | OB | 100%
114483 | I491TM02-0CCTD03-003-003 | Sheet 3of3 Tundish Car1 Transport 6.343533.Z_003_00 | 00 | 2015-10-07 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-11 11:50 | IFI | OB | 100%
114484 | I491TM02-0CCTD03-004-001 | Sheet 1of3 Tundish Car2 Transport 6.343534.S_001_00 | 00 | 2015-10-07 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-11 11:50 | IFI | OB | 100%
114485 | I491TM02-0CCTD03-004-002 | Sheet 2of3 Tundish Car2 Transport 6.343534.S_002_00 | 00 | 2015-10-07 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-11 11:50 | IFI | OB | 100%
114486 | I491TM02-0CCTD03-004-003 | Sheet 3of3 Tundish Car2 Transport 6.343534.S_003_00 | 00 | 2015-10-07 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-11 11:50 | IFI | OB | 100%
114487 | I491TM02-0CCTD03-005-001 | Tundish Car Location 6.343534.S_003_00 6.276227.B_001_00 | 00 | 2015-10-07 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-11 11:50 | IFI | OB | 100%
114488 | I491TM02-0CCTD04-001-001 | Tundish Snorkle Support 8.566952.E_001_00 | 00 | 2015-10-07 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-11 11:50 | IFI | OB | 100%
114489 | I491TM02-0CCTD05-001-001 | DTE Cylinder Connection 8.606665.W_001_01 | 00 | 2015-10-07 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-11 11:51 | IFI | OB | 100%
114490 | I491TM02-0CCTD06-001-001 | Sheet 1of2 FNC System 8.680009.W_001_00 | 00 | 2015-10-07 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-11 11:51 | IFI | OB | 100%
114491 | I491TM02-0CCTD06-001-002 | Sheet 2of2 FNC System 8.680009.W_002_00 | 00 | 2015-10-07 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-11 11:51 | IFI | OB | 100%
114492 | I491TM02-0CCTD06-002-001 | FNC Cylinder Stroke Gauging 6.038921.P_001_00 | 00 | 2015-10-07 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-11 11:51 | IFI | OB | 100%
114493 | I491TM02-0CCTD07-001-001 | Nozzle Change Device 8.052694.B_001_06 | 00 | 2015-10-07 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-11 11:51 | IFI | OB | 100%
114494 | I491TM02-0CCTD07-002-001 | Nozzle Assembly Tool 8.052692.G_001_02 | 00 | 2015-10-07 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-11 11:51 | IFI | OB | 100%
114495 | I491TM02-0CCTD07-003-001 | Measurment Device 8.052693.A_001_01 | 00 | 2015-10-07 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-11 11:52 | IFI | OB | 100%
114496 | I491TM02-0CCTD08-001-001 | Strand Cutting Device 8.260916.K_001_02A | 00 | 2015-10-07 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-11 11:52 | IFI | OB | 100%
132739 | I491TM02-0CCTH04-001-001 | CCM CS Machine ta375179_0001_1 | 00 | 2018-01-17 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | TAM | 2018-02-01 10:41 | IFI | OB | 100%
133432 | I491TM02-0CCTK91-001-001 | SCALE PIT EQUIPMENT ARRANGEMENT | 00 | 2018-07-03 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2018-07-10 09:07 | IFA | OB | 100%
114581 | I491TM02-0CCTM01-001-001 | Cooling Bed Mechanical Connection 8.106881.T_001_01 | 00 | 2015-10-18 11:12 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-18 11:12 | IFI | OB | 100%
112626 | I491TM02-0CHEU01-001-001 | Teeming Crane 320-80-5tx29m-a K2-1567.0001A | 00 | 2014-07-20 | Indeterminate | Drawing | Basic | Crane and Hiosts | Mechanical | TAM | 2014-07-28 10:30 | IFA | AC |  | 95%
112627 | I491TM02-0CHEU01-002-001 | Laminated Hook Traverse and Hook Block K2-1567.0003A | 00 | 2014-07-20 | Indeterminate | Drawing | Basic | Crane and Hiosts | Mechanical | TAM | 2014-07-28 10:30 | IFA | AC |  | 95%
112628 | I491TM02-0CHEU02-001-001 | Scrap Charging Crane 90-30-5tx29m K2-1567.0002A | 00 | 2014-07-20 | Indeterminate | Drawing | Basic | Crane and Hiosts | Mechanical | TAM | 2014-07-28 10:30 | IFA | AC |  | 95%
112629 | I491TM02-0CHEU02-002-001 | Scrap Bucket and Ladle Scrap Charging Crane K2-1567.0004A | 00 | 2014-07-20 | Indeterminate | Drawing | Basic | Crane and Hiosts | Mechanical | TAM | 2014-07-28 10:31 | IFA | AC |  | 95%
112875 | I491TM02-0CHEU03-001-001 | Empty ladle handling crane 90/30/5t x 27m | 00 | 2014-09-10 | Indeterminate | Drawing | Basic | Crane and Hiosts | Mechanical | TAM | 2014-09-13 14:45 | IFA | AC |  | 95%
112876 | I491TM02-0CHEU04-001-001 | Tundish handling crane 90/30/5t x 27m | 00 | 2014-09-10 | Indeterminate | Drawing | Basic | Crane and Hiosts | Mechanical | TAM | 2014-09-13 14:45 | IFA | AC |  | 95%
112877 | I491TM02-0CHEU05-001-001 | Billet handling crane 28/5t x 32m | 00 | 2014-09-10 | Indeterminate | Drawing | Basic | Crane and Hiosts | Mechanical | TAM | 2014-09-13 14:45 | IFA | AC |  | 95%
112878 | I491TM02-0CHEU07-001-001 | scrap loading crane 20t x 30m | 00 | 2014-09-10 | Indeterminate | Drawing | Basic | Crane and Hiosts | Mechanical | TAM | 2014-09-13 14:45 | IFA | AC |  | 95%
133009 | I491TM02-0CHEU10-001-001 | GENERAL ARRANGEMENT FOR JIB CRANE 6.3 TON EAF Electrode Joining 1-7 | 00 | 2018-03-17 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | TAM | 2018-03-18 15:44 | IFI | OB | 100%
133010 | I491TM02-0CHEU10-001-002 | GENERAL ARRANGEMENT FOR JIB CRANE 6.3 TON EAF Electrode Joining 2-7 | 00 | 2018-03-17 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | TAM | 2018-03-18 15:44 | IFI | OB | 100%
133011 | I491TM02-0CHEU10-001-003 | POWER SUPPLY INSTALLATION DRAWING JIB CRANE 6.3 TON EAF Electrode Joining 3-7 | 00 | 2018-03-17 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | TAM | 2018-03-18 15:44 | IFI | OB | 100%
133012 | I491TM02-0CHEU10-001-004 | MANUFACTURING DETAILS FOR STEEL STRUCTURE JIB CRANE 6.3TON EAF Electrode Joining 4-7 | 00 | 2018-03-17 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | TAM | 2018-03-18 15:44 | IFI | OB | 100%
133013 | I491TM02-0CHEU10-001-005 | MANUFACTURING DETAILS FOR STEEL STRUCTURE JIB CRANE 6.3TON EAF Electrode Joining 5-7 | 00 | 2018-03-17 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | TAM | 2018-03-18 15:44 | IFI | OB | 100%
133014 | I491TM02-0CHEU10-001-006 | MANUFACTURING DETAILS FOR STEEL STRUCTURE JIB CRANE 6.3TON EAF Electrode Joining 6-7 | 00 | 2018-03-17 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | TAM | 2018-03-18 15:44 | IFI | OB | 100%
133015 | I491TM02-0CHEU10-001-007 | MANUFACTURING DETAILS FOR STEEL STRUCTURE JIB CRANE 6.3TON EAF Electrode Joining 7-7 | 00 | 2018-03-17 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | TAM | 2018-03-18 15:44 | IFI | OB | 100%
133016 | I491TM02-0CHEU11-001-001 | GENERAL ARRANGEMENT FOR JIB CRANE 5 TON LADLE RELINING 1-7 | 00 | 2018-03-17 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | TAM | 2018-03-18 16:08 | IFI | OB | 100%
133017 | I491TM02-0CHEU11-001-002 | GENERAL ARRANGEMENT FOR JIB CRANE 5 TON LADLE RELINING 2-7 | 00 | 2018-03-17 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | TAM | 2018-03-18 16:08 | IFI | OB | 100%
133018 | I491TM02-0CHEU11-001-003 | POWER SUPPLY INSTALLATION DRAWING JIB CRANE 5 TON LADLE RELINING 3-7 | 00 | 2018-03-17 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | TAM | 2018-03-18 16:08 | IFI | OB | 100%
133019 | I491TM02-0CHEU11-001-004 | MANUFACTURING DETAILS FOR STEEL STRUCTURE JIB CRANE 5 TON LADLE RELINING 4-7 | 00 | 2018-03-17 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | TAM | 2018-03-18 16:08 | IFI | OB | 100%
133020 | I491TM02-0CHEU11-001-005 | MANUFACTURING DETAILS FOR STEEL STRUCTURE JIB CRANE 5 TON LADLE RELINING 5-7 | 00 | 2018-03-17 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | TAM | 2018-03-18 16:08 | IFI | OB | 100%
133021 | I491TM02-0CHEU11-001-006 | MANUFACTURING DETAILS FOR STEEL STRUCTURE JIB CRANE 5 TON LADLE RELINING 6-7 | 00 | 2018-03-17 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | TAM | 2018-03-18 16:08 | IFI | OB | 100%
133022 | I491TM02-0CHEU11-001-007 | MANUFACTURING DETAILS FOR STEEL STRUCTURE JIB CRANE 5TON LADLE RELINING 7-7 | 00 | 2018-03-17 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | TAM | 2018-03-18 16:08 | IFI | OB | 100%
112630 | I491TM02-0CHRH91-001-001 | Crane Rail A120 K2-1567.0006A | 00 | 2014-07-20 | Indeterminate | Drawing | Basic | Crane and Hiosts | Mechanical | TAM | 2014-07-28 10:31 | IFA | AC |  | 95%
15746 | I491TM02-0CPAA91-001-004 | General Arrangement Drawing For Compressed Air Plant (1-4) | 03 | 2013-10-01 | Indeterminate | Drawing | Basic | Compressed Air Production Plant | Mechanical | HAVAYAR |  | IFC | AFC | 100%
15747 | I491TM02-0CPAA91-001-005 | General Arrangement Drawing For Compressed Air Plant (2-4) | 03 | 2013-10-01 | Indeterminate | Drawing | Basic | Compressed Air Production Plant | Mechanical | HAVAYAR |  | IFC | AFC | 100%
15748 | I491TM02-0CPAA91-001-006 | General Arrangement Drawing For Compressed Air Plant (3-4) | 03 | 2013-10-01 | Indeterminate | Drawing | Basic | Compressed Air Production Plant | Mechanical | HAVAYAR |  | IFC | AFC | 100%
15749 | I491TM02-0CPAA91-001-007 | General Arrangement Drawing For Compressed Air Plant (4-4) | 03 | 2013-10-01 | Indeterminate | Drawing | Basic | Compressed Air Production Plant | Mechanical | HAVAYAR |  | IFC | AFC | 100%
15753 | I491TM02-0DTAA91-001-004 | Fume Treatment Plant Layout Dedusting System For Fournace 140 Ton Eaf+Lf & Mh General Lay-Out | 07 | 2013-08-18 | Indeterminate | Drawing | Basic | Fume Treatment Equipment | Mechanical | TAM |  | IFA | A | 100%
15754 | I491TM02-0DTAA91-002-001 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH LAY-OUT BAGS FILTER & SILO | 01 | 2013-09-11 | Indeterminate | Drawing | Basic | Fume Treatment Equipment | Mechanical | HASCON |  | IFI | OB | 100%
15755 | I491TM02-0DTAA91-003-001 | Dedusting System Fournace 140 Ton Eaf+Lf & Mh View &Section Stack Zone | 02 | 2013-08-18 | Indeterminate | Drawing | Basic | Fume Treatment Equipment | Mechanical | HASCON |  | IFA | A | 100%
15756 | I491TM02-0DTAA91-004-001 | Dedusting System Fournace 140 Ton Eaf+Lf & Mh Lay-Out Ducts Of Scrap Yard | 03 | 2013-08-18 | Indeterminate | Drawing | Basic | Fume Treatment Equipment | Mechanical | HASCON |  | IFA | A | 100%
15757 | I491TM02-0DTAA91-005-001 | Dedusting System Fournace 140 Ton Eaf+Lf & Mh Airpin Cooler + Mixing Chamber | 02 | 2013-08-18 | Indeterminate | Drawing | Basic | Fume Treatment Equipment | Mechanical | HASCON |  | IFA | A | 100%
15758 | I491TM02-0DTAA91-006-001 | Dedusting System Fournace 140 Ton Eaf+Lf & Mh Wievs Cooling Duct & Settling Chamber | 03 | 2013-08-18 | Indeterminate | Drawing | Basic | Fume Treatment Equipment | Mechanical | HASCON |  | IFA | A | 100%
112321 | I491TM02-0DTAA91-007-001 | DEDUSTING SYSTEM FOURNACE 140Ton EAF+LF & MH Layout Horizontal Cyclone | 00 | 2014-06-01 | Indeterminate | Drawing | Basic | Fume Treatment Equipment | Mechanical | HASCON | 2014-06-07 09:50 | IFI | OB | 100%
15759 | I491TM02-0DTAA91-008-001 | Dedusting System Fournace 140 Ton Eaf+Lf & Mh Lay-Out Expansion Joints | 00 | 2013-08-18 | Indeterminate | Drawing | Basic | Fume Treatment Equipment | Mechanical | HASCON |  | IFA | A | 100%
15760 | I491TM02-0DTAA91-009-001 | Dedusting System Fournace 140 Ton Eaf+Lf & Mh Lay-Out Ducts Support Duct Zone Slag Damping Area | 00 | 2013-08-18 | Indeterminate | Drawing | Basic | Fume Treatment Equipment | Mechanical | HASCON |  | IFA | A | 100%
15761 | I491TM02-0DTCC01-001-001 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH SETTLING CHAMBER : ROO FASSEMBLY | 00 | 2013-09-11 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON |  | IFI | OB | 100%
113389 | I491TM02-0DTCP01-001-001 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH MAIN FANS - DIMENSIONAL | 01 | 2015-02-21 14:56 | Indeterminate | Drawing | Basic | Fume Treatment Equipment | Mechanical | TAM | 2015-02-21 14:56 | IFI | OB | 100%
113390 | I491TM02-0DTCP01-003-001 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH LF FAN - ASSEMBLY | 01 | 2015-02-21 15:08 | Indeterminate | Drawing | Basic | Fume Treatment Equipment | Mechanical | TAM | 2015-02-21 15:08 | IFI | OB | 100%
113391 | I491TM02-0DTCP01-005-001 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH PRIMARY BOOSTER FAN - ASSEMBLY | 01 | 2015-02-21 15:08 | Indeterminate | Drawing | Basic | Fume Treatment Equipment | Mechanical | TAM | 2015-02-21 15:08 | IFI | OB | 100%
15762 | I491TM02-0DTCS01-001-001 | Dedusting System Fournace 140 Ton Eaf+Lf & Mh Natural Cooler Assembly | 01 | 2013-05-08 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | TAM |  | IFA | A | 100%
15763 | I491TM02-0DTCS01-001-002 | Dedusting System Fournace 140 Ton Eaf+Lf & Mh Natural Cooler Assembly | 03 | 2013-05-08 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | TAM |  | IFA | A | 100%
15764 | I491TM02-0DTCS01-002-001 | Dedusting System Fournace 140 Ton Eaf+Lf & Mh Natural Cooler Rank Detail | 03 | 2013-05-08 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON |  | IFA | A | 100%
15765 | I491TM02-0DTCS01-003-001 | Dedusting System Fournace 140 Ton Eaf+Lf & Mh Natural Cooler Inlet Collector | 01 | 2013-05-08 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON |  | IFA | A | 100%
15766 | I491TM02-0DTCS01-004-001 | Dedusting System Fournace 140 Ton Eaf+Lf & Mh Cooler Outlet Collector | 01 | 2013-05-08 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON |  | IFA | A | 100%
15767 | I491TM02-0DTCS01-005-001 | Dedusting System Fournace 140 Ton Eaf+Lf & Mh Restraints Details | 01 | 2013-05-08 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON |  | IFA | A | 100%
15768 | I491TM02-0DTCS01-006-001 | Dedusting System Fournace 140 Ton Eaf+Lf & Mh Inspection Door ∅600 Detail | 01 | 2013-05-08 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON |  | IFA | A | 100%
15769 | I491TM02-0DTCS01-007-001 | Dedusting System Fournace 140 Ton Eaf+Lf & Mh Restraints Plan | 00 | 2013-05-08 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON |  | IFA | A | 100%
15770 | I491TM02-0DTCS01-008-001 | Dedusting System Fournace 140 Ton Eaf+Lf & Mh Expansion Joint "G1"-"G2" On Inlet Collector | 01 | 2013-05-08 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON |  | IFA | A | 100%
15771 | I491TM02-0DTCS01-009-001 | Dedusting System Fournace 140 Ton Eaf+Lf & Mh Expansion Joint "G3"-"G4" On Outlet Collector | 01 | 2013-05-08 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON |  | IFA | A | 100%
15772 | I491TM02-0DTCS01-010-001 | Dedusting System Fournace 140 Ton Eaf+Lf & Mh Inspection Door ∅500 Detail | 01 | 2013-05-08 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON |  | IFA | A | 100%
15773 | I491TM02-0DTCS01-011-001 | Dedusting System Fournace 140 Ton Eaf+Lf & Mh Airpin Cooler - Exp. Joint | 00 | 2013-05-08 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON |  | IFA | A | 100%
15774 | I491TM02-0DTCS01-012-001 | Dedusting System Fournace 140 Ton Eaf+Lf & Mh Airpin Cooler - Exp. Joint Chain Conveyor Discharge | 00 | 2013-05-08 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON |  | IFA | A | 100%
112322 | I491TM02-0DTCS02-001-001 | DEDUSTING SYSTEM FOURNACE 140Ton EAF+LF & MH NATURAL COOLER STRUCTURE ASSEMBLY | 01 | 2014-06-01 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2014-06-07 09:50 | IFI | OB | 100%
112323 | I491TM02-0DTCS02-002-001 | DEDUSTING SYSTEM FOURNACE 140Ton EAF+LF & MH NATURAL COOLER STRUCTURE ASSEMBLY | 00 | 2014-06-01 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | HASCON | 2014-06-07 09:50 | IFI | OB | 100%
112324 | I491TM02-0DTCV01-001-001 | DEDUSTING SYSTEM FOURNACE 140Ton EAF+LF & MH Lay-out Dust Transport | 00 | 2014-06-01 | Indeterminate | Drawing | Basic | Fume Treatment Equipment | Mechanical | HASCON | 2014-06-07 09:50 | IFI | OB | 100%
15775 | I491TM02-0DTCY01-001-001 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH HORIZZONTAL CYCLON - ASSEMBLY | 03 | 2013-09-11 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON |  | IFI | OB | 100%
15779 | I491TM02-0DTDE02-001-004 | Dedusting System Fournace 140 Ton Eaf+Lf & Mh Mixing Chamber - General Assembly | 03 | 2013-06-01 | Indeterminate | Drawing | Basic | Fume Treatment Equipment | Mechanical | HASCON |  | IFC | A | 100%
15783 | I491TM02-0DTDE02-002-004 | Dedusting System Fournace 140 Ton Eaf+Lf & Mh Mixing Chamber Body Assembly | 04 | 2013-06-01 | Indeterminate | Drawing | Basic | Fume Treatment Equipment | Mechanical | HASCON |  | IFC | A | 100%
15787 | I491TM02-0DTDE02-003-004 | Dedusting System Fournace 140 Ton Eaf+Lf & Mh Mixing Chamber - Hopper | 02 | 2013-06-01 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON |  | IFC | A | 100%
15791 | I491TM02-0DTDE02-004-004 | Dedusting System Fournace 140 Ton Eaf+Lf & Mh Mixing Chamber - Hopper | 02 | 2013-06-01 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON |  | IFC | A | 100%
15795 | I491TM02-0DTDE02-005-004 | Dedusting System Fournace 140 Ton Eaf+Lf & Mh Mixing Chamber - Frontal Panel | 01 | 2013-06-01 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON |  | IFC | A | 100%
15799 | I491TM02-0DTDE02-006-004 | Dedusting System Fournace 140 Ton Eaf+Lf & Mh Mixing Chamber - Rear Panel | 02 | 2013-06-01 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON |  | IFC | A | 100%
15803 | I491TM02-0DTDE02-007-004 | Dedusting System Fournace 140 Ton Eaf+Lf & Mh Mixing Chamber - Lateral Inlet Panel | 01 | 2013-06-01 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON |  | IFC | A | 100%
15807 | I491TM02-0DTDE02-008-004 | Dedusting System Fournace 140 Ton Eaf+Lf & Mh Mixing Chamber - Lateral Exit Panel | 01 | 2013-06-01 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON |  | IFC | A | 100%
15811 | I491TM02-0DTDE02-009-004 | Dedusting System Fournace 140 Ton Eaf+Lf & Mh Mixing Chamber - Roof Panel | 01 | 2013-06-01 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON |  | IFC | A | 100%
15815 | I491TM02-0DTDE02-010-004 | Dedusting System Fournace 140 Ton Eaf+Lf & Mh Mixing Chamber - Internal Panel And Struts | 01 | 2013-06-01 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON |  | IFC | A | 100%
15819 | I491TM02-0DTDE02-011-004 | Dedusting System Fournace 140 Ton Eaf+Lf & Mh Mixing Chamber - Spark Arrester | 01 | 2013-06-01 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON |  | IFC | A | 100%
15823 | I491TM02-0DTDE02-012-004 | Dedusting System Fournace 140 Ton Eaf+Lf & Mh Mixing Chamber - Pressure Relief Door | 01 | 2013-06-01 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON |  | IFC | A | 100%
15827 | I491TM02-0DTDE02-013-004 | Dedusting System Fournace 140 Ton Eaf+Lf & Mh Mixing Chamber - Inspection Door ∅600 | 01 | 2013-06-01 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON |  | IFC | A | 100%
15831 | I491TM02-0DTDE02-014-004 | Dedusting System Fournace 140 Ton Eaf+Lf & Mh Mixing Chamber -Assembly Detail | 00 | 2013-06-01 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON |  | IFC | A | 100%
15835 | I491TM02-0DTDE02-015-004 | Dedusting System Fournace 140 Ton Eaf+Lf & Mh Bag Filter - Mixing Chamber Exp. Joint | 00 | 2013-06-01 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON |  | IFC | A | 100%
112325 | I491TM02-0DTDE03-001-001 | DEDUSTING SYSTEM FOURNACE 140Ton EAF+LF & MH MIXING CHAMBER - STRUCTURE ASSEMBLY | 00 | 2014-06-01 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | HASCON | 2014-06-07 09:51 | IFI | OB | 100%
15839 | I491TM02-0DTFL01-001-002 | Dedusting System Fournace 140 Ton Eaf+Lf & Mh Bag Filter - Assembly | 03 | 2013-06-01 | Indeterminate | Drawing | Basic | Fume Treatment Equipment | Mechanical | HASCON |  | IFC | AFC | 100%
15841 | I491TM02-0DTFL01-002-002 | Dedusting System Fournace 140 Ton Eaf+Lf & Mh Bag Filter - Assembly Section | 02 | 2013-06-01 | Indeterminate | Drawing | Basic | Fume Treatment Equipment | Mechanical | HASCON |  | IFC | AFC | 100%
15843 | I491TM02-0DTFL01-003-002 | Dedusting System Fournace 140 Ton Eaf+Lf & Mh Bag Filter - Assembly Section | 02 | 2013-06-01 | Indeterminate | Drawing | Basic | Fume Treatment Equipment | Mechanical | HASCON |  | IFC | AFC | 100%
15845 | I491TM02-0DTFL01-004-002 | Dedusting System Fournace 140 Ton Eaf+Lf & Mh Bag Filter - Assembly Section And Detail | 01 | 2013-06-01 | Indeterminate | Drawing | Basic | Fume Treatment Equipment | Mechanical | HASCON |  | IFC | AFC | 100%
15847 | I491TM02-0DTFL01-005-002 | Dedusting System Fournace 140 Ton Eaf+Lf & Mh Bag Filter - Assembly | 04 | 2013-06-01 | Indeterminate | Drawing | Basic | Fume Treatment Equipment | Mechanical | HASCON |  | IFC | AFC | 100%
115239 | I491TM02-0DTFL04-001-001 | Penthouse Bag Filter - Structure Assembly | 00 | 2016-05-07 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2016-05-14 10:16 | IFI | OB | 100%
115240 | I491TM02-0DTFL04-002-001 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH PENTHOUSE STRUCTURE DETAIL | 00 | 2016-05-07 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2016-05-14 10:16 | IFI | OB | 100%
115241 | I491TM02-0DTFL04-003-001 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH PENTHOUSE DOOR | 00 | 2016-05-07 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2016-05-14 10:16 | IFI | OB | 100%
115242 | I491TM02-0DTFL04-004-001 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH PENTHOUSE DOOR | 00 | 2016-05-07 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2016-05-14 10:16 | IFI | OB | 100%
112326 | I491TM02-0DTFL06-001-001 | DEDUSTING SYSTEM FOURNACE 140Ton EAF+LF & MH STAIR - BAGS FILTER & SILO STRUCTURE ASSEMBLY | 00 | 2014-06-01 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | HASCON | 2014-06-07 09:51 | IFI | OB | 100%
15848 | I491TM02-0DTFL07-001-001 | DEDUSTING SYSTEM FOURNACE 140Ton EAF+LF & MH DRI FILTER ASSEMBLY | 02 | 2013-09-11 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON |  | IFI | OB | 100%
112663 | I491TM02-0DTFL08-001-001 | DRI Filter- Structure Assembly | 00 | 2014-08-09 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | HASCON | 2014-08-18 09:29 | IFA | A | 100%
15850 | I491TM02-0DTHD01-001-002 | Dedusting System Fournace 140Ton Eaflf&Mh Canopy Hood General Dimension | 02 | 2012-10-13 | Indeterminate | Drawing | Basic | Fume Treatment Equipment | Mechanical | HASCON |  | IFC | AFC | 100%
15851 | I491TM02-0DTHD01-001-003 | Dedusting System Fournace 140Ton Eaflf&Mh Canopy Hood General Dimension | 04 | 2013-04-06 | Indeterminate | Miscellaneous(MISC) | Basic | Fume Treatment Equipment | Mechanical | HASCON |  | IFC | AFC | 100%
15852 | I491TM02-0DTPP02-001-001 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH GENERAL ASSEMBLY WCD | 01 | 2013-09-11 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON |  | IFI | OB | 100%
15853 | I491TM02-0DTST02-001-001 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH STACK - STAIR ASSEMBLY | 01 | 2013-09-11 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON |  | IFI | OB | 100%
112327 | I491TM02-0DTST02-002-001 | DEDUSTING SYSTEM FOURNACE 140Ton EAF+LF & MH STACK - STAIR DETAILS | 00 | 2014-06-01 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | HASCON | 2014-06-07 09:51 | IFI | OB | 100%
112328 | I491TM02-0DTTK01-001-001 | DEDUSTING SYSTEM FOURNACE 140Ton EAF+LF & MH Silo And STAIR Assembly | 00 | 2014-06-01 | Indeterminate | Drawing | Basic | Fume Treatment Equipment | Mechanical | HASCON | 2014-06-07 09:51 | IFI | OB | 100%
112329 | I491TM02-0DTTK01-005-001 | DEDUSTING SYSTEM FOURNACE 140Ton EAF+LF & MH SILO CATWALK OF SERVICE | 00 | 2014-06-01 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2014-06-07 09:52 | IFI | OB | 100%
15854 | I491TM02-0DTTK02-001-001 | Dedusting System Fournace 140 Ton Eaf+Lf & Mh Silo Structure - Assembly | 00 | 2013-05-06 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON |  | IFA | AFC | 100%
114950 | I491TM02-0EAAA91-001-001 | ELECTRIC ARC FURNACE COMPONENTS 1-6 | 00 | 2016-02-24 | Indeterminate | Drawing | Basic | Electric Arc Furnace | Mechanical | FUCHS | 2016-02-28 10:36 | IFA | A | 100%
114951 | I491TM02-0EAAA91-002-001 | ELECTRIC ARC FURNACE COMPONENTS 2-6 | 00 | 2016-02-24 | Indeterminate | Drawing | Basic | Electric Arc Furnace | Mechanical | FUCHS | 2016-02-28 10:36 | IFA | A | 100%
114952 | I491TM02-0EAAA91-003-001 | ELECTRIC ARC FURNACE COMPONENTS 3-6 | 00 | 2016-02-24 | Indeterminate | Drawing | Basic | Electric Arc Furnace | Mechanical | FUCHS | 2016-02-28 10:36 | IFA | A | 100%
114953 | I491TM02-0EAAA91-004-001 | ELECTRIC ARC FURNACE COMPONENTS 4-6 | 00 | 2016-02-24 | Indeterminate | Drawing | Basic | Electric Arc Furnace | Mechanical | FUCHS | 2016-02-28 10:36 | IFA | A | 100%
114954 | I491TM02-0EAAA91-005-001 | ELECTRIC ARC FURNACE COMPONENTS 5-6 | 00 | 2016-02-24 | Indeterminate | Drawing | Basic | Electric Arc Furnace | Mechanical | FUCHS | 2016-02-28 10:36 | IFA | A | 100%
114955 | I491TM02-0EAAA91-006-001 | ELECTRIC ARC FURNACE COMPONENTS 6-6 | 00 | 2016-02-24 | Indeterminate | Drawing | Basic | Electric Arc Furnace | Mechanical | FUCHS | 2016-02-28 10:36 | IFA | A | 100%
130098 | I491TM02-0EABT01-001-001 | D-31.00.000.123C LADLE OPERATION CYCLE EAF LADLE TRANSFER CAR AT EAF | 00 | 2017-01-08 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS | 2017-01-09 09:08 | IFI | OB | 100%
15855 | I491TM02-0EAFM01-001-001 | Installation Upper Parttap Hole Filling Device Shell | 00 | 2012-03-10 | Indeterminate | Drawing | Basic | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
130099 | I491TM02-0EALW01-001-001 | D-30.00.000.390A HUBSAEULEN LIFTING COLUMN LAYOUT EAF | 00 | 2017-01-08 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS | 2017-01-09 09:08 | IFI | OB | 100%
130100 | I491TM02-0EALW01-002-001 | D-30.00.000.295B LIFTING COULUM PHASE1+2+3 GANTRY | 00 | 2017-01-08 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS | 2017-01-09 09:09 | IFI | OB | 100%
130101 | I491TM02-0EALW01-003-001 | D-30.00.000.397 ELECTROD LIFTING DEVICE EAF ROLLER BRACKET | 00 | 2017-01-08 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS | 2017-01-09 09:09 | IFI | OB | 100%
131096 | I491TM02-0MDCH01-001-002 | Dolomite & Lime Technology & Loading For Two Way Chute Md-Ch-01-01 | 02 | 2017-08-23 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | TAM | 2017-08-26 12:21 | IFC | AFC | 100%
131098 | I491TM02-0MDCH02-001-002 | Ferro Alloy Charging Technology & Loading For Two Way Chute Md-Ch-02-01 | 02 | 2017-08-23 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | TAM | 2017-08-26 13:01 | IFC | AFC | 100%
15860 | I491TM02-0MDCH03-001-001 | Eaf Ferro Alloy Storage Bins Technology & Loading For Emergency Discharge Chute Md-Ch-03-01 | 00 | 2013-10-07 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | TAM |  | IFA | A | 100%
15861 | I491TM02-0MDCH04-001-001 | Lf Ferro Alloy Storage Bins Technology & Loading For Emergency Discharge Chute Md-Ch-04-01 | 00 | 2013-10-07 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | TAM |  | IFA | A | 100%
131097 | I491TM02-0MDCH05-001-002 | Bin Charging Dri Technology & Loading For Two Way Chute Md-Ch-05-01 | 02 | 2017-08-23 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | TAM | 2017-08-26 12:22 | IFC | AFC | 100%
15864 | I491TM02-0MDCH07-001-001 | Bin Charging (Dri) Technology & Loading For Emergency Discharge Chute Md-Ch-07-01 | 00 | 2013-10-07 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | TAM |  | IFA | A | 100%
15865 | I491TM02-0MDCH08-001-001 | Eaf Dri Storage Bins Technology & Loading For Emergency Discharge Chute Md-Ch-08-01 | 00 | 2013-10-07 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | TAM |  | IFA | A | 100%
15866 | I491TM02-0MDCH12-001-001 | Bin Charging Dri Technology & Loading For Two Way Chute Md-Ch-12-01 | 00 | 2013-07-13 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | TAM |  | IFI | OB | 100%
15867 | I491TM02-0MDCH14-001-001 | Eaf Tapping Charging Technology & Loading For Emergency Discharge Chute Md-Ch-14-01 | 00 | 2013-10-07 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | DATIS |  | IFA | A | 100%
15868 | I491TM02-0MDCH15-001-001 | Ferro Alloy Charging Technology & Loading For Two Way Chute Md-Ch-15-01 | 00 | 2013-07-13 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | TAM |  | IFI | OB | 100%
15869 | I491TM02-0MDCH16-001-001 | Eaf Tapping Charging Technology & Loading For Two Way Chute Md-Ch-16-01 | 00 | 2013-07-13 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | TAM |  | IFI | OB | 100%
15870 | I491TM02-0MDCH19-001-001 | Lf Charging Technology & Loading For Emergency Discharge Chute Md-Ch-19-01 | 00 | 2013-10-07 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | TAM |  | IFA | A | 100%
112413 | I491TM02-0MDCV01-001-001 | Dolomite & Lime Technology & Loading For Pocket B.C. Md-Cv-01-01 | 01 | 2014-06-25 11:19 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | DATIS | 2014-06-25 11:19 | IFC | AFC | 100%
112414 | I491TM02-0MDCV02-001-001 | Dolomite & Lime Technology & Loading For Reversible B.C. Md-Cv-02-01 | 01 | 2014-06-25 11:19 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | DATIS | 2014-06-25 11:19 | IFC | AFC | 100%
112415 | I491TM02-0MDCV03-001-001 | Ferro Alloy Charging Technology & Loading For B.C. Md-Cv-03-01 | 01 | 2014-06-25 11:19 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | DATIS | 2014-06-25 11:19 | IFC | AFC | 100%
15875 | I491TM02-0MDCV04-001-002 | Ferro Alloy Charging Technology & Loading For Reversible B.C. Md-Cv-04-01 | 01 | 2013-07-23 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | DATIS |  | IFC | AC |  | 95%
15876 | I491TM02-0MDCV04-002-001 | Ferro Alloy Charging Belt Conveyor Specification Reversible B.C. Md-Cv-04-01 | 00 | 2013-07-23 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | DATIS |  | IFA | AC |  | 95%
131081 | I491TM02-0MDCV05-001-001 | Ferro Alloy Charging Technology & Loading For Shuttle B.C. Md-Cv-05-01 | 01 | 2017-08-23 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | DATIS | 2017-08-26 12:16 | IFC | AFC | 100%
131082 | I491TM02-0MDCV05-002-001 | Ferro Alloy Charging Belt Conveyor Specification Shuttle B.C. Md-Cv-05-01 | 01 | 2017-08-23 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | DATIS | 2017-08-26 12:16 | IFC | AFC | 100%
131070 | I491TM02-0MDCV06-001-001 | Ferro Alloy Charging Technology & Loading For Shuttle B.C. Md-Cv-06-01 | 01 | 2017-08-23 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | IKS | 2017-08-26 12:11 | IFC | AFC | 100%
131071 | I491TM02-0MDCV06-002-001 | Ferro Alloy Charging Belt Conveyor Specification Shuttle B.C. Md-Cv-06-01 | 01 | 2017-08-23 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | DATIS | 2017-08-26 12:11 | IFC | AFC | 100%
15883 | I491TM02-0MDCV07-001-002 | Bin Charging (Dri) Technology & Loading For B.C. Md-Cv-07-01 | 01 | 2013-07-23 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | DATIS |  | IFC | AC |  | 95%
15884 | I491TM02-0MDCV07-002-001 | Bin Charging (Dri) Belt Conveyor Specification B.C. Md-Cv-07-01 | 00 | 2013-07-23 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | DATIS |  | IFA | AC |  | 95%
15886 | I491TM02-0MDCV08-001-002 | Bin Charging (Dri) Technology & Loading For B.C. Md-Cv-08-01 | 01 | 2013-07-23 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | DATIS |  | IFC | AC |  | 95%
15887 | I491TM02-0MDCV08-002-001 | Bin Charging (Dri) Belt Conveyor Specification B.C. Md-Cv-08-01 | 00 | 2013-07-23 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | DATIS |  | IFA | AC |  | 95%
15888 | I491TM02-0MDCV09-001-001 | Bin Charging (Dri) Technology & Loading For Shuttle B.C. Md-Cv-09-01 | 01 | 2013-07-23 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | DATIS |  | IFA | AC |  | 95%
15889 | I491TM02-0MDCV09-002-001 | Bin Charging (Dri) Belt Conveyor Specification Shuttle B.C. Md-Cv-09-01 | 00 | 2013-07-23 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | DATIS |  | IFA | AC |  | 95%
131083 | I491TM02-0MDCV12-001-001 | Eaf 5Th Hole Charging Technology & Loading For B.C. Md-Cv-12-01 | 01 | 2017-08-23 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | DATIS | 2017-08-26 12:16 | IFC | AFC | 100%
131084 | I491TM02-0MDCV12-002-001 | Eaf 5Th Hole Charging Belt Conveyor Specification B.C. Md-Cv-12-01 | 01 | 2017-08-23 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | DATIS | 2017-08-26 12:17 | IFC | AFC | 100%
131085 | I491TM02-0MDCV13-001-001 | Eaf 5Th Hole Charging Technology & Loading For Pocket B.C. Md-Cv-13-01 | 01 | 2017-08-23 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | DATIS | 2017-08-26 12:19 | IFC | AFC | 100%
131086 | I491TM02-0MDCV13-002-001 | Eaf 5Th Hole Charging Belt Conveyor Specification Pocket B.C. Md-Cv-13-01 | 01 | 2017-08-23 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | DATIS | 2017-08-26 12:19 | IFC | AFC | 100%
131087 | I491TM02-0MDCV14-001-001 | Eaf 5Th Hole Charging Technology & Loading For B.C. Md-Cv-14-01 | 01 | 2017-08-23 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | DATIS | 2017-08-26 12:19 | IFC | AFC | 100%
131088 | I491TM02-0MDCV14-002-001 | Eaf 5Th Hole Charging Belt Conveyor Specification B.C. Md-Cv-14-01 | 01 | 2017-08-23 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | DATIS | 2017-08-26 12:19 | IFC | AFC | 100%
131089 | I491TM02-0MDCV15-001-001 | Eaf Tapping Charging Technology & Loading For Pocket B.C. Md-Cv-15-01 | 01 | 2017-08-23 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | DATIS | 2017-08-26 12:19 | IFC | AFC | 100%
131090 | I491TM02-0MDCV15-002-001 | Eaf Tapping Charging Belt Conveyor Specification Pocket B.C. Md-Cv-15-01 | 01 | 2017-08-23 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | DATIS | 2017-08-26 12:20 | IFC | AFC | 100%
131091 | I491TM02-0MDCV16-001-001 | Eaf Tapping Charging Technology & Loading For B.C. Md-Cv-16-01 | 01 | 2017-08-23 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | DATIS | 2017-08-26 12:20 | IFC | AFC | 100%
131092 | I491TM02-0MDCV16-002-001 | Eaf Tapping Charging Belt Conveyor Specification B.C. Md-Cv-16-01 | 01 | 2017-08-23 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | DATIS | 2017-08-26 12:20 | IFC | AFC | 100%
131093 | I491TM02-0MDCV17-001-001 | Eaf Tapping Charging Technology & Loading For B.C. Md-Cv-17-01 | 01 | 2017-08-23 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | TAM | 2017-08-26 12:20 | IFC | AFC | 100%
131094 | I491TM02-0MDCV17-002-001 | Eaf Tapping Charging Belt Conveyor Specification B.C. Md-Cv-17-01 | 01 | 2017-08-23 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | TAM | 2017-08-26 12:20 | IFC | AFC | 100%
131072 | I491TM02-0MDCV18-001-001 | Lf Charging Technology & Loading For Reversible B.C. Md-Cv-18-01 | 01 | 2017-08-23 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | DATIS | 2017-08-26 12:12 | IFC | AFC | 100%
131073 | I491TM02-0MDCV18-002-001 | Lf Charging Belt Conveyor Specification Reversible B.C. Md-Cv-18-01 | 01 | 2017-08-23 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | DATIS | 2017-08-26 12:12 | IFC | AFC | 100%
131075 | I491TM02-0MDCV19-001-001 | LF CHARGING TECHNOLOGY & LOADING FOR B.C. MD-CV-19-01 | 01 | 2017-08-23 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | DATIS | 2017-08-26 12:13 | IFC | AFC | 100%
131074 | I491TM02-0MDCV19-002-001 | Eaf 5Th Hole Charging Belt Conveyor Specification Pocket B.C. Md-Cv-13-01 | 01 | 2017-08-23 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | DATIS | 2017-08-26 12:12 | IFC | AFC | 100%
112536 | I491TM02-0MDFE01-001-001 | DRI DOSIFICATION Dimension drawing | 01 | 2014-07-07 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | TAM | 2014-07-12 16:50 | IFI | OB | 100%
112537 | I491TM02-0MDFE02-001-001 | Charge coal and dolomite dosification Dimension drawing | 01 | 2014-07-07 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | TAM | 2014-07-12 16:50 | IFI | OB | 100%
112538 | I491TM02-0MDFE03-001-001 | Coarse lime dosification Dimension drawing | 01 | 2014-07-07 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | TAM | 2014-07-12 16:51 | IFI | OB | 100%
112539 | I491TM02-0MDFE04-001-001 | MHS Vibrating Feeder Assy 76271 | 01 | 2014-07-07 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | TAM | 2014-07-12 16:51 | IFI | OB | 100%
112540 | I491TM02-0MDFE05-001-001 | MHS Vibrating Feeder Assy 76272 | 01 | 2014-07-07 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | TAM | 2014-07-12 16:51 | IFI | OB | 100%
112541 | I491TM02-0MDFE06-001-001 | MHS Vibrating Feeder Assy 76273 | 01 | 2014-07-07 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | TAM | 2014-07-12 16:51 | IFI | OB | 100%
135058 | I491TM02-0MDSI01-001-001 | CARBON & LIME INJECTION SILOS TECHNOLOGY & LOADING FOR CARBON & LIME INJECTION SILOS MD-SI-01&02 | 03 | 2019-02-25 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | TAM | 2019-03-05 14:38 | IFC | AC |  | 95%
112416 | I491TM02-0MDTK01-001-001 | Dolomite And Lime Technology & Loading For Hopper Md-Tk-01-01 | 01 | 2014-06-25 11:20 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | DATIS | 2014-06-25 11:20 | IFC | AFC | 100%
112417 | I491TM02-0MDTK02-001-001 | Dolomite & Lime Technology & Loading for BINS MD-TK-02-01 Up to MD-TK-04-01 | 01 | 2014-06-25 11:20 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | DATIS | 2014-06-25 11:20 | IFC | AFC | 100%
112418 | I491TM02-0MDTK05-001-001 | Ferro Alloy Discharging Technology & Loading For Hopper Md-Tk-05-01 | 01 | 2014-06-25 11:20 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | DATIS | 2014-06-25 11:20 | IFC | AFC | 100%
131076 | I491TM02-0MDTK06-001-001 | Eaf Ferro Alloy Storage Bins Technology & Loading For Storage Bin Md-Tk-06-01 | 01 | 2017-08-23 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | DATIS | 2017-08-26 12:13 | IFC | AFC | 100%
131077 | I491TM02-0MDTK07-001-001 | Eaf Ferro Alloy Storage Bins Technology & Loading For Storage Bin Md-Tk-07-01 | 01 | 2017-08-23 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | DATIS | 2017-08-26 12:13 | IFC | AFC | 100%
131078 | I491TM02-0MDTK08-001-001 | Eaf Ferro Alloy Storage Bins Technology & Loading For Storage Bin Md-Tk-08-01 | 01 | 2017-08-23 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | DATIS | 2017-08-26 12:14 | IFC | AFC | 100%
131079 | I491TM02-0MDTK09-001-001 | EAF FERRO ALLOY STORAGE BINS TECHNOLOGY & LOADING FOR FERRO ALLOY BINS MD-TK-09~16-01 | 01 | 2017-08-23 | Indeterminate | Drawing | Basic | Material Handling | Mechanical | DATIS | 2017-08-26 12:15 | IFC | AFC | 100%
15913 | I491TM02-0MDTK17-001-001 | LF Ferro Alloy Storage BINS technology & Loading for Ferro Alloy BINS MD-TK-17-01 up to MD-TK-28-01 | 00 | 2013-07-02 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | TAM |  | IFA | AFC | 100%
131080 | I491TM02-0MDTK29-001-001 | EAF DRI Storage BINS Technology & Loading for DRI BINS MD-TK-29-01 up to MD-TK-32-01 | 01 | 2017-08-23 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | TAM | 2017-08-26 12:16 | IFC | AFC | 100%
15915 | I491TM02-0MDTK33-001-001 | Eaf Movable Weighing Hopper Technology & Loading For Movable Weighing Hopper Md-Tk-33-01 | 00 | 2013-07-13 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | TAM |  | IFI | OB | 100%
15916 | I491TM02-0MDTK34-001-001 | Eaf Surge Hoppers Technology & Loading For Surge Hoppers Md-Tk-34/35-01 | 00 | 2013-07-13 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | TAM |  | IFI | OB | 100%
15917 | I491TM02-0MDTK36-001-001 | Lf Fixed Weighing Hoppers Technology & Loading For Fixed Weighing Hoppers Md-Tk-36/37/38-01 | 00 | 2013-07-13 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | TAM |  | IFI | OB | 100%
15918 | I491TM02-0MDTK39-001-001 | Lf Surge Hopper Technology & Loading For Surge Hopper Md-Tk-39-01 | 00 | 2013-07-13 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | TAM |  | IFI | OB | 100%
15920 | I491TM02-0MDTT03-001-001 | Bin Charging (Dri) Technology Drawing For Transfer Tower Md-Tt-03-01 | 01 | 2013-07-23 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | TAM |  | IFC | AC |  | 95%
15921 | I491TM02-0MMCT01-001-001 | General Arrangment Drawings For Cooling System Ct01 | 00 | 2013-06-08 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Piping & Utility | TAM |  | IFI | OB | 100%
15922 | I491TM02-0MMCT01-002-001 | Internal Arrangment For Cooling System Ct01 | 00 | 2013-05-19 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Piping & Utility | TAM |  | IFI | OB | 100%
15923 | I491TM02-0MMCT01-003-001 | Packing Arrangment For Cooling System Ct01 | 00 | 2013-05-19 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Piping & Utility | TAM |  | IFI | OB | 100%
15924 | I491TM02-0MMCT01-004-001 | Drift Eliminator Arrangment For Cooling System Ct01 | 00 | 2013-05-19 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Piping & Utility | TAM |  | IFI | OB | 100%
15925 | I491TM02-0MMCT01-005-001 | Water Distribution System (G.R.P) For Cooling System Ct01 | 00 | 2013-05-19 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Piping & Utility | TAM |  | IFI | OB | 100%
15926 | I491TM02-0MMCT01-006-001 | Ventilation Group Detail For Cooling System (Ct01) | 00 | 2013-05-26 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Piping & Utility | TAM |  | IFI | OB | 100%
15927 | I491TM02-0MMCT01-007-001 | Drive Shaft Assembly For Cooling System (Ct01) | 00 | 2013-05-26 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Piping & Utility | TAM |  | IFI | OB | 100%
15928 | I491TM02-0MMCT02-001-001 | General Arrangment Drawings For Cooling System Ct02 | 00 | 2013-06-08 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Piping & Utility | TAM |  | IFI | OB | 100%
15929 | I491TM02-0MMCT02-002-001 | Internal Arrangment For Cooling System Ct02 | 00 | 2013-05-19 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Piping & Utility | TAM |  | IFI | OB | 100%
15930 | I491TM02-0MMCT02-003-001 | Packing Arrangment For Cooling System Ct02 | 00 | 2013-05-19 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Piping & Utility | TAM |  | IFI | OB | 100%
15931 | I491TM02-0MMCT02-004-001 | Drift Eliminator Arrangment For Cooling System Ct02 | 00 | 2013-05-19 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Piping & Utility | TAM |  | IFI | OB | 100%
15932 | I491TM02-0MMCT02-005-001 | Water Distribution System (G.R.P) For Cooling System Ct02 | 00 | 2013-05-19 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Piping & Utility | TAM |  | IFI | OB | 100%
15933 | I491TM02-0MMCT02-006-001 | Ventilation Group Detail For Cooling System (Ct02) | 00 | 2013-05-26 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Piping & Utility | TAM |  | IFI | OB | 100%
15934 | I491TM02-0MMCT02-007-001 | Drive Shaft Assembly For Cooling System (Ct02) | 00 | 2013-05-26 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Piping & Utility | TAM |  | IFI | OB | 100%
134639 | I491TM02-0PXFD91-001-001 | Melt Shop Debricking Machine General Drawing10800008_Unidachs | 00 | 2018-12-12 | Indeterminate | Drawing | Detail | Mobile Equipment | Mechanical | TAM | 2018-12-17 09:25 | IFI | OB | 100%
15936 | I491TM02-0PXLM01-001-002 | Ladle 1-2 | 01 | 2013-11-10 | Indeterminate | Drawing | Basic | Ladle Furnace Auxiliary | Mechanical | INTECO |  | IFC | AFC | 100%
15937 | I491TM02-0PXLM01-001-003 | Ladle 2-2 | 01 | 2013-11-10 | Indeterminate | Drawing | Basic | Ladle Furnace Auxiliary | Mechanical | INTECO |  | IFC | AFC | 100%
115787 | I491TM02-0PXSG01-001-001 | Ladle Slide Gate System MP_CAD-10831180_c | 01 | 2016-06-26 | Indeterminate | Drawing | Basic | Melt Shop Auxiliaries | Mechanical | TAM | 2016-06-29 10:28 | IFC | AFC | 100%
114635 | I491TM02-0RXLE03-001-001 | LF Roof Stand | 00 | 2015-10-26 11:20 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | TAM | 2015-10-26 11:20 | IFA | AFC | 100%
16072 | I491TM02-ODTPP02-001-001 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH GENERAL ASSEMBLY WCD sheet1 | 00 | 2013-09-11 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | TAM |  | IFI | OB | 100%
111933 | I491TM02-ODTPP02-001-002 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH GENERAL ASSEMBLY WCD sheet2 | 00 | 2013-09-11 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | TAM | 2014-05-08 11:09 | IFI | OB | 100%
15939 | I491TM03-0DTHD01-001-002 | Dedusting System Fournace 140Ton Eaflf&Mh Canopy Hood Load On Roof | 02 | 2012-10-13 | Indeterminate | Drawing | Basic | Fume Treatment Equipment | Mechanical | HASCON |  | IFC | AFC | 100%
15940 | I491TM03-0DTHD01-001-003 | Dedusting System Fournace 140Ton Eaflf&Mh Canopy Hood Load On Roof | 05 | 2013-04-06 | Indeterminate | Miscellaneous(MISC) | Basic | Fume Treatment Equipment | Mechanical | HASCON |  | IFC | AFC | 100%
15941 | I491TM03-0EAAA91-001-001 | Piping And Equipment Loading Plan On Steel Making Shop | 00 | 2012-08-01 | Indeterminate | Miscellaneous(MISC) | Basic | Melt Shop Main Building | Mechanical | INTECO |  | IFA | AC |  | 95%
15942 | I491TM03-0LFAA91-001-001 | Furnace Foundation Civil Works Lf | 00 | 2012-03-14 | Indeterminate | Drawing | Detail | Ladle Furnace | Civil and Steel Structure | INTECO |  | IFI | OB | 100%
15943 | I491TM03-0LFAA91-002-001 | Furnace Foundation Civil Works Lf | 00 | 2012-03-14 | Indeterminate | Drawing | Detail | Ladle Furnace | Civil and Steel Structure | INTECO |  | IFI | OB | 100%
15944 | I491TM03-0LFAA91-003-001 | Furnace Foundation Civil Works Lf | 00 | 2012-03-14 | Indeterminate | Drawing | Detail | Ladle Furnace | Civil and Steel Structure | INTECO |  | IFI | OB | 100%
129794 | I491TM04-0ASCP01-001-001 | ASP Turbo Compressor | 00 | 2016-11-12 09:25 | Indeterminate | Drawing | Detail | Air Separation Plant Main Building | Mechanical | TAM | 2016-11-12 09:25 | IFI | OB | 100%
130057 | I491TM04-0ASCP02-001-001 | ASP Booster Air Cpmpressor | 00 | 2016-12-31 | Indeterminate | Drawing | Detail | Air Separation Plant | Mechanical | TAM | 2017-01-02 10:08 | IFI | OB | 100%
130675 | I491TM04-0ASTK02-001-001 | Liquid Nitrogen Tank Foundation Drawing | 01 | 2017-06-07 10:38 | Indeterminate | Drawing | Detail | Air Separation Plant | Civil and Steel Structure | TAM | 2017-06-07 10:38 | IFC | AFC | 100%
114616 | I491TM04-0CCHY91-030-001 | Mould Oscilation Hydraulic 6.374973.A_001_00 | 00 | 2015-10-26 10:47 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-26 10:47 | IFI | OB | 100%
133309 | I491TM04-0CHEU12-001-001 | EAF Hydraulic Room Lift and Carry System A Installation Layout | 00 | 2018-06-16 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | TAM | 2018-06-26 10:12 | IFA | AC |  | 95%
15945 | I491TM04-0EAAA01-001-001 | Electric Arc Furnace Tilting Frame | 00 | 2012-03-10 | Indeterminate | Drawing | Basic | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
130102 | I491TM04-0EAAA02-001-001 | D-34.00.000.060D DRIVE UNIT TILTING DEVICE 1-2 | 00 | 2017-01-08 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS | 2017-01-09 09:09 | IFI | OB | 100%
130103 | I491TM04-0EAAA02-001-002 | D-34.00.000.060D DRIVE UNIT TILTING DEVICE 2-2 | 00 | 2017-01-08 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS | 2017-01-09 09:10 | IFI | OB | 100%
130104 | I491TM04-0EAAA03-001-001 | D-34.00.000.051D FITTING TILTING FRAM ALLOY FUNNEL 1-2 | 00 | 2017-01-08 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS | 2017-01-09 09:12 | IFI | OB | 100%
130105 | I491TM04-0EAAA03-001-002 | D-34.00.000.051D FITTING TILTING FRAM ALLOY FUNNEL 2-2 | 00 | 2017-01-08 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS | 2017-01-09 09:12 | IFI | OB | 100%
130106 | I491TM04-0EAAA04-002-001 | D-10.00.001.390D UPPER SHELL | 00 | 2017-01-08 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS | 2017-01-09 09:13 | IFI | OB | 100%
15946 | I491TM04-0EAEO01-001-001 | Swiveling Device- Gantry Eaf | 00 | 2012-03-10 | Indeterminate | Drawing | Basic | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
15947 | I491TM04-0EAEO02-001-001 | Locking Device -Gantry Eaf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
15948 | I491TM04-0EAEO03-001-001 | Transformer Eaf- Position Indication Gantry Eaf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | TAM |  | IFI | OB | 100%
15949 | I491TM04-0EAEO04-001-001 | Gantry- Electric Arc Furnace | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
15950 | I491TM04-0EAFE01-001-001 | Dri Addition Roof Eaf | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
15951 | I491TM04-0EAFE02-001-001 | Dri Addition Roof Eaf | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
15952 | I491TM04-0EAFG01-001-001 | Electric Arc Furnace Deckel | 00 | 2012-03-10 | Indeterminate | Drawing | Basic | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
15953 | I491TM04-0EAFG02-001-001 | Electric Arc Furnace Deckel | 00 | 2012-03-10 | Indeterminate | Drawing | Basic | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
15954 | I491TM04-0EAFK01-001-001 | Tilting Frame Rocker Rail | 00 | 2012-03-10 | Indeterminate | Drawing | Basic | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
15955 | I491TM04-0EAFM01-001-001 | Tap Hole Filling Shell | 00 | 2012-03-10 | Indeterminate | Drawing | Basic | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
15956 | I491TM04-0EAFM02-001-001 | Lower Part Tap Hole Filling Device Shell | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
15957 | I491TM04-0EAFM03-001-001 | Lower Part -Tap Hole Filling Device Shell | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
15958 | I491TM04-0EAFM04-001-001 | Swivel Pipe- Lower Part | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
15959 | I491TM04-0EAFM05-001-001 | Upper Part-Tap Hole Filling Device Shell | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | TAM |  | IFI | OB | 100%
113213 | I491TM04-0EAFM06-001-001 | Lower Shell-Heat Protection | 01 | 2015-01-07 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS | 2015-01-10 15:08 | IFI | OB | 100%
15961 | I491TM04-0EAFM07-001-001 | Upper Shell-Turanlage | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
15962 | I491TM04-0EAFM08-001-001 | Upper Shell-Turanlage | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
15963 | I491TM04-0EAFM09-001-001 | Slagdoor Cylinder -Door System | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
15964 | I491TM04-0EAFM10-001-001 | Door System -Drive Unit | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
15965 | I491TM04-0EAFM11-001-001 | Shell Electric Arc Furnace | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
15966 | I491TM04-0EAFM12-001-001 | Shell-Upper Shell | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
115290 | I491TM04-0EAFM13-002-001 | EF.02.234.ASD-D-31.00.000.229F PANEL TYPE D | 00 | 2016-05-10 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS | 2016-05-24 17:01 | IFI | OB | 100%
115291 | I491TM04-0EAFM14-003-001 | EF.02.234.ASD-D-31.00.000.230E PANEL TYPE D | 00 | 2016-05-10 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS | 2016-05-24 17:01 | IFI | OB | 100%
15967 | I491TM04-0EAIH01-001-001 | Piping -Electrode Arms Eaf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
15968 | I491TM04-0EAIH02-001-001 | Support Arm Phase 1 Electrode Arms Eaf | 00 | 2013-12-29 07:21 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
15969 | I491TM04-0EAIH03-001-001 | Support Arm Phase 2 Electrode Arms Eaf | 00 | 2013-12-29 07:21 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
15970 | I491TM04-0EAIH04-001-001 | Support Arm Phase 3 Electrode Arms Eaf | 00 | 2013-12-29 07:21 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
15971 | I491TM04-0EAIH05-001-001 | Electrode Arms Electric Arc Furnace | 00 | 2013-12-29 07:21 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
15974 | I491TM04-0EAII01-001-003 | Heat Protection -Lifting Columns Eaf | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
15975 | I491TM04-0EAII02-001-001 | Roller Bracket- Electrode Lifting Device Eaf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
15976 | I491TM04-0EAII03-001-001 | Locking Device -Electrode Lifting Device Ef | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
15978 | I491TM04-0EAII04-001-002 | Lifting Columns Complete Phase 1+2+3 Electrode Lifting Device Eaf | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
15979 | I491TM04-0EAII06-001-001 | Roller Bracket-Electrode Lifting Device Eaf | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | TAM |  | IFI | OB | 100%
130095 | I491TM04-0LFBT01-007-001 | D-34.00.000.087 E- NATURAL GAS PIPING TILTING FRAME | 00 | 2017-01-09 09:02 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | FUCHS | 2017-01-09 09:02 | IFI | OB | 100%
130096 | I491TM04-0LFBT03-001-001 | D-31.00.000.156A ENERGY SUPPLY LC LF STEEL STRUCTURE | 00 | 2017-01-09 09:02 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | FUCHS | 2017-01-09 09:02 | IFI | OB | 100%
15980 | I491TM04-0LFIH01-001-001 | Release Cylinder Clamp Box | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
15982 | I491TM04-0LFLE01-001-002 | Roof Ladle Furnace | 00 | 2012-03-10 | Indeterminate | Drawing | Basic | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
15984 | I491TM04-0LFLE02-001-002 | Piping Electrode Arms Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | TAM |  | IFI | OB | 100%
15985 | I491TM04-0LFLE03-001-001 | Roof Ladle Furnace | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
15986 | I491TM04-0LFLE04-001-001 | Roof Ladle Furnace | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
15987 | I491TM04-0LFLE05-001-001 | STEEL STRUCTURE ROOF LF | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Civil and Steel Structure | INTECO |  | IFI | OB | 100%
15988 | I491TM04-0LFLE06-001-001 | Holder Steel Structure Roof Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Civil and Steel Structure | INTECO |  | IFI | OB | 100%
15989 | I491TM04-0LFLE07-001-001 | HOLDER STEEL STRUCTURE ROOF LF | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Civil and Steel Structure | INTECO |  | IFI | OB | 100%
15990 | I491TM04-0LFLE08-001-001 | HOLDER STEEL STRUCTURE ROOF LF | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Civil and Steel Structure | INTECO |  | IFI | OB | 100%
15991 | I491TM04-0LFLE10-001-001 | ALLOY UNIT - ROOF LF | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
113569 | I491TM04-0LFLE10-002-001 | ALLOY UNIT - ROOF LF | 00 | 2015-05-06 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | TAM | 2015-05-27 16:07 | IFI | OB | 100%
113570 | I491TM04-0LFLE10-003-001 | ALLOY UNIT - ROOF LF | 00 | 2015-05-06 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | TAM | 2015-05-27 16:07 | IFI | OB | 100%
113571 | I491TM04-0LFLE10-004-001 | ALLOY UNIT - ROOF LF | 00 | 2015-05-06 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | TAM | 2015-05-27 16:07 | IFI | OB | 100%
113572 | I491TM04-0LFLE10-005-001 | ALLOY UNIT - ROOF LF | 00 | 2015-05-06 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | TAM | 2015-05-27 16:07 | IFI | OB | 100%
113573 | I491TM04-0LFLE10-006-001 | ALLOY UNIT - ROOF LF | 00 | 2015-05-06 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | TAM | 2015-05-27 16:07 | IFI | OB | 100%
113574 | I491TM04-0LFLE10-007-001 | ALLOY UNIT - ROOF LF | 00 | 2015-05-06 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | TAM | 2015-05-27 16:07 | IFI | OB | 100%
113575 | I491TM04-0LFLE10-008-001 | ALLOY UNIT - ROOF LF | 00 | 2015-05-06 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | TAM | 2015-05-27 16:07 | IFI | OB | 100%
113576 | I491TM04-0LFLE10-009-001 | ALLOY UNIT - ROOF LF | 00 | 2015-05-06 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | TAM | 2015-05-27 16:07 | IFI | OB | 100%
15992 | I491TM04-0LFLE11-001-001 | SLIDER - ALLOY UNIT ROOF LF | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
113577 | I491TM04-0LFLE11-002-001 | SLIDER - ALLOY UNIT ROOF LF | 00 | 2015-05-06 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | TAM | 2015-05-27 16:08 | IFI | OB | 100%
113578 | I491TM04-0LFLE11-003-001 | SLIDER - ALLOY UNIT ROOF LF | 00 | 2015-05-06 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | TAM | 2015-05-27 16:08 | IFI | OB | 100%
113579 | I491TM04-0LFLE11-004-001 | SLIDER - ALLOY UNIT ROOF LF | 00 | 2015-05-06 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | TAM | 2015-05-27 16:08 | IFI | OB | 100%
113580 | I491TM04-0LFLE11-005-001 | SLIDER - ALLOY UNIT ROOF LF | 00 | 2015-05-06 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | TAM | 2015-05-27 16:08 | IFI | OB | 100%
113581 | I491TM04-0LFLE12-001-001 | Cylinder-Alloy Unt Roof Lf | 01 | 2015-05-06 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | FUCHS | 2015-05-27 16:08 | IFI | OB | 100%
15994 | I491TM04-0LFLE13-001-001 | LANCE OPENING - ROOF LF | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
115305 | I491TM04-0LFLE13-002-001 | LF.07.220.MAD-D-20.00.001.223 ROUND BAR | 00 | 2016-05-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | FUCHS | 2016-05-25 09:09 | IFI | OB | 100%
115306 | I491TM04-0LFLE13-003-001 | LF.07.220.MAD-D-20.00.001.224 ROUND BAR | 00 | 2016-05-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | FUCHS | 2016-05-25 09:09 | IFI | OB | 100%
115307 | I491TM04-0LFLE13-004-001 | LF.07.220.MAD-D-20.00.001.225 ROUND BAR | 00 | 2016-05-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | FUCHS | 2016-05-25 09:09 | IFI | OB | 100%
115308 | I491TM04-0LFLE13-005-001 | LF.07.220.DED-D-20.00.001.226 PLATE | 00 | 2016-05-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | FUCHS | 2016-05-25 09:09 | IFI | OB | 100%
115309 | I491TM04-0LFLE13-006-001 | LF.07.220.DED-D-20.00.001.227 PLATE | 00 | 2016-05-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | FUCHS | 2016-05-25 09:09 | IFI | OB | 100%
115310 | I491TM04-0LFLE13-007-001 | LF.07.220.DED-D-20.00.001.228 PLATE | 00 | 2016-05-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | FUCHS | 2016-05-25 09:09 | IFI | OB | 100%
15995 | I491TM04-0LFLE14-001-001 | Cylinder-Lance Opening Roof Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
113582 | I491TM04-0LFLE14-002-001 | FUNNEL - ALLOY UNIT ROOF LF | 00 | 2015-05-06 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | TAM | 2015-05-27 16:08 | IFI | OB | 100%
113583 | I491TM04-0LFLE14-003-001 | PIPE - ALLOY UNIT ROOF LF | 00 | 2015-05-06 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | TAM | 2015-05-27 16:08 | IFI | OB | 100%
15996 | I491TM04-0LFLE15-001-001 | Opening For Wire Feeding Roof Lf | 00 | 2012-03-10 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
15997 | I491TM04-0LFLE16-001-001 | Exhaust Roof Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
15998 | I491TM04-0LFLE17-001-001 | Exhaust Hood Accessories Exhaust Roof Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
15999 | I491TM04-0LFLE18-001-001 | Center Piece Exhaust Roof Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16000 | I491TM04-0LFLE19-001-001 | Working Door System Roof Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16001 | I491TM04-0LFLE20-001-001 | Working Door System Roof Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16002 | I491TM04-0LFLE21-001-001 | Working Door System Roof Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16003 | I491TM04-0LFLE22-001-001 | Door Roof Working Door Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16004 | I491TM04-0LFLE23-001-001 | Door Cylinder Roof Working Door Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16005 | I491TM04-0LFLE24-001-001 | Door Roof Working Door Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16006 | I491TM04-0LFLE25-001-001 | Water Piping Roof Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16007 | I491TM04-0LFLW01-001-001 | Electrode Lifting Device Lf Ladle Furnace | 00 | 2012-03-10 | Indeterminate | Drawing | Basic | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16008 | I491TM04-0LFLW02-001-001 | Electrode Lifting Device Lf Ladle Furnace | 00 | 2012-03-10 | Indeterminate | Drawing | Basic | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16009 | I491TM04-0LFLW03-001-001 | Electrode Lifting Device Lf Ladle Furnace | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16010 | I491TM04-0LFLW04-001-001 | Roller Bracket-Electrode Lifting Device Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
113584 | I491TM04-0LFLW04-002-001 | ROLLER BRACKET WITH EMERGENCY GUIDE - ELECTRODE LIFTING DEVICE LF | 00 | 2015-05-06 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | TAM | 2015-05-27 16:09 | IFI | OB | 100%
16011 | I491TM04-0LFLW06-001-001 | Locking Device-Electrode Lifting Device Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16012 | I491TM04-0LFLW08-001-001 | Lifting Cylinder-Electrode Lifting Device Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16014 | I491TM04-0LFRL01-001-002 | Gantry Ladle Furnace | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16015 | I491TM04-0LFRL03-001-001 | Roof Lifting Device Ladle Funrnace | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16016 | I491TM04-0LFRL04-001-001 | Roof Lifting Device Ladle Funrnace | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16017 | I491TM04-0LFRL05-001-001 | Roof Lifting Device Ladle Funrnace | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16018 | I491TM04-0LFRL06-001-001 | Lifting & Support Structure Roof Lifting Device Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16019 | I491TM04-0LFRL07-001-001 | Roller Bracket Roof Lifting Device Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16020 | I491TM04-0LFRL08-001-001 | Piping Roof Lifting Device Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
130051 | I491TM04-0MMHE01-001-001 | Plate Heat Exchanger AM30-FF-ASM | 00 | 2016-12-28 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Mechanical | TAM | 2017-01-01 12:02 | IFI | OB | 100%
130052 | I491TM04-0MMHE01-002-001 | Plate Heat Exchanger AM30-FF-ASM | 00 | 2016-12-28 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Mechanical | TAM | 2017-01-01 12:02 | IFI | OB | 100%
130053 | I491TM04-0MMHE02-001-001 | Plate Heat ExchangerT20S-FF-ASM | 00 | 2016-12-28 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Mechanical | TAM | 2017-01-01 12:02 | IFI | OB | 100%
130054 | I491TM04-0MMHE02-002-001 | Plate Heat ExchangerT20S-FF-ASM | 00 | 2016-12-28 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Mechanical | TAM | 2017-01-01 12:02 | IFI | OB | 100%
130055 | I491TM04-0MMHE03-001-001 | Plate Heat Exchanger AM15D-FF-ASM | 00 | 2016-12-28 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Mechanical | TAM | 2017-01-01 12:02 | IFI | OB | 100%
130056 | I491TM04-0MMHE03-002-001 | Plate Heat Exchanger AM15D-FF-ASM | 00 | 2016-12-28 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Mechanical | TAM | 2017-01-01 12:02 | IFI | OB | 100%
130242 | I491TM04-0MMOS01-001-001 | OIL Skimmer Installation WCP Sedimentation System 1-2 | 00 | 2017-01-16 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Mechanical | TAM | 2017-01-17 11:30 | IFI | OB | 100%
130243 | I491TM04-0MMOS01-001-002 | OIL Skimmer Installation WCP Sedimentation System 2-2 | 00 | 2017-01-16 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Mechanical | TAM | 2017-01-17 11:30 | IFI | OB | 100%
114652 | I491TM04-0MMTK01-001-001 | Emergency Tank Mechanical Basic of Design | 00 | 2015-10-26 13:37 | Indeterminate | Miscellaneous(MISC) | Basic | Water Treatment & Cooling System | Civil and Steel Structure | TAM | 2015-10-26 13:37 | IFA | A | 100%
114653 | I491TM04-0MMTK01-001-002 | BASIS OF DESIGN (MECHANICAL) EMERGENCY WATER TANK | 00 | 2015-10-26 13:37 | Indeterminate | Drawing | Basic | Water Treatment & Cooling System | Civil and Steel Structure | TAM | 2015-10-26 13:37 | IFA | A | 100%
16021 | I491TM04-0MTRL01-001-001 | Lubrication System Piping Gantry Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | TAM |  | IFI | OB | 100%
16022 | I491TM04-0RXBT91-001-001 | Ladle Operation Cycle Ladle Transfer Car At Lf | 00 | 2012-08-04 | Indeterminate | Drawing | Basic | Ladle Furnace Auxiliary | Mechanical | TAM |  | IFA | A | 100%
16023 | I491TM04-0RXBT91-002-001 | Ladle Transfer Car At Lf Ladle Operation Cycle | 00 | 2012-08-04 | Indeterminate | Drawing | Basic | Ladle Furnace Auxiliary | Mechanical | TAM |  | IFA | A | 100%
16024 | I491TM04-0RXBT91-003-001 | Ladle Operation Cycle Ladle Transfer Car At Lf | 00 | 2012-08-04 | Indeterminate | Drawing | Basic | Ladle Furnace Auxiliary | Mechanical | TAM |  | IFA | A | 100%
112195 | I491TM04-0RXLE02-001-001 | LF Roof Changing Stand AUXILARY PLATFORM ON LADLE FOR LF ROOF | 00 | 2014-05-14 | Indeterminate | Drawing | Basic | Ladle Furnace Auxiliary | Mechanical | TAM | 2014-05-17 11:44 | IFA | A | 100%
112196 | I491TM04-0RXLE03-001-001 | LF Roof Stand Gestell SHORT_DESC | 00 | 2014-05-14 | Indeterminate | Drawing | Basic | Ladle Furnace Auxiliary | Mechanical | TAM | 2014-05-17 11:45 | IFA | A | 100%
112197 | I491TM04-0RXLW01-001-001 | LF Lifting Device LIFTING BEAM | 00 | 2014-05-14 | Indeterminate | Drawing | Basic | Ladle Furnace Auxiliary | Mechanical | TAM | 2014-05-17 11:45 | IFA | A | 100%
129418 | I491TM04-0SHBT01-001-001 | Guide drawing for Scrap Bucket Transfer car SY.01.000.LAY-D.31.00.000.070 1-2 | 02 | 2016-08-29 | Indeterminate | Drawing | Basic | Scrap Yard Equipment | Mechanical | FUCHS | 2016-08-31 10:33 | IFC | AC |  | 95%
130246 | I491TM04-0SHBT01-001-002 | Guide drawing for Scrap Bucket Transfer car SY.01.000.LAY-D.31.00.000.070 2-2 | 02 | 2017-01-16 | Indeterminate | Drawing | Basic | Scrap Yard Equipment | Mechanical | FUCHS | 2017-01-22 09:36 | IFC | AFC | 100%
16026 | I491TM04-0SHIK01-001-001 | Guide Drawing For Scrap Bucket | 00 | 2012-04-07 | Indeterminate | Drawing | Basic | Scrap Yard Equipment | Mechanical | FUCHS |  | IFA | AC |  | 95%
16030 | I491TM04-0SXBT01-005-001 | Ladle Car Fittings-Rail Cleaner | 00 | 2013-03-03 | Indeterminate | Drawing | Basic | Eaf Auxiliaries | Automation and Instrumentation | INTECO |  | IFA | AC |  | 95%
16027 | I491TM04-0SXBT91-001-001 | Ladle Transfer Car At Eaf Ladle Operation Cycle | 00 | 2012-08-04 | Indeterminate | Drawing | Basic | Eaf Auxiliaries | Mechanical | TAM |  | IFA | A | 100%
16028 | I491TM04-0SXBT91-002-001 | Ladle Operation Cycle Ladle Transfer Car At Eaf | 00 | 2012-08-04 | Indeterminate | Drawing | Basic | Eaf Auxiliaries | Mechanical | TAM |  | IFA | A | 100%
16029 | I491TM04-0SXBT91-003-001 | Ladle Operation Cycle Ladle Transfer Car At Eaf | 00 | 2012-08-04 | Indeterminate | Drawing | Basic | Eaf Auxiliaries | Mechanical | TAM |  | IFA | A | 100%
16031 | I491TM04-0SXBT91-005-001 | Ladle Car Fittings-Brake Shoe | 00 | 2013-03-03 | Indeterminate | Drawing | Basic | Eaf Auxiliaries | Mechanical | INTECO |  | IFA | AC |  | 95%
114741 | I491TM04-0SXCJ01-001-001 | Carbon Injection Machine D-36.00.000.001_REV.A | 00 | 2015-12-06 | Indeterminate | Drawing | Detail | Eaf Auxiliaries | Mechanical | TAM | 2015-12-07 10:58 | IFI | OB | 100%
114742 | I491TM04-0SXCJ01-002-001 | Carbon Injection Machine D-36.00.000.002_REV.A | 00 | 2015-12-06 | Indeterminate | Drawing | Detail | Eaf Auxiliaries | Mechanical | TAM | 2015-12-07 10:58 | IFI | OB | 100%
114743 | I491TM04-0SXCJ01-003-001 | Carbon Injection Machine D-36.00.000.003_REV.A | 00 | 2015-12-06 | Indeterminate | Drawing | Detail | Eaf Auxiliaries | Mechanical | TAM | 2015-12-07 10:58 | IFI | OB | 100%
114750 | I491TM04-0SXCJ91-001-001 | Carbon Injection Silo Basic D-36.00.000.006 | 00 | 2015-12-06 | Indeterminate | Drawing | Basic | Eaf Auxiliaries | Mechanical | FUCHS | 2015-12-07 11:11 | IFA | AC |  | 95%
114744 | I491TM04-0SXCJ91-002-001 | Carbon Injection Loadcell D-36.00.000.008 | 00 | 2015-12-06 | Indeterminate | Drawing | Detail | Eaf Auxiliaries | Mechanical | TAM | 2015-12-07 10:58 | IFI | OB | 100%
112189 | I491TM04-0SXLW01-001-001 | EAF CROSS BEAM LIFTING DEVICES 1-3 | 00 | 2014-05-14 | Indeterminate | Drawing | Basic | Eaf Auxiliaries | Mechanical | TAM | 2014-05-17 11:37 | IFA | A | 100%
112190 | I491TM04-0SXLW01-001-002 | EAF CROSS BEAM LIFTING DEVICES 2-3 | 00 | 2014-05-14 | Indeterminate | Drawing | Basic | Eaf Auxiliaries | Mechanical | TAM | 2014-05-17 11:37 | IFA | A | 100%
112191 | I491TM04-0SXLW01-001-003 | EAF CROSS BEAM LIFTING DEVICES 3-3 | 00 | 2014-05-14 | Indeterminate | Drawing | Basic | Eaf Auxiliaries | Mechanical | TAM | 2014-05-17 11:37 | IFA | A | 100%
129475 | I491TM04-0WACS91-001-001 | Rack & Shelf System of Warehouses layout | 01 | 2016-09-11 09:51 | Indeterminate | Drawing | Detail | Warehouse | Mechanical | TAM | 2016-09-11 09:51 | IFC | AFC | 100%
130107 | I491TM04-0XEIN01-001-001 | D-10.00.001.569G PIPING - MEASSURING UNIT COMPLETE FLOW WATER EAF/LF | 00 | 2017-01-08 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS | 2017-01-09 09:13 | IFI | OB | 100%
134091 | I491TM05-0ASCP02-001-001 | Booster Air Compressor Assy 14_1_Comp Assy_4507832 (5 Sheet) | 00 | 2018-08-15 | Indeterminate | Miscellaneous(MISC) | Detail | Air Separation Plant Main Building | Mechanical | TAM | 2018-08-21 13:07 | IFI | OB | 100%
115773 | I491TM05-0BTAA01-001-001 | Bucket transfer car and Truck for scrap bucket Catalogue | 00 | 2016-06-21 14:38 | Indeterminate | Miscellaneous(MISC) | Detail | Scrap Yard Equipment | Mechanical | TAM | 2016-06-21 14:38 | IFI | OB | 100%
114510 | I491TM05-0CCCC91-001-001 | Sheet 1of3 CCM Cooling Chamber 8.566967.E_001_00 | 00 | 2015-10-11 15:05 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-11 15:05 | IFI | OB | 100%
114512 | I491TM05-0CCCC91-001-002 | Sheet 2of3 CCM Cooling Chamber 8.566967.E_002_00 | 00 | 2015-10-11 15:05 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-11 15:05 | IFI | OB | 100%
114511 | I491TM05-0CCCC91-001-003 | Sheet 3of3 CCM Cooling Chamber 8.566967.E_003_00 | 00 | 2015-10-11 15:05 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-11 15:05 | IFI | OB | 100%
114452 | I491TM05-0CCCP91-001-001 | CCM Mould Fume Exhust Systsm 8.687864.F_001_00 | 00 | 2015-10-06 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-10 14:22 | IFI | OB | 100%
114551 | I491TM05-0CCCZ01-001-001 | CCM Crop Excavation 8.610573.H_001_00 | 00 | 2015-10-13 11:34 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-13 11:34 | IFI | OB | 100%
114497 | I491TM05-0CCFF01-001-001 | Sheet 1of4 Tundish Refractory 6.329591.V_001_00 | 00 | 2015-10-07 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-11 11:52 | IFI | OB | 100%
114498 | I491TM05-0CCFF01-001-002 | Sheet 2of4 Tundish Refractory 6.329591.V_002_00 | 00 | 2015-10-07 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-11 11:52 | IFI | OB | 100%
114499 | I491TM05-0CCFF01-001-003 | Sheet 3of4 Tundish Refractory 6.329591.V_003_00 | 00 | 2015-10-07 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-11 11:52 | IFI | OB | 100%
114500 | I491TM05-0CCFF01-001-004 | Sheet 4of4 Tundish Refractory 6.329591.V_004_00 | 00 | 2015-10-07 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-11 11:52 | IFI | OB | 100%
132578 | I491TM05-0CCFF02-001-001 | Tundish Template SIS.TDF.000B-0717 | 00 | 2017-12-23 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2017-12-27 10:56 | IFI | OB | 100%
132579 | I491TM05-0CCFF02-002-001 | Tundish Template SIS.TDF.001D-0717 | 00 | 2017-12-23 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2017-12-27 10:56 | IFI | OB | 100%
132580 | I491TM05-0CCFF02-003-001 | Tundish TemplateSIS.TDF.002D-0717 | 00 | 2017-12-23 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2017-12-27 10:56 | IFI | OB | 100%
132581 | I491TM05-0CCFF02-004-001 | Tundish Template SIS.TDF.003D-0717 | 00 | 2017-12-23 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2017-12-27 10:56 | IFI | OB | 100%
132582 | I491TM05-0CCFF02-005-001 | Tundish Template SIS.TDF.004D-0717 | 00 | 2017-12-23 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2017-12-27 10:56 | IFI | OB | 100%
132583 | I491TM05-0CCFF02-006-001 | Tundish Template SIS.TDF.005D-0717 | 00 | 2017-12-23 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2017-12-27 10:56 | IFI | OB | 100%
132584 | I491TM05-0CCFF02-007-001 | Tundish Template SIS.TDF.006D-0717 | 00 | 2017-12-23 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2017-12-27 10:56 | IFI | OB | 100%
132585 | I491TM05-0CCFF02-008-001 | Tundish Template SIS.TDF.007D-0717 | 00 | 2017-12-23 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2017-12-27 10:56 | IFI | OB | 100%
132586 | I491TM05-0CCFF02-009-001 | Tundish Template SIS.TDF.008D-0717 | 00 | 2017-12-23 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2017-12-27 10:56 | IFI | OB | 100%
132587 | I491TM05-0CCFF02-010-001 | Tundish Template SIS.TDF.009D-0717 | 00 | 2017-12-23 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2017-12-27 10:56 | IFI | OB | 100%
132588 | I491TM05-0CCFF02-011-001 | Tundish Template SIS.TDF.010D-0717 | 00 | 2017-12-23 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2017-12-27 10:56 | IFI | OB | 100%
132589 | I491TM05-0CCFF02-012-001 | Tundish Template SIS.TDF.011D-0717 | 00 | 2017-12-23 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2017-12-27 10:56 | IFI | OB | 100%
132590 | I491TM05-0CCFF02-013-001 | Tundish Template SIS.TDF.020A1-0717 | 00 | 2017-12-23 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2017-12-27 10:56 | IFI | OB | 100%
132591 | I491TM05-0CCFF02-014-001 | Tundish Template SIS.TDF.020A2-0717 | 00 | 2017-12-23 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2017-12-27 10:56 | IFI | OB | 100%
132592 | I491TM05-0CCFF02-015-001 | Tundish Template SIS.TDF.030B-0717 | 00 | 2017-12-23 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2017-12-27 10:57 | IFI | OB | 100%
132593 | I491TM05-0CCFF02-016-001 | Tundish TemplateSIS.TDF.040C-0717 | 00 | 2017-12-23 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2017-12-27 10:57 | IFI | OB | 100%
132594 | I491TM05-0CCFF02-017-001 | Tundish Template SIS.TDF.050C-0717 | 00 | 2017-12-23 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2017-12-27 10:57 | IFI | OB | 100%
132595 | I491TM05-0CCFF02-018-001 | Tundish Template SIS.TDF.060B-0717 | 00 | 2017-12-23 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2017-12-27 10:57 | IFI | OB | 100%
132596 | I491TM05-0CCFF02-019-001 | Tundish Template SIS.TDF.065B-0717 | 00 | 2017-12-23 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2017-12-27 10:57 | IFI | OB | 100%
132597 | I491TM05-0CCFF02-020-001 | Tundish Template SIS.TDF.070C-0717 | 00 | 2017-12-23 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2017-12-27 10:57 | IFI | OB | 100%
132598 | I491TM05-0CCFF02-021-001 | Tundish Template SIS.TDF.075B-0717 | 00 | 2017-12-23 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2017-12-27 10:57 | IFI | OB | 100%
132599 | I491TM05-0CCFF02-022-001 | Tundish Template SIS.TDF.080B-0717 | 00 | 2017-12-23 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2017-12-27 10:57 | IFI | OB | 100%
132600 | I491TM05-0CCFF02-023-001 | Tundish Template SIS.TDF.085B-0717 | 00 | 2017-12-23 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2017-12-27 10:57 | IFI | OB | 100%
132601 | I491TM05-0CCFF02-024-001 | Tundish Template SIS.TDF.090B-0717 | 00 | 2017-12-23 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2017-12-27 10:57 | IFI | OB | 100%
132602 | I491TM05-0CCFF02-025-001 | Tundish Template SIS.TDF.095B-0717 | 00 | 2017-12-23 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2017-12-27 10:57 | IFI | OB | 100%
132604 | I491TM05-0CCFF03-001-001 | Tundish Template SIS.TVF.000B-0717 | 00 | 2017-12-23 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2017-12-27 11:00 | IFI | OB | 100%
132605 | I491TM05-0CCFF03-002-001 | Tundish Template SIS.TVF.001D-0717 | 00 | 2017-12-23 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2017-12-27 11:00 | IFI | OB | 100%
132606 | I491TM05-0CCFF03-003-001 | Tundish Template SIS.TVF.002D-0717 | 00 | 2017-12-23 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2017-12-27 11:00 | IFI | OB | 100%
132607 | I491TM05-0CCFF03-004-001 | Tundish Template SIS.TVF.003D-0717 | 00 | 2017-12-23 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2017-12-27 11:00 | IFI | OB | 100%
132608 | I491TM05-0CCFF03-005-001 | Tundish Template SIS.TVF.004D-0717 | 00 | 2017-12-23 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2017-12-27 11:00 | IFI | OB | 100%
132609 | I491TM05-0CCFF03-006-001 | Tundish Template SIS.TVF.005D-0717 | 00 | 2017-12-23 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2017-12-27 11:00 | IFI | OB | 100%
132610 | I491TM05-0CCFF03-007-001 | Tundish Template SIS.TVF.006D-0717 | 00 | 2017-12-23 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2017-12-27 11:00 | IFI | OB | 100%
132611 | I491TM05-0CCFF03-008-001 | Tundish Template SIS.TVF.007D-0717 | 00 | 2017-12-23 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2017-12-27 11:00 | IFI | OB | 100%
132612 | I491TM05-0CCFF03-009-001 | Tundish Template SIS.TVF.020A-0717 | 00 | 2017-12-23 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2017-12-27 11:00 | IFI | OB | 100%
132613 | I491TM05-0CCFF03-010-001 | Tundish Template SIS.TVF.030A-0717 | 00 | 2017-12-23 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2017-12-27 11:00 | IFI | OB | 100%
132614 | I491TM05-0CCFF03-011-001 | Tundish Template SIS.TVF.040B-0717 | 00 | 2017-12-23 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2017-12-27 11:00 | IFI | OB | 100%
132615 | I491TM05-0CCFF03-012-001 | Tundish Template SIS.TVF.050B-0717 | 00 | 2017-12-23 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2017-12-27 11:00 | IFI | OB | 100%
132616 | I491TM05-0CCFF03-013-001 | Tundish Template SIS.TVF.060B-0717 | 00 | 2017-12-23 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2017-12-27 11:00 | IFI | OB | 100%
132617 | I491TM05-0CCFF03-014-001 | Tundish Template SIS.TVF.070D-0717 | 00 | 2017-12-23 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2017-12-27 11:00 | IFI | OB | 100%
114617 | I491TM05-0CCHY91-001-001 | CCM Ladle Turret and Tundish Car Hydraulic 8.496715.T_001_01 | 00 | 2015-10-26 10:47 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-26 10:47 | IFI | OB | 100%
114618 | I491TM05-0CCHY91-006-001 | CCM Extraction Straightening Unit 8.496743.E_001_02 | 00 | 2015-10-26 10:48 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-26 10:48 | IFI | OB | 100%
114619 | I491TM05-0CCHY91-007-001 | CCM Strand Cutting Device 8.496741.C_001_01A | 00 | 2015-10-26 10:48 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-26 10:48 | IFI | OB | 100%
114620 | I491TM05-0CCHY91-008-001 | CCM Slide Gate Unit 8.496742.D_001_01A | 00 | 2015-10-26 10:48 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-26 10:48 | IFI | OB | 100%
114621 | I491TM05-0CCHY91-009-001 | CCM Ladle Slide Gate Test 8.496741.C_001_01A | 00 | 2015-10-26 10:48 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-26 10:48 | IFI | OB | 100%
114455 | I491TM05-0CCHY91-012-001 | Mould Lubrication Unit 8.426099.W_001_02 | 00 | 2015-10-06 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-10 14:23 | IFI | OB | 100%
114622 | I491TM05-0CCHY91-020-001 | CCM Run Out Unit 8.496732.R_001_01 | 00 | 2015-10-26 10:49 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-26 10:49 | IFI | OB | 100%
114623 | I491TM05-0CCHY91-027-001 | CCM Acumulators Stand 8.632478.L_001_01F | 00 | 2015-10-26 10:49 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-26 10:49 | IFI | OB | 100%
114624 | I491TM05-0CCHY91-029-001 | CCM Oscill Benches Accumulators 8.496725.V_001_01A | 00 | 2015-10-26 10:50 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-26 10:50 | IFI | OB | 100%
114625 | I491TM05-0CCHY91-030-001 | Mould Oscilation Hydraulic 8.336267.Q_001_03 | 00 | 2015-10-26 10:51 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-26 10:51 | IFI | OB | 100%
114626 | I491TM05-0CCHY91-030-002 | Mould Oscillatores Unit 8.496723.T_001_01A | 00 | 2015-10-26 10:51 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-26 10:51 | IFI | OB | 100%
114627 | I491TM05-0CCHY91-032-001 | CCM Out Accumulator 8.632478.L_001_01F | 00 | 2015-10-26 10:51 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-26 10:51 | IFI | OB | 100%
132575 | I491TM05-0CCIJ01-001-001 | Storeage Box for CCM Radioactive Mould Level Sensor | 00 | 2017-12-19 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2017-12-27 09:43 | IFI | OB | 100%
114628 | I491TM05-0CCLB01-001-001 | CCM Grease Tank 8.425877.W_001_04 | 00 | 2015-10-26 10:51 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-26 10:51 | IFI | OB | 100%
114535 | I491TM05-0CCLK04-001-001 | Ladle Shroude Manipulator 8.566951 | 00 | 2015-10-13 10:14 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-13 10:14 | IFI | OB | 100%
114536 | I491TM05-0CCLK04-002-001 | Ladle Shroude Manipulator 8.566951 | 00 | 2015-10-13 10:15 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-13 10:15 | IFI | OB | 100%
114501 | I491TM05-0CCLW01-001-001 | CCM Tundish Lifting Beam 8.692211.C_001_00 | 00 | 2015-10-07 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-11 11:52 | IFI | OB | 100%
114462 | I491TM05-0CCLW02-001-001 | Sheet 1of2 CCM Mould Quick Change Device 8.680172.N_001_01A | 00 | 2015-10-06 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-10 14:25 | IFI | OB | 100%
114465 | I491TM05-0CCLW02-001-002 | Sheet 2of2 CCM Mould Quick Change Device 8.680172.N_002_01A | 00 | 2015-10-06 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-11 10:42 | IFI | OB | 100%
114451 | I491TM05-0CCLW03-001-001 | Movement Tention Rod 5.118772.D_001_00C | 00 | 2015-10-06 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-10 14:22 | IFI | OB | 100%
114456 | I491TM05-0CCMI01-001-001 | Mould Maintenance Stand 8.650386.W_001_00 | 00 | 2015-10-06 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-10 14:23 | IFI | OB | 100%
114463 | I491TM05-0CCMI03-001-001 | CCM Mould Stand 8.422502.T_001_00 | 00 | 2015-10-06 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-11 10:38 | IFI | OB | 100%
114460 | I491TM05-0CCMJ06-001-001 | Mould powder Feeding 8.566949.K_001_00 | 00 | 2015-10-06 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-10 14:25 | IFI | OB | 100%
114461 | I491TM05-0CCMJ06-002-001 | Mould powder Feeding 6.267282.G_001_00 | 00 | 2015-10-06 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-10 14:25 | IFI | OB | 100%
114502 | I491TM05-0CCPN01-001-001 | OP Pannel Support 8.566953.F_001_00 | 00 | 2015-10-07 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-11 11:52 | IFI | OB | 100%
114566 | I491TM05-0CCPW02-004-001 | Sheet 1of2 LCT Beam 5.966363.E_001_00 | 00 | 2015-10-18 11:10 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-18 11:10 | IFI | OB | 100%
114567 | I491TM05-0CCPW02-004-002 | Sheet 2of2 LCT Beam 5.966363.E_002_00 | 00 | 2015-10-18 11:10 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-18 11:10 | IFI | OB | 100%
114464 | I491TM05-0CCRB01-001-001 | Radioactive Detector 6.267228.H_001_00A | 00 | 2015-10-06 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-11 10:38 | IFI | OB | 100%
114552 | I491TM05-0CCRJ05-001-001 | CCM CRT 8.610601.V_001_01 | 00 | 2015-10-13 11:34 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-13 11:34 | IFI | OB | 100%
114553 | I491TM05-0CCRJ05-002-001 | CCM CRT Assy 6.343532.X_001_00 | 00 | 2015-10-13 11:34 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-13 11:34 | IFI | OB | 100%
114554 | I491TM05-0CCRJ05-002-002 | CCM CRT Guard 8.610590.P_001_00 La | 00 | 2015-10-13 11:34 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-13 11:34 | IFI | OB | 100%
114555 | I491TM05-0CCRL04-001-001 | Sheet 1of2 CCM DRT Guard 8.610606.T_001_00 | 00 | 2015-10-13 11:35 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-13 11:35 | IFI | OB | 100%
114556 | I491TM05-0CCRL04-001-002 | Sheet 2of2 CCM DRT Guard 8.610606.T_002_00 | 00 | 2015-10-13 11:35 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-13 11:35 | IFI | OB | 100%
114557 | I491TM05-0CCRL10-002-001 | CCM ART Frame 7.033018.M_001_00 | 00 | 2015-10-13 11:35 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-13 11:35 | IFI | OB | 100%
114503 | I491TM05-0CCSO03-001-001 | CCM Stopper Rod Stand 8.443598.F_001_01 | 00 | 2015-10-07 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-11 11:53 | IFI | OB | 100%
114517 | I491TM05-0CCSQ01-001-001 | Sheet 1of2 Steam Duct 8566968N_001 | 00 | 2015-10-11 15:06 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-11 15:06 | IFI | OB | 100%
114518 | I491TM05-0CCSQ01-001-002 | Sheet 2of2 Steam Duct 8566968N_002 | 00 | 2015-10-11 15:06 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-11 15:06 | IFI | OB | 100%
114422 | I491TM05-0CCTD10-001-001 | CCM Tundish Drying Station 6.267310.Q_001_00 | 00 | 2015-10-03 12:01 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-03 12:01 | IFA | A | 100%
114504 | I491TM05-0CCTD13-001-001 | Sheet 1of3 Tundish Tiltung Stand 8.704944.Q_001_00A | 00 | 2015-10-07 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-11 11:53 | IFI | OB | 100%
114505 | I491TM05-0CCTD13-001-002 | Sheet 2of3 Tundish Tiltung Stand 8.704944.Q_002_00A | 00 | 2015-10-07 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-11 11:53 | IFI | OB | 100%
114506 | I491TM05-0CCTD13-001-003 | Sheet 3of3 Tundish Tiltung Stand 8.704944.Q_003_00A | 00 | 2015-10-07 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-11 11:53 | IFI | OB | 100%
133384 | I491TM05-0CHEU02-001-001 | 7.2.2.1 assembly drawing conductor line F45_500 red. PE K2-1567.0100A | 00 | 2018-06-25 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-07 11:37 | IFI | OB | 100%
133385 | I491TM05-0CHEU02-002-001 | 7.2.2.2 assembly drawing crane rail K2-1567.0200A 1-2 | 00 | 2018-06-25 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-07 11:37 | IFI | OB | 100%
133387 | I491TM05-0CHEU02-002-002 | 7.2.2.2 assembly drawing crane rail K2-1567.0200A 2-2 | 00 | 2018-06-25 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-07 11:37 | IFI | OB | 100%
133388 | I491TM05-0CHEU02-003-001 | 7.2.2.3 Lifting and attach. points_K2-1567.4000A-1 1-2 | 00 | 2018-06-25 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-07 11:37 | IFI | OB | 100%
133386 | I491TM05-0CHEU02-003-002 | 7.2.2.3 Lifting and attach. points_K2-1567.4000A-1 2-2 | 00 | 2018-06-25 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-07 11:37 | IFI | OB | 100%
133389 | I491TM05-0CHEU02-004-001 | 7.2.2.4 scrap charging crane 90-30-5tx29m_lubrication plan_K2-1567.4000A-2 | 00 | 2018-06-25 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-07 11:37 | IFI | OB | 100%
133390 | I491TM05-0CHEU02-005-001 | 7.2.2.5 crane scrap charging crane_K2-1567.4000A-3 | 00 | 2018-06-25 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-07 11:37 | IFI | OB | 100%
133391 | I491TM05-0CHEU02-006-001 | 7.2.2.6 trolley 90t_K2-1567.5000A-1 | 00 | 2018-06-25 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-07 11:37 | IFI | OB | 100%
133392 | I491TM05-0CHEU02-007-001 | 7.2.2.7 main hoist 90t_K2-1567.5500A | 00 | 2018-06-25 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-07 11:37 | IFI | OB | 100%
133393 | I491TM05-0CHEU02-008-001 | 7.2.2.8 auxiliary hoist 30t _ K2-1567.5900A | 00 | 2018-06-25 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-07 11:37 | IFI | OB | 100%
133394 | I491TM05-0CHEU02-009-001 | 7.2.2.9 auxiliary hoist 5t_K2-1567.2600A-1 | 00 | 2018-06-25 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-07 11:37 | IFI | OB | 100%
133396 | I491TM05-0CHEU02-010-001 | 7.2.2.10 hook block 90t K2-1567.5700A-1 | 00 | 2018-06-25 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-07 11:37 | IFI | OB | 100%
133395 | I491TM05-0CHEU02-011-001 | 7.2.2.11 hook block 30t K2-1567.5800A-1 | 00 | 2018-06-25 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-07 11:37 | IFI | OB | 100%
133649 | I491TM05-0CHEU03-001-001 | 7.2.2.1 Lifting and attachement points K2-1570.0100A-1 1-2 | 00 | 2018-07-08 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-12 11:12 | IFI | OB | 100%
133648 | I491TM05-0CHEU03-001-002 | 7.2.2.1 Lifting and attachement points K2-1570.0100A-2 2-2 | 00 | 2018-07-08 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-12 11:12 | IFI | OB | 100%
133647 | I491TM05-0CHEU03-002-001 | 7.2.2.2 Lubrication plan K2-1570.0100A-2 | 00 | 2018-07-08 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-12 11:12 | IFI | OB | 100%
133646 | I491TM05-0CHEU03-003-001 | 7.2.2.3 Head girder K2-1570.0300A-3 | 00 | 2018-07-08 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-12 11:12 | IFI | OB | 100%
133645 | I491TM05-0CHEU03-004-001 | 7.2.2.4 Main girder K2-1570.0200A-3 | 00 | 2018-07-08 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-12 11:12 | IFI | OB | 100%
133644 | I491TM05-0CHEU03-005-001 | 7.2.2.5 Crane bridge double-girder crane K2-1570.0100A-3 | 00 | 2018-07-08 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-12 11:12 | IFI | OB | 100%
133643 | I491TM05-0CHEU03-006-001 | 7.2.2.6 Currency collector platform K2-1570.0700B-3 | 00 | 2018-07-08 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-12 11:12 | IFI | OB | 100%
133642 | I491TM05-0CHEU03-007-001 | 7.2.2.7 Trolley 90-30-5t K2-1570.1500A-3 | 00 | 2018-07-08 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-12 11:12 | IFI | OB | 100%
133641 | I491TM05-0CHEU03-008-001 | 7.2.2.8 Main hoist 90t K2-1570.1800A-3 | 00 | 2018-07-08 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-12 11:12 | IFI | OB | 100%
133640 | I491TM05-0CHEU03-009-001 | 7.2.2.9 Auxiliary hoist 30t K2-1570.0900A-3 | 00 | 2018-07-08 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-12 11:12 | IFI | OB | 100%
133639 | I491TM05-0CHEU03-010-001 | 7.2.2.10 Auxiliary hoist 5t K2-1570.0960A-3 | 00 | 2018-07-08 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-12 11:12 | IFI | OB | 100%
133638 | I491TM05-0CHEU03-011-001 | 7.2.2.11 Hook block 90t K2-1567.5700A-1 | 00 | 2018-07-08 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-12 11:12 | IFI | OB | 100%
133637 | I491TM05-0CHEU03-012-001 | 7.2.2.12 Hook block 30t - K2-1567.5800B-1 1-2 | 00 | 2018-07-08 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-12 11:11 | IFI | OB | 100%
133656 | I491TM05-0CHEU04-001-001 | 7.2.2.1 Lifting and attachement points K2-1570.1000A-1 1-2 | 00 | 2018-07-08 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-12 11:13 | IFI | OB | 100%
133655 | I491TM05-0CHEU04-001-002 | 7.2.2.1 Lifting and attachement points K2-1570.1000A-2 2-2 | 00 | 2018-07-08 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-12 11:13 | IFI | OB | 100%
133654 | I491TM05-0CHEU04-002-001 | 7.2.2.2 Lubrication plan K2-1570.1000A-2 | 00 | 2018-07-08 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-12 11:13 | IFI | OB | 100%
133653 | I491TM05-0CHEU04-003-001 | 7.2.2.3 Head girder K2-1570.0300A-3 | 00 | 2018-07-08 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-12 11:13 | IFI | OB | 100%
133652 | I491TM05-0CHEU04-004-001 | 7.2.2.4 Main girder K2-1570.0200A-3 | 00 | 2018-07-08 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-12 11:13 | IFI | OB | 100%
133651 | I491TM05-0CHEU04-005-001 | 7.2.2.5 Crane bridge double-girder crane K2-1570.1000A-3 | 00 | 2018-07-08 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-12 11:12 | IFI | OB | 100%
133650 | I491TM05-0CHEU04-006-001 | 7.2.2.6 Currency collector platform K2-1570.0700B-3 | 00 | 2018-07-08 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-12 11:12 | IFI | OB | 100%
133679 | I491TM05-0CHEU04-007-001 | 7.2.2.7 Trolley 90-30-5t K2-1570.1600A | 00 | 2018-07-08 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-14 08:37 | IFI | OB | 100%
133684 | I491TM05-0CHEU04-008-001 | 7.2.2.8 Main hoist 90t K2-1570.1800A-3 | 00 | 2018-07-08 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-14 08:38 | IFI | OB | 100%
133683 | I491TM05-0CHEU04-009-001 | 7.2.2.9 Auxiliary hoist 30 t K2-1570.1900A-3 | 00 | 2018-07-08 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-14 08:38 | IFI | OB | 100%
133682 | I491TM05-0CHEU04-010-001 | 7.2.2.10 Auxiliary hoist 5t K2-1570.0980A-3 | 00 | 2018-07-08 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-14 08:38 | IFI | OB | 100%
133681 | I491TM05-0CHEU04-011-001 | 7.2.2.11 Hook block 90t K2-1567.5700A-1 | 00 | 2018-07-08 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-14 08:38 | IFI | OB | 100%
133680 | I491TM05-0CHEU04-012-001 | 7.2.2.12 Hook block 30t - K2-1567.5800B-1 | 00 | 2018-07-08 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-14 08:37 | IFI | OB | 100%
133695 | I491TM05-0CHEU05-001-001 | 7.2.2.1 Lifting and attachment points K2-1570.2000A-1 | 00 | 2018-07-08 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-14 08:39 | IFI | OB | 100%
133694 | I491TM05-0CHEU05-002-001 | 7.2.2.2 Lubrication plan K2-1570.2000A-2 | 00 | 2018-07-08 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-14 08:38 | IFI | OB | 100%
133693 | I491TM05-0CHEU05-003-001 | 7.2.2.3 Head girder K2-1570.2300A-3 | 00 | 2018-07-08 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-14 08:38 | IFI | OB | 100%
133692 | I491TM05-0CHEU05-004-001 | 7.2.2.4 Main girder K2-1570.2200A-3 | 00 | 2018-07-08 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-14 08:38 | IFI | OB | 100%
133691 | I491TM05-0CHEU05-005-001 | 7.2.2.5 Crane K2-1570.2000A-3 | 00 | 2018-07-08 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-14 08:38 | IFI | OB | 100%
133690 | I491TM05-0CHEU05-006-001 | 7.2.2.6 Currency collector platform K2-1570.2700A-3 | 00 | 2018-07-08 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-14 08:38 | IFI | OB | 100%
133689 | I491TM05-0CHEU05-007-001 | 7.2.2.7 Trolley K2-1570.3200A-3 | 00 | 2018-07-08 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-14 08:38 | IFI | OB | 100%
133688 | I491TM05-0CHEU05-008-001 | 7.2.2.8 Trolley 28t translation K2-1570.3000A-3 | 00 | 2018-07-08 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-14 08:38 | IFI | OB | 100%
133687 | I491TM05-0CHEU05-009-001 | 7.2.2.9 Main hoist 28t K2-1570.3700B-3 | 00 | 2018-07-08 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-14 08:38 | IFI | OB | 100%
133686 | I491TM05-0CHEU05-010-001 | 7.2.2.10 Auxiliary hoist 5t K2-1570.3900A-3 | 00 | 2018-07-08 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-14 08:38 | IFI | OB | 100%
133685 | I491TM05-0CHEU05-011-001 | 7.2.2.11 Magnet traverse K2-1570.3600A-3 | 00 | 2018-07-08 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-14 08:38 | IFI | OB | 100%
133700 | I491TM05-0CHEU06-001-001 | 7.2.2.1 Lifting and attachment points K2-1570.2100A-1 | 00 | 2018-07-08 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-14 08:39 | IFI | OB | 100%
133699 | I491TM05-0CHEU06-002-001 | 7.2.2.2 Lubrication plan K2-1570.2100A-2 | 00 | 2018-07-08 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-14 08:39 | IFI | OB | 100%
133698 | I491TM05-0CHEU06-003-001 | 7.2.2.3 Head girder K2-1570.2300A-3 | 00 | 2018-07-08 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-14 08:39 | IFI | OB | 100%
133697 | I491TM05-0CHEU06-004-001 | 7.2.2.4 Main girder K2-1570.2200A-3 | 00 | 2018-07-08 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-14 08:39 | IFI | OB | 100%
133696 | I491TM05-0CHEU06-005-001 | 7.2.2.5 Crane K2-1570.2100A-3 | 00 | 2018-07-08 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-14 08:39 | IFI | OB | 100%
133728 | I491TM05-0CHEU06-006-001 | 7.2.2.6 Currency collector platform K2-1570.2700A-3 | 00 | 2018-07-08 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-14 09:59 | IFI | OB | 100%
133727 | I491TM05-0CHEU06-007-001 | 7.2.2.7 Trolley K2-1570.3200A-3 | 00 | 2018-07-08 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-14 09:59 | IFI | OB | 100%
133726 | I491TM05-0CHEU06-008-001 | 7.2.2.8 Trolley 28t translation K2-1570.3100A-3 | 00 | 2018-07-08 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-14 09:59 | IFI | OB | 100%
133725 | I491TM05-0CHEU06-009-001 | 7.2.2.9 Main hoist 28t K2-1570.3700B-3 | 00 | 2018-07-08 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-14 09:59 | IFI | OB | 100%
133724 | I491TM05-0CHEU06-010-001 | 7.2.2.10 Auxiliary hoist 5t K2-1570.3900A-3 | 00 | 2018-07-08 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-14 09:59 | IFI | OB | 100%
133723 | I491TM05-0CHEU06-011-001 | 7.2.2.11 Magnet traverse K2-1570.3600A-3 | 00 | 2018-07-08 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-14 09:59 | IFI | OB | 100%
133737 | I491TM05-0CHEU07-001-001 | 7.2.2.1 Lifting and attachement points K2-1570.4000A-1 | 00 | 2018-07-08 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-14 10:00 | IFI | OB | 100%
133736 | I491TM05-0CHEU07-002-001 | 7.2.2.2 Lubrication plan K2-1570.4000A-2 | 00 | 2018-07-08 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-14 10:00 | IFI | OB | 100%
133735 | I491TM05-0CHEU07-003-001 | 7.2.2.3 Head girder K2-1570.4300A-3 | 00 | 2018-07-08 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-14 10:00 | IFI | OB | 100%
133734 | I491TM05-0CHEU07-004-001 | 7.2.2.4 Main girder K2-1570.4200A-3 | 00 | 2018-07-08 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-14 10:00 | IFI | OB | 100%
133733 | I491TM05-0CHEU07-005-001 | 7.2.2.5 Crane K2-1570.4000A-3 | 00 | 2018-07-08 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-14 10:00 | IFI | OB | 100%
133732 | I491TM05-0CHEU07-006-001 | 7.2.2.6 Currency collector platform K2-1570.4370B-3 | 00 | 2018-07-08 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-14 10:00 | IFI | OB | 100%
133731 | I491TM05-0CHEU07-007-001 | 7.2.2.7 Trolley 20t K2-1570.4700A-3 | 00 | 2018-07-08 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-14 10:00 | IFI | OB | 100%
133730 | I491TM05-0CHEU07-008-001 | 7.2.2.8 Hoist K2-1570.5000A-3 | 00 | 2018-07-08 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-14 10:00 | IFI | OB | 100%
133729 | I491TM05-0CHEU07-009-001 | 7.2.2.9 Hook block K2-1570.5100A-3 | 00 | 2018-07-08 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-14 10:00 | IFI | OB | 100%
133744 | I491TM05-0CHEU08-001-001 | 7.2.2.1 Lifting and attachement points K2-1570.4100A-1 | 00 | 2018-07-08 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-14 10:01 | IFI | OB | 100%
133743 | I491TM05-0CHEU08-002-001 | 7.2.2.2 Lubrication plan K2-1570.4100A-2 | 00 | 2018-07-08 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-14 10:01 | IFI | OB | 100%
133742 | I491TM05-0CHEU08-003-001 | 7.2.2.3 Head girder K2-1570.4300A-3 | 00 | 2018-07-08 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-14 10:01 | IFI | OB | 100%
133741 | I491TM05-0CHEU08-004-001 | 7.2.2.4 Main girder K2-1570.4200A-3 | 00 | 2018-07-08 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-14 10:01 | IFI | OB | 100%
133740 | I491TM05-0CHEU08-005-001 | 7.2.2.5 Crane K2-1570.4100A-3 | 00 | 2018-07-08 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-14 10:01 | IFI | OB | 100%
133739 | I491TM05-0CHEU08-006-001 | 7.2.2.6 Currency collector platform K2-1570.4370B-3 | 00 | 2018-07-08 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-14 10:01 | IFI | OB | 100%
133738 | I491TM05-0CHEU08-007-001 | 7.2.2.7 Trolley K2-1570.6000A-3 | 00 | 2018-07-08 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-14 10:01 | IFI | OB | 100%
133762 | I491TM05-0CHEU08-008-001 | 7.2.2.8 Hoist K2-1570.5000A-3 | 00 | 2018-07-08 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-14 11:23 | IFI | OB | 100%
133761 | I491TM05-0CHEU08-009-001 | 7.2.2.9 Hook block K2-1570.5100A-3 | 00 | 2018-07-08 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-14 11:23 | IFI | OB | 100%
132740 | I491TM05-0CHEU09-001-001 | GENERAL ARRANGEMENT FOR JIB CRANE 3 TON TUNDISH PREPARATION | 00 | 2018-01-17 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Civil and Steel Structure | TAM | 2018-02-01 10:41 | IFI | OB | 100%
133119 | I491TM05-0CHEU10-001-001 | Assembly Drawing K2-1567.5400A | 00 | 2018-05-08 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | TAM | 2018-05-14 14:01 | IFI | OB | 100%
133120 | I491TM05-0CHEU10-010-001 | Similary DIN 15407 K2-15675480C | 00 | 2018-05-08 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | TAM | 2018-05-14 14:01 | IFI | OB | 100%
134440 | I491TM05-0CHEU11-001-001 | GENERAL ARRANGEMENT FOR JIB CRANE 5TON LADLE COVER | 00 | 2018-11-28 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | TAM | 2018-12-01 10:33 | IFI | OB | 100%
134460 | I491TM05-0CHEU12-001-001 | GA SEDIMITATION CRANE-P1 | 00 | 2018-12-02 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | TAM | 2018-12-08 09:22 | IFI | OB | 100%
16034 | I491TM05-0CPCP01-001-003 | Outline Drawing For Air Compressor plant | 01 | 2013-05-25 | Indeterminate | Drawing | Detail | Compressed Air Production Plant | Piping & Utility | HAVAYAR |  | IFC | AFC | 100%
16038 | I491TM05-0CPDR01-001-003 | Outline Drawings For Air Dryer (Act-900)Plant For Compressed Air Plant | 01 | 2013-05-25 | Indeterminate | Drawing | Detail | Compressed Air Production Plant | Piping & Utility | HAVAYAR |  | IFC | AFC | 100%
16041 | I491TM05-0CPTK01-001-003 | Outline Drawings For Air Receiver(Hy_10000) For Compressed Air Plant | 01 | 2013-05-25 | Indeterminate | Drawing | Detail | Compressed Air Production Plant | Piping & Utility | HAVAYAR |  | IFC | AFC | 100%
111638 | I491TM05-0CPTK02-001-001 | Outline Drawings for Air Receiver (HY- 10000) for compressed air plant | 00 | 2014-03-03 | Indeterminate | Drawing | Basic | Compressed Air Production Plant | Piping & Utility | TAM | 2014-04-24 14:34 | IFI | OB | 100%
16042 | I491TM05-0DTCC01-002-001 | DEDUSTING SYSTEM FOURNACE 140Ton EAF+LF & MH SETTLING CHAMBER DOOR | 00 | 2013-09-11 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | TAM |  | IFI | OB | 100%
16043 | I491TM05-0DTCC01-003-001 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH SETTLING CHAMBER : ROOF PANEL | 00 | 2013-09-11 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | TAM |  | IFI | OB | 100%
16044 | I491TM05-0DTCC01-004-001 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH SETTLING CHAMBER : ROOF PANEL | 00 | 2013-09-11 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | TAM |  | IFI | OB | 100%
16045 | I491TM05-0DTCC01-005-001 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH SETTLING CHAMBER : ROOF PANEL | 01 | 2013-09-11 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | TAM |  | IFI | OB | 100%
16046 | I491TM05-0DTCC01-006-001 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH SETTLING CHAMBER : ROOF PANEL | 01 | 2013-09-11 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | TAM |  | IFI | OB | 100%
16047 | I491TM05-0DTCC01-007-001 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH SETTLING CHAMBER : ROOF PANEL | 01 | 2013-09-11 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | TAM |  | IFI | OB | 100%
16048 | I491TM05-0DTCC01-008-001 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH SETTLING CHAMBER : ROOF PANEL | 01 | 2013-09-11 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | TAM |  | IFI | OB | 100%
16049 | I491TM05-0DTCC01-009-001 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH SETTLING CHAMBER : ROOF PANEL | 01 | 2013-09-11 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | TAM |  | IFI | OB | 100%
115228 | I491TM05-0DTCP01-006-001 | FAN TYPE: 35L-142-710 SWSI General assembly & foundation dwg | 00 | 2016-05-07 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2016-05-14 10:14 | IFI | OB | 100%
113392 | I491TM05-0DTCP01-007-001 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH FAN HOUSING AND INLET BOX DRAWING WITH DETAILS 1-2 | 00 | 2015-02-21 15:08 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2015-02-21 15:08 | IFI | OB | 100%
113393 | I491TM05-0DTCP01-007-002 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH FAN HOUSING AND INLET BOX DRAWING WITH DETAILS 2-2 | 00 | 2015-02-21 15:08 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | TAM | 2015-02-21 15:08 | IFI | OB | 100%
113394 | I491TM05-0DTCP01-008-001 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH FAN HOUSING AND INLET BOX DRAWING WITH DETAILS 1-2 | 00 | 2015-02-21 15:08 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2015-02-21 15:08 | IFI | OB | 100%
113395 | I491TM05-0DTCP01-008-002 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH FAN HOUSING AND INLET BOX DRAWING WITH DETAILS 2-2 | 00 | 2015-02-21 15:08 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | TAM | 2015-02-21 15:08 | IFI | OB | 100%
113396 | I491TM05-0DTCP01-010-001 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH FAN CASING 1-2 | 00 | 2015-02-21 15:09 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2015-02-21 15:09 | IFI | OB | 100%
113397 | I491TM05-0DTCP01-010-002 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH FAN CASING 2-2 | 00 | 2015-02-21 15:09 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | TAM | 2015-02-21 15:09 | IFI | OB | 100%
113398 | I491TM05-0DTCP01-013-001 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH ELECTRIC MOTOR BASEFRAME AND FIXED SUPPORT PEDESTAL | 00 | 2015-02-21 15:09 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | TAM | 2015-02-21 15:09 | IFI | OB | 100%
113399 | I491TM05-0DTCP01-014-001 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH FREE SUPPORT PEDESTAL AND SOLEPLATE | 00 | 2015-02-21 15:09 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | TAM | 2015-02-21 15:09 | IFI | OB | 100%
113400 | I491TM05-0DTCP01-015-001 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH FOUNDATION BOLTS | 00 | 2015-02-21 15:10 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | TAM | 2015-02-21 15:10 | IFI | OB | 100%
113401 | I491TM05-0DTCP01-016-001 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH ELECTRIC MOTOR BASEFRAME AND FIXED SUPPORT PEDESTAL | 00 | 2015-02-21 15:10 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | TAM | 2015-02-21 15:10 | IFI | OB | 100%
113402 | I491TM05-0DTCP01-017-001 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH FREE SUPPORT PEDESTAL AND SOLEPLATE | 00 | 2015-02-21 15:11 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | TAM | 2015-02-21 15:11 | IFI | OB | 100%
113403 | I491TM05-0DTCP01-018-001 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH FOUNDATION BOLTS | 00 | 2015-02-21 15:11 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | TAM | 2015-02-21 15:11 | IFI | OB | 100%
113404 | I491TM05-0DTCP01-019-001 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH ELECTRIC MOTOR BASEFRAME AND SUPPORTS PEDESTAL | 00 | 2015-02-21 15:11 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | TAM | 2015-02-21 15:11 | IFI | OB | 100%
113405 | I491TM05-0DTCP01-020-001 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH FOUNDATION BOLTS | 00 | 2015-02-21 15:11 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | TAM | 2015-02-21 15:11 | IFI | OB | 100%
115216 | I491TM05-0DTCP01-022-001 | FAN TYPE: 45L-630 SWSI General assembly & foundation dwg | 00 | 2016-05-07 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2016-05-14 10:12 | IFI | OB | 100%
115229 | I491TM05-0DTCP01-026-001 | Fan tpye : 35L-142/710 SWSI Inlet flexible connection | 00 | 2016-05-07 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2016-05-14 10:14 | IFI | OB | 100%
115230 | I491TM05-0DTCP01-027-001 | Fan type : 35L-142/710 SWSI Outlet flexible connection | 00 | 2016-05-07 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2016-05-14 10:15 | IFI | OB | 100%
115231 | I491TM05-0DTCP01-033-001 | Fan type : 35L-142/710 SWSI Belt guard | 00 | 2016-05-07 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2016-05-14 10:15 | IFI | OB | 100%
115232 | I491TM05-0DTCP01-034-001 | Fan type : 35L-142/710 SWSI Inlet cone | 00 | 2016-05-07 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2016-05-14 10:15 | IFI | OB | 100%
115233 | I491TM05-0DTCP01-035-001 | Fan type : 35L-142/710 SWSI Pedestal | 00 | 2016-05-07 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2016-05-14 10:15 | IFI | OB | 100%
115234 | I491TM05-0DTCP01-036-001 | Fan type : 35L-142/710 SWSI Shaft guard | 00 | 2016-05-07 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2016-05-14 10:15 | IFI | OB | 100%
115217 | I491TM05-0DTCP01-038-001 | Fan type : 45L-142/630 SWSI Belt guard | 00 | 2016-05-07 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2016-05-14 10:12 | IFI | OB | 100%
115218 | I491TM05-0DTCP01-039-001 | Fan type : 45L-142/630 SWSI Inlet cone | 00 | 2016-05-07 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2016-05-14 10:12 | IFI | OB | 100%
115219 | I491TM05-0DTCP01-040-001 | Fan type : 45L-142/630 SWSI Pedestal | 00 | 2016-05-07 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2016-05-14 10:12 | IFI | OB | 100%
115220 | I491TM05-0DTCP01-041-001 | Fan type : 45L-142/630 SWSI Shaft guard | 00 | 2016-05-07 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2016-05-14 10:12 | IFI | OB | 100%
115221 | I491TM05-0DTCP01-043-001 | Ventilatore tipo :35L-142/710 SWSI Assieme regolatore di portata | 00 | 2016-05-07 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2016-05-14 10:12 | IFI | OB | 100%
115235 | I491TM05-0DTCP01-044-001 | Fan type : 35L-142/710 SWSI Baseframe | 00 | 2016-05-07 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2016-05-14 10:16 | IFI | OB | 100%
115245 | I491TM05-0DTCP01-045-001 | Ventilatore tipo :45L-142/630 SWSI Assieme regolatore di portata | 00 | 2016-05-07 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2016-05-14 15:28 | IFI | OB | 100%
115222 | I491TM05-0DTCP01-046-001 | Fan type : 45L-142/630 SWSI Baseframe | 00 | 2016-05-07 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2016-05-14 10:12 | IFI | OB | 100%
115224 | I491TM05-0DTCP01-047-001 | Fan type : 45L-142/630 SWSI ASSEMBLY WITH PART LIST | 00 | 2016-05-07 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2016-05-14 10:13 | IFI | OB | 100%
115225 | I491TM05-0DTCP01-049-001 | Fan type : 45L-142/630 SWSI CASING | 00 | 2016-05-07 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2016-05-14 10:13 | IFI | OB | 100%
115223 | I491TM05-0DTCP01-050-001 | Fan type : 45L-142/630 SWSI VIBRATION SENSOR PLATE | 00 | 2016-05-07 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2016-05-14 10:12 | IFI | OB | 100%
115236 | I491TM05-0DTCP01-051-001 | FAN TYPE : 35L-142/710 SWSI ASSEMBLY WITH PART LIST | 00 | 2016-05-07 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2016-05-14 10:16 | IFI | OB | 100%
115237 | I491TM05-0DTCP01-053-001 | FAN TYPE : 35L-142/710 SWSI CASING | 00 | 2016-05-07 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2016-05-14 10:16 | IFI | OB | 100%
115238 | I491TM05-0DTCP01-054-001 | Fan type : 35L-142/710 SWSI VIBRATION SENSOR PLATE | 00 | 2016-05-07 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2016-05-14 10:16 | IFI | OB | 100%
130304 | I491TM05-0DTCP01-055-001 | Ass.part-list.BOOSTER.Prim.Duct_FDP003 CF003 | 00 | 2017-02-07 10:50 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | TAM | 2017-02-07 10:50 | IFI | OB | 100%
130305 | I491TM05-0DTCP01-056-001 | Ass.part-list.LF.BOOSTER_FDP004 CF002 | 00 | 2017-02-07 10:50 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | TAM | 2017-02-07 10:50 | IFI | OB | 100%
130306 | I491TM05-0DTCP01-057-001 | Ass.part-list.MAIN.FAN_FDP12.13.14.15 CF001 | 00 | 2017-02-07 10:50 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | TAM | 2017-02-07 10:50 | IFI | OB | 100%
113406 | I491TM05-0DTCV01-003-001 | Dust Transport - Filter - Manual Coulisse Dampers | 00 | 2015-02-21 15:11 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2015-02-21 15:11 | IFI | OB | 100%
113407 | I491TM05-0DTCV01-004-001 | Dust Transport - Filter - Chain Conveyors | 00 | 2015-02-21 15:11 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2015-02-21 15:11 | IFI | OB | 100%
113408 | I491TM05-0DTCV01-005-001 | Dust Transport - Filter - Rotary valve | 00 | 2015-02-21 15:12 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2015-02-21 15:12 | IFI | OB | 100%
113409 | I491TM05-0DTCV01-006-001 | Dust Transport - Filter to Buket Elevator - Trasversal Chain Conveyor | 00 | 2015-02-21 15:12 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2015-02-21 15:12 | IFI | OB | 100%
113410 | I491TM05-0DTCV01-007-001 | Dust Transport - Silo - Buket Elevator | 00 | 2015-02-21 15:12 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2015-02-21 15:12 | IFI | OB | 100%
113411 | I491TM05-0DTCV01-008-001 | Dust Transport - Silo - Screw Conveyor | 00 | 2015-02-21 15:20 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2015-02-21 15:20 | IFI | OB | 100%
113412 | I491TM05-0DTCV01-009-001 | Dust Transport - Silo - Manual Coulisse damper | 00 | 2015-02-21 15:20 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2015-02-21 15:20 | IFI | OB | 100%
113413 | I491TM05-0DTCV01-010-001 | Dust Transport - Silo - Pneumatic Coulisse Damper | 00 | 2015-02-21 15:21 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2015-02-21 15:21 | IFI | OB | 100%
113414 | I491TM05-0DTCV01-011-001 | Dust Transport - Silo - Rotory valve | 00 | 2015-02-21 15:21 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2015-02-21 15:21 | IFI | OB | 100%
113415 | I491TM05-0DTCV01-012-001 | Dust Transport - Silo - Telescopic Bellow | 00 | 2015-02-21 15:21 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2015-02-21 15:21 | IFI | OB | 100%
16050 | I491TM05-0DTCV01-013-001 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH DUST TRANSPORT- HAIRPING COOLER - CHAIN CONVEYORS | 00 | 2013-09-11 | Indeterminate | Drawing | Basic | Fume Treatment Equipment | Mechanical | HASCON |  | IFI | OB | 100%
16051 | I491TM05-0DTCV01-014-001 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH DUST TRANSPORT - HAIRPIN COOLER - ROTARY FEEDER | 00 | 2013-09-11 | Indeterminate | Drawing | Basic | Fume Treatment Equipment | Mechanical | HASCON |  | IFI | OB | 100%
16052 | I491TM05-0DTCV01-015-001 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH DUST TRANSPORT- HAIRPING COOLER - TRANSVERSAL CHAIN CONVEYORS | 00 | 2013-09-11 | Indeterminate | Drawing | Basic | Fume Treatment Equipment | Mechanical | HASCON |  | IFI | OB | 100%
16053 | I491TM05-0DTCV01-016-001 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH DUST TRANSPORT - MIXING CHAMBER - ROTARY FEEDERS | 00 | 2013-09-11 | Indeterminate | Drawing | Basic | Fume Treatment Equipment | Mechanical | HASCON |  | IFI | OB | 100%
16054 | I491TM05-0DTCV01-017-001 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH DUST TRANSPORT- MIXING CHAMBER-CHAIN CONVEYOR | 00 | 2013-09-11 | Indeterminate | Drawing | Basic | Fume Treatment Equipment | Mechanical | HASCON |  | IFI | OB | 100%
16055 | I491TM05-0DTCV01-018-001 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH DUST TRANSPORT - MIXING CHAMBER - MANUAL COULISSE DAMPER | 00 | 2013-09-11 | Indeterminate | Drawing | Basic | Fume Treatment Equipment | Mechanical | HASCON |  | IFI | OB | 100%
16056 | I491TM05-0DTCV01-019-001 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH DUST TRANSPORT - HORIZONTAL CYCLON - ROTARY FEEDER | 00 | 2013-09-11 | Indeterminate | Drawing | Basic | Fume Treatment Equipment | Mechanical | HASCON |  | IFI | OB | 100%
113416 | I491TM05-0DTCV01-020-001 | Dust Transport - DRI - Screw Conveyor | 00 | 2015-02-21 15:22 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2015-02-21 15:22 | IFI | OB | 100%
113417 | I491TM05-0DTCV01-021-001 | Dust Transport - DRI - Rotary valve | 00 | 2015-02-21 15:22 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2015-02-21 15:22 | IFI | OB | 100%
134375 | I491TM05-0DTCV01-022-001 | Dust Transport - Bin Activator | 00 | 2018-11-13 10:18 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2018-11-13 10:18 | IFI | OB | 100%
113418 | I491TM05-0DTCV01-023-001 | Dust Transport - Silo's accessories | 00 | 2015-02-21 15:22 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2015-02-21 15:22 | IFI | OB | 100%
113419 | I491TM05-0DTCV01-024-001 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH DUST TRANSPORT - CYCLON-MANUAL COULISSE DAMPER | 00 | 2015-02-21 15:22 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | TAM | 2015-02-21 15:22 | IFI | OB | 100%
113420 | I491TM05-0DTCV01-025-001 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH DUST TRANSPORT -DRI-PNEUMATIC COULISSE DAMPER | 00 | 2015-02-21 15:22 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | TAM | 2015-02-21 15:22 | IFI | OB | 100%
115375 | I491TM05-0DTCV13-001-001 | Dedusting System Faurnace 140 Ton Eaf+Lf & mh Dust Transport - Hairping Cooler- Chain Conveyors | 00 | 2016-05-24 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | TAM | 2016-05-25 10:29 | IFI | OB | 100%
115376 | I491TM05-0DTCV15-001-001 | Dedusting System Faurnace 140 Ton Eaf+Lf & mh Dust Transport - Hairping Cooler- Chain Conveyors | 00 | 2016-05-24 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | TAM | 2016-05-25 10:29 | IFI | OB | 100%
115377 | I491TM05-0DTCV17-001-001 | Dedusting System Faurnace 140 Ton Eaf+Lf & mh Dust Transport - Mixing Chamber- Chain Conveyors | 00 | 2016-05-24 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | TAM | 2016-05-25 10:29 | IFI | OB | 100%
115227 | I491TM05-0DTCY01-002-001 | DEDUSTING SYSTEM FOURNACE 140Ton EAF+LF & MH ORIZZONTAL CYCLON - CONSTRUCTION | 00 | 2016-05-07 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2016-05-14 10:13 | IFI | OB | 100%
113421 | I491TM05-0DTDE05-001-001 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH MHS-GENERAL ASSEMBLY EAF | 00 | 2015-02-21 15:51 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2015-02-21 15:51 | IFI | OB | 100%
113422 | I491TM05-0DTDE05-002-001 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH MHS-GENERAL ASSEMBLY LF | 00 | 2015-02-21 15:52 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2015-02-21 15:52 | IFI | OB | 100%
113423 | I491TM05-0DTDE05-003-001 | MHS- Receiving Area - Routing | 00 | 2015-02-21 15:52 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2015-02-21 15:52 | IFI | OB | 100%
113424 | I491TM05-0DTDE05-004-001 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH MHS-GENERAL ASSEMBLY DRI | 00 | 2015-02-21 15:53 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2015-02-21 15:53 | IFI | OB | 100%
129974 | I491TM05-0DTDE05-019-001 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH DUCT FROM EAF AREA TO SECONDARY DUCT-ASSEMBLY 1-3 | 00 | 2016-12-13 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2016-12-20 09:42 | IFI | OB | 100%
129981 | I491TM05-0DTDE05-019-002 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH DUCT FROM EAF AREA TO SECONDARY DUCT-DETAILS 2-3 | 00 | 2016-12-13 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2016-12-20 09:42 | IFI | OB | 100%
129975 | I491TM05-0DTDE05-019-003 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH DUCT FROM EAF AREA TO SECONDARY DUCT-DETAILS 3-3 | 00 | 2016-12-13 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2016-12-20 09:42 | IFI | OB | 100%
129976 | I491TM05-0DTDE05-020-001 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH DUCT FROM RECEIVING AREA TO SECONDARY DUCT-ASSEMBLY 1-2 | 00 | 2016-12-13 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2016-12-20 09:42 | IFI | OB | 100%
129977 | I491TM05-0DTDE05-020-002 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH DUCT FROM RECEIVING AREA TO SECONDARY DUCT-DETAILS 2-2 | 00 | 2016-12-13 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2016-12-20 09:42 | IFI | OB | 100%
129978 | I491TM05-0DTDE05-021-001 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH DUCT FROM LF AREA TO SECONDARY DUCT-ASSEMBLY 1-3 | 00 | 2016-12-13 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2016-12-20 09:42 | IFI | OB | 100%
129979 | I491TM05-0DTDE05-021-002 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH DUCT FROM LF AREA TO SECONDARY DUCT-DETAILS 2-3 | 00 | 2016-12-13 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2016-12-20 09:42 | IFI | OB | 100%
129980 | I491TM05-0DTDE05-021-003 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH DUCT FROM LF AREA TO SECONDARY DUCT DETAILS 3-3 | 00 | 2016-12-13 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2016-12-20 09:42 | IFI | OB | 100%
16057 | I491TM05-0DTDE08-001-001 | DEDUSTING SYSTEM FOURNACE 140Ton EAF+LF & MH DAMPER %%c2700 - ASSEMBLY | 00 | 2013-09-11 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON |  | IFI | OB | 100%
16058 | I491TM05-0DTDE08-002-001 | DEDUSTING SYSTEM FOURNACE 140Ton EAF+LF & MH DAMPER %%c3100 - ASSEMBLY | 00 | 2013-09-11 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON |  | IFI | OB | 100%
16059 | I491TM05-0DTDE08-003-001 | DEDUSTING SYSTEM FOURNACE 140Ton EAF+LF & MH DAMPER %%c3300 - ASSEMBLY | 00 | 2013-09-11 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON |  | IFI | OB | 100%
16060 | I491TM05-0DTDE08-004-001 | DEDUSTING SYSTEM FOURNACE 140Ton EAF+LF & MH DAMPER 1400x1400 - ASSEMBLY | 00 | 2013-09-11 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON |  | IFI | OB | 100%
16061 | I491TM05-0DTDE08-005-001 | DEDUSTING SYSTEM FOURNACE 140Ton EAF+LF & MH DAMPER 800x800 - ASSEMBLY | 00 | 2013-09-11 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON |  | IFI | OB | 100%
112330 | I491TM05-0DTFB01-001-001 | DEDUSTING SYSTEM FOURNACE 140Ton EAF+LF & MH WCD STRUCTURE SUPPORT (POS.15) ASSEMBLY | 00 | 2014-06-01 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | TAM | 2014-06-07 09:52 | IFI | OB | 100%
15778 | I491TM05-0DTFL02-001-003 | Dedusting System Furnace 140 Ton Eaf+Lf & Mh Bag Filter - Lateral Hopper Construction | 03 | 2013-06-01 | Indeterminate | Drawing | Basic | Fume Treatment Equipment | Mechanical | HASCON |  | IFC | AFC | 100%
15782 | I491TM05-0DTFL02-002-003 | Dedusting System Furnace 140 Ton Eaf+Lf & Mh Bag Filter - Lateral Hopper Construction | 03 | 2013-06-01 | Indeterminate | Drawing | Basic | Fume Treatment Equipment | Mechanical | HASCON |  | IFC | AFC | 100%
15786 | I491TM05-0DTFL02-003-003 | Dedusting System Furnace 140 Ton Eaf+Lf & Mh Bag Filter - Lateral Hopper Construction | 03 | 2013-06-01 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON |  | IFC | AFC | 100%
15790 | I491TM05-0DTFL02-004-003 | Dedusting System Furnace 140 Ton Eaf+Lf & Mh Bag Filter - Lateral Hopper Construction | 03 | 2013-06-01 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON |  | IFC | AFC | 100%
15794 | I491TM05-0DTFL02-005-003 | Dedusting System Furnace 140 Ton Eaf+Lf & Mh Bag Filter - Hopper Support Detail Construction | 01 | 2013-06-01 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON |  | IFC | AFC | 100%
15798 | I491TM05-0DTFL02-006-003 | Dedusting System Furnace 140 Ton Eaf+Lf & Mh Bag Filter - Esternal Panels Construction | 02 | 2013-06-01 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON |  | IFC | AFC | 100%
15802 | I491TM05-0DTFL02-007-003 | Dedusting System Furnace 140 Ton Eaf+Lf & Mh Bag Filter - Esternal Panels Construction | 02 | 2013-06-01 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON |  | IFC | AFC | 100%
15806 | I491TM05-0DTFL02-008-003 | Dedusting System Furnace 140 Ton Eaf+Lf & Mh Bag Filter - Inlet/Outlet Panels Construction | 02 | 2013-06-01 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON |  | IFC | AFC | 100%
15810 | I491TM05-0DTFL02-009-003 | Dedusting System Furnace 140 Ton Eaf+Lf & Mh Bag Filter - Internal Panels Construction | 02 | 2013-06-01 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON |  | IFC | AFC | 100%
15814 | I491TM05-0DTFL02-010-003 | Dedusting System Furnace 140 Ton Eaf+Lf & Mh Bag Filter - Internal Panels Construction | 02 | 2013-06-01 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON |  | IFC | AFC | 100%
15818 | I491TM05-0DTFL02-011-003 | Dedusting System Furnace 140 Ton Eaf+Lf & Mh Bag Filter - Internal Panels Construction | 02 | 2013-06-01 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON |  | IFC | AFC | 100%
15822 | I491TM05-0DTFL02-012-003 | Dedusting System Furnace 140 Ton Eaf+Lf & Mh Bag Filter - Central Tunnel | 02 | 2013-06-01 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON |  | IFC | AFC | 100%
15826 | I491TM05-0DTFL02-013-003 | Dedusting System Furnace 140 Ton Eaf+Lf & Mh Bag Filter - Inlet Filter Damper Detail | 02 | 2013-06-01 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON |  | IFC | AFC | 100%
15830 | I491TM05-0DTFL02-014-003 | Dedusting System Furnace 140 Ton Eaf+Lf & Mh Bag Filter - Inlet/Outlet Panels Construction | 02 | 2013-06-01 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON |  | IFC | AFC | 100%
15834 | I491TM05-0DTFL02-015-003 | Dedusting System Furnace 140 Ton Eaf+Lf & Mh Bag Filter - Central Tunnel | 02 | 2013-06-01 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON |  | IFC | AFC | 100%
15837 | I491TM05-0DTFL03-010-002 | Dedusting System Fournace 140 Ton Eaf+Lf & Mh Bag Filter - Inspection Door ∅600 | 01 | 2013-06-01 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | TAM |  | IFC | AFC | 100%
134376 | I491TM05-0DTFL03-024-001 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH MAIN BAG FILTER - CAGE 6519-F53 | 00 | 2018-11-13 10:18 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | TAM | 2018-11-13 10:18 | IFI | OB | 100%
115226 | I491TM05-0DTFL05-001-001 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH BAG FILTER STRUCTURE ASSEMBLY | 00 | 2016-05-07 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2016-05-14 10:13 | IFI | OB | 100%
16062 | I491TM05-0DTFL06-003-001 | Dedusting System Furnace 140 Ton Eaf+Lf & Mh Stair For Bag Filter & Silo - Details | 00 | 2013-05-06 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | TAM |  | IFA | AFC | 100%
16063 | I491TM05-0DTFL06-003-002 | Dedusting System Furnace 140 Ton Eaf+Lf & Mh Stair For Bag Filter & Silo - Details | 00 | 2013-05-06 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | TAM |  | IFA | AFC | 100%
16064 | I491TM05-0DTFL06-003-003 | Dedusting System Furnace 140 Ton Eaf+Lf & Mh Stair For Bag Filter & Silo - Details | 00 | 2013-05-06 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | TAM |  | IFA | AFC | 100%
112653 | I491TM05-0DTFL07-010-001 | DEDUSTING SYSTEM FOURNACE 140Ton EAF+LF & MH DRI FILTER - PANELS 1-2 | 00 | 2014-08-09 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | TAM | 2014-08-18 09:00 | IFI | OB | 100%
112652 | I491TM05-0DTFL07-010-002 | DEDUSTING SYSTEM FOURNACE 140Ton EAF+LF & MH DRI FILTER - PANELS 2-2 | 00 | 2014-08-09 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | TAM | 2014-08-18 09:00 | IFI | OB | 100%
112654 | I491TM05-0DTFL07-012-001 | DEDUSTING SYSTEM FOURNACE 140Ton EAF+LF & MH DRI FILTER - FRAME PROTECTION | 00 | 2014-08-09 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2014-08-18 09:00 | IFI | OB | 100%
112655 | I491TM05-0DTFL07-013-001 | DEDUSTING SYSTEM FOURNACE 140Ton EAF+LF & MH DRI FILTER TIE RODS INSIDE CELLS | 00 | 2014-08-09 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2014-08-18 09:01 | IFI | OB | 100%
112656 | I491TM05-0DTFL07-014-001 | DEDUSTING SYSTEM FOURNACE 140Ton EAF+LF & MH DRI FILTER LADDER | 00 | 2014-08-09 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2014-08-18 09:01 | IFI | OB | 100%
112657 | I491TM05-0DTFL07-015-001 | DEDUSTING SYSTEM FOURNACE 140Ton EAF+LF & MH DRI FILTER HANDRAIL | 00 | 2014-08-09 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2014-08-18 09:01 | IFI | OB | 100%
112658 | I491TM05-0DTFL07-016-001 | DEDUSTING SYSTEM FOURNACE 140Ton EAF+LF & MH DRI FILTER HATCH %%c400 | 00 | 2014-08-09 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2014-08-18 09:02 | IFI | OB | 100%
112659 | I491TM05-0DTFL07-017-001 | DEDUSTING SYSTEM FOURNACE 140Ton EAF+LF & MH DRI FILTER HOPPER | 00 | 2014-08-09 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2014-08-18 09:02 | IFI | OB | 100%
112660 | I491TM05-0DTFL07-019-001 | DEDUSTING SYSTEM FOURNACE 140Ton EAF+LF & MH DRI FILTER CARTRIDGE | 00 | 2014-08-09 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2014-08-18 09:03 | IFI | OB | 100%
112661 | I491TM05-0DTFL07-020-001 | DEDUSTING SYSTEM FOURNACE 140Ton EAF+LF & MH DRI FILTER BIG BAG SYSTEM | 00 | 2014-08-09 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2014-08-18 09:04 | IFI | OB | 100%
112662 | I491TM05-0DTFL07-021-001 | DEDUSTING SYSTEM FOURNACE 140Ton EAF+LF & MH DRI FILTER PENTHOUSE | 00 | 2014-08-09 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2014-08-18 09:04 | IFI | OB | 100%
134377 | I491TM05-0DTFL07-022-001 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH MAIN DRI FILTER - CAGE 6519-F124 | 00 | 2018-11-13 10:18 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | TAM | 2018-11-13 10:18 | IFI | OB | 100%
112341 | I491TM05-0DTPP02-021-001 | DEDUSTING SYSTEM FOURNACE 140Ton EAF+LF & MH ASSEMBLY SUPPORT STRUCTURE WCD T1 | 00 | 2014-06-01 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | HASCON | 2014-06-07 10:29 | IFI | OB | 100%
112342 | I491TM05-0DTPP02-028-001 | DEDUSTING SYSTEM FOURNACE 140Ton EAF+LF & MH ASSEMBLY STRUCTURE SUPPORT WCD-T5 | 00 | 2014-06-01 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | HASCON | 2014-06-07 10:29 | IFI | OB | 100%
16065 | I491TM05-0DTPP05-001-001 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH DUCT FROM CANOPY TO MIXING CHAMBER "Y" ø 3300 | 00 | 2013-09-11 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON |  | IFI | OB | 100%
111934 | I491TM05-0DTPP05-001-002 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH DUCT FROM CANOPY TO MIXING CHAMBER ø 4600 | 00 | 2013-09-11 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2014-05-08 11:11 | IFI | OB | 100%
111948 | I491TM05-0DTPP05-001-003 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH DUCT FROM CANOPY TO MIXING CHAMBER ø 5000 | 00 | 2013-09-11 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2014-05-08 11:40 | IFI | OB | 100%
111949 | I491TM05-0DTPP05-001-004 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH DUCT FROM CANOPY TO MIXING CHAMBER ø 5000 | 00 | 2013-09-11 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2014-05-08 11:40 | IFI | OB | 100%
111950 | I491TM05-0DTPP05-001-005 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH DUCT - INSPECTION DOOR | 00 | 2013-09-11 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2014-05-08 11:40 | IFI | OB | 100%
111951 | I491TM05-0DTPP05-001-006 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH DUCT FROM WCD TO HAIRPIN COOLER ø3100 Aisi+Iracore1 | 00 | 2013-09-11 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2014-05-08 11:40 | IFI | OB | 100%
111952 | I491TM05-0DTPP05-001-007 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH DUCT FROM WCD TO HAIRPIN COOLER ø3100 Iracore1 | 00 | 2013-09-11 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2014-05-08 11:40 | IFI | OB | 100%
111953 | I491TM05-0DTPP05-001-008 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH DUCT Saddle ø5000 | 00 | 2013-09-11 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2014-05-08 11:40 | IFI | OB | 100%
111954 | I491TM05-0DTPP05-001-009 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH DUCT Saddle ø3100 | 00 | 2013-09-11 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2014-05-08 11:40 | IFI | OB | 100%
112915 | I491TM05-0DTPP05-001-010 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH DUCT FROM HAIRPIN COOLER BY-PASS ø2700 | 01 | 2014-09-21 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2014-09-22 09:49 | IFI | OB | 100%
111956 | I491TM05-0DTPP05-001-011 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH DUCT Saddle ø2700 | 00 | 2013-09-11 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2014-05-08 11:40 | IFI | OB | 100%
111957 | I491TM05-0DTPP05-001-012 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH DUCT Saddle ø3300 + ø4600 | 00 | 2013-09-11 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2014-05-08 11:40 | IFI | OB | 100%
111958 | I491TM05-0DTPP05-001-013 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH DUCT FROM MIXING CHAMBER TO MAIN FILTERS | 00 | 2013-09-11 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2014-05-08 11:40 | IFI | OB | 100%
111959 | I491TM05-0DTPP05-001-014 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH DUCT FROM MIXING CHAMBER TO MAIN FILTERS - WALKWAY | 00 | 2013-09-11 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2014-05-08 11:40 | IFI | OB | 100%
111960 | I491TM05-0DTPP05-001-015 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH DUCT FROM MAIN FAN TO STACK | 00 | 2013-09-11 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2014-05-08 11:40 | IFI | OB | 100%
115243 | I491TM05-0DTPP05-001-016 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH DUCT FROM MAIN FAN TO STACK-DETAIL | 00 | 2016-05-07 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2016-05-14 10:16 | IFI | OB | 100%
112916 | I491TM05-0DTPP06-001-001 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH DUCT FROM LF - GENERAL ASSEMBLY | 01 | 2014-09-21 | Indeterminate | Drawing | Basic | Fume Treatment Equipment | Mechanical | HASCON | 2014-09-22 09:50 | IFI | OB | 100%
16067 | I491TM05-0DTPP06-002-001 | DEDUSTING SYSTEM FOURNACE 140Ton EAF+LF & MH DUCT FROM LF - DUCT DETAIL sheet1 | 00 | 2013-09-11 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | TAM |  | IFI | OB | 100%
16068 | I491TM05-0DTPP06-002-002 | DEDUSTING SYSTEM FOURNACE 140Ton EAF+LF & MH DUCT FROM LF - DUCT DETAIL sheet2 | 00 | 2013-09-11 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | TAM |  | IFI | OB | 100%
112919 | I491TM05-0DTPP06-003-001 | DEDUSTING SYSTEM FOURNACE 140Ton EAF+LF & MH DUCT FROM LF - DETAIL sheet1 | 01 | 2014-09-21 | Indeterminate | Drawing | Basic | Fume Treatment Equipment | Mechanical | TAM | 2014-09-22 10:16 | IFI | OB | 100%
16070 | I491TM05-0DTPP06-003-002 | DEDUSTING SYSTEM FOURNACE 140Ton EAF+LF & MH DUCT FROM LF - DETAIL sheet2 | 00 | 2013-09-11 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | TAM |  | IFI | OB | 100%
16071 | I491TM05-0DTPP06-003-003 | DEDUSTING SYSTEM FOURNACE 140Ton EAF+LF & MH DUCT FROM LF - DETAIL sheet3 | 00 | 2013-09-11 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | TAM |  | IFI | OB | 100%
16073 | I491TM05-0DTPP06-003-004 | DEDUSTING SYSTEM FOURNACE 140Ton EAF+LF & MH DUCT FROM LF - DETAIL sheet4 | 00 | 2013-09-11 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | TAM |  | IFI | OB | 100%
16074 | I491TM05-0DTPP07-001-001 | DEDUSTING SYSTEM FOURNACE 140Ton EAF+LF & MH DRI - DUCT INLET | 00 | 2013-09-11 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON |  | IFI | OB | 100%
16075 | I491TM05-0DTPP07-002-001 | DEDUSTING SYSTEM FOURNACE 140Ton EAF+LF & MH DRI - DUCT FROM DRI FILTER TO FAN | 00 | 2013-09-11 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON |  | IFI | OB | 100%
112309 | I491TM05-0DTST01-001-001 | DEDUSTING SYSTEM FOURNACE 140Ton EAF+LF & MH DUCT-FROM BAG FILTER "A-B" TO STACK (CONCRETE) | 00 | 2014-06-01 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2014-06-07 09:00 | IFI | OB | 100%
112311 | I491TM05-0DTST01-001-002 | DEDUSTING SYSTEM FOURNACE 140Ton EAF+LF & MH DUCT-FROM BAG FILTER "A-B" TO STACK (CONCRETE) | 00 | 2014-06-01 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2014-06-07 09:03 | IFI | OB | 100%
112313 | I491TM05-0DTST01-002-001 | DEDUSTING SYSTEM FOURNACE 140Ton EAF+LF & MH DUCT-FROM BAG FILTER "C-D" TO STACK (CONCRETE) | 00 | 2014-06-01 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2014-06-07 09:06 | IFI | OB | 100%
112314 | I491TM05-0DTST01-002-002 | DEDUSTING SYSTEM FOURNACE 140Ton EAF+LF & MH DUCT-FROM BAG FILTER "C-D" TO STACK (CONCRETE) | 00 | 2014-06-01 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2014-06-07 09:06 | IFI | OB | 100%
112336 | I491TM05-0DTST01-003-001 | DEDUSTING SYSTEM FOURNACE 140Ton EAF+LF & MH DUCT FROM BAG FILTER TO STACK - INSPECTION DOOR %%c600 | 00 | 2014-06-01 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2014-06-07 10:25 | IFI | OB | 100%
112338 | I491TM05-0DTST01-004-002 | DEDUSTING SYSTEM FOURNACE 140Ton EAF+LF & MH DUCT FROM STACK (CONCRETE) TO MAIN FANS POS. 3 2-2 | 00 | 2014-06-01 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2014-06-07 10:26 | IFI | OB | 100%
115244 | I491TM05-0DTST01-008-001 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH Outlet silencer inernal panel | 00 | 2016-05-07 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2016-05-14 10:17 | IFI | OB | 100%
16076 | I491TM05-0DTST01-009-001 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH STACK -ASSEMBLY | 01 | 2013-09-11 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON |  | IFI | OB | 100%
16077 | I491TM05-0DTST01-010-001 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH STACK - DETAILS | 01 | 2013-09-11 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON |  | IFI | OB | 100%
16078 | I491TM05-0DTST01-011-001 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH STACK - PLATFORM & LADDERS | 01 | 2013-09-11 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON |  | IFI | OB | 100%
16079 | I491TM05-0DTST01-012-001 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH STACK - INSPECTION DOORS 600x800 | 01 | 2013-09-11 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON |  | IFI | OB | 100%
16080 | I491TM05-0DTST01-013-001 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH STACK - INSPECTION DOORS 1300x600 | 01 | 2013-09-11 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON |  | IFI | OB | 100%
16081 | I491TM05-0DTST01-014-001 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH STACK - PLATFORM +36000 | 01 | 2013-09-11 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON |  | IFI | OB | 100%
16082 | I491TM05-0DTST01-015-001 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH STACK - HOIST | 01 | 2013-09-11 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON |  | IFI | OB | 100%
16083 | I491TM05-0DTST02-003-001 | Dedusting System Fournace 140 Ton Eaf+Lf & Mh Stair For Chimney - Details | 00 | 2013-05-06 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | TAM |  | IFA | AFC | 100%
16084 | I491TM05-0DTST02-003-002 | Dedusting System Fournace 140 Ton Eaf+Lf & Mh Stair For Chimney - Details | 00 | 2013-05-06 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | TAM |  | IFA | AFC | 100%
16085 | I491TM05-0DTST02-003-003 | Dedusting System Fournace 140 Ton Eaf+Lf & Mh Stair For Chimney - Details | 00 | 2013-05-06 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | TAM |  | IFA | AFC | 100%
112337 | I491TM05-0DTST02-004-001 | DEDUSTING SYSTEM FOURNACE 140Ton EAF+LF & MH DUCT FROM STACK (CONCRETE) TO MAIN FANS POS. 3 1-2 | 00 | 2014-06-01 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2014-06-07 10:26 | IFI | OB | 100%
112339 | I491TM05-0DTST02-005-001 | DEDUSTING SYSTEM FOURNACE 140Ton EAF+LF & MH STACK - STAIR LADDERS | 00 | 2014-06-01 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | HASCON | 2014-06-07 10:26 | IFI | OB | 100%
112340 | I491TM05-0DTST02-006-001 | DEDUSTING SYSTEM FOURNACE 140Ton EAF+LF & MH STACK - STAIR HANDRAILS + PLATFORM +17970 1-2 | 00 | 2014-06-01 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | HASCON | 2014-06-07 10:27 | IFI | OB | 100%
16086 | I491TM05-0DTST03-001-001 | DEDUSTING SYSTEM FOURNACE 140Ton EAF+LF & MH STRUCTURE SUPPORT DUCT OUT CANOPY pos.19 - ASSEMBLY | 00 | 2014-06-01 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | TAM |  | IFI | OB | 100%
16087 | I491TM05-0DTST03-002-001 | Dedusting System Fournace 140 Ton Eaf+Lf & Mh Support Duct Secondary Fume (Pos.16&17) Assembly | 00 | 2013-10-07 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | TAM |  | IFI | OB | 100%
16088 | I491TM05-0DTST03-002-002 | Dedusting System Fournace 140 Ton Eaf+Lf & Mh Support Duct Secondary Fume (Pos.16&17) Assembly | 00 | 2013-10-07 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | TAM |  | IFI | OB | 100%
16089 | I491TM05-0DTST03-002-003 | Dedusting System Fournace 140 Ton Eaf+Lf & Mh Support Duct Secondary Fume (Pos.16&17) Assembly | 00 | 2013-10-07 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | TAM |  | IFI | OB | 100%
16090 | I491TM05-0DTST03-002-004 | Dedusting System Fournace 140 Ton Eaf+Lf & Mh Support Duct Secondary Fume (Pos.16&17) Assembly | 00 | 2013-10-07 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | TAM |  | IFI | OB | 100%
16091 | I491TM05-0DTST03-002-005 | Dedusting System Fournace 140 Ton Eaf+Lf & Mh Support Duct Secondary Fume (Pos.16&17) Assembly | 00 | 2013-10-07 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | TAM |  | IFI | OB | 100%
16092 | I491TM05-0DTST03-002-006 | Dedusting System Fournace 140 Ton Eaf+Lf & Mh Support Duct Secondary Fume (Pos.16&17) Details | 00 | 2013-10-07 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | TAM |  | IFI | OB | 100%
16093 | I491TM05-0DTST03-002-007 | Dedusting System Fournace 140 Ton Eaf+Lf & Mh Support Duct Support Duct Secondary Fume (Pos.16&17) Details | 00 | 2013-10-07 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | TAM |  | IFI | OB | 100%
16094 | I491TM05-0DTST03-002-008 | Dedusting System Fournace 140 Ton Eaf+Lf & Mh Support Duct Structure Duct Secondary Fumes - Walkway | 00 | 2013-10-07 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | TAM |  | IFI | OB | 100%
16095 | I491TM05-0DTST03-002-009 | Dedusting System Fournace 140 Ton Eaf+Lf & Mh Support Duct Support Duct Secondary Fume (Pos.16&17) Assembly | 00 | 2013-10-07 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | TAM |  | IFI | OB | 100%
16096 | I491TM05-0DTST03-004-001 | Dedusting System Fournace 140 Ton Eaf+Lf & Mh Support Duct Structure Support-Duct Zone 18 | 00 | 2013-10-07 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | TAM |  | IFI | OB | 100%
16097 | I491TM05-0DTST03-004-002 | Dedusting System Fournace 140 Ton Eaf+Lf & Mh Support Duct Structure Support-Duct Zone 18 Details | 00 | 2013-10-07 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | TAM |  | IFI | OB | 100%
16098 | I491TM05-0DTST03-005-001 | Dedusting System Fournace 140 Ton Eaf+Lf & Mh Support Duct Structure Support Duct Inlet Hairpin Cooler (Pos.10)-Assembly | 00 | 2013-10-07 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | TAM |  | IFI | OB | 100%
16099 | I491TM05-0DTST03-006-001 | Dedusting System Fournace 140 Ton Eaf+Lf & Mh Support Duct Support Duct Outlet Hairpin Cooler (Pos.10) Assembly | 00 | 2013-10-07 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | TAM |  | IFI | OB | 100%
112917 | I491TM05-0DTST03-006-002 | Dedusting System Fournace 140 Ton Eaf+Lf & Mh Support Duct Outlet From Bypass To Main Booster (Pos.10) Assembly | 01 | 2014-09-21 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | TAM | 2014-09-22 09:54 | IFI | OB | 100%
16101 | I491TM05-0DTST03-007-001 | Dedusting System Fournace 140 Ton Eaf+Lf & Mh Support Duct By-Pass (Pos.20) Assembly | 00 | 2013-10-07 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | TAM |  | IFI | OB | 100%
16102 | I491TM05-0DTST03-009-001 | Dedusting System Fournace 140 Ton Eaf+Lf & Mh Dri Support Duct | 00 | 2013-10-07 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | TAM |  | IFI | OB | 100%
16103 | I491TM05-0DTST03-009-002 | Dedusting System Fournace 140 Ton Eaf+Lf & Mh Structure Support Duct Outlet Dri Filter (Pos.11) Assembly | 00 | 2013-10-07 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | TAM |  | IFI | OB | 100%
16104 | I491TM05-0DTST03-009-003 | Dedusting System Fournace 140 Ton Eaf+Lf & Mh Structure Support Duct Inlet Mixing Chamber (Pos.5) Assembly | 00 | 2013-10-07 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | TAM |  | IFI | OB | 100%
16105 | I491TM05-0DTST03-010-001 | Dedusting System Fournace 140 Ton Eaf+Lf & Mh Support Duct Outlet Mixing Chamber (Pos.5) Assembly | 00 | 2013-10-07 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | TAM |  | IFI | OB | 100%
16106 | I491TM05-0DTST03-010-002 | Dedusting System Fournace 140 Ton Eaf+Lf & Mh Support Duct Outlet Mixing Chamber (Pos.5) Stair For Mixing | 00 | 2013-10-07 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | TAM |  | IFI | OB | 100%
16107 | I491TM05-0DTST03-011-001 | Dedusting System Fournace 140 Ton Eaf+Lf & Mh Support Duct Inlet Main Filters (Pos.5) Assembly | 00 | 2013-10-07 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | TAM |  | IFI | OB | 100%
16108 | I491TM05-0DTST03-012-001 | Dedusting System Fournace 140 Ton Eaf+Lf & Mh Support Duct Outlet Main Filters (Pos.3) Assembly | 00 | 2013-10-07 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | TAM |  | IFI | OB | 100%
16109 | I491TM05-0DTST03-013-001 | Dedusting System Fournace 140 Ton Eaf+Lf & Mh Support Duct Outlet Main Filters To Concrete (Pos.3) Assembly | 00 | 2013-10-07 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | TAM |  | IFI | OB | 100%
16110 | I491TM05-0DTST03-013-002 | Dedusting System Fournace 140 Ton Eaf+Lf & Mh Support Duct From Main Filter To Silencer (Pos.3) Assembly | 00 | 2013-10-07 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | TAM |  | IFI | OB | 100%
112918 | I491TM05-0DTST03-015-001 | DEDUSTING SYSTEM FOURNACE 140Ton EAF+LF & MH DUCT FROM LF - STRUCTURE DETAIL | 01 | 2014-09-21 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | TAM | 2014-09-22 09:57 | IFI | OB | 100%
16112 | I491TM05-0DTST03-015-002 | DEDUSTING SYSTEM FOURNACE 140Ton EAF+LF & MH DUCT FROM LF - STRUCTURE DETAIL | 00 | 2014-06-01 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | TAM |  | IFI | OB | 100%
16113 | I491TM05-0DTST03-015-003 | DEDUSTING SYSTEM FOURNACE 140Ton EAF+LF & MH DUCT FROM LF - STRUCTURE DETAIL | 00 | 2014-06-01 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | TAM |  | IFI | OB | 100%
16111 | I491TM05-0DTST03-015-004 | DEDUSTING SYSTEM FOURNACE 140Ton EAF+LF & MH DUCT FROM LF - SUPPORT DETAIL | 00 | 2014-06-01 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Civil and Steel Structure | TAM |  | IFI | OB | 100%
112315 | I491TM05-0DTTK01-002-001 | DEDUSTING SYSTEM FOURNACE 140Ton EAF+LF & MH SILO - DETAILS 1-2 | 00 | 2014-06-01 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2014-06-07 09:06 | IFI | OB | 100%
112319 | I491TM05-0DTTK01-002-002 | DEDUSTING SYSTEM FOURNACE 140Ton EAF+LF & MH SILO - DETAILS 2-2 | 00 | 2014-06-01 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2014-06-07 09:12 | IFI | OB | 100%
112317 | I491TM05-0DTTK01-003-001 | DEDUSTING SYSTEM FOURNACE 140Ton EAF+LF & MH SILO'S EQUIPMENTS ASSEMBLY | 00 | 2014-06-01 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2014-06-07 09:09 | IFI | OB | 100%
112318 | I491TM05-0DTTK01-004-001 | DEDUSTING SYSTEM FOURNACE 140Ton EAF+LF & MH SILO HANDRAIL | 00 | 2014-06-01 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | HASCON | 2014-06-07 09:09 | IFI | OB | 100%
16114 | I491TM05-0DTTK02-002-001 | Dedusting System Fournace 140 Ton Eaf+Lf & Mh Silo Structure - Details | 00 | 2013-05-06 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | TAM |  | IFA | AFC | 100%
16115 | I491TM05-0DTTK02-003-001 | Dedusting System Fournace 140 Ton Eaf+Lf & Mh Silo'S Structures -Handrails | 00 | 2013-05-06 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Mechanical | TAM |  | IFA | AFC | 100%
16116 | I491TM05-0EABR01-001-001 | Burner Panel | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
130108 | I491TM05-0EABR01-002-001 | D-10.00.000.074A PIPE BY FLUSHING PIPE NATURAL GAS EAF | 00 | 2017-01-08 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS | 2017-01-09 09:13 | IFI | OB | 100%
16117 | I491TM05-0EABR02-001-001 | Burner Panel | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16118 | I491TM05-0EABR03-001-001 | Jetlance Front Part Burner Panel | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
130109 | I491TM05-0EABR05-001-001 | D-10.00.003.322A FOx-TECHNOLOGY UPPER SHELL | 00 | 2017-01-08 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS | 2017-01-09 09:13 | IFI | OB | 100%
16119 | I491TM05-0EACJ01-001-001 | Carbon Lance Burner System | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16120 | I491TM05-0EAEA01-001-001 | Bottom Bubbling-Lower Shell | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16121 | I491TM05-0EAEA02-001-001 | Bottom Temp.Measurem. Lower Shell Lower Shell-Bottom Bubbling | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16122 | I491TM05-0EAFE01-001-001 | Alloy System Roof Eaf | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16123 | I491TM05-0EAFE02-001-001 | Alloy System Roof Eaf | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16124 | I491TM05-0EAFE03-001-001 | Alloy System Roof Eaf | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16125 | I491TM05-0EAFE04-001-001 | Alloy System Roof Eaf | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16126 | I491TM05-0EAFE05-001-001 | Alloy System Roof Eaf | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16127 | I491TM05-0EAFE06-001-001 | Alloy System Roof Eaf | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16128 | I491TM05-0EAFE07-001-001 | Water Cooled Socket Alloy System-Roof Eaf | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16129 | I491TM05-0EAFE08-001-001 | Funnel Alloy System-Roof Eaf | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16130 | I491TM05-0EAFE09-001-001 | Funnel Alloy System-Roof Eaf | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16131 | I491TM05-0EAFE10-001-001 | Funnel Alloy System-Roof Eaf | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16132 | I491TM05-0EAFE11-001-001 | Funnel Alloy System-Roof Eaf | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16133 | I491TM05-0EAFE12-001-001 | Funnel Alloy System-Roof Eaf | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16134 | I491TM05-0EAFE13-001-001 | Funnel Alloy System-Roof Eaf | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16135 | I491TM05-0EAFE14-001-001 | Funnel Alloy System-Roof Eaf | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16136 | I491TM05-0EAFE15-001-001 | Funnel Socket Diverter Alloy System-Roof Eaf | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16137 | I491TM05-0EAFF01-001-001 | Refractory Concrete Roof Eaf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16138 | I491TM05-0EAFG01-001-001 | Panel Support Roof Eaf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16139 | I491TM05-0EAFG02-001-001 | Off Gas Duct Roof Eaf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16140 | I491TM05-0EAFG03-001-001 | Piping Elbow-Roof Eaf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16141 | I491TM05-0EAFG04-001-001 | Fume Take Off Off Gas Duct Roof Eaf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16142 | I491TM05-0EAFG05-001-001 | Guage Off Gas Duct Roof Eaf | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16143 | I491TM05-0EAFG06-001-001 | Sealing Disk Off Gas Duct Roof Eaf | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16144 | I491TM05-0EAFG07-001-001 | Sealing Disk Off Gas Duct Roof Eaf | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16145 | I491TM05-0EAFG08-001-001 | Hood Suspension Roof Eaf | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
115264 | I491TM05-0EAFG08-004-001 | EF.07.500.WLD-D-20.00.002.732 SUPPORT 2 LEFT | 00 | 2016-05-10 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS | 2016-05-24 16:51 | IFI | OB | 100%
115265 | I491TM05-0EAFG08-005-001 | EF.07.500.WLD-D-20.00.002.734 SUPPORT 2 RIGHT | 00 | 2016-05-10 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS | 2016-05-24 16:51 | IFI | OB | 100%
115266 | I491TM05-0EAFG08-006-001 | EF.07.500.WLD-D-20.00.002.735 SUPPORT 1 RIGHT | 00 | 2016-05-10 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS | 2016-05-24 16:51 | IFI | OB | 100%
115267 | I491TM05-0EAFG08-007-001 | EF.07.500.WLD-D-20.00.002.736 SUPPORT 1 LEFT | 00 | 2016-05-10 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS | 2016-05-24 16:51 | IFI | OB | 100%
115268 | I491TM05-0EAFG08-008-001 | EF.07.500.WLD-D-20.00.002.738 SUPPORT 3 RIGHT | 00 | 2016-05-10 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS | 2016-05-24 16:51 | IFI | OB | 100%
115269 | I491TM05-0EAFG08-009-001 | EF.07.500.WLD-D-20.00.002.741 SUPPORT 3 LEFT | 00 | 2016-05-10 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS | 2016-05-24 16:51 | IFI | OB | 100%
115270 | I491TM05-0EAFG08-010-001 | EF.07.500.WLD-D-20.00.002.743 SUPPORT 4 LEFT | 00 | 2016-05-10 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS | 2016-05-24 16:51 | IFI | OB | 100%
115271 | I491TM05-0EAFG08-011-001 | EF.07.500.WLD-D-20.00.002.744 SUPPORT 4 RIGHT | 00 | 2016-05-10 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS | 2016-05-24 16:51 | IFI | OB | 100%
115272 | I491TM05-0EAFG08-012-001 | EF.07.500.WLD-D-20.00.002.746 SUPPORT 5 LEFT | 00 | 2016-05-10 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS | 2016-05-24 16:51 | IFI | OB | 100%
115273 | I491TM05-0EAFG08-013-001 | EF.07.500.WLD-D-20.00.002.747 SUPPORT 5 RIGHT | 00 | 2016-05-10 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS | 2016-05-24 16:51 | IFI | OB | 100%
115274 | I491TM05-0EAFG08-014-001 | EF.07.500.WLD-D-20.00.002.748 SUPPORT 6 LEFT | 00 | 2016-05-10 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS | 2016-05-24 16:51 | IFI | OB | 100%
16146 | I491TM05-0EAFG09-001-001 | Hood Suspension Roof Eaf | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16147 | I491TM05-0EAFG10-001-001 | Hood Suspension Roof Eaf | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16148 | I491TM05-0EAFG11-001-001 | Hood Suspension Roof Eaf | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16149 | I491TM05-0EAFG12-001-001 | Hood Suspension Roof Eaf | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16150 | I491TM05-0EAFG13-001-001 | Hood Suspension Roof Eaf | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16151 | I491TM05-0EAFG14-001-001 | Hood Suspension Roof Eaf | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16152 | I491TM05-0EAFG15-001-001 | Hood Suspension Roof Eaf | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16153 | I491TM05-0EAFG16-001-001 | Hood Suspension Roof Eaf | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16154 | I491TM05-0EAFG17-001-001 | Hood Suspension Roof Eaf | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16155 | I491TM05-0EAFG18-001-001 | Hood Suspension Roof Eaf | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16156 | I491TM05-0EAFG19-001-001 | Hood Suspension Roof Eaf | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16157 | I491TM05-0EAFG20-001-001 | Hood Suspension Roof Eaf | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
115275 | I491TM05-0EAFG21-001-001 | EF.07.500.WLD-D-20.00.002.749 SUPPORT 6 RIGHT | 00 | 2016-05-10 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS | 2016-05-24 16:52 | IFI | OB | 100%
115276 | I491TM05-0EAFG22-001-001 | EF.07.500.WLD-D-20.00.002.750 SUPPORT 7 | 00 | 2016-05-10 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS | 2016-05-24 16:52 | IFI | OB | 100%
16158 | I491TM05-0EAFK01-001-001 | Fittings Tilting Frame- Heat Protection | 00 | 2012-03-10 | Indeterminate | Drawing | Basic | Electric Arc Furnace | Mechanical | TAM |  | IFI | OB | 100%
16159 | I491TM05-0EAFK02-001-001 | Device Unit Tilting Frame -Locking Device | 00 | 2012-03-13 | Indeterminate | Drawing | Basic | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16160 | I491TM05-0EAFK03-001-001 | Electro Tilting Frame -Tipping Angle Indicator | 00 | 2012-03-13 | Indeterminate | Drawing | Basic | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16161 | I491TM05-0EAFM01-001-001 | Bolt Ø 30 X 100 | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16162 | I491TM05-0EAFM01-001-002 | Upper Shell Balcony Panel | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16163 | I491TM05-0EAFM02-001-001 | Swivel Pipe Lower Part | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16164 | I491TM05-0EAFM03-001-001 | Upper Part Console -Tap Hole Filling Device Shell | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | TAM |  | IFI | OB | 100%
16165 | I491TM05-0EAFM04-001-001 | Upper Part Console Funnel-Tap Hole Filling Device Shell | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16166 | I491TM05-0EAFM05-001-001 | Upper Part Funnel-Tap Hole Filling Device Shell | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16167 | I491TM05-0EAFM06-001-001 | Upper Part- Tap Hole Filling Device Shell | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
113206 | I491TM05-0EAFM07-001-001 | Shell Lower Shell | 01 | 2015-01-07 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS | 2015-01-10 14:27 | IFI | OB | 100%
113207 | I491TM05-0EAFM08-001-001 | Shell Lower Shell | 01 | 2015-01-07 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS | 2015-01-10 14:27 | IFI | OB | 100%
16170 | I491TM05-0EAFM09-001-001 | Door System -Drive Unit | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16171 | I491TM05-0EAFM10-001-001 | Door System-Drive Unit | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16172 | I491TM05-0EAFM11-001-001 | Door System-Slag Door | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16173 | I491TM05-0EAFM12-001-001 | Door System--Slag Door | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16174 | I491TM05-0EAFM15-001-001 | Balcony Panel Connection | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16175 | I491TM05-0EAFM16-001-001 | Balcony Panel Bracket | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16176 | I491TM05-0EAFM17-001-001 | Upper Shell Balcony Panel | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16177 | I491TM05-0EAFM18-001-001 | Balcony Panel Water Circuit | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16178 | I491TM05-0EAFM19-001-001 | Uppper Shell Balcony Panel | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | TAM |  | IFI | OB | 100%
16179 | I491TM05-0EASG01-001-001 | Bottom Tapping | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
113208 | I491TM05-0EASG02-001-001 | Lower Shell-Slag Restraining Block | 01 | 2015-01-07 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | TAM | 2015-01-10 14:27 | IFI | OB | 100%
113209 | I491TM05-0EASG03-001-001 | Lower Shell-Slag Restraining Block | 01 | 2015-01-07 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS | 2015-01-10 14:28 | IFI | OB | 100%
135150 | I491TM05-0EAWD01-001-001 | Remotely controlled protection gate for EAF room windows Driving System Layout | 01 | 2019-03-09 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | TAM | 2019-03-18 10:42 | IFC | AFC | 100%
16182 | I491TM05-0LFIH01-001-001 | Release Cylinder Clamp Box | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | TAM |  | IFI | OB | 100%
16183 | I491TM05-0LFLE01-001-001 | STEEL STRUCTURE ROOF LF | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Civil and Steel Structure | INTECO |  | IFI | OB | 100%
16184 | I491TM05-0LFLE02-001-001 | Holder Steel Structure Roof Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Civil and Steel Structure | INTECO |  | IFI | OB | 100%
16185 | I491TM05-0LFLE03-001-001 | Holder Steel Structure Roof Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Civil and Steel Structure | INTECO |  | IFI | OB | 100%
16186 | I491TM05-0LFLE04-001-001 | Working Door System Roof Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16187 | I491TM05-0LFLE05-001-001 | Door Roof Working Door Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16188 | I491TM05-0LFLE06-001-001 | Bracket Roof Working Door Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16189 | I491TM05-0LFLE07-001-001 | Bracket Roof Working Door Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16190 | I491TM05-0LFLE08-001-001 | Bracket Roof Working Door Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16191 | I491TM05-0LFLW01-001-001 | Lifting Cylinder Lifting Columns | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16193 | I491TM05-0LFRL01-001-002 | Gantry Ladle Furnace | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | TAM |  | IFI | OB | 100%
16195 | I491TM05-0LFRL02-001-002 | Gantry Housing Gantry Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16198 | I491TM05-0LFRL03-001-003 | Gantry Ladle Furnace | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16199 | I491TM05-0LFRL03-001-004 | Gantry Heat Protection | 00 | 2012-03-10 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16201 | I491TM05-0LFRL04-001-002 | Lubrication System Piping Gantry Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16203 | I491TM05-0LFRL05-001-002 | Lubrication System Piping Gantry Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16204 | I491TM05-0LFRL12-001-001 | Roof Lifting Device Ladle Funrnace | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16205 | I491TM05-0LFRL13-001-001 | Roof Lifting Device Ladle Funrnace | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16206 | I491TM05-0LFRL14-001-001 | Roller Bracket Roof Lifting Device Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16207 | I491TM05-0LFRL15-001-001 | Lifting Cylinder Roof Lifting Device Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16208 | I491TM05-0LFRL17-001-001 | Locking Device Roof Lifting Device Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16209 | I491TM05-0LFRL18-001-001 | Piping Roof Lifting Device Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
112168 | I491TM05-0MDCV01-001-001 | POCKET B.C. MD-CV-01-01 GENERAL ASSEMBLY BW = 1000 | 00 | 2014-05-14 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | DATIS | 2014-05-17 09:44 | IFI | AC |  | 95%
112169 | I491TM05-0MDCV02-001-001 | REVERSIBLE B.C. MD-CV-02-01 GENERAL ASSEMBLY BW = 650 | 00 | 2014-05-14 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | DATIS | 2014-05-17 09:44 | IFI | AC |  | 95%
112170 | I491TM05-0MDCV03-001-001 | B.C. MD-CV-03-01 GENERAL ASSEMBLY BW = 650 | 00 | 2014-05-14 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | DATIS | 2014-05-17 09:44 | IFI | AC |  | 95%
112171 | I491TM05-0MDCV04-001-001 | REVERSIBLE B.C MD-CV-04-01 GENERAL ASSEMBLY BW = 650 | 00 | 2014-05-14 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | DATIS | 2014-05-17 09:45 | IFI | AC |  | 95%
112172 | I491TM05-0MDCV05-001-001 | SHUTTLE B.C. MD-CV-05-01 GENERAL ASSEMBLY BW = 650 | 00 | 2014-05-14 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | DATIS | 2014-05-17 09:45 | IFI | AC |  | 95%
112173 | I491TM05-0MDCV06-001-001 | SHUTTLE B.C. MD-CV-06-01 GENERAL ASSEMBLY BW = 650 | 00 | 2014-05-14 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | DATIS | 2014-05-17 09:45 | IFI | AC |  | 95%
112174 | I491TM05-0MDCV07-001-001 | B.C. MD-CV-07-01 GENERAL ASSEMBLY BW = 1000 | 00 | 2014-05-14 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | DATIS | 2014-05-17 09:45 | IFI | AC |  | 95%
112175 | I491TM05-0MDCV08-001-001 | B.C. MD-CV-08-01 GENERAL ASSEMBLY BW=1000 | 00 | 2014-05-14 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | DATIS | 2014-05-17 09:46 | IFI | AC |  | 95%
112176 | I491TM05-0MDCV09-001-001 | SHUTTLE B.C. MD-CV-09-01 GENERAL ASSEMBLY BW=1000 | 00 | 2014-05-14 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | DATIS | 2014-05-17 09:46 | IFI | AC |  | 95%
112177 | I491TM05-0MDCV16-001-001 | B.C. MD-CV-16-01 GENERAL ASSEMBLY BW = 650 | 00 | 2014-05-14 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | DATIS | 2014-05-17 09:48 | IFI | AC |  | 95%
112178 | I491TM05-0MDCV19-001-001 | B.C. MD-CV-19-01 GENERAL ASSEMBLY BW = 650 | 00 | 2014-05-14 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | DATIS | 2014-05-17 09:48 | IFI | AC |  | 95%
111384 | I491TM05-0MDCV92-001-001 | Std Part Carrying Idler 35° And Support Bw 650 | 01 | 2013-12-25 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | DATIS | 2014-04-17 15:37 | IFI | OB | 100%
111385 | I491TM05-0MDCV92-002-001 | Std Part Impact Idler 35° And Support Bw 650 | 01 | 2013-12-25 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | DATIS | 2014-04-17 15:38 | IFI | OB | 100%
111386 | I491TM05-0MDCV92-003-001 | Std Part Carrying Idler 20° And Support Bw 650 | 01 | 2013-12-25 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | DATIS | 2014-04-17 15:41 | IFI | OB | 100%
111388 | I491TM05-0MDCV92-004-001 | Std Part Carrying Idler 10° And Support Bw 650 | 01 | 2013-12-25 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | DATIS | 2014-04-17 15:42 | IFI | OB | 100%
111390 | I491TM05-0MDCV92-005-002 | STD PART CARRYING SELF-ALIGNMENT IDLER 35° (TYPE 1) BW 650 | 01 | 2013-07-13 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | DATIS | 2014-04-17 15:49 | IFI | OB | 100%
111832 | I491TM05-0MDCV92-006-001 | Std Part Carrying Self-Alignment Idler 35° (Type 2) Bw 650 | 01 | 2013-12-25 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | DATIS | 2014-05-01 13:24 | IFI | OB | 100%
111833 | I491TM05-0MDCV92-007-001 | Std Part Flat Return Idler And Support (Type 1) Bw 650 | 01 | 2013-12-25 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | DATIS | 2014-05-01 13:25 | IFI | OB | 100%
111834 | I491TM05-0MDCV92-008-001 | Std Part Flat Return Idler And Support (Type 2) Bw 650 | 01 | 2013-12-25 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | DATIS | 2014-05-01 13:25 | IFI | OB | 100%
111835 | I491TM05-0MDCV92-009-001 | Std Part Return Self-Alignment Idler (Type 1) Bw 650 | 01 | 2013-12-25 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | DATIS | 2014-05-01 13:25 | IFI | OB | 100%
111836 | I491TM05-0MDCV92-010-001 | Std Part Return Self-Alignment Idler (Type 2) Bw 650 | 01 | 2013-12-25 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | DATIS | 2014-05-01 13:26 | IFI | OB | 100%
111837 | I491TM05-0MDCV92-011-001 | Std Part Impact Idler 20° And Support Bw 650 | 01 | 2013-12-25 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | DATIS | 2014-05-01 13:26 | IFI | OB | 100%
111838 | I491TM05-0MDCV92-016-001 | Std Part Carrying Idler 35° And Support Bw 800 | 01 | 2013-12-25 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | DATIS | 2014-05-01 13:28 | IFI | OB | 100%
111839 | I491TM05-0MDCV92-017-001 | Std Part Impact Idler 35° And Support Bw 800 | 01 | 2013-12-25 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | DATIS | 2014-05-01 13:29 | IFI | OB | 100%
111840 | I491TM05-0MDCV92-018-001 | Std Part Carrying Idler 20° And Support Bw 800 | 01 | 2013-12-25 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | DATIS | 2014-05-01 13:29 | IFI | OB | 100%
111841 | I491TM05-0MDCV92-019-001 | Std Part Carrying Idler 10° And Support Bw 800 | 01 | 2013-12-25 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | DATIS | 2014-05-01 13:30 | IFI | OB | 100%
111842 | I491TM05-0MDCV92-021-001 | Std Part Flat Return Idler And Support Bw 800 | 01 | 2013-12-25 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | DATIS | 2014-05-01 13:30 | IFI | OB | 100%
111843 | I491TM05-0MDCV92-026-001 | Std Part Carrying Idler 35° And Support Bw 1000 | 01 | 2013-12-25 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | DATIS | 2014-05-01 13:30 | IFI | OB | 100%
111844 | I491TM05-0MDCV92-027-001 | Std Part Carrying Idler 35° And Support Bw 1000 | 01 | 2013-12-25 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | DATIS | 2014-05-01 13:31 | IFI | OB | 100%
111845 | I491TM05-0MDCV92-028-001 | Std Part Carrying Idler 20° And Support Bw 1000 | 01 | 2013-12-25 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | DATIS | 2014-05-01 13:31 | IFI | OB | 100%
111846 | I491TM05-0MDCV92-029-001 | Std Part Carrying Idler 10° And Support Bw 1000 | 01 | 2013-12-25 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | DATIS | 2014-05-01 13:34 | IFI | OB | 100%
111847 | I491TM05-0MDCV92-030-001 | Std Part Carrying Self-Alignment Idler 35° Bw 1000 | 01 | 2013-12-25 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | DATIS | 2014-05-01 13:34 | IFI | OB | 100%
111850 | I491TM05-0MDCV92-031-001 | Std Part Flat Return Idler And Support (Type 1) Bw 1000 | 01 | 2013-12-25 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | TAM | 2014-05-01 13:58 | IFI | OB | 100%
111851 | I491TM05-0MDCV92-032-001 | Std Part Flat Return Idler And Support (Type 2) Bw 1000 | 01 | 2013-12-25 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | TAM | 2014-05-01 13:59 | IFI | OB | 100%
111848 | I491TM05-0MDCV92-033-001 | Std Part Return Self-Alignment Bw 1000 | 01 | 2013-12-25 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | DATIS | 2014-05-01 13:34 | IFI | OB | 100%
16224 | I491TM05-0MDCV92-034-001 | Std Part Inverted Return Idler 15° And Support Bw 1000 | 00 | 2013-07-13 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | DATIS |  | IFI | OB | 100%
111849 | I491TM05-0MDCV92-035-001 | Std Part Carrying Idler 20° And Support Bw 1000 | 01 | 2013-12-25 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | DATIS | 2014-05-01 13:34 | IFI | OB | 100%
16226 | I491TM05-0MDCV92-041-001 | STD PART FEEDING DEVICE (TYPE 1) BW 650 | 00 | 2013-07-13 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | DATIS |  | IFI | OB | 100%
16227 | I491TM05-0MDCV92-043-001 | STD PART FEEDING DEVICE (TYPE 2) BW 650 | 00 | 2013-07-13 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | DATIS |  | IFI | OB | 100%
16228 | I491TM05-0MDCV92-045-001 | Std Part Feeding Device Bw 800 | 00 | 2013-07-13 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | DATIS |  | IFI | OB | 100%
16229 | I491TM05-0MDCV92-048-001 | Std Part Feeding Device Bw 1000 | 00 | 2013-07-13 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | DATIS |  | IFI | OB | 100%
16230 | I491TM05-0MDCV92-051-001 | Std Part Belt Cover Bw 650 | 00 | 2013-10-15 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | DATIS |  | IFA | A | 100%
135517 | I491TM05-0MDSG01-001-001 | Slide Gate BASE FRAME | 00 | 2019-07-09 09:55 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | TAM | 2019-07-09 09:55 | IFI | OB | 100%
135516 | I491TM05-0MDSG01-002-001 | Slide Gate BASE FRAME - Down side | 00 | 2019-07-09 09:55 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | TAM | 2019-07-09 09:55 | IFI | OB | 100%
135515 | I491TM05-0MDSG01-003-001 | Slide Gate Gate | 00 | 2019-07-09 09:55 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | TAM | 2019-07-09 09:55 | IFI | OB | 100%
135514 | I491TM05-0MDSG01-004-001 | Slide Gate Cover Plate | 00 | 2019-07-09 09:55 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | TAM | 2019-07-09 09:55 | IFI | OB | 100%
135513 | I491TM05-0MDSG01-005-001 | Slide Gate Guide | 00 | 2019-07-09 09:55 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | TAM | 2019-07-09 09:55 | IFI | OB | 100%
135512 | I491TM05-0MDSG01-006-001 | Slide Gate Joint | 00 | 2019-07-09 09:55 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | TAM | 2019-07-09 09:55 | IFI | OB | 100%
135511 | I491TM05-0MDSG01-007-001 | Slide Gate ASSEMBLY | 00 | 2019-07-09 09:55 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | TAM | 2019-07-09 09:55 | IFI | OB | 100%
135518 | I491TM05-0MDSG01-101-001 | Slide Gate | 00 | 2019-07-09 10:27 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | TAM | 2019-07-09 10:27 | IFI | OB | 100%
135059 | I491TM05-0MDSI01-001-001 | CARBON INJECTION SILOS MD-SI-01-01 ASSEMBLY DRAWING | 02 | 2019-02-25 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | TAM | 2019-03-05 14:40 | IFI | OB | 100%
135060 | I491TM05-0MDSI01-002-001 | CARBON INJECTION SILOS MD-SI-01-02 UPPER PART & ROOF | 02 | 2019-02-25 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | TAM | 2019-03-05 14:40 | IFI | OB | 100%
134449 | I491TM05-0MDSI01-003-001 | CARBON INJECTION SILOS MD-SI-01-03 MIDDLE PART WITH SUPPORT | 01 | 2018-12-08 09:10 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | TAM | 2018-12-08 09:10 | IFI | OB | 100%
135061 | I491TM05-0MDSI01-004-001 | CARBON INJECTION SILOS MD-SI-01-04 LOWER PART | 02 | 2019-02-25 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | TAM | 2019-03-05 14:41 | IFI | OB | 100%
134451 | I491TM05-0MDSI01-005-001 | CARBON INJECTION SILOS MD-SI-01-05 MANHOLE | 01 | 2018-12-08 09:10 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | TAM | 2018-12-08 09:10 | IFI | OB | 100%
135062 | I491TM05-0MDSI02-001-001 | LIME INJECTION SILOS MD-SI-02-01 ASSEMBLY DRAWING | 02 | 2019-02-25 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | TAM | 2019-03-05 14:41 | IFI | OB | 100%
135063 | I491TM05-0MDSI02-002-001 | LIME INJECTION SILOS MD-SI-02-02 UPPER PART & ROOF | 02 | 2019-02-25 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | TAM | 2019-03-05 14:41 | IFI | OB | 100%
134454 | I491TM05-0MDSI02-003-001 | LIME INJECTION SILOS MD-SI-02-03 MIDDLE PART WITH SUPPORT | 01 | 2018-12-08 09:10 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | TAM | 2018-12-08 09:10 | IFI | OB | 100%
135064 | I491TM05-0MDSI02-004-001 | LIME INJECTION SILOS MD-SI-02-04 LOWER PART | 02 | 2019-02-25 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | TAM | 2019-03-05 14:41 | IFI | OB | 100%
134456 | I491TM05-0MDSI02-005-001 | CARBON INJECTION SILOS MD-SI-02-05 MANHOLE | 01 | 2018-12-08 09:10 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | TAM | 2018-12-08 09:10 | IFI | OB | 100%
112264 | I491TM05-0MDTK02-001-001 | FINE LIME BIN MD-TK-02-01 ASSEMBLY DRAWING | 00 | 2014-05-21 09:12 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | DATIS | 2014-05-21 09:12 | IFI | AC |  | 95%
112265 | I491TM05-0MDTK03-001-001 | DOLOMITE BIN MD-TK-03-01 ASSEMBLY DRAWING | 00 | 2014-05-21 09:13 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | DATIS | 2014-05-21 09:13 | IFI | AC |  | 95%
112263 | I491TM05-0MDTK04-001-001 | COARSE LIME BIN MD-TK-04-01 ASSEMBLY DRAWING | 00 | 2014-05-21 09:12 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | DATIS | 2014-05-21 09:12 | IFI | AC |  | 95%
112157 | I491TM05-0MDTK09-001-001 | EAF FERRO ALLOY STORAGE BINS ASSEMBLY DRAWING FOR FERRO ALLOY BINS MD-TK-09~16-01 | 00 | 2014-05-07 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | DATIS | 2014-05-17 09:19 | IFI | OB | 100%
112158 | I491TM05-0MDTK09-002-001 | EAF FERRO ALLOY STORAGE BINS ASSEMBLY | 00 | 2014-05-07 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | DATIS | 2014-05-17 09:20 | IFI | OB | 100%
112159 | I491TM05-0MDTK09-003-001 | EAF FERRO ALLOY STORAGE BINS UPPER PART | 00 | 2014-05-07 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | DATIS | 2014-05-17 09:20 | IFI | OB | 100%
112160 | I491TM05-0MDTK09-004-001 | EAF FERRO ALLOY STORAGE BINS MIDDLE PART | 00 | 2014-05-07 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | DATIS | 2014-05-17 09:20 | IFI | OB | 100%
112161 | I491TM05-0MDTK09-005-001 | EAF FERRO ALLOY STORAGE BINS LOWER PART | 00 | 2014-05-07 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | DATIS | 2014-05-17 09:21 | IFI | OB | 100%
112162 | I491TM05-0MDTK09-006-001 | EAF FERRO ALLOY STORAGE BINS ROOF | 00 | 2014-05-07 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | DATIS | 2014-05-17 09:21 | IFI | OB | 100%
112163 | I491TM05-0MDTK17-001-001 | LF FERRO ALLOY STORAGE BINS ASSEMBLY DRAWING FOR FERRO ALLOY BINS MD-TK-17~28-01 | 00 | 2014-05-07 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | TAM | 2014-05-17 09:22 | IFI | OB | 100%
112164 | I491TM05-0MDTK17-002-001 | LF FERRO ALLOY STORAGE BINS BIN ASSEMBLY 1 | 00 | 2014-05-07 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | TAM | 2014-05-17 09:22 | IFI | OB | 100%
112165 | I491TM05-0MDTK17-003-001 | LF FERRO ALLOY STORAGE BINS BODY & STIFFENER | 00 | 2014-05-07 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | TAM | 2014-05-17 09:22 | IFI | OB | 100%
112166 | I491TM05-0MDTK17-004-001 | LF FERRO ALLOY STORAGE BINS ROOF | 00 | 2014-05-07 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | TAM | 2014-05-17 09:22 | IFI | OB | 100%
112167 | I491TM05-0MDTK17-005-001 | LF FERRO ALLOY STORAGE BINS WEAR PLATES | 00 | 2014-05-07 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | TAM | 2014-05-17 09:23 | IFI | OB | 100%
114777 | I491TM05-0MDTK29-010-001 | EAF DRI STORAGE BINS N2 PIPING DRAWING FOR DRI BINS MD-TK-29~32-01 | 00 | 2015-12-15 | Indeterminate | Drawing | Detail | Material Handling | Piping & Utility | DATIS | 2015-12-26 14:07 | IFI | OB | 100%
16241 | I491TM05-0MMCT01-001-001 | Fan Stack For Cooling System(Ct1) | 00 | 2013-01-28 | Indeterminate | Drawing | Basic | Water Treatment & Cooling System | Piping & Utility | TAM |  | IFI | OB | 100%
16242 | I491TM05-0MMCT01-002-001 | Fan Detail For Cooling System(Ct1) | 00 | 2013-01-28 | Indeterminate | Drawing | Basic | Water Treatment & Cooling System | Piping & Utility | TAM |  | IFI | OB | 100%
114932 | I491TM05-0MMCT01-003-001 | HUB DETAIL FOR COOLING SYSTEM (CT01) | 00 | 2016-02-24 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Piping & Utility | TAM | 2016-02-28 08:54 | IFI | OB | 100%
114934 | I491TM05-0MMCT01-004-001 | DRIVE SHAFT DETAIL FOR COOLING SYSTEM (CT01) 1-2 | 00 | 2016-02-24 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Piping & Utility | TAM | 2016-02-28 08:54 | IFI | OB | 100%
114933 | I491TM05-0MMCT01-004-002 | DRIVE SHAFT DETAIL FOR COOLING SYSTEM (CT01) 2-2 | 00 | 2016-02-24 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Piping & Utility | TAM | 2016-02-28 08:54 | IFI | OB | 100%
16244 | I491TM05-0MMCT01-005-002 | Gear Reducer & Electromotor Base Plate For Cooling System (Ct01) | 00 | 2013-05-26 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Piping & Utility | TAM |  | IFI | OB | 100%
16245 | I491TM05-0MMCT01-006-001 | Nozzle Detail For Cooling System(Ct1) | 00 | 2013-01-28 | Indeterminate | Drawing | Basic | Water Treatment & Cooling System | Piping & Utility | TAM |  | IFI | OB | 100%
114935 | I491TM05-0MMCT01-007-001 | SIDE STREAM FILTER SHOP DRAWING for Water Cooling System | 00 | 2016-02-24 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Piping & Utility | TAM | 2016-02-28 08:55 | IFI | OB | 100%
16246 | I491TM05-0MMCT02-001-001 | Fan Stack For Cooling System(Ct2) | 00 | 2013-01-28 | Indeterminate | Drawing | Basic | Water Treatment & Cooling System | Piping & Utility | TAM |  | IFI | OB | 100%
16247 | I491TM05-0MMCT02-002-001 | Fan Detail For Cooling System(Ct2) | 00 | 2013-01-28 | Indeterminate | Drawing | Basic | Water Treatment & Cooling System | Piping & Utility | TAM |  | IFI | OB | 100%
114936 | I491TM05-0MMCT02-003-001 | HUB DETAIL FOR COOLING SYSTEM (CT02) | 00 | 2016-02-24 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Piping & Utility | TAM | 2016-02-28 08:55 | IFI | OB | 100%
114938 | I491TM05-0MMCT02-004-001 | DRIVE SHAFT DETAIL FOR COOLING SYSTEM (CT02) 1-2 | 00 | 2016-02-24 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Piping & Utility | TAM | 2016-02-28 08:55 | IFI | OB | 100%
114937 | I491TM05-0MMCT02-004-002 | DRIVE SHAFT DETAIL FOR COOLING SYSTEM (CT02) 2-2 | 00 | 2016-02-24 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Piping & Utility | TAM | 2016-02-28 08:55 | IFI | OB | 100%
16249 | I491TM05-0MMCT02-005-002 | Gear Reducer & Electromotor Base Plate For Cooling System (Ct02) | 00 | 2013-05-26 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Piping & Utility | TAM |  | IFI | OB | 100%
16250 | I491TM05-0MMCT02-006-001 | Nozzle Detail For Cooling System(Ct2) | 00 | 2013-01-28 | Indeterminate | Drawing | Basic | Water Treatment & Cooling System | Piping & Utility | TAM |  | IFI | OB | 100%
114939 | I491TM05-0MMCT02-007-001 | SIDE STREAM FILTER SHOP DRAWING for Water Cooling System | 00 | 2016-02-24 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Piping & Utility | TAM | 2016-02-28 08:59 | IFI | OB | 100%
115004 | I491TM05-0PXLM01-001-001 | A331100037B_General 1-2 | 01 | 2016-03-07 14:52 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | DHHI | 2016-03-07 14:52 | IFI | OB | 100%
115005 | I491TM05-0PXLM01-001-002 | A331100037B_General 2-2 | 00 | 2016-03-07 14:52 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | DHHI | 2016-03-07 14:52 | IFI | OB | 100%
115006 | I491TM05-0PXLM01-002-001 | C1331100100021B_Ladle Body | 00 | 2016-03-07 14:52 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | DHHI | 2016-03-07 14:52 | IFI | OB | 100%
115007 | I491TM05-0PXLM01-003-001 | C1331100100021B_Ladle Body | 00 | 2016-03-07 14:52 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | DHHI | 2016-03-07 14:52 | IFI | OB | 100%
115008 | I491TM05-0PXLM01-004-001 | B2331100000061_Lifting Arm | 00 | 2016-03-07 14:52 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | DHHI | 2016-03-07 14:52 | IFI | OB | 100%
115010 | I491TM05-0PXLM01-005-001 | C1331100000149_Lifting Arm | 00 | 2016-03-07 14:52 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | DHHI | 2016-03-07 14:52 | IFI | OB | 100%
115009 | I491TM05-0PXLM01-006-001 | C2331100000150_Lever | 00 | 2016-03-07 14:52 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | DHHI | 2016-03-07 14:52 | IFI | OB | 100%
115011 | I491TM05-0PXLM01-007-001 | C2331100000151_Hanger | 00 | 2016-03-07 14:52 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | DHHI | 2016-03-07 14:52 | IFI | OB | 100%
115012 | I491TM05-0PXLM01-008-001 | C2331100000152_Pin | 00 | 2016-03-07 14:52 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | DHHI | 2016-03-07 14:52 | IFI | OB | 100%
115013 | I491TM05-0PXLM01-009-001 | C2331100000153_Supporting Plate(Left) | 00 | 2016-03-07 14:52 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | DHHI | 2016-03-07 14:52 | IFI | OB | 100%
115014 | I491TM05-0PXLM01-010-001 | E010013246_Pin of Lifting Arm | 00 | 2016-03-07 14:52 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | DHHI | 2016-03-07 14:52 | IFI | OB | 100%
115016 | I491TM05-0PXLM01-011-001 | E010013250_Trunnion 1-2 | 00 | 2016-03-07 14:52 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | DHHI | 2016-03-07 14:52 | IFI | OB | 100%
115015 | I491TM05-0PXLM01-011-002 | E010013250_Trunnion 2-2 | 00 | 2016-03-07 14:52 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | DHHI | 2016-03-07 14:52 | IFI | OB | 100%
115017 | I491TM05-0PXLM01-012-001 | E160007142_Brace | 00 | 2016-03-07 14:52 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | DHHI | 2016-03-07 14:52 | IFI | OB | 100%
115018 | I491TM05-0PXLM01-013-001 | E220040883_Base Plate | 00 | 2016-03-07 14:52 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | DHHI | 2016-03-07 14:52 | IFI | OB | 100%
115019 | I491TM05-0PXLM01-014-001 | E990012164_Ladle Bottom | 00 | 2016-03-07 14:52 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | DHHI | 2016-03-07 14:52 | IFI | OB | 100%
115020 | I491TM05-0PXLM01-015-001 | G990023843_Copper | 00 | 2016-03-07 14:52 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | DHHI | 2016-03-07 14:52 | IFI | OB | 100%
115021 | I491TM05-0PXLM01-016-001 | B1331100100019_Tilting Device | 00 | 2016-03-07 14:52 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | DHHI | 2016-03-07 14:52 | IFI | OB | 100%
115022 | I491TM05-0PXLM01-017-001 | C2331100000154_Supporting Plate(Right) | 00 | 2016-03-07 14:52 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | DHHI | 2016-03-07 14:52 | IFI | OB | 100%
115023 | I491TM05-0PXLM01-018-001 | E010013241_Pin of Tilting Device | 00 | 2016-03-07 14:52 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | DHHI | 2016-03-07 14:52 | IFI | OB | 100%
115024 | I491TM05-0PXLM01-019-001 | E010013244_Shaft | 00 | 2016-03-07 14:52 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | DHHI | 2016-03-07 14:52 | IFI | OB | 100%
115025 | I491TM05-0PXLM01-020-001 | E020004808_Pin of Hanger | 00 | 2016-03-07 14:52 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | DHHI | 2016-03-07 14:52 | IFI | OB | 100%
115026 | I491TM05-0PXLM01-021-001 | E020004809_Plug Pin | 00 | 2016-03-07 14:52 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | DHHI | 2016-03-07 14:52 | IFI | OB | 100%
115027 | I491TM05-0PXLM01-022-001 | E040015201_Bush(Pin) | 00 | 2016-03-07 14:52 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | DHHI | 2016-03-07 14:52 | IFI | OB | 100%
115028 | I491TM05-0PXLM01-023-001 | E040015202_Bush(Trunion) | 00 | 2016-03-07 14:52 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | DHHI | 2016-03-07 14:52 | IFI | OB | 100%
115029 | I491TM05-0PXLM01-024-001 | E040015203_Bush(Pin of Lifting Arm) | 00 | 2016-03-07 14:52 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | DHHI | 2016-03-07 14:52 | IFI | OB | 100%
115030 | I491TM05-0PXLM01-025-001 | E070006290_Link | 00 | 2016-03-07 14:52 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | DHHI | 2016-03-07 14:52 | IFI | OB | 100%
115031 | I491TM05-0PXLM01-026-001 | E220040830_Baffle(Lifting Arm) | 00 | 2016-03-07 14:52 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | DHHI | 2016-03-07 14:52 | IFI | OB | 100%
115032 | I491TM05-0PXLM01-027-001 | E220040835_Shaft End Baffle I | 00 | 2016-03-07 14:52 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | DHHI | 2016-03-07 14:52 | IFI | OB | 100%
115033 | I491TM05-0PXLM01-028-001 | E220040841_Lever Plate | 00 | 2016-03-07 14:52 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | DHHI | 2016-03-07 14:52 | IFI | OB | 100%
115034 | I491TM05-0PXLM01-029-001 | E220040842_Shaft End Baffle II | 00 | 2016-03-07 14:52 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | DHHI | 2016-03-07 14:52 | IFI | OB | 100%
115035 | I491TM05-0PXLM01-030-001 | E220040843_Steel Plate(Left) | 00 | 2016-03-07 14:52 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | DHHI | 2016-03-07 14:52 | IFI | OB | 100%
115036 | I491TM05-0PXLM01-031-001 | E220040844_Steel Plate(Right) | 00 | 2016-03-07 14:52 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | DHHI | 2016-03-07 14:52 | IFI | OB | 100%
115037 | I491TM05-0PXLM01-032-001 | E220040854_Baffle(Pin of Lifting Arm) | 00 | 2016-03-07 14:52 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | DHHI | 2016-03-07 14:52 | IFI | OB | 100%
115038 | I491TM05-0PXLM01-033-001 | E220040857_Lifting Arm Plate | 00 | 2016-03-07 14:52 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | DHHI | 2016-03-07 14:52 | IFI | OB | 100%
115039 | I491TM05-0PXLM01-034-001 | E990012165_Handle | 00 | 2016-03-07 14:52 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | DHHI | 2016-03-07 14:52 | IFI | OB | 100%
114394 | I491TM05-0PXLM02-001-001 | A331100038-Emergency Ladle | 00 | 2015-09-20 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | DHHI | 2015-09-22 09:49 | IFI | AC |  | 95%
115040 | I491TM05-0PXLM03-001-001 | A311800005B_B-type Ladle Cover | 01 | 2016-03-07 14:53 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | DHHI | 2016-03-07 14:53 | IFI | OB | 100%
115041 | I491TM05-0PXLM03-002-001 | C2311800000082B_Half Cover 1 | 00 | 2016-03-07 14:53 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | DHHI | 2016-03-07 14:53 | IFI | OB | 100%
115042 | I491TM05-0PXLM03-003-001 | C2311800000083B_Half Cover 2 | 00 | 2016-03-07 14:53 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | DHHI | 2016-03-07 14:53 | IFI | OB | 100%
115043 | I491TM05-0PXLM03-004-001 | C2311800000087B_Handle of B-type Ladle Cover | 00 | 2016-03-07 14:53 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | DHHI | 2016-03-07 14:53 | IFI | OB | 100%
115044 | I491TM05-0PXLM04-001-001 | A311800004B_A-type Ladle Cover | 01 | 2016-03-07 14:53 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | DHHI | 2016-03-07 14:53 | IFI | OB | 100%
115045 | I491TM05-0PXLM04-002-001 | C2311800000085_Half Cover3 | 00 | 2016-03-07 14:53 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | DHHI | 2016-03-07 14:53 | IFI | OB | 100%
115046 | I491TM05-0PXLM04-003-001 | C2311800000086_Half Cover4 | 00 | 2016-03-07 14:53 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | DHHI | 2016-03-07 14:53 | IFI | OB | 100%
115047 | I491TM05-0PXLM04-004-001 | C2311800000084B_Handle of A-type Ladle Cover | 00 | 2016-03-07 14:53 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | DHHI | 2016-03-07 14:53 | IFI | OB | 100%
114636 | I491TM05-0RXBT03-001-001 | AX.01.320.ASD-D-31.00.000.155A WEIGHING DEVICE | 00 | 2015-10-26 11:21 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | TAM | 2015-10-26 11:21 | IFA | AFC | 100%
118071 | I491TM05-0RXEA01-001-001 | Settling Stand foe ladle in Purging Station 1-2 | 02 | 2016-08-01 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | TAM | 2016-08-04 09:29 | IFI | OB | 100%
118070 | I491TM05-0RXEA01-001-002 | Settling Stand foe ladle in Purging Station 2-2 | 00 | 2016-08-01 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | TAM | 2016-08-04 09:29 | IFI | OB | 100%
133234 | I491TM05-0RXEA01-002-001 | Saddle of Horizontal Station General 1-2 | 00 | 2018-06-09 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | TAM | 2018-06-11 10:51 | IFI | OB | 100%
133235 | I491TM05-0RXEA01-002-002 | Saddle of Horizontal Station Welding 2-2 | 00 | 2018-06-09 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | TAM | 2018-06-11 10:51 | IFI | OB | 100%
133236 | I491TM05-0RXEA01-003-001 | Saddle of Horizontal Pre-heating Station Welding 1-2 | 00 | 2018-06-09 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | TAM | 2018-06-11 10:51 | IFI | OB | 100%
133237 | I491TM05-0RXEA01-003-002 | Saddle of Horizontal Pre-heating Station Welding (parts) 2-2 | 00 | 2018-06-09 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | TAM | 2018-06-11 10:51 | IFI | OB | 100%
114724 | I491TM05-0RXGA01-001-001 | EMERGENCY STIRRING LANCE LANCES ASSEMBLY DRAWING | 00 | 2015-11-28 | Indeterminate | Drawing | Detail | Ladle Furnace Auxiliary | Mechanical | CEBA | 2015-12-05 15:10 | IFA | AC |  | 95%
114725 | I491TM05-0RXGA01-002-001 | EMERGENCY STIRRING LANCE ARGON LINE | 00 | 2015-11-28 | Indeterminate | Drawing | Detail | Ladle Furnace Auxiliary | Mechanical | CEBA | 2015-12-05 15:10 | IFA | AC |  | 95%
114638 | I491TM05-0RXLE02-001-001 | LF Roof Carrier | 01 | 2015-10-26 11:21 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | TAM | 2015-10-26 11:21 | IFC | AFC | 100%
114639 | I491TM05-0RXLE03-001-001 | LF Roof Stand | 01 | 2015-10-26 11:21 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | TAM | 2015-10-26 11:21 | IFC | AFC | 100%
114782 | I491TM05-0RXLW01-001-001 | LF Roof Lifting Beam | 02 | 2015-12-21 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | TAM | 2015-12-27 10:05 | IFC | AFC | 100%
114783 | I491TM05-0RXLW01-002-001 | LF Roof Lifting Beam ASSEMBLY | 01 | 2015-12-21 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | TAM | 2015-12-27 10:06 | IFC | AFC | 100%
114784 | I491TM05-0RXLW01-003-001 | LF Roof Lifting Beam AUXILIARY LAYOUT | 01 | 2015-12-21 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | TAM | 2015-12-27 10:06 | IFC | AFC | 100%
16253 | I491TM05-0SXBT91-002-003 | Ladle Transfer Car Eaf Wheel Assembly | 01 | 2013-10-09 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | TAM |  | IFI | OB | 100%
16256 | I491TM05-0SXBT91-003-003 | Wheel Assembly W.A Driven With Flange | 01 | 2013-10-09 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | TAM |  | IFI | OB | 100%
16259 | I491TM05-0SXBT91-004-003 | Wheel Assembly W.A Driven With Flange | 01 | 2013-10-09 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | TAM |  | IFI | OB | 100%
16262 | I491TM05-0SXBT91-005-003 | Wheel Assembly W.A Driven Without Flange | 01 | 2013-10-09 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | TAM |  | IFI | OB | 100%
16265 | I491TM05-0SXBT91-006-003 | Wheel Assembly Wheel Ass.Not Driven W.F.L | 01 | 2013-10-09 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | TAM |  | IFI | OB | 100%
16268 | I491TM05-0SXBT91-007-003 | Wheel Assembly Wheel Ass.Not Driven W.F.L | 01 | 2013-10-09 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | TAM |  | IFI | OB | 100%
16271 | I491TM05-0SXBT91-008-003 | Wheel Assembly Wheel Ass.Not Driven W.F.L | 01 | 2013-10-09 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | TAM |  | IFI | OB | 100%
16274 | I491TM05-0SXBT91-009-003 | Wheel Assembly Wa Driven With Flange | 01 | 2013-10-09 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | TAM |  | IFI | OB | 100%
114641 | I491TM05-0SXFG01-001-001 | EAF Roof Temporary Stand | 01 | 2015-10-26 13:22 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | TAM | 2015-10-26 13:22 | IFC | AFC | 100%
114642 | I491TM05-0SXFG01-002-001 | EAF Roof Temporary Stand with Ladder | 01 | 2015-10-26 13:22 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | TAM | 2015-10-26 13:22 | IFC | AFC | 100%
130256 | I491TM05-0SXFM03-001-001 | Lower Shell Temporary Stand Welding 1-3 | 02 | 2017-01-23 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | TAM | 2017-01-24 16:19 | IFC | AFC | 100%
130255 | I491TM05-0SXFM03-001-002 | Lower Shell Temporary Stand Welding Parts 2-3 | 01 | 2017-01-23 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | TAM | 2017-01-24 16:19 | IFC | AFC | 100%
130254 | I491TM05-0SXFM03-001-003 | Lower Shell Temporary Stand Installation 3-3 | 01 | 2017-01-23 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | TAM | 2017-01-24 16:19 | IFC | AFC | 100%
114643 | I491TM05-0SXFM04-001-001 | Upper Shell Stand | 01 | 2015-10-26 13:22 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | TAM | 2015-10-26 13:22 | IFC | AFC | 100%
118068 | I491TM05-0SXHB01-001-001 | Saddle of Horizontal Station in Horizontal Ladle Preheater and Debricking Stations 1-2 | 00 | 2016-08-01 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | TAM | 2016-08-04 09:28 | IFI | OB | 100%
118069 | I491TM05-0SXHB01-001-002 | Saddle of Horizontal Station Welding in Horizontal Ladle Preheater and Debricking Stations 2-2 | 00 | 2016-08-01 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | TAM | 2016-08-04 09:28 | IFI | OB | 100%
114644 | I491TM05-0SXIE03-001-001 | Electrode Settle Stand | 01 | 2015-10-26 13:22 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | TAM | 2015-10-26 13:22 | IFC | AFC | 100%
114645 | I491TM05-0SXLD02-001-001 | Ladle Centring Stand | 01 | 2015-10-26 13:23 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | TAM | 2015-10-26 13:23 | IFC | AFC | 100%
114646 | I491TM05-0SXLW01-001-001 | EAF CROSS BEAM ASSY | 02 | 2015-10-26 13:23 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | TAM | 2015-10-26 13:23 | IFC | AFC | 100%
114647 | I491TM05-0SXLW01-002-001 | EAF CROSS BEAM CONNECTING PLATES | 02 | 2015-10-26 13:23 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | TAM | 2015-10-26 13:23 | IFC | AFC | 100%
114648 | I491TM05-0SXLW01-003-001 | EAF CROSS BEAM SHAFT | 02 | 2015-10-26 13:23 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | TAM | 2015-10-26 13:23 | IFC | AFC | 100%
114649 | I491TM05-0SXLW01-004-001 | EAF CROSS BEAM SHAFT HOLDER | 02 | 2015-10-26 13:23 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | TAM | 2015-10-26 13:23 | IFC | AFC | 100%
114752 | I491TM06-0ASCT01-001-001 | Air Cooling Tower General Drawing | 00 | 2015-12-08 | Indeterminate | Drawing | Detail | Air Separation Plant | Piping & Utility | Fortune | 2015-12-26 12:53 | IFI | OB | 100%
114753 | I491TM06-0ASCT01-002-001 | Water Cooling Tower General Drawing | 00 | 2015-12-08 | Indeterminate | Drawing | Detail | Air Separation Plant | Piping & Utility | Fortune | 2015-12-26 12:53 | IFI | OB | 100%
114754 | I491TM06-0ASFL01-001-001 | Instrument Gas Filter General Drawing | 00 | 2015-12-08 | Indeterminate | Drawing | Detail | Air Separation Plant | Piping & Utility | Fortune | 2015-12-26 12:53 | IFI | OB | 100%
114755 | I491TM06-0ASHX01-001-001 | Electrical Heater General Drawing | 00 | 2015-12-08 | Indeterminate | Drawing | Detail | Air Separation Plant | Piping & Utility | Fortune | 2015-12-26 12:53 | IFI | OB | 100%
114756 | I491TM06-0ASIJ01-001-001 | Cold box general drawing | 00 | 2015-12-08 | Indeterminate | Drawing | Detail | Air Separation Plant | Piping & Utility | Fortune | 2015-12-26 12:54 | IFI | OB | 100%
114757 | I491TM06-0ASPS01-001-001 | Absorber General Drawing | 00 | 2015-12-08 | Indeterminate | Drawing | Detail | Air Separation Plant | Piping & Utility | Fortune | 2015-12-26 12:54 | IFI | OB | 100%
114758 | I491TM06-0ASPS01-002-001 | PPU Skid General Drawings Sheet 1 | 00 | 2015-12-08 | Indeterminate | Drawing | Detail | Air Separation Plant | Piping & Utility | Fortune | 2015-12-26 12:54 | IFI | OB | 100%
114759 | I491TM06-0ASPS01-002-002 | PPU Skid General Drawings Sheet 2 | 00 | 2015-12-08 | Indeterminate | Drawing | Detail | Air Separation Plant | Piping & Utility | Fortune | 2015-12-26 12:54 | IFI | OB | 100%
114760 | I491TM06-0ASSL01-001-001 | Silencer General Drawing (SL1201) | 00 | 2015-12-08 | Indeterminate | Drawing | Detail | Air Separation Plant | Piping & Utility | Fortune | 2015-12-26 12:54 | IFI | OB | 100%
114761 | I491TM06-0ASSL02-001-001 | Oxygen Silencer General Drawing | 00 | 2015-12-08 | Indeterminate | Drawing | Detail | Air Separation Plant | Piping & Utility | Fortune | 2015-12-26 12:55 | IFI | OB | 100%
114762 | I491TM06-0ASSL03-001-001 | Nitrogen Silencer General Drawing | 00 | 2015-12-08 | Indeterminate | Drawing | Detail | Air Separation Plant | Piping & Utility | Fortune | 2015-12-26 12:55 | IFI | OB | 100%
114763 | I491TM06-0ASTK01-001-001 | Liquid Oxygen Tank General Drawing | 00 | 2015-12-08 | Indeterminate | Drawing | Detail | Air Separation Plant | Piping & Utility | Fortune | 2015-12-26 12:55 | IFI | OB | 100%
114764 | I491TM06-0ASTK02-001-001 | Liquid Nitrogen Tank General Drawing | 00 | 2015-12-08 | Indeterminate | Drawing | Detail | Air Separation Plant | Piping & Utility | Fortune | 2015-12-26 12:55 | IFI | OB | 100%
114765 | I491TM06-0ASTK03-001-001 | Liquid Argon Tank General Drawing | 00 | 2015-12-08 | Indeterminate | Drawing | Detail | Air Separation Plant | Piping & Utility | Fortune | 2015-12-26 12:55 | IFI | OB | 100%
114766 | I491TM06-0ASTK04-001-001 | Oxygen Buffer Tank General Drawing | 00 | 2015-12-08 | Indeterminate | Drawing | Detail | Air Separation Plant | Piping & Utility | Fortune | 2015-12-26 12:56 | IFI | OB | 100%
114767 | I491TM06-0ASTK05-001-001 | Nitrogen Buffer Tank General Drawing | 00 | 2015-12-08 | Indeterminate | Drawing | Detail | Air Separation Plant | Piping & Utility | Fortune | 2015-12-26 12:56 | IFI | OB | 100%
114768 | I491TM06-0ASTK06-001-001 | Argon Buffer Tank General Drawing | 00 | 2015-12-08 | Indeterminate | Drawing | Detail | Air Separation Plant | Piping & Utility | Fortune | 2015-12-26 12:56 | IFI | OB | 100%
114769 | I491TM06-0ASVS01-001-001 | Waste Liquid Vaporizer General Drawing | 00 | 2015-12-08 | Indeterminate | Drawing | Detail | Air Separation Plant | Piping & Utility | Fortune | 2015-12-26 12:56 | IFI | OB | 100%
114770 | I491TM06-0ASVS02-001-001 | Liquid Oxygen Vaporizer General Grawing | 00 | 2015-12-08 | Indeterminate | Drawing | Detail | Air Separation Plant | Piping & Utility | Fortune | 2015-12-26 12:57 | IFI | OB | 100%
114771 | I491TM06-0ASVS03-001-001 | Liquid Nitrogen Vaporizer General Drawing | 00 | 2015-12-08 | Indeterminate | Drawing | Detail | Air Separation Plant | Piping & Utility | Fortune | 2015-12-26 12:57 | IFI | OB | 100%
114772 | I491TM06-0ASVS04-001-001 | Liquid Argon Vaporizer General Drawing | 00 | 2015-12-08 | Indeterminate | Drawing | Detail | Air Separation Plant | Piping & Utility | Fortune | 2015-12-26 12:57 | IFI | OB | 100%
114773 | I491TM06-0ASXX01-001-001 | DCAC Skid General Drawing | 00 | 2015-12-08 | Indeterminate | Drawing | Detail | Air Separation Plant | Piping & Utility | Fortune | 2015-12-26 12:57 | IFI | OB | 100%
114774 | I491TM06-0ASXX02-001-001 | Nitrogen Pressure Reducer General Drawing | 00 | 2015-12-08 | Indeterminate | Drawing | Detail | Air Separation Plant | Piping & Utility | Fortune | 2015-12-26 12:58 | IFI | OB | 100%
114775 | I491TM06-0ASXX03-001-001 | Argon Pressure Reducer General Drawing | 00 | 2015-12-08 | Indeterminate | Drawing | Detail | Air Separation Plant | Piping & Utility | Fortune | 2015-12-26 12:58 | IFI | OB | 100%
114776 | I491TM06-0ASXX04-001-001 | After Cooler General Drawing | 00 | 2015-12-08 | Indeterminate | Drawing | Detail | Air Separation Plant | Piping & Utility | Fortune | 2015-12-26 12:58 | IFI | OB | 100%
131364 | I491TM06-0MYAA91-001-009 | Maintenance Work Shop Spaces And Equipments layout Plan | 08 | 2017-10-08 | Indeterminate | Drawing | Basic | Maintenance Workshop | Mechanical | TAM | 2017-10-11 14:08 | IFC | AFC | 100%
131164 | I491TM07-0CCAA91-001-001 | Contineous Casting Machine Bill Of Material | 00 | 2017-09-12 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2017-09-17 12:37 | IFI | AC |  | 95%
132577 | I491TM07-0CCFF02-001-001 | CCM TUNDISH REFRACTORY TEMPLATE FOR PERMANENT LINING BOM | 00 | 2017-12-23 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2017-12-27 10:55 | IFI | OB | 100%
132603 | I491TM07-0CCFF03-001-001 | CCM TUNDISH REFRACTORY TEMPLATE FOR TUNDISH WEAR BOM | 00 | 2017-12-23 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2017-12-27 10:59 | IFI | OB | 100%
134227 | I491TM07-0CCHB01-001-001 | Combustion System For Tundish Preheating System | 00 | 2018-09-22 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | CEBA | 2018-09-30 11:39 | IFI | OB | 100%
134226 | I491TM07-0CCHB01-002-001 | Hydraulic Equipment For Tundish Preheating Station | 00 | 2018-09-22 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | CEBA | 2018-09-30 11:39 | IFI | OB | 100%
134225 | I491TM07-0CCHB02-001-001 | Combustion Equipment For Sen Preheating Stove | 00 | 2018-09-22 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | CEBA | 2018-09-30 11:39 | IFI | OB | 100%
134224 | I491TM07-0CCHB03-001-001 | Combustion Equipment For Sen & Nozzle Preheating Station (Venturi Type) | 00 | 2018-09-22 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | CEBA | 2018-09-30 11:38 | IFI | OB | 100%
134229 | I491TM07-0CCTD10-001-001 | Combustion System For Tundish Drying Station | 00 | 2018-09-22 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | CEBA | 2018-09-30 11:39 | IFI | OB | 100%
134228 | I491TM07-0CCTD10-002-001 | Hydraulic Equipment For Tundish Drying Station | 00 | 2018-09-22 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | CEBA | 2018-09-30 11:39 | IFI | OB | 100%
115277 | I491TM07-0EAFG08-004-001 | EF.07.500.WLD-D-20.00.002.732 SUPPORT 2 LEFT BOM | 00 | 2016-05-10 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS | 2016-05-24 16:57 | IFI | OB | 100%
115278 | I491TM07-0EAFG08-005-001 | EF.07.500.WLD-D-20.00.002.734 SUPPORT 2 RIGHT BOM | 00 | 2016-05-10 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS | 2016-05-24 16:57 | IFI | OB | 100%
115279 | I491TM07-0EAFG08-006-001 | EF.07.500.WLD-D-20.00.002.735 SUPPORT 1 RIGHT BOM | 00 | 2016-05-10 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS | 2016-05-24 16:57 | IFI | OB | 100%
115280 | I491TM07-0EAFG08-007-001 | EF.07.500.WLD-D-20.00.002.736 SUPPORT 1 LEFT BOM | 00 | 2016-05-10 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS | 2016-05-24 16:57 | IFI | OB | 100%
115281 | I491TM07-0EAFG08-008-001 | EF.07.500.WLD-D-20.00.002.738 SUPPORT 3 RIGHT BOM | 00 | 2016-05-10 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS | 2016-05-24 16:57 | IFI | OB | 100%
115282 | I491TM07-0EAFG08-009-001 | EF.07.500.WLD-D-20.00.002.741 SUPPORT 3 LEFT BOM | 00 | 2016-05-10 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS | 2016-05-24 16:57 | IFI | OB | 100%
115283 | I491TM07-0EAFG08-010-001 | EF.07.500.WLD-D-20.00.002.743 SUPPORT 4 LEFT BOM | 00 | 2016-05-10 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS | 2016-05-24 16:57 | IFI | OB | 100%
115284 | I491TM07-0EAFG08-011-001 | EF.07.500.WLD-D-20.00.002.744 SUPPORT 4 RIGHT BOM | 00 | 2016-05-10 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS | 2016-05-24 16:57 | IFI | OB | 100%
115285 | I491TM07-0EAFG08-012-001 | EF.07.500.WLD-D-20.00.002.746 SUPPORT 5 LEFT BOM | 00 | 2016-05-10 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS | 2016-05-24 16:57 | IFI | OB | 100%
115286 | I491TM07-0EAFG08-013-001 | EF.07.500.WLD-D-20.00.002.747 SUPPORT 5 RIGHT BOM | 00 | 2016-05-10 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS | 2016-05-24 16:57 | IFI | OB | 100%
115287 | I491TM07-0EAFG08-014-001 | EF.07.500.WLD-D-20.00.002.748 SUPPORT 6 LEFT BOM | 00 | 2016-05-10 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS | 2016-05-24 16:57 | IFI | OB | 100%
115288 | I491TM07-0EAFG21-001-001 | EF.07.500.WLD-D-20.00.002.749 SUPPORT 6 RIGHT BOM | 00 | 2016-05-10 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS | 2016-05-24 17:00 | IFI | OB | 100%
115289 | I491TM07-0EAFG22-001-001 | EF.07.500.WLD-D-20.00.002.750 SUPPORT 7.1 BOM | 00 | 2016-05-10 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS | 2016-05-24 17:00 | IFI | OB | 100%
130097 | I491TM07-0LFRL01-001-001 | D-20.00.001.504 Bill Of Material ELECTRO.1 | 00 | 2017-01-09 09:04 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | FUCHS | 2017-01-09 09:04 | IFI | OB | 100%
112388 | I491TM07-0MMCT01-001-001 | Material Take Off For Cooling Tower (Internals) For Cooling System (Ct01) | 00 | 2013-06-12 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Piping & Utility | TAM | 2014-06-10 10:38 | IFI | OB | 100%
16285 | I491TM07-0MMCT02-001-001 | Material Take Off For Cooling Tower (Internals) For Cooling System (Ct02) | 00 | 2013-06-12 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Piping & Utility | TAM |  | IFI | OB | 100%
114682 | I491TM07-0PXHB91-002-001 | Horizontal Ladle Preheater Bill of Material | 00 | 2015-11-23 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop Auxiliaries | Mechanical | TAM | 2015-11-24 10:58 | IFI | OB | 100%
114728 | I491TM07-0RXGA01-001-001 | Emergency Stirring Lance Bill of Materia | 00 | 2015-12-05 15:17 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace Auxiliary | Mechanical | CEBA | 2015-12-05 15:17 | IFI | OB | 100%
114733 | I491TM07-0RXLY01-001-001 | Temperature and Sampling Manipulator Bill of Material | 00 | 2015-11-28 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace Auxiliary | Mechanical | CEBA | 2015-12-07 10:34 | IFI | OB | 100%
114721 | I491TM07-0RXWH91-001-001 | Wire Feeder Bill of Material | 00 | 2015-11-28 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace Auxiliary | Mechanical | CEBA | 2015-12-01 11:20 | IFI | A | 100%
114751 | I491TM07-0SXCJ91-001-001 | Carbon Injection System Bill of Material | 00 | 2015-12-07 11:16 | Indeterminate | Miscellaneous(MISC) | Detail | Eaf Auxiliaries | Mechanical | TAM | 2015-12-07 11:16 | IFI | OB | 100%
114705 | I491TM07-0SXHB91-003-001 | Vertical Ladle Preheater Bill of Material | 00 | 2015-11-24 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop Auxiliaries | Mechanical | CEBA | 2015-11-25 10:23 | IFI | OB | 100%
114677 | I491TM07-0SXLD91-001-001 | Vertical Ladle Dryer Bill of Material | 00 | 2015-11-22 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop Auxiliaries | Mechanical | TAM | 2015-11-23 11:25 | IFI | OB | 100%
133399 | I491TM08-0CHEU02-001-001 | 7.2.3.1 roller Ø188 with rotating groove_K1-76.0860E-2-a | 00 | 2018-06-25 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-07 11:37 | IFI | OB | 100%
133398 | I491TM08-0CHEU02-002-001 | 7.2.3.2 pulley Ø700 for rope_K1-93.5780D-701 | 00 | 2018-06-25 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-07 11:37 | IFI | OB | 100%
133397 | I491TM08-0CHEU02-003-001 | 7.2.3.3 pulley Ø460 for rope 20_K1-93.5460E-460-d | 00 | 2018-06-25 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-07 11:37 | IFI | OB | 100%
133764 | I491TM08-0CHEU03-001-001 | 7.2.3.1 Assembly drawing trolley 90-30-5t K2-1570.1500A-4 | 00 | 2018-07-08 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-14 11:24 | IFI | OB | 100%
133763 | I491TM08-0CHEU03-002-001 | 7.2.3.2 Assembly drawing crane bridge K2-1570.0100A-4 | 00 | 2018-07-08 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-14 11:24 | IFI | OB | 100%
133766 | I491TM08-0CHEU04-001-001 | 7.2.4.1 Assembly drawing trolley 90-30-5t K2-1570.1600A-4 | 00 | 2018-07-08 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-14 11:25 | IFI | OB | 100%
133765 | I491TM08-0CHEU04-002-001 | 7.2.4.2 Assembly drawing crane bridge K2-1570.1000A-4 | 00 | 2018-07-08 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-14 11:25 | IFI | OB | 100%
133769 | I491TM08-0CHEU05-001-001 | 7.2.3.1 Assembly drawing crane bridge K2-1570.2000A-4 | 00 | 2018-07-08 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-14 11:25 | IFI | OB | 100%
133768 | I491TM08-0CHEU05-002-001 | 7.2.3.2 Assembly drawing trolley 28t K2-1570.3000A-4 | 00 | 2018-07-08 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-14 11:25 | IFI | OB | 100%
133767 | I491TM08-0CHEU05-003-001 | 7.2.3.3 Assembly drawing trolley 28t K2-1570.3100A-4 | 00 | 2018-07-08 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-14 11:25 | IFI | OB | 100%
133772 | I491TM08-0CHEU06-001-001 | 7.2.3.1 Assembly drawing crane bridge K2-1570.2100A-4 | 00 | 2018-07-08 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-14 11:26 | IFI | OB | 100%
133771 | I491TM08-0CHEU06-002-001 | 7.2.3.2 Assembly drawing trolley 28t K2-1570.3000A-4 | 00 | 2018-07-08 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-14 11:26 | IFI | OB | 100%
133770 | I491TM08-0CHEU06-003-001 | 7.2.3.3 Assembly drawing trolley 28t K2-1570.3100A-4 | 00 | 2018-07-08 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-14 11:26 | IFI | OB | 100%
133774 | I491TM08-0CHEU07-001-001 | 7.2.3.1 Crane bridge K2-1570.4000A-4 | 00 | 2018-07-08 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-14 11:26 | IFI | OB | 100%
133773 | I491TM08-0CHEU07-002-001 | 7.2.3.2 Trolley K2-1570.4700A-4 | 00 | 2018-07-08 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-14 11:26 | IFI | OB | 100%
133776 | I491TM08-0CHEU08-001-001 | 7.2.3.1 Crane bridge K2-1570.4100A-4 | 00 | 2018-07-08 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-14 11:27 | IFI | OB | 100%
133775 | I491TM08-0CHEU08-002-001 | 7.2.3.2 Trolley K2-1570.6000A-4 | 00 | 2018-07-08 | Indeterminate | Drawing | Detail | Crane and Hiosts | Mechanical | Voith | 2018-07-14 11:27 | IFI | OB | 100%
114726 | I491TM08-0RXGA01-001-001 | EMERGENCY STIRRING LANCE SPARE PARTS DRAWING | 00 | 2015-11-28 | Indeterminate | Drawing | Detail | Ladle Furnace Auxiliary | Mechanical | CEBA | 2015-12-05 15:10 | IFA | AC |  | 95%
114731 | I491TM08-0RXLY01-001-001 | TEMPERATURE & SAMPLING MANIPULATOR SPARE PARTS DRAWING | 00 | 2015-11-28 | Indeterminate | Drawing | Detail | Ladle Furnace Auxiliary | Mechanical | CEBA | 2015-12-07 10:05 | IFA | AC |  | 95%
114719 | I491TM08-0RXWH91-001-001 | WIRE INJECTION MACHINE SPARE PARTS 090-DM-04137-2 | 00 | 2015-11-28 | Indeterminate | Drawing | Detail | Ladle Furnace Auxiliary | Mechanical | TAM | 2015-12-01 10:06 | IFA | A | 100%
114685 | I491TM08-0SXHB01-002-001 | HORIZONTAL LADLE PREHEATER SPARE PARTS DRAWING | 00 | 2015-11-23 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | TAM | 2015-11-24 10:58 | IFA | A | 100%
114737 | I491TM08-0SXHB91-003-001 | VERTICAL LADLE PREHEATER SPARE PARTS DRAWING | 00 | 2015-11-30 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | CEBA | 2015-12-07 10:44 | IFA | AC |  | 95%
114679 | I491TM08-0SXLD91-001-001 | VERTICAL LADLE DRYER SPARE PARTS DRAWING | 00 | 2015-11-22 | Indeterminate | Drawing | Detail | Melt Shop Auxiliaries | Mechanical | TAM | 2015-11-23 11:25 | IFA | A | 100%
16287 | I491TM09-0CPDR01-001-002 | Mechanical Calculation For Dryer (Hdt-90) For Compressed Air Plant | 01 | 2013-05-25 | Indeterminate | Miscellaneous(MISC) | Detail | Compressed Air Production Plant | Piping & Utility | HAVAYAR |  | IFC | AFC | 100%
16289 | I491TM09-0CPTK01-001-002 | Mechanical Calculation For Air Receiver(Hy10000) For Compressed Air Plant | 01 | 2013-05-25 | Indeterminate | Miscellaneous(MISC) | Detail | Compressed Air Production Plant | Piping & Utility | HAVAYAR |  | IFC | AFC | 100%
16290 | I491TM09-0MDCH92-001-001 | Calculation Sheet For Material Handling System Diverters | 00 | 2013-10-02 | Indeterminate | Miscellaneous(MISC) | Basic | Material Handling | Mechanical | DATIS |  | IFI | OB | 100%
16291 | I491TM09-0MDCH92-002-001 | Calculation Sheet For Material Handling System Swiveling Chutes | 00 | 2013-10-02 | Indeterminate | Miscellaneous(MISC) | Detail | Material Handling | Mechanical | TAM |  | IFI | OB | 100%
16292 | I491TM09-0MDCV92-001-001 | Calculation Sheet For Belt Conveyors Of Material Handling System | 00 | 2013-06-18 | Indeterminate | Miscellaneous(MISC) | Basic | Material Handling | Mechanical | DATIS |  | IFI | OB | 100%
16293 | I491TM09-0MDTK92-001-001 | Calculation Sheet For Melt Shop Storage Bins | 00 | 2013-06-08 | Indeterminate | Miscellaneous(MISC) | Basic | Material Handling | Mechanical | DATIS |  | IFI | OB | 100%
16294 | I491TM09-0MDTK92-002-001 | Calculation Sheet For Outdoor Storage Bins | 00 | 2013-06-08 | Indeterminate | Miscellaneous(MISC) | Basic | Material Handling | Mechanical | DATIS |  | IFI | OB | 100%
113103 | I491TM09-0OFAM91-001-001 | calculation Book Office Mechanical | 01 | 2014-12-10 | Indeterminate | Miscellaneous(MISC) | Detail | Office - Canteen - Locker & Shower For Melt Shop | Civil and Steel Structure | TAM | 2014-12-15 08:51 | IFC | AC |  | 95%
16295 | I491TM99-0DTPP91-001-001 | Basic Data For Duct Work Of Ftp | 00 | 2012-05-15 | Indeterminate | Miscellaneous(MISC) | Basic | Fume Treatment Equipment | Mechanical | HASCON |  | IFA | AC |  | 95%
130110 | I491TM99-0EAFG03-001-001 | D-10.00.002.467A SHIPPING DRAWING OFF GAS DUCT ROOF EAF | 00 | 2017-01-08 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS | 2017-01-09 09:16 | IFI | OB | 100%
130111 | I491TM99-0EAFM01-001-001 | D-31.00.000.262D WATER BALCONY PANELS WATER UPPER SHELL | 00 | 2017-01-08 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS | 2017-01-09 09:16 | IFI | OB | 100%
130112 | I491TM99-0EAFM02-001-001 | D-10.00.002.656E FOx-TECHNOLOGY UPPER SHELL | 00 | 2017-01-08 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS | 2017-01-09 09:17 | IFI | OB | 100%
130113 | I491TM99-0EAFM03-001-001 | D-31.00.000.269A WATER AT SHELL FLEXIBLE HOSES DN50-1400 | 00 | 2017-01-08 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS | 2017-01-09 09:17 | IFI | OB | 100%
130114 | I491TM99-0EAFM03-001-002 | D-20.00.003.166 VERROHRUNG TRAFOHAUSWAND WADDER LF | 00 | 2017-01-08 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS | 2017-01-09 09:19 | IFI | OB | 100%
130116 | I491TM99-0EASS01-001-001 | D-30.00.000.564G STEEL STRUCTURE | 00 | 2017-01-08 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS | 2017-01-09 09:20 | IFI | OB | 100%
130115 | I491TM99-0EASS01-003-001 | D-10.00.003.724 SHIPPING DRAWING ROOF PANEL ROOF EAF | 00 | 2017-01-08 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS | 2017-01-09 09:20 | IFI | OB | 100%
113585 | I491TM99-0LFAA92-002-001 | LADLE FURNACE - STEEL PRODUCTION | 00 | 2015-05-06 | Indeterminate | Miscellaneous(MISC) | Basic | Ladle Furnace | Mechanical | FUCHS | 2015-05-27 16:10 | IFI | OB | 100%
113586 | I491TM99-0LFAA92-003-001 | LADLE FURNACE - STEEL PRODUCTION | 00 | 2015-05-06 | Indeterminate | Miscellaneous(MISC) | Basic | Ladle Furnace | Mechanical | FUCHS | 2015-05-27 16:10 | IFI | OB | 100%
113587 | I491TM99-0LFAA92-004-001 | LADLE FURNACE - STEEL PRODUCTION | 00 | 2015-05-06 | Indeterminate | Drawing | Basic | Ladle Furnace | Mechanical | FUCHS | 2015-05-27 16:10 | IFI | OB | 100%
113588 | I491TM99-0LFAA92-005-001 | LADLE FURNACE - STEEL PRODUCTION | 00 | 2015-05-06 | Indeterminate | Drawing | Basic | Ladle Furnace | Mechanical | FUCHS | 2015-05-27 16:10 | IFI | OB | 100%
113589 | I491TM99-0LFLE91-001-001 | EARTHING - GANTRY LF | 00 | 2015-05-06 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | TAM | 2015-05-27 16:10 | IFI | OB | 100%
113590 | I491TM99-0LFLE91-002-001 | EARTHING - GANTRY LF | 00 | 2015-05-06 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | TAM | 2015-05-27 16:10 | IFI | OB | 100%
113591 | I491TM99-0LFLE91-003-001 | EARTHING - GANTRY LF | 00 | 2015-05-06 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | TAM | 2015-05-27 16:10 | IFI | OB | 100%
16297 | I491TM99-0MDAA91-002-002 | Design Criteria For Belt Conveyors , Bins & Pocket Belt Conveyors | 01 | 2013-09-01 | Indeterminate | Miscellaneous(MISC) | Basic | Material Handling | Mechanical | DATIS |  | IFC | AFC | 100%
16298 | I491TM99-0MDAA91-003-001 | Process Description For Material Handling System | 00 | 2013-06-11 | Indeterminate | Miscellaneous(MISC) | Basic | Material Handling | Mechanical | DATIS |  | IFA | A | 100%
16299 | I491TM99-0MDAA91-004-001 | Data Sheet For Pocket Belt Of Conveyors | 03 | 2013-07-13 | Indeterminate | Miscellaneous(MISC) | Basic | Material Handling | Mechanical | DATIS |  | IFI | OB | 100%
16300 | I491TM99-0MDAA91-004-002 | Data sheet For Drive Units Of Material Handling Equipment | 02 | 2013-07-13 | Indeterminate | Miscellaneous(MISC) | Basic | Material Handling | Mechanical | DATIS |  | IFI | OB | 100%
115771 | I491TM99-0MDAA91-008-001 | MATERIAL HANDLING SYSTEM SAFETY LAYOUT FOR EAF | 00 | 2016-06-21 14:30 | Indeterminate | Miscellaneous(MISC) | Detail | Material Handling | Mechanical | DATIS | 2016-06-21 14:30 | IFA | AC |  | 95%
115766 | I491TM99-0MDAA91-009-001 | MATERIAL HANDLING SYSTEM SAFETY LAYOUT FOR EAF SECTION A-A & B-B & C-C & D-D | 00 | 2016-06-21 14:30 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | DATIS | 2016-06-21 14:30 | IFA | AC |  | 95%
115767 | I491TM99-0MDAA91-010-001 | MATERIAL HANDLING SYSTEM SAFETY LAYOUT FOR EAF SECTION E-E & F-F & G-G | 00 | 2016-06-21 14:30 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | DATIS | 2016-06-21 14:30 | IFA | AC |  | 95%
115768 | I491TM99-0MDAA91-011-001 | MATERIAL HANDLING SYSTEM SAFETY LAYOUT FOR EAF SECTION H-H & J-J & K-K | 00 | 2016-06-21 14:30 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | DATIS | 2016-06-21 14:30 | IFA | AC |  | 95%
115769 | I491TM99-0MDAA91-012-001 | MATERIAL HANDLING SYSTEM SAFETY LAYOUT DRI CHARGING | 00 | 2016-06-21 14:30 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | DATIS | 2016-06-21 14:30 | IFA | AC |  | 95%
115770 | I491TM99-0MDAA91-013-001 | MATERIAL HANDLING SYSTEM SAFETY LAYOUT FOR LF AREA | 00 | 2016-06-21 14:30 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | DATIS | 2016-06-21 14:30 | IFA | AC |  | 95%
16302 | I491TM99-0MEAC92-001-002 | Technical Specification And Data Sheet For Mechanical Hvac System | 01 | 2012-01-17 | Indeterminate | Miscellaneous(MISC) | Basic | Main Electrical Substation And Distribution Network | Electrical | TAM |  | IFC | AFC | 100%
16304 | I491TM99-0MEEG92-001-002 | Technical Specification And Data Sheet For Standby Diesel Generator | 01 | 2012-01-17 | Indeterminate | Miscellaneous(MISC) | Basic | Main Electrical Substation And Distribution Network | Electrical | TAM |  | IFC | AFC | 100%
134640 | I491TM99-0PXFD91-001-001 | Melt Shop Debricking Machine Safety Decals -10800491 | 00 | 2018-12-12 | Indeterminate | Drawing | Detail | Mobile Equipment | Mechanical | TAM | 2018-12-17 09:25 | IFI | OB | 100%
16307 | I491TM99-0SHIK92-001-003 | Welding Procedure Specification (Wps) For Scrap Bucket | 02 | 2012-10-21 | Indeterminate | Miscellaneous(MISC) | Detail | Scrap Yard Equipment | Mechanical | TAM |  | IFC | AFC | 100%
16311 | I491TM99-0SXBT92-001-004 | Welding Procedure Specification (Wps) For Transfer Car | 03 | 2013-03-04 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop Auxiliaries | Mechanical | TAM |  | IFC | AFC | 100%
16312 | I491TMO1-0CPFL02-001-001 | Data Sheet Pre Filter (Afm 0706) For Compressed Air Plant | 01 | 2013-05-25 | Indeterminate | Miscellaneous(MISC) | Detail | Compressed Air Production Plant | Piping & Utility | TAM |  | IFC | AFC | 100%
113347 | I491TQ02-999AA91-001-004 | General Inspection Procedure | 02 | 2011-12-31 | Indeterminate | Miscellaneous(MISC) | Detail | General | Mechanical | TAM | 2015-02-17 14:14 | IFC | AFC | 100%
115652 | I491TQ03-0AAVA92-001-001 | Quality Control Plan (QCP) For Casting Valves | 01 | 2016-05-30 | Indeterminate | Miscellaneous(MISC) | Basic | General | Piping & Utility | TAM | 2016-05-31 11:31 | IFC | AFC | 100%
130315 | I491TQ03-0ASAA01-001-001 | Quality Control Plan (QCP) ForAir Separation Plant | 03 | 2017-02-13 | Indeterminate | Miscellaneous(MISC) | Basic | Air Separation Plant | Piping & Utility | TAM | 2017-02-16 10:37 | IFC | AFC | 100%
16324 | I491TQ03-0CAAA01-001-004 | Quality Control Plan (Qcp) For Compressed Air Plant | 03 | 2013-11-06 | Indeterminate | Miscellaneous(MISC) | Basic | Compressed Air Production Plant | Piping & Utility | TAM |  | IFC | AFC | 100%
130253 | I491TQ03-0CCAA01-001-001 | Quality Control Plan (QCP) For New Billet ccm For 800 KTPY | 01 | 2017-01-22 | Indeterminate | Miscellaneous(MISC) | Basic | Continuous Casting Machine (CCM) | Mechanical | TAM | 2017-01-24 15:32 | IFC | AFC | 100%
133126 | I491TQ03-0CCTK01-001-001 | Qualty Control PLAN (QCP) for Air Receivers | 00 | 2018-05-08 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2018-05-15 09:13 | IFA | AC |  | 95%
16326 | I491TQ03-0CHEU01-001-002 | Quality Control Plan (Qcp) For Low Duty Cranes | 01 | 2013-05-18 | Indeterminate | Miscellaneous(MISC) | Detail | Crane and Hiosts | Mechanical | Crane supplier |  | IFC | A | 100%
132945 | I491TQ03-0CHEU02-001-001 | Quality Control PLAN (QCP) for Low DUTY CRANES & MONORAILS | 04 | 2018-02-28 | Indeterminate | Miscellaneous(MISC) | Basic | Crane and Hiosts | Mechanical | TAM | 2018-03-12 14:06 | IFC | AC |  | 95%
132931 | I491TQ03-0CHEU03-001-001 | Quality Control PLAN (QCP) for GANTRY CRANE & JIB CRANE | 01 | 2018-02-19 10:17 | Indeterminate | Miscellaneous(MISC) | Detail | Crane and Hiosts | Mechanical | TAM | 2018-02-19 10:17 | IFC | AFC | 100%
133167 | I491TQ03-0CHEU04-001-001 | Quality Control PLAN (QCP) for: LAMINATED HOOK TRAVERSE CAP. 80 T | 01 | 2018-05-23 | Indeterminate | Miscellaneous(MISC) | Detail | Crane and Hiosts | Mechanical | TAM | 2018-05-28 15:02 | IFC | AFC | 100%
132678 | I491TQ03-0CPDR01-001-001 | Quality Control Plan (Qcp) For Air Dryer & Air Receiver | 01 | 2018-01-13 13:18 | Indeterminate | Miscellaneous(MISC) | Detail | Compressed Air Production Plant | Mechanical | HAVAYAR | 2018-01-13 13:18 | IFC | AFC | 100%
132034 | I491TQ03-0CPFL01-001-001 | Quality Control Plan (QCP) for Filter Case | 01 | 2017-11-15 | Indeterminate | Miscellaneous(MISC) | Detail | Compressed Air Production Plant | Mechanical | HAVAYAR | 2017-11-25 09:47 | IFC | AFC | 100%
11764 | I491TQ03-0DTAA91-002-001 | Painting List For Fume Treatment Plant | 00 | 2013-05-06 | Indeterminate | Miscellaneous(MISC) | Basic | Fume Treatment Equipment | Mechanical | HASCON |  | IFA | AC |  | 95%
130262 | I491TQ03-0DTCP01-001-001 | Quality Control Plan (Qcp) For FAN CASING | 01 | 2017-01-25 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Equipment | Mechanical | FARABARD | 2017-01-31 15:45 | IFC | AFC | 100%
129790 | I491TQ03-0DTCV01-001-001 | Quality Control Plan (QCP) For FTP Chain Conveyor | 02 | 2016-11-09 | Indeterminate | Miscellaneous(MISC) | Basic | Fume Treatment Equipment | Mechanical | TAM | 2016-11-12 09:19 | IFC | AFC | 100%
114940 | I491TQ03-0DTDE01-001-001 | Quality Control Plan (QCP) For WATER COOLED DUCT & WATER COOLED PANEL | 02 | 2016-02-24 | Indeterminate | Miscellaneous(MISC) | Basic | Fume Treatment Equipment | Mechanical | TAM | 2016-02-28 09:13 | IFC | AFC | 100%
132691 | I491TQ03-0DTDE02-001-001 | Quality Control Plan (QCP) for Dedusting Duct | 00 | 2018-01-15 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Equipment | Mechanical | TAM | 2018-01-20 10:06 | IFA | A | 100%
111641 | I491TQ03-0DTFL01-001-001 | "Quality Control Plan FOR FTP EQUIPMENT & STEEL STRUCTURE" | 01 | 2014-03-08 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Equipment | Mechanical | TAM | 2014-04-24 14:47 | IFC | AFC | 100%
114307 | I491TQ03-0DTFL02-001-001 | Quailty Control Plan ( QCP) for Dedusting Bag house Cages | 01 | 2015-09-01 | Indeterminate | Miscellaneous(MISC) | Basic | Fume Treatment Equipment | Mechanical | TAM | 2015-09-02 11:02 | IFC | AFC | 100%
131399 | I491TQ03-0EAEC01-001-001 | QUALITY CONTROL PLAN (QCP) FOR Electrode Recovery Tong | 01 | 2017-10-16 | Indeterminate | Miscellaneous(MISC) | Detail | Electric Arc Furnace | Mechanical | TAM | 2017-10-18 10:10 | IFC | AFC | 100%
112777 | I491TQ03-0EAFG01-001-001 | Quality Control plan (QCP) for Upper Shell and EAF and LF Roof | 01 | 2014-09-06 18:00 | Indeterminate | Miscellaneous(MISC) | Detail | Electric Arc Furnace | Mechanical | TAM | 2014-09-06 18:00 | IFC | AFC | 100%
112274 | I491TQ03-0EAFM01-001-001 | Quality Control Plan (QCP) For EAF Lower Shell | 01 | 2014-05-24 | Indeterminate | Miscellaneous(MISC) | Detail | Electric Arc Furnace | Mechanical | TAM | 2014-05-26 15:47 | IFC | AFC | 100%
135328 | I491TQ03-0EASG01-001-001 | Quality Control Plan (QCP) For Slider Bottom Tapping | 00 | 2019-05-08 | Indeterminate | Miscellaneous(MISC) | Detail | Electric Arc Furnace | Mechanical | TAM | 2019-05-11 09:16 | IFA | AC |  | 95%
132858 | I491TQ03-0LFCT01-001-001 | QUALITY CONTROL PLAN (QCP) FOR HVAC COOLING TOWERS | 01 | 2018-02-05 08:51 | Indeterminate | Miscellaneous(MISC) | Basic | Ladle Furnace | Mechanical | TAM | 2018-02-05 08:51 | IFC | AFC | 100%
112277 | I491TQ03-0MBAA92-001-001 | "QUALIITY CONTROL PLAN FOR MEDIIA DIISTRIIBUTIION" | 01 | 2014-05-24 | Indeterminate | Miscellaneous(MISC) | Detail | Media Distribution System | Piping & Utility | TAM | 2014-05-26 15:48 | IFC | AFC | 100%
113083 | I491TQ03-0MDAA01-001-001 | Quality control plan QCP for MHS | 02 | 2014-11-23 | Indeterminate | Miscellaneous(MISC) | Detail | Material Handling | Piping & Utility | TAM | 2014-11-25 08:19 | IFC | OB | 100%
113694 | I491TQ03-0MDCH01-001-001 | Quality Control Plan (QCP) for Static Chute | 01 | 2015-05-31 | Indeterminate | Miscellaneous(MISC) | Basic | Material Handling | Mechanical | FUCHS | 2015-06-02 15:41 | IFC | AFC | 100%
11766 | I491TQ03-0MMCT01-001-002 | Quality Control Plan (Qcp) For Cooling System | 01 | 2013-04-06 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Piping & Utility | TAM |  | IFC | AFC | 100%
112888 | I491TQ03-0MMCW01-001-001 | Quality control plan QCP for Cooling Water System | 02 | 2014-09-17 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Piping & Utility | TAM | 2014-09-18 15:27 | IFC | AFC | 100%
130703 | I491TQ03-0MMCW02-001-001 | QUALITY CONTROL PLAN (QCP) FOR WTP SYSTEM | 00 | 2017-06-19 | Indeterminate | Miscellaneous(MISC) | Basic | Water Treatment System | Mechanical | TAM | 2017-06-21 11:16 | IFA | AC |  | 95%
130127 | I491TQ03-0MMHE01-001-001 | Quality Control Plan (QCP) for Plate Heat Exchanger | 01 | 2017-01-10 | Indeterminate | Miscellaneous(MISC) | Basic | Water Treatment & Cooling System | Piping & Utility | TAM | 2017-01-15 09:34 | IFC | AFC | 100%
130547 | I491TQ03-0MMOS01-001-001 | Quality Control Plan (QCP) For Oil Skimmer | 01 | 2017-05-03 | Indeterminate | Miscellaneous(MISC) | Basic | Water Treatment & Cooling System | Mechanical | TAM | 2017-05-06 14:09 | IFC | AFC | 100%
131165 | I491TQ03-0MMTK01-001-001 | Quality Control Plan (QCP) For Emergrncy tank | 02 | 2017-09-12 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Mechanical | TAM | 2017-09-17 12:40 | IFC | AFC | 100%
114397 | I491TQ03-0MNAA91-001-001 | QCP for MCC Panels | 00 | 2015-09-22 09:58 | Indeterminate | Miscellaneous(MISC) | Basic | General | Electrical | TAM | 2015-09-22 09:58 | IFA | A | 100%
114779 | I491TQ03-0MNAA91-002-001 | ITP for Control and Remote Panels | 02 | 2015-12-19 | Indeterminate | Miscellaneous(MISC) | Detail | General | Automation and Instrumentation | TAM | 2015-12-27 09:53 | IFC | AFC | 100%
135326 | I491TQ03-0MRAC02-001-001 | Quality Control Plan (QCP) For Package Unit | 00 | 2019-05-08 | Indeterminate | Miscellaneous(MISC) | Detail | Air Conditioning and Ventilation | Mechanical | TAM | 2019-05-11 09:11 | IFA | AC |  | 95%
114838 | I491TQ03-0MRAC92-001-001 | Quality Control Plan (QCP) For HVAC (Vol 01) | 01 | 2016-01-24 | Indeterminate | Miscellaneous(MISC) | Basic | Air Conditioning and Ventilation | Mechanical | TAM | 2016-02-02 09:35 | IFC | AFC | 100%
16329 | I491TQ03-0MSAA01-001-002 | Qualiity Control Plan For Fiire Fiightiing System (Voll..01) | 01 | 2013-10-15 | Indeterminate | Miscellaneous(MISC) | Detail | Fire Fighting System | Piping & Utility | TAM |  | IFC | AFC | 100%
115380 | I491TQ03-0MSAA01-002-001 | QUALITY CONTROL PLAN (QCP) FOR FIRE FIGHTING SYSTEM (Vol.02) | 03 | 2016-05-24 | Indeterminate | Miscellaneous(MISC) | Basic | Fire Fighting System | Piping & Utility | TAM | 2016-05-25 10:35 | IFC | AFC | 100%
111579 | I491TQ03-0MXAA91-001-003 | Quality Control Plan | 04 | 2014-02-18 | Indeterminate | Miscellaneous(MISC) | Detail | General | Civil and Steel Structure | TAM | 2014-04-23 17:45 | IFC | AFC | 100%
115804 | I491TQ03-0MXVA92-001-001 | WELDING PROCEDURE SPECIFICATION (WPS) For Casting Valves | 01 | 2016-07-03 10:55 | Indeterminate | Miscellaneous(MISC) | Basic | General | Piping & Utility | TAM | 2016-07-03 10:55 | IFC | A | 100%
16336 | I491TQ03-0SHIK92-001-002 | Quality Control Plan (Qcp) For Scrap Bucket | 01 | 2013-04-07 | Indeterminate | Drawing | Detail | Scrap Yard Equipment | Mechanical | TAM |  | IFC | AFC | 100%
113088 | I491TQ03-0SXAC01-001-001 | Quality Control Plan QCP for Aerator And Louver | 01 | 2014-12-01 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2014-12-06 10:25 | IFC | AFC | 100%
116173 | I491TQ03-0SXSS01-001-001 | Quality Control Plan (Qc plan) For EAF & LF Auxiliary Steel Structurs | 02 | 2016-07-13 | Indeterminate | Miscellaneous(MISC) | Basic | Eaf Auxiliaries | Mechanical | TAM | 2016-07-18 15:52 | IFC | AFC | 100%
131171 | I491TQ03-0SXSS02-001-001 | Quality Control Plan (QCP) For LF & EAF Saddle Stand | 00 | 2017-09-12 | Indeterminate | Miscellaneous(MISC) | Basic | Eaf Auxiliaries | Mechanical | TAM | 2017-09-17 14:07 | IFA | AC |  | 95%
134092 | I491TQ04-0ASCP02-001-001 | INSPECTIION AND TEST PLAN For AIR BOOSTEER COMPRESSORPACKAGE MOTOR DRIVEN | 00 | 2018-08-15 | Indeterminate | Miscellaneous(MISC) | Detail | Air Separation Plant Main Building | Mechanical | TAM | 2018-08-21 13:07 | IFI | OB | 100%
16339 | I491TQ04-0CAAA01-001-001 | Hydrostatic Test Procedure For Air Dryer (Hdt-90)& Air Receiver For Compressed Air Plant | 01 | 2013-05-14 | Indeterminate | Miscellaneous(MISC) | Basic | Compressed Air Production Plant | Piping & Utility | TAM |  | IFC | AFC | 100%
111296 | I491TQ04-0CAAA01-002-001 | Performance Test Procedure For Air Compressor | 01 | 2013-12-09 | Indeterminate | Miscellaneous(MISC) | Detail | Compressed Air Production Plant | Piping & Utility | TAM | 2014-04-15 12:08 | IFC | AFC | 100%
130437 | I491TQ04-0MMOS01-001-001 | Prformance Test Perocedure For Oil Skimmer | 00 | 2017-04-17 10:35 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Mechanical | TAM | 2017-04-17 10:35 | IFI | OB | 100%
16343 | I491TQ04-0MXAA91-001-002 | General Technical Specification For Painting Quality Control | 00 | 2011-12-18 | Indeterminate | Miscellaneous(MISC) | Detail | General | Mechanical | TAM |  | IFC | AFC | 100%
135140 | I491TQ07-0CCAA91-001-001 | Manual for CCM General Safety Rules | 00 | 2019-03-06 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2019-03-09 13:37 | IFI | OB | 100%
135141 | I491TQ07-0CCAA91-002-001 | Manual for Safety & Risk Prevention Rules for Operators | 00 | 2019-03-06 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Mechanical | TAM | 2019-03-09 13:37 | IFI | OB | 100%
130438 | I491TQ08-0ASAA01-001-001 | Welding Procedure Specification (WPS) Air Separation Plant | 00 | 2017-04-08 | Indeterminate | Miscellaneous(MISC) | Detail | Air Separation Plant | Mechanical | TAM | 2017-04-17 10:40 | IFA | AC |  | 95%
112392 | I491TQ08-0CAAA01-001-001 | Wps & Pqr For Absorber Air Dryer And Air Receiver Of Compressed Air Plant | 02 | 2013-06-08 | Indeterminate | Miscellaneous(MISC) | Detail | Compressed Air Production Plant | Piping & Utility | TAM | 2014-06-10 11:40 | IFC | AFC | 100%
16346 | I491TQ08-0CHEU01-001-003 | Weldiing Procedure Specification (Wps) For Low Duty Cranes | 02 | 2013-07-10 | Indeterminate | Miscellaneous(MISC) | Detail | Crane and Hiosts | Mechanical | Crane supplier |  | IFC | AC |  | 95%
111642 | I491TQ08-0DTFL01-001-001 | "WELDIING PROCEDURE SPECIIFIICATIION ((WPS)) FOR FTP EQUIIPMENT & STEEL STRUCTURE" | 01 | 2014-03-08 | Indeterminate | Miscellaneous(MISC) | Detail | Fume Treatment Equipment | Mechanical | TAM | 2014-04-24 14:48 | IFC | AFC | 100%
112275 | I491TQ08-0EAFG01-001-001 | "Welldiing Procedure Speciiffiicatiion (WPS) For Furnace Roof & Upper Shell" | 01 | 2014-05-24 | Indeterminate | Miscellaneous(MISC) | Detail | Electric Arc Furnace | Mechanical | TAM | 2014-05-26 15:48 | IFC | AFC | 100%
113210 | I491TQ08-0EAFM01-001-001 | Wellding Procedure Specification ((WPS)) For EAF Lower Shell | 02 | 2015-01-07 | Indeterminate | Miscellaneous(MISC) | Detail | Electric Arc Furnace | Mechanical | TAM | 2015-01-10 14:29 | IFC | AFC | 100%
112276 | I491TQ08-0MBAA92-001-001 | Welldiing Procedure Specification (WPS) For Media Distribution | 01 | 2014-05-24 | Indeterminate | Miscellaneous(MISC) | Detail | Media Distribution System | Piping & Utility | TAM | 2014-05-26 15:48 | IFC | AFC | 100%
130735 | I491TQ08-0MBAA92-002-001 | Welldiing Procedure Specification (WPS) For Stainless Steel Piping | 02 | 2017-07-02 | Indeterminate | Miscellaneous(MISC) | Detail | Media Distribution System | Piping & Utility | TAM | 2017-07-04 13:31 | IFC | AC |  | 95%
112921 | I491TQ08-0MDCV01-001-001 | WPS for MHS Conveyors | 00 | 2014-09-21 | Indeterminate | Miscellaneous(MISC) | Detail | Material Handling | Mechanical | TAM | 2014-09-22 10:22 | IFA | AC |  | 95%
114163 | I491TQ08-0MDCV01-005-001 | WPS for MHS Bin and Hopper | 01 | 2015-07-06 | Indeterminate | Miscellaneous(MISC) | Detail | Material Handling | Mechanical | TAM | 2015-07-11 09:49 | IFC | AC |  | 95%
112733 | I491TQ08-0MMAA01-001-001 | WELDING PROCEDURE SPECIFICATION (WPS) FOR COOLING WATER SYSTEM | 01 | 2014-08-30 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Piping & Utility | TAM | 2014-09-02 09:50 | IFC | AFC | 100%
131132 | I491TQ08-0MMTK01-001-001 | Welding Procedure Specification (WPS) for Emergency Tank | 00 | 2017-08-28 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Mechanical | TAM | 2017-09-06 14:31 | IFA | AC |  | 95%
16349 | I491TQ08-0MSAA01-001-002 | Weldiing Procedure Speciifiicatiion (Wps) For Fiire Fiightiing System | 01 | 2013-10-15 | Indeterminate | Miscellaneous(MISC) | Detail | Fire Fighting System | Piping & Utility | TAM |  | IFC | AFC | 100%
16350 | I491TQ08-0MSAA01-001-003 | Std Part Belt Cover Bw 1000 | 00 | 2013-10-15 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | TAM |  | IFA | A | 100%
114216 | I491TQ08-0MXSS91-002-001 | Welding Procedure Specification (WPS) For Steel Structure _Vol.2 | 01 | 2015-08-04 | Indeterminate | Miscellaneous(MISC) | Basic | General | Mechanical | TAM | 2015-08-09 10:22 | IFC | A | 100%
114910 | I491TQ08-0SXAC01-001-001 | Welding Procedure Specification (WPS) for Aerator and Louver | 02 | 2016-02-13 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop Main Building | Civil and Steel Structure | TAM | 2016-02-14 14:42 | IFA | AFC | 100%
116225 | I491TQ08-0SXSS01-001-001 | Wellding Procedure Specification (WPS) For EAF & LF Auxiliary Steel Structure | 01 | 2016-07-20 09:22 | Indeterminate | Miscellaneous(MISC) | Basic | Eaf Auxiliaries | Mechanical | TAM | 2016-07-20 09:22 | IFC | A | 100%
135531 | I491TQ99-0CHAA91-001-001 | Cranes ارزیابی ریسک برای | 00 | 2019-07-15 | Indeterminate | Miscellaneous(MISC) | Detail | Crane and Hiosts | Mechanical | TAM | 2019-07-20 09:50 | IFI | OB | 100%
135055 | I491TQ99-0EAAA91-001-001 | ارزیابی ریسک کوره قوس الکتریکی ) تیم ارزیابی ریسک پروژه فولاد بردسیر) | 00 | 2019-02-24 | Indeterminate | Miscellaneous(MISC) | Detail | Electric Arc Furnace | Mechanical | TAM | 2019-03-05 14:30 | IFI | OB | 100%
135185 | I491TQ99-0LFAA91-001-001 | ارزیابی ریسک کوره پاتیلی ) تیم ارزیابی ریسک پروژه فولاد بردسیر) | 00 | 2019-03-18 12:36 | Indeterminate | Miscellaneous(MISC) | Detail | Ladle Furnace | Mechanical | TAM | 2019-03-18 12:36 | IFI | OB | 100%
135529 | I491TQ99-0MEAA91-001-001 | Substation and Electrical Distribution System ارزیابی ریسک برای | 00 | 2019-07-15 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Electrical | TAM | 2019-07-20 09:46 | IFI | OB | 100%
134956 | I491TQ99-0MXAA91-001-001 | Health and safety risks management Procedure | 00 | 2019-01-09 | Indeterminate | Miscellaneous(MISC) | Basic | General | Mechanical | TAM | 2019-01-12 11:39 | IFA | AFC | 100%
114228 | I491TR01-0CCAA91-001-001 | P.U. HC11 - CONTINUOUS CASTING MACHINE (C.C.M.) PIPING SCOPE LAYOUT PIPING KEY PLAN | 00 | 2015-08-05 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Piping & Utility | DANIELI | 2015-08-09 11:53 | IFI | OB | 100%
114229 | I491TR01-0CCAA91-002-001 | P.U. HC11 - C.C.M. PIPING SCOPE LAYOUT (P.S.L.) AREA 10 PLAN FROM EL-800 TO EL.+2600 | 00 | 2015-08-05 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Piping & Utility | DANIELI | 2015-08-09 11:53 | IFI | OB | 100%
114230 | I491TR01-0CCAA91-003-001 | P.U. HC11 - C.C.M. PIPING SCOPE LAYOUT (P.S.L.) AREA 10 PLAN FROM EL+2600 TO EL.+4600 | 00 | 2015-08-05 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Piping & Utility | DANIELI | 2015-08-09 11:53 | IFI | OB | 100%
114231 | I491TR01-0CCAA91-004-001 | P.U. HC11 - C.C.M. PIPING SCOPE LAYOUT (P.S.L.) AREA 10 PLAN FROM EL+4600 TO EL.+8000 | 00 | 2015-08-05 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Piping & Utility | DANIELI | 2015-08-09 11:53 | IFI | OB | 100%
114232 | I491TR01-0CCAA91-005-001 | P.U. HC11 - C.C.M. PIPING SCOPE LAYOUT (P.S.L.) AREA 10 PLAN FROM EL.+8000 TO EL.+9700 | 00 | 2015-08-05 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Piping & Utility | DANIELI | 2015-08-09 11:53 | IFI | OB | 100%
114233 | I491TR01-0CCAA91-006-001 | P.U. HC11 - C.C.M. PIPING SCOPE LAYOUT (P.S.L.) AREA 10 PLAN FROM EL+9700 TO OVER | 00 | 2015-08-05 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Piping & Utility | DANIELI | 2015-08-09 11:53 | IFI | OB | 100%
114234 | I491TR01-0CCAA91-007-001 | P.U. HC11 - C.C.M. PIPING SCOPE LAYOUT (P.S.L.) AREA 10 SECTION 1-1 TO 8-8 | 00 | 2015-08-05 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Piping & Utility | DANIELI | 2015-08-09 11:53 | IFI | OB | 100%
114235 | I491TR01-0CCAA91-008-001 | P.U. HC11 - C.C.M. PIPING SCOPE LAYOUT (P.S.L.) AREA 10 SECTION 9-9 | 00 | 2015-08-05 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Piping & Utility | DANIELI | 2015-08-09 11:53 | IFI | OB | 100%
114236 | I491TR01-0CCAA91-009-001 | P.U. HC11 - C.C.M. PIPING SCOPE LAYOUT (P.S.L.) AREA 11 PLAN FROM EL.-2800 TO EL.-850 | 00 | 2015-08-05 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Piping & Utility | DANIELI | 2015-08-09 11:53 | IFI | OB | 100%
114237 | I491TR01-0CCAA91-010-001 | P.U. HC11 - C.C.M. PIPING SCOPE LAYOUT (P.S.L.) AREA 11 PLAN FROM EL.-850 TO EL.+60 | 00 | 2015-08-05 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Piping & Utility | DANIELI | 2015-08-09 11:53 | IFI | OB | 100%
114238 | I491TR01-0CCAA91-011-001 | P.U. HC11 - C.C.M. PIPING SCOPE LAYOUT (P.S.L.) AREA 11 PLAN FROM EL.+60 TO EL.+3000 | 00 | 2015-08-05 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Piping & Utility | DANIELI | 2015-08-09 11:53 | IFI | OB | 100%
114239 | I491TR01-0CCAA91-012-001 | P.U. HC11 - C.C.M. PIPING SCOPE LAYOUT (P.S.L.) AREA 11 PLAN FROM EL.+3000 TO OVER | 00 | 2015-08-05 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Piping & Utility | DANIELI | 2015-08-09 11:53 | IFI | OB | 100%
114240 | I491TR01-0CCAA91-013-001 | P.U. HC11 - C.C.M. PIPING SCOPE LAYOUT (P.S.L.) AREA 12 PLAN FROM EL.-2800 TO EL.-800 | 00 | 2015-08-05 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Piping & Utility | DANIELI | 2015-08-09 11:53 | IFI | OB | 100%
114241 | I491TR01-0CCAA91-014-001 | P.U. HC11 - C.C.M. PIPING SCOPE LAYOUT (P.S.L.) AREA 12 PLAN FROM EL.-800 TO EL.-250 | 00 | 2015-08-05 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Piping & Utility | DANIELI | 2015-08-09 11:53 | IFI | OB | 100%
114242 | I491TR01-0CCAA91-015-001 | P.U. HC11 - C.C.M. PIPING SCOPE LAYOUT (P.S.L.) AREA 12 PLAN FROM EL.-250 TO OVER | 00 | 2015-08-05 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Piping & Utility | DANIELI | 2015-08-09 11:53 | IFI | OB | 100%
114243 | I491TR01-0CCAA91-016-001 | P.U. HC11 - C.C.M. PIPING SCOPE LAYOUT (P.S.L.) AREA 13 PLAN FROM EL-3000 TO EL.+3000 | 00 | 2015-08-05 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Piping & Utility | DANIELI | 2015-08-09 11:53 | IFI | OB | 100%
114244 | I491TR01-0CCAA91-017-001 | P.U. HC11 - C.C.M. PIPING SCOPE LAYOUT (P.S.L.) AREA 13 PLAN FROM EL+3000 TO OVER | 00 | 2015-08-05 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Piping & Utility | DANIELI | 2015-08-09 11:53 | IFI | OB | 100%
114245 | I491TR01-0CCAA91-018-001 | P.U. HC11 - C.C.M. PIPING SCOPE LAYOUT (P.S.L.) AREA 13 SECTION 1-1 TO 5-5 | 00 | 2015-08-05 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Piping & Utility | DANIELI | 2015-08-09 11:53 | IFI | OB | 100%
114246 | I491TR01-0CCAA91-019-001 | P.U. HY11 - TUNDISH DRYING PIPING SCOPE LAYOUT (P.S.L.) AREA 14 PLAN FROM EL+0.00 TO OVER | 00 | 2015-08-05 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Piping & Utility | DANIELI | 2015-08-09 11:53 | IFI | OB | 100%
114247 | I491TR01-0CCAA91-020-001 | P.U. HY11 - TUNDISH TILTING PIPING SCOPE LAYOUT (P.S.L.) AREA 15 PLAN FROM EL+0.00 TO OVER | 00 | 2015-08-05 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Piping & Utility | DANIELI | 2015-08-09 11:53 | IFI | OB | 100%
16351 | I491TR01-0EAFK01-001-001 | Piping Tilting Frame- Pneumatic | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16352 | I491TR01-0EAFK02-001-001 | Piping Tilting Frame- Natural Gas | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Piping & Utility | FUCHS |  | IFI | OB | 100%
16353 | I491TR01-0EAFK03-001-001 | Oxygen- Piping Tilting Frame | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Piping & Utility | FUCHS |  | IFI | OB | 100%
134897 | I491TR01-0LAXL01-001-001 | EAF Laboratory Penumatic Shooting System Cabling1 1-5 | 00 | 2018-12-24 | Indeterminate | Drawing | Detail | Laboratory | Automation and Instrumentation | TAM | 2018-12-31 10:44 | IFI | OB | 100%
134896 | I491TR01-0LAXL01-001-002 | EAF Laboratory Penumatic Shooting System Cabling1 2-5 | 00 | 2018-12-24 | Indeterminate | Drawing | Detail | Laboratory | Automation and Instrumentation | TAM | 2018-12-31 10:44 | IFI | OB | 100%
134895 | I491TR01-0LAXL01-001-003 | EAF Laboratory Penumatic Shooting System Cabling1 3-5 | 00 | 2018-12-24 | Indeterminate | Drawing | Detail | Laboratory | Automation and Instrumentation | TAM | 2018-12-31 10:44 | IFI | OB | 100%
134894 | I491TR01-0LAXL01-001-004 | EAF Laboratory Penumatic Shooting System Cabling1 4-5 | 00 | 2018-12-24 | Indeterminate | Drawing | Detail | Laboratory | Automation and Instrumentation | TAM | 2018-12-31 10:44 | IFI | OB | 100%
134893 | I491TR01-0LAXL01-001-005 | EAF Laboratory Penumatic Shooting System Cabling1 5-5 | 00 | 2018-12-24 | Indeterminate | Drawing | Detail | Laboratory | Automation and Instrumentation | TAM | 2018-12-31 10:44 | IFI | OB | 100%
134901 | I491TR01-0LAXL01-002-001 | LF Laboratory Penumatic Shooting System Cabling2 1-4 | 00 | 2018-12-24 | Indeterminate | Drawing | Detail | Laboratory | Automation and Instrumentation | TAM | 2018-12-31 10:44 | IFI | OB | 100%
134900 | I491TR01-0LAXL01-002-002 | LF Laboratory Penumatic Shooting System Cabling2 2-4 | 00 | 2018-12-24 | Indeterminate | Drawing | Detail | Laboratory | Automation and Instrumentation | TAM | 2018-12-31 10:44 | IFI | OB | 100%
134899 | I491TR01-0LAXL01-002-003 | LF Laboratory Penumatic Shooting System Cabling2 3-4 | 00 | 2018-12-24 | Indeterminate | Drawing | Detail | Laboratory | Automation and Instrumentation | TAM | 2018-12-31 10:44 | IFI | OB | 100%
134898 | I491TR01-0LAXL01-002-004 | LF Laboratory Penumatic Shooting System Cabling2 4-4 | 00 | 2018-12-24 | Indeterminate | Drawing | Detail | Laboratory | Automation and Instrumentation | TAM | 2018-12-31 10:44 | IFI | OB | 100%
134903 | I491TR01-0LAXL01-003-001 | CCM Laboratory Penumatic Shooting System Cabling3 1-2 | 00 | 2018-12-24 | Indeterminate | Drawing | Detail | Laboratory | Automation and Instrumentation | TAM | 2018-12-31 10:44 | IFI | OB | 100%
134902 | I491TR01-0LAXL01-003-002 | CCM Laboratory Penumatic Shooting System Cabling3 2-2 | 00 | 2018-12-24 | Indeterminate | Drawing | Detail | Laboratory | Automation and Instrumentation | TAM | 2018-12-31 10:44 | IFI | OB | 100%
11769 | I491TR01-0MBAA91-001-001 | Piping 3D Modeling | 00 | 2013-02-24 | Indeterminate | Miscellaneous(MISC) | Detail | Media Distribution System | Piping & Utility | TAM |  | IFA | AC |  | 95%
11768 | I491TR01-0MBAA91-001-002 | Piping 3D Modeling | 00 | 2013-02-24 | Indeterminate | Miscellaneous(MISC) | Detail | Media Distribution System | Piping & Utility | TAM |  | IFA | AC |  | 95%
131166 | I491TR01-0MBPP91-001-001 | Piping Plan for Workshop Ware-house, Office, ASP Substation WCP Substation, SMP Substation | 00 | 2017-09-12 | Indeterminate | Drawing | Detail | Media Distribution System | Piping & Utility | TAM | 2017-09-17 12:44 | IFI | OB | 100%
16354 | I491TR01-0MDAA91-001-001 | Media Distribution Main Rout | 00 | 2012-02-21 | Indeterminate | Drawing | Basic | Media Distribution System | Mechanical | TAM |  | IFA | A | 100%
129817 | I491TR01-0MMCF91-001-001 | PLOT PLAN AND EQUIPMENT LAYOUT FOR COOLING SYSTEM (Sedimentation) | 00 | 2016-11-19 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Piping & Utility | TAM | 2016-11-23 10:56 | IFI | OB | 100%
115160 | I491TR02-0ASAA91-001-001 | Piping Layout Air Separation Plant 1-6 | 00 | 2016-04-26 | Indeterminate | Drawing | Detail | Air Separation Plant | Piping & Utility | TAM | 2016-05-03 14:49 | IFI | OB | 100%
115155 | I491TR02-0ASAA91-001-002 | Piping Layout Air Separation Plant 2-6 | 00 | 2016-04-26 | Indeterminate | Drawing | Detail | Air Separation Plant | Piping & Utility | TAM | 2016-05-03 14:49 | IFI | OB | 100%
115156 | I491TR02-0ASAA91-001-003 | Piping Layout Air Separation Plant 3-6 | 00 | 2016-04-26 | Indeterminate | Drawing | Detail | Air Separation Plant | Piping & Utility | TAM | 2016-05-03 14:49 | IFI | OB | 100%
115157 | I491TR02-0ASAA91-001-004 | Piping Layout Air Separation Plant 4-6 | 00 | 2016-04-26 | Indeterminate | Drawing | Detail | Air Separation Plant | Piping & Utility | TAM | 2016-05-03 14:49 | IFI | OB | 100%
115158 | I491TR02-0ASAA91-001-005 | Piping Layout Air Separation Plant 5-6 | 00 | 2016-04-26 | Indeterminate | Drawing | Detail | Air Separation Plant | Piping & Utility | TAM | 2016-05-03 14:49 | IFI | OB | 100%
115159 | I491TR02-0ASAA91-001-006 | Piping Layout Air Separation Plant 6-6 | 00 | 2016-04-26 | Indeterminate | Drawing | Detail | Air Separation Plant | Piping & Utility | TAM | 2016-05-03 14:49 | IFI | OB | 100%
134093 | I491TR02-0ASCP02-001-001 | Booster Air Compressor Pipe Assy 08_1 AIR PIPING 24652059 | 00 | 2018-08-15 | Indeterminate | Drawing | Detail | Air Separation Plant Main Building | Mechanical | TAM | 2018-08-21 13:07 | IFI | OB | 100%
115786 | I491TR02-0DTAA91-001-001 | PIPING PLAN DRAWING For FUME TREATMENT PLANT | 00 | 2016-06-26 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Piping & Utility | TAM | 2016-06-28 13:32 | IFI | OB | 100%
16355 | I491TR02-0DTPP08-001-001 | Dedusting System Faurnace 140 Ton Eaf+Lf & Mh Compressed Air Line Plan View & Detail | 00 | 2013-09-30 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Piping & Utility | HASCON |  | IFI | OB | 100%
16356 | I491TR02-0DTPP08-002-001 | Dedusting System Faurnace 140 Ton Eaf+Lf & Mh Compressed Air Line Top Filter A-B | 00 | 2013-09-30 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Piping & Utility | HASCON |  | IFI | OB | 100%
16357 | I491TR02-0DTPP08-003-001 | Dedusting System Faurnace 140 Ton Eaf+Lf & Mh Compressed Air Line Top Filter C-D | 00 | 2013-09-30 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Piping & Utility | HASCON |  | IFI | OB | 100%
16358 | I491TR02-0DTPP08-004-001 | Dedusting System Faurnace 140 Ton Eaf+Lf & Mh Compressed Air Line Hoppers Filter C-D & Stack | 00 | 2013-09-30 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Piping & Utility | HASCON |  | IFI | OB | 100%
16359 | I491TR02-0DTPP08-005-001 | Dedusting System Faurnace 140 Ton Eaf+Lf & Mh Compressed Air Line Hoppers Filter A-B | 00 | 2013-09-30 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Piping & Utility | HASCON |  | IFI | OB | 100%
16360 | I491TR02-0DTPP08-006-001 | Dedusting System Faurnace 140 Ton Eaf+Lf & Mh Compressed Air Line Air Line Silo | 00 | 2013-09-30 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Piping & Utility | HASCON |  | IFI | OB | 100%
16361 | I491TR02-0DTPP08-007-001 | Dedusting System Faurnace 140 Ton Eaf+Lf & Mh Compressed Air Line Top Filters-Delta P | 00 | 2013-09-30 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Piping & Utility | HASCON |  | IFI | OB | 100%
16362 | I491TR02-0DTPP08-008-001 | Dedusting System Faurnace 140 Ton Eaf+Lf & Mh Compressed Air Line Natural Cooler-Delta P Assembly | 00 | 2013-09-30 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Piping & Utility | HASCON |  | IFI | OB | 100%
16363 | I491TR02-0DTPP08-009-001 | Dedusting System Faurnace 140 Ton Eaf+Lf & Mh Compressed Air Line Natural Cooler Isometric Delta P | 00 | 2013-09-30 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Piping & Utility | HASCON |  | IFI | OB | 100%
112664 | I491TR02-0DTPP08-010-001 | DEDUSTING SYSTEM FOURNACE 140 Ton EAF+LF & MH NITROGEN LINE - DRI FILTER | 00 | 2014-08-09 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Piping & Utility | HASCON | 2014-08-18 09:38 | IFI | OB | 100%
115152 | I491TR02-0EAAA91-001-001 | PIPING PLAN DRAWINGS for Electric Arc Furnace Piping Plan High Current Section 1-4 | 01 | 2016-04-23 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Piping & Utility | TAM | 2016-05-03 14:28 | IFC | OB | 100%
114214 | I491TR02-0EAAA91-001-002 | PIPING PLAN DRAWINGS for Electric Arc Furnace Piping Plan Trans Arrange Final 2-4 | 00 | 2015-08-03 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Piping & Utility | TAM | 2015-08-09 10:18 | IFI | OB | 100%
114215 | I491TR02-0EAAA91-001-003 | PIPING PLAN DRAWINGS for Electric Arc Furnace EAF Piping Plan Valve Stand Plan 3-4 | 00 | 2015-08-03 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Piping & Utility | TAM | 2015-08-09 10:18 | IFI | OB | 100%
115153 | I491TR02-0EAAA91-001-004 | PIPING PLAN DRAWINGS for Electric Arc Furnace Piping Plan EAF Top View 4-4 | 00 | 2016-04-23 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Piping & Utility | TAM | 2016-05-03 14:35 | IFC | OB | 100%
16364 | I491TR02-0EAEJ01-001-001 | Shell Water Hoses At Shell | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16365 | I491TR02-0EAEJ02-001-001 | Shell Water Hoses At Shell | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16366 | I491TR02-0EAEJ03-001-001 | Shell Water Hoses At Shell | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16367 | I491TR02-0EAEJ05-001-001 | Shell Water Hoses At Shell | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16368 | I491TR02-0EAEJ06-001-001 | Water Upper Shell Water Balcony Panel | 00 | 2012-03-11 | Indeterminate | Miscellaneous(MISC) | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16369 | I491TR02-0EAEJ07-001-001 | Water At Upper Shell Water Door Tunnel | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16370 | I491TR02-0EAEJ08-001-001 | Water At Shell Water At Lower Shell | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16372 | I491TR02-0EAFG01-001-002 | Piping- Roof Eaf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16373 | I491TR02-0EAFG03-001-001 | Water -Piping Roof Eaf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16374 | I491TR02-0EAFG04-001-001 | Water- Piping Roof Eaf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16375 | I491TR02-0EAFG05-001-001 | Water- Piping Roof Eaf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16376 | I491TR02-0EAFG06-001-001 | Main Water Conneciton -Piping Roof Eaf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | TAM |  | IFI | OB | 100%
16377 | I491TR02-0EAFG07-001-001 | Heat Panel Roof Eaf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16378 | I491TR02-0EAFG08-001-001 | Heat Panel Roof Eaf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | TAM |  | IFI | OB | 100%
16379 | I491TR02-0EAFM01-001-001 | Wall Cooling Elements- Upper Shell | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16380 | I491TR02-0EAFM02-001-001 | Upper Shell-Wall Cooling Elements | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | TAM |  | IFI | OB | 100%
16381 | I491TR02-0EAFM03-001-001 | Upper Shell Water At Shell | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
132805 | I491TR02-0MBPP91-001-001 | Piping Plan Drawings T.O.P. Layout | 01 | 2018-01-28 | Indeterminate | Drawing | Detail | Media Distribution System | Piping & Utility | TAM | 2018-02-03 15:25 | IFC | AFC | 100%
16383 | I491TR02-0MBPP91-002-001 | Piping Plan Drawings | 00 | 2013-03-11 | Indeterminate | Drawing | Detail | Media Distribution System | Piping & Utility | TAM |  | IFA | AC |  | 95%
16386 | I491TR02-0MBPP91-002-002 | Piping Plan Drawings | 00 | 2013-03-11 | Indeterminate | Drawing | Detail | Media Distribution System | Piping & Utility | TAM |  | IFA | AC |  | 95%
16387 | I491TR02-0MBPP91-002-003 | Piping Plan Drawings | 00 | 2013-03-11 | Indeterminate | Drawing | Detail | Media Distribution System | Piping & Utility | TAM |  | IFA | AC |  | 95%
16388 | I491TR02-0MBPP91-002-004 | Piping Plan Drawings | 00 | 2013-03-11 | Indeterminate | Drawing | Detail | Media Distribution System | Piping & Utility | TAM |  | IFA | AC |  | 95%
16389 | I491TR02-0MBPP91-002-005 | Piping Plan Drawings | 00 | 2013-03-11 | Indeterminate | Drawing | Detail | Media Distribution System | Piping & Utility | TAM |  | IFA | AC |  | 95%
16390 | I491TR02-0MBPP91-002-006 | Piping Plan Drawings | 00 | 2013-03-11 | Indeterminate | Drawing | Detail | Media Distribution System | Piping & Utility | TAM |  | IFA | AC |  | 95%
16391 | I491TR02-0MBPP91-002-007 | Piping Plan Drawings | 00 | 2013-03-11 | Indeterminate | Drawing | Detail | Media Distribution System | Piping & Utility | TAM |  | IFA | AC |  | 95%
16392 | I491TR02-0MBPP91-002-008 | Piping Plan Drawings | 00 | 2013-03-11 | Indeterminate | Drawing | Detail | Media Distribution System | Piping & Utility | TAM |  | IFA | AC |  | 95%
16393 | I491TR02-0MBPP91-002-009 | Piping Plan Drawings | 00 | 2013-03-11 | Indeterminate | Drawing | Detail | Media Distribution System | Piping & Utility | TAM |  | IFA | AC |  | 95%
16384 | I491TR02-0MBPP91-002-010 | Piping Plan Drawings | 00 | 2013-03-11 | Indeterminate | Drawing | Detail | Media Distribution System | Piping & Utility | TAM |  | IFA | AC |  | 95%
16385 | I491TR02-0MBPP91-002-011 | Piping Plan Drawings | 00 | 2013-03-11 | Indeterminate | Drawing | Detail | Media Distribution System | Piping & Utility | TAM |  | IFA | AC |  | 95%
135180 | I491TR02-0MDSI01-001-001 | Carbon & Lime Injection Line PIPING PLAN 1-3 | 00 | 2019-03-18 12:29 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | TAM | 2019-03-18 12:29 | IFA | A | 100%
135179 | I491TR02-0MDSI01-001-002 | Carbon & Lime Injection Line PIPING PLAN 2-3 | 00 | 2019-03-18 12:29 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | TAM | 2019-03-18 12:29 | IFA | A | 100%
135178 | I491TR02-0MDSI01-001-003 | Carbon & Lime Injection Line PIPING PLAN 3-3 | 00 | 2019-03-18 12:29 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | TAM | 2019-03-18 12:29 | IFA | A | 100%
129818 | I491TR02-0MMCF91-001-001 | PIPING Plan for Sedimentation Sand Filters Water Cooling Plant | 00 | 2016-11-19 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Piping & Utility | TAM | 2016-11-23 10:57 | IFI | OB | 100%
129820 | I491TR02-0MMCF91-002-001 | Piping Isometric View for Sedimentation Water Cooling Plant 1-2 | 00 | 2016-11-19 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Piping & Utility | TAM | 2016-11-23 11:00 | IFI | OB | 100%
129819 | I491TR02-0MMCF91-002-002 | Piping Isometric View for Sedimentation Water Cooling Plant 2-2 | 00 | 2016-11-19 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Piping & Utility | TAM | 2016-11-23 11:00 | IFI | OB | 100%
113681 | I491TR02-0MMCT01-001-001 | Piping Layout CT01 and CT02 | 00 | 2015-05-30 09:47 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Piping & Utility | TAM | 2015-05-30 09:47 | IFI | OB | 100%
16394 | I491TR02-0NGAA91-001-001 | Natural Gas Pressure Reduction Station Piping Plan Metering And Regulating Station | 00 | 2012-12-16 | Indeterminate | Drawing | Detail | Natural Gas Reducing Station | Piping & Utility | TAM |  | IFA | AC |  | 95%
115166 | I491TR03-0ASAA91-001-001 | PIPE.ISOMETRIC.DRAWING Air Separation Plant 1~183 | 00 | 2016-04-26 | Indeterminate | Drawing | Detail | Air Separation Plant | Piping & Utility | Fortune | 2016-05-04 10:47 | IFI | OB | 100%
115169 | I491TR03-0ASAA91-003-001 | PIPING.INSULATION.DIAGRAM AIR.SEPARATION.PLANT 1-3 | 00 | 2016-04-26 | Indeterminate | Drawing | Detail | Air Separation Plant | Piping & Utility | Fortune | 2016-05-04 10:47 | IFI | OB | 100%
115167 | I491TR03-0ASAA91-003-002 | PIPING.INSULATION.DIAGRAM AIR.SEPARATION.PLANT 2-3 | 00 | 2016-04-26 | Indeterminate | Drawing | Detail | Air Separation Plant | Piping & Utility | Fortune | 2016-05-04 10:47 | IFI | OB | 100%
115168 | I491TR03-0ASAA91-003-003 | PIPING.INSULATION.DIAGRAM AIR.SEPARATION.PLANT 3-3 | 00 | 2016-04-26 | Indeterminate | Drawing | Detail | Air Separation Plant | Piping & Utility | Fortune | 2016-05-04 10:47 | IFI | OB | 100%
135086 | I491TR03-0CCAA91-001-001 | Isometric Piping Drawing For CCM UNIT (1079 SHEET) | 00 | 2019-03-02 | Indeterminate | Miscellaneous(MISC) | Detail | Continuous Casting Machine (CCM) | Piping & Utility | TAM | 2019-03-09 12:47 | IFI | OB | 100%
135344 | I491TR03-0CPPP92-001-001 | CAP Isometric Drawing for Compressed Air Piping | 00 | 2019-05-15 | Indeterminate | Drawing | Detail | Compressed Air Production Plant | Piping & Utility | HAVAYAR | 2019-05-21 10:36 | IFI | OB | 100%
115207 | I491TR03-0DTAA91-001-001 | Isometric Piping Drawing For Fume Treatment Plant CA-100-D16PS-03001 7 Sheet | 00 | 2016-05-04 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Piping & Utility | TAM | 2016-05-11 09:01 | IFI | OB | 100%
115211 | I491TR03-0DTAA91-002-001 | Isometric Piping Drawing For Fume Treatment Plant CW-600-D16JS-03011CTD 14 Sheet | 00 | 2016-05-04 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Piping & Utility | TAM | 2016-05-11 09:01 | IFI | OB | 100%
115210 | I491TR03-0DTAA91-003-001 | Isometric Piping Drawing For Fume Treatment Plant CW-600-D16JS-03012DTC 14 Sheet | 00 | 2016-05-04 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Piping & Utility | TAM | 2016-05-11 09:01 | IFI | OB | 100%
115209 | I491TR03-0DTAA91-004-001 | Isometric Piping Drawing For Fume Treatment Plant CWR-600-D16JS-03010DTC 24 Sheet | 00 | 2016-05-04 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Piping & Utility | TAM | 2016-05-11 09:01 | IFI | OB | 100%
115208 | I491TR03-0DTAA91-005-001 | Isometric Piping Drawing For Fume Treatment Plant N2-040-D16PS-03001 5 Sheet | 00 | 2016-05-04 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Piping & Utility | TAM | 2016-05-11 09:01 | IFI | OB | 100%
115212 | I491TR03-0DTAA91-006-001 | Isometric Piping Drawing For Fume Treatment Plant NG-040-D16JS-03001 9 Sheet | 00 | 2016-05-04 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Piping & Utility | TAM | 2016-05-11 09:01 | IFI | OB | 100%
115213 | I491TR03-0DTAA91-007-001 | Isometric Piping Drawing For Fume Treatment Plant OX-025-S16CH-03001 6 Sheet | 00 | 2016-05-04 | Indeterminate | Drawing | Basic | Fume Treatment Equipment | Piping & Utility | TAM | 2016-05-11 09:01 | IFI | OB | 100%
115214 | I491TR03-0DTAA91-008-001 | Isometric Piping Drawing For Fume Treatment Plant PW-015-D16ES-03001 11 Sheet | 00 | 2016-05-04 | Indeterminate | Drawing | Basic | Fume Treatment Equipment | Piping & Utility | TAM | 2016-05-11 09:01 | IFI | OB | 100%
131172 | I491TR03-0DTPP01-001-001 | DRI De-Dusting System Duct Work 1-4 | 00 | 2017-09-17 14:14 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Piping & Utility | TAM | 2017-09-17 14:14 | IFI | OB | 100%
131173 | I491TR03-0DTPP01-001-002 | DRI De-Dusting System Duct Work 2-4 | 00 | 2017-09-17 14:14 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Piping & Utility | TAM | 2017-09-17 14:14 | IFI | OB | 100%
131174 | I491TR03-0DTPP01-001-003 | DRI De-Dusting System Duct Work 3-4 | 00 | 2017-09-17 14:14 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Piping & Utility | TAM | 2017-09-17 14:14 | IFI | OB | 100%
131175 | I491TR03-0DTPP01-001-004 | DRI De-Dusting System Duct Work 4-4 | 00 | 2017-09-17 14:14 | Indeterminate | Drawing | Detail | Fume Treatment Equipment | Piping & Utility | TAM | 2017-09-17 14:14 | IFI | OB | 100%
114248 | I491TR03-0EAAA91-001-001 | EAF Isometric Piping | 00 | 2015-08-08 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Piping & Utility | TAM | 2015-08-10 09:43 | IFI | OB | 100%
16395 | I491TR03-0EAEJ01-001-001 | Water At Shell Water At Lower Shell | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16396 | I491TR03-0EAEJ02-001-001 | Water Shell Flexible Hose Dn50-700 | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16397 | I491TR03-0EAEJ03-001-001 | Water Shell Flexible Hose Dn50-900 | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16398 | I491TR03-0EAEJ04-001-001 | Water Shell Flexible Hose Dn50-1100 | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16399 | I491TR03-0EAEJ05-001-001 | Water Shell Flexible Hose Dn50-1400 | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16400 | I491TR03-0EAEJ06-001-001 | Water Shell Flexible Hose Dn50-2700 | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16401 | I491TR03-0EAEJ07-001-001 | Water Shell Flexible Hose Dn40-670 | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16402 | I491TR03-0EAEJ08-001-001 | Water Shell Flexible Hose Dn40-1670 | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16403 | I491TR03-0EAEJ09-001-001 | Water Shell Flexible Hose Dn40-2170 | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16404 | I491TR03-0EAFG01-001-001 | Pneumatic- Piping Roof Eaf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16405 | I491TR03-0EAFG02-001-001 | Pneumatic -Piping Roof Eaf | 00 | 2012-03-10 | Indeterminate | Miscellaneous(MISC) | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16406 | I491TR03-0EAFG03-001-001 | Pneumatic -Piping Roof Eaf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16407 | I491TR03-0EAFG04-001-001 | Pneumatic -Piping Roof Eaf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16408 | I491TR03-0EAFG05-001-001 | Main Water Conneciton -Piping Roof Eaf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16409 | I491TR03-0EAFG06-001-001 | Panel Typ A Roof Eaf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16410 | I491TR03-0EAFG07-001-001 | Panel Typ B Roof Eaf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16411 | I491TR03-0EAFG08-001-001 | Panel Typ C Roof Eaf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16412 | I491TR03-0EAFG09-001-001 | Off Gas Duct Roof Eaf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16413 | I491TR03-0EAFG10-001-001 | Piping Elbow-Roof Eaf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16414 | I491TR03-0EAFG11-001-001 | Piping Elbow-Roof Eaf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16415 | I491TR03-0EAFG12-001-001 | Piping Elbow-Roof Eaf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16416 | I491TR03-0EAFG13-001-001 | Piping Elbow-Roof Eaf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16417 | I491TR03-0EAFG14-001-001 | Distributor Elbow-Roof Eaf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16418 | I491TR03-0EAFM01-001-001 | Water Ring-Steel Structure | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16419 | I491TR03-0EAFM02-001-001 | Water Ring-Steel Structure | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16420 | I491TR03-0EAFM03-001-001 | Water Ring-Steel Structure | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16421 | I491TR03-0EAFM04-001-001 | Water Ring-Steel Structure | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16422 | I491TR03-0EAFM05-001-001 | Water Ring-Steel Structure | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16423 | I491TR03-0EAFM06-001-001 | Wall Cooling Elements-Panel Type A | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | TAM |  | IFI | OB | 100%
16424 | I491TR03-0EAFM07-001-001 | Wall Cooling Elements-Panel Type A | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | TAM |  | IFI | OB | 100%
16425 | I491TR03-0EAFM08-001-001 | Wall Cooling Elements-Panel Type B | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | TAM |  | IFI | OB | 100%
16426 | I491TR03-0EAFM09-001-001 | Wall Cooling Elements-Panel Type B | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16427 | I491TR03-0EAFM10-001-001 | Wall Cooling Elements-Panel Type D | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16428 | I491TR03-0EAFM11-001-001 | Wall Cooling Elements-Panel Type E | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16429 | I491TR03-0EAFM12-001-001 | Wall Cooling Elements-Panel Type E | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16430 | I491TR03-0EAFM13-001-001 | Wall Cooling Elements-Panel Type E | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | TAM |  | IFI | OB | 100%
16431 | I491TR03-0EAFM14-001-001 | Wall Cooling Elements-Panel Type F | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16432 | I491TR03-0EAFM15-001-001 | Wall Cooling Elements-Panel Type F | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16433 | I491TR03-0EAFM16-001-001 | Wall Cooling Elements-Panel Type F | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16434 | I491TR03-0EAFM17-001-001 | Balcony Panel Water Circuit | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16435 | I491TR03-0EAFM18-001-001 | Upper Shell Door Channel | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16436 | I491TR03-0EAFM19-001-001 | Water At Shell From Piece G 2" | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
132774 | I491TR03-0EAPP01-001-001 | EAF De-dusting System Duct Work 1-3 | 00 | 2018-01-23 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | TAM | 2018-02-03 13:14 | IFI | AC |  | 95%
132775 | I491TR03-0EAPP01-001-002 | EAF De-dusting System Duct Work 2-3 | 00 | 2018-01-23 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | TAM | 2018-02-03 13:14 | IFI | AC |  | 95%
132776 | I491TR03-0EAPP01-001-003 | EAF De-dusting System Duct Work 4-3 | 00 | 2018-01-23 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | TAM | 2018-02-03 13:14 | IFI | AC |  | 95%
115730 | I491TR03-0LFAA91-001-001 | LF Isometric Piping QWR-200-D16JS-LF-004 (18 Sheet) | 00 | 2016-06-13 | Indeterminate | Drawing | Detail | Ladle Furnace | Piping & Utility | FUCHS | 2016-06-14 14:01 | IFI | OB | 100%
115722 | I491TR03-0LFAA91-002-001 | LF Isometric Piping QWS-200-D16JS-LF-003 (2 Sheet) | 00 | 2016-06-13 | Indeterminate | Drawing | Detail | Ladle Furnace | Piping & Utility | FUCHS | 2016-06-14 14:01 | IFI | OB | 100%
115723 | I491TR03-0LFAA91-003-001 | LF Isometric Piping CWR-200-D16JS-LF-002 (2 Sheet) | 00 | 2016-06-13 | Indeterminate | Drawing | Detail | Ladle Furnace | Piping & Utility | FUCHS | 2016-06-14 14:01 | IFI | OB | 100%
115724 | I491TR03-0LFAA91-004-001 | LF Isometric Piping CWS-200-D16JS-LF-001 (2 Sheet) | 00 | 2016-06-13 | Indeterminate | Drawing | Detail | Ladle Furnace | Piping & Utility | FUCHS | 2016-06-14 14:01 | IFI | OB | 100%
115725 | I491TR03-0LFAA91-005-001 | LF Isometric Piping AR-015-D16PS-LF-012 (2 Sheet) | 00 | 2016-06-13 | Indeterminate | Drawing | Detail | Ladle Furnace | Piping & Utility | FUCHS | 2016-06-14 14:01 | IFI | OB | 100%
115726 | I491TR03-0LFAA91-006-001 | LF Isometric Piping EW-100-D16PS-LF001_Sht_1 | 00 | 2016-06-13 | Indeterminate | Drawing | Detail | Ladle Furnace | Piping & Utility | FUCHS | 2016-06-14 14:01 | IFI | OB | 100%
115727 | I491TR03-0LFAA91-007-001 | LF Isometric Piping IA-015-D16ES-LF-001B1 (2 Sheet) | 00 | 2016-06-13 | Indeterminate | Drawing | Detail | Ladle Furnace | Piping & Utility | FUCHS | 2016-06-14 14:01 | IFI | OB | 100%
115728 | I491TR03-0LFAA91-008-001 | LF Isometric Piping CA-20-D16PS-LF-010_Sht_1 | 00 | 2016-06-13 | Indeterminate | Drawing | Detail | Ladle Furnace | Piping & Utility | FUCHS | 2016-06-14 14:01 | IFI | OB | 100%
115729 | I491TR03-0LFAA91-009-001 | LF Isometric Piping N2-015-D16PS-LF-011 (2 Sheet) | 00 | 2016-06-13 | Indeterminate | Drawing | Detail | Ladle Furnace | Piping & Utility | FUCHS | 2016-06-14 14:01 | IFI | OB | 100%
131177 | I491TR03-0LFPP01-001-001 | LF MHS De-Dusting Duct Work 1-4 | 00 | 2017-09-17 15:30 | Indeterminate | Drawing | Detail | Ladle Furnace | Piping & Utility | TAM | 2017-09-17 15:30 | IFI | OB | 100%
131178 | I491TR03-0LFPP01-001-002 | LF MHS De-Dusting Duct Work 2-4 | 00 | 2017-09-17 15:30 | Indeterminate | Drawing | Detail | Ladle Furnace | Piping & Utility | TAM | 2017-09-17 15:30 | IFI | OB | 100%
131179 | I491TR03-0LFPP01-001-003 | LF MHS De-Dusting Duct Work 3-4 | 00 | 2017-09-17 15:30 | Indeterminate | Drawing | Detail | Ladle Furnace | Piping & Utility | TAM | 2017-09-17 15:30 | IFI | OB | 100%
131180 | I491TR03-0LFPP01-001-004 | LF MHS De-Dusting Duct Work 4-4 | 00 | 2017-09-17 15:30 | Indeterminate | Drawing | Detail | Ladle Furnace | Piping & Utility | TAM | 2017-09-17 15:30 | IFI | OB | 100%
16437 | I491TR03-0MBPP91-001-001 | Isometric Drawings | 00 | 2013-03-09 | Indeterminate | Miscellaneous(MISC) | Detail | Media Distribution System | Piping & Utility | TAM |  | IFI | OB | 100%
115187 | I491TR03-0MBPP91-002-001 | Isometric drawings For NG Line From Gas Station To Meltshop | 00 | 2016-05-03 | Indeterminate | Miscellaneous(MISC) | Basic | Media Distribution System | Piping & Utility | TAM | 2016-05-04 11:22 | IFI | OB | 100%
133064 | I491TR03-0MBPP91-003-001 | Isometric drawings Emergency Tank Piping | 00 | 2018-04-16 | Indeterminate | Miscellaneous(MISC) | Detail | Media Distribution System | Piping & Utility | TAM | 2018-04-17 09:46 | IFI | OB | 100%
132031 | I491TR03-0MDPP01-001-001 | FERRO ALLOY DEDUSTING SYSTEMS DUCT WORK 1-3 | 00 | 2017-11-14 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | TAM | 2017-11-25 09:43 | IFI | OB | 100%
132032 | I491TR03-0MDPP01-001-002 | FERRO ALLOY DEDUSTING SYSTEMS DUCT WORK 2-3 | 00 | 2017-11-14 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | TAM | 2017-11-25 09:43 | IFI | OB | 100%
132033 | I491TR03-0MDPP01-001-003 | FERRO ALLOY DEDUSTING SYSTEMS DUCT WORK 3-3 | 00 | 2017-11-14 | Indeterminate | Drawing | Detail | Material Handling | Mechanical | TAM | 2017-11-25 09:43 | IFI | OB | 100%
115381 | I491TR03-0MMCF91-001-001 | Isometric Drawings for Sand Filter Piping Of Sedimentation Tank (Water Cooling Plant) | 00 | 2016-05-25 10:39 | Indeterminate | Miscellaneous(MISC) | Detail | Media Distribution System | Piping & Utility | TAM | 2016-05-25 10:39 | IFI | OB | 100%
113708 | I491TR03-0MMCT01-001-001 | Isometric Drawing For Cooling System CT01 | 00 | 2015-06-13 10:03 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Piping & Utility | TAM | 2015-06-13 10:03 | IFI | OB | 100%
113710 | I491TR03-0MMCT01-002-001 | Isometric Drawing TAM pipe Rack pipes | 00 | 2015-06-13 10:07 | Indeterminate | Miscellaneous(MISC) | Detail | Water Treatment & Cooling System | Piping & Utility | TAM | 2015-06-13 10:07 | IFI | OB | 100%
113709 | I491TR03-0MMCT02-001-001 | Isometric Drawing For Cooling System CT02 | 00 | 2015-06-13 10:03 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Piping & Utility | TAM | 2015-06-13 10:03 | IFI | OB | 100%
134136 | I491TR03-0MMTK01-001-001 | WTP - EMERGENCY TANK - PIPE RACK SITE PLAN | 00 | 2018-09-04 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Civil and Steel Structure | TAM | 2018-09-09 14:27 | IFI | OB | 100%
113592 | I491TR04-0LFLB92-002-001 | LUBRICATION SYSTEM - PIPING GANTRY LF | 00 | 2015-05-06 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | TAM | 2015-05-27 16:11 | IFI | OB | 100%
16438 | I491TR04-0MBPP91-001-001 | Line List | 00 | 2013-03-10 | Indeterminate | Miscellaneous(MISC) | Detail | Media Distribution System | Piping & Utility | TAM |  | IFI | OB | 100%
114227 | I491TR05-0CCAA91-001-001 | P.U HC11 &HY11 CCM PIPING LINE LIST | 00 | 2015-08-05 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Electrical | TAM | 2015-08-09 11:14 | IFI | OB | 100%
16439 | I491TR05-0CPPP92-001-001 | Piping Line List Compressed Air Plant | 00 | 2013-03-11 | Indeterminate | Miscellaneous(MISC) | Detail | Compressed Air Production Plant | Piping & Utility | HAVAYAR |  | IFI | OB | 100%
114818 | I491TR06-0ASAA91-001-001 | Piping Characteristics List For Air Separation Plant | 00 | 2016-01-23 | Indeterminate | Miscellaneous(MISC) | Detail | Air Separation Plant | Piping & Utility | TAM | 2016-01-24 09:45 | IFI | OB | 100%
135447 | I491TR06-0MBAA91-001-002 | Winterization Study for Media Distribution | 01 | 2019-06-08 | Indeterminate | Miscellaneous(MISC) | Detail | Media Distribution System | Mechanical | TAM | 2019-06-10 09:24 | IFC | AFC | 100%
115171 | I491TR07-0ASAA91-001-001 | Pipe rack detail drawing 1-2 | 00 | 2016-04-26 | Indeterminate | Drawing | Detail | Air Separation Plant | Piping & Utility | Fortune | 2016-05-04 10:48 | IFI | OB | 100%
115170 | I491TR07-0ASAA91-001-002 | Pipe rack detail drawing 2-2 | 00 | 2016-04-26 | Indeterminate | Drawing | Detail | Air Separation Plant | Piping & Utility | Fortune | 2016-05-04 10:48 | IFI | OB | 100%
115182 | I491TR07-0ASAA91-002-001 | Pipe Supports detail drawing 1-11 | 00 | 2016-04-26 | Indeterminate | Drawing | Detail | Air Separation Plant | Piping & Utility | Fortune | 2016-05-04 10:48 | IFI | OB | 100%
115172 | I491TR07-0ASAA91-002-002 | Pipe Supports detail drawing 2-11 | 00 | 2016-04-26 | Indeterminate | Drawing | Detail | Air Separation Plant | Piping & Utility | Fortune | 2016-05-04 10:48 | IFI | OB | 100%
115173 | I491TR07-0ASAA91-002-003 | Pipe Supports detail drawing 3-11 | 00 | 2016-04-26 | Indeterminate | Drawing | Detail | Air Separation Plant | Piping & Utility | Fortune | 2016-05-04 10:48 | IFI | OB | 100%
115174 | I491TR07-0ASAA91-002-004 | Pipe Supports detail drawing 4-11 | 00 | 2016-04-26 | Indeterminate | Drawing | Detail | Air Separation Plant | Piping & Utility | Fortune | 2016-05-04 10:48 | IFI | OB | 100%
115175 | I491TR07-0ASAA91-002-005 | Pipe Supports detail drawing 5-11 | 00 | 2016-04-26 | Indeterminate | Drawing | Detail | Air Separation Plant | Piping & Utility | Fortune | 2016-05-04 10:48 | IFI | OB | 100%
115176 | I491TR07-0ASAA91-002-006 | Pipe Supports detail drawing 6-11 | 00 | 2016-04-26 | Indeterminate | Drawing | Detail | Air Separation Plant | Piping & Utility | Fortune | 2016-05-04 10:48 | IFI | OB | 100%
115177 | I491TR07-0ASAA91-002-007 | Pipe Supports detail drawing 7-11 | 00 | 2016-04-26 | Indeterminate | Drawing | Detail | Air Separation Plant | Piping & Utility | Fortune | 2016-05-04 10:48 | IFI | OB | 100%
115178 | I491TR07-0ASAA91-002-008 | Pipe Supports detail drawing 8-11 | 00 | 2016-04-26 | Indeterminate | Drawing | Detail | Air Separation Plant | Piping & Utility | Fortune | 2016-05-04 10:48 | IFI | OB | 100%
115179 | I491TR07-0ASAA91-002-009 | Pipe Supports detail drawing 9-11 | 00 | 2016-04-26 | Indeterminate | Drawing | Detail | Air Separation Plant | Piping & Utility | Fortune | 2016-05-04 10:48 | IFI | OB | 100%
115180 | I491TR07-0ASAA91-002-010 | Pipe Supports detail drawing 10-11 | 00 | 2016-04-26 | Indeterminate | Drawing | Detail | Air Separation Plant | Piping & Utility | Fortune | 2016-05-04 10:48 | IFI | OB | 100%
115181 | I491TR07-0ASAA91-002-011 | Pipe Supports detail drawing 11-11 | 00 | 2016-04-26 | Indeterminate | Drawing | Detail | Air Separation Plant | Piping & Utility | Fortune | 2016-05-04 10:48 | IFI | OB | 100%
16441 | I491TR07-0EAFG01-001-001 | Heat Panel Roof Eaf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | TAM |  | IFI | OB | 100%
16442 | I491TR07-0EAFK01-001-001 | Piping Tilting Frame- Water | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16443 | I491TR07-0EAFM01-001-001 | Upper Shell Door Channel | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16444 | I491TR07-0EAFM02-001-001 | Upper Shell Door Channel | 00 | 2012-03-11 | Indeterminate | Drawing | Detail | Electric Arc Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
134908 | I491TR07-0LAXL01-001-001 | Laboratory Penumatic Shooting System Support Type 1 | 00 | 2018-12-24 | Indeterminate | Drawing | Detail | Laboratory | Automation and Instrumentation | TAM | 2018-12-31 10:45 | IFI | OB | 100%
134907 | I491TR07-0LAXL01-002-001 | Laboratory Penumatic Shooting System Support Type 2 | 00 | 2018-12-24 | Indeterminate | Drawing | Detail | Laboratory | Automation and Instrumentation | TAM | 2018-12-31 10:45 | IFI | OB | 100%
134906 | I491TR07-0LAXL01-003-001 | Laboratory Penumatic Shooting System Support Type 3 | 00 | 2018-12-24 | Indeterminate | Drawing | Detail | Laboratory | Automation and Instrumentation | TAM | 2018-12-31 10:45 | IFI | OB | 100%
134905 | I491TR07-0LAXL01-004-001 | Laboratory Penumatic Shooting System Support Type 4 | 00 | 2018-12-24 | Indeterminate | Drawing | Detail | Laboratory | Automation and Instrumentation | TAM | 2018-12-31 10:45 | IFI | OB | 100%
134904 | I491TR07-0LAXL01-005-001 | Laboratory Penumatic Shooting System Support Type 5 | 00 | 2018-12-24 | Indeterminate | Drawing | Detail | Laboratory | Automation and Instrumentation | TAM | 2018-12-31 10:45 | IFI | OB | 100%
132782 | I491TR07-0MBPP91-006-001 | Standard Pipe Support Drawings | 01 | 2018-01-27 | Indeterminate | Drawing | Basic | Media Distribution System | Piping & Utility | TAM | 2018-02-03 14:43 | IFC | AC |  | 95%
132793 | I491TR07-0MBPP91-006-002 | Standard Pipe Support Drawings | 01 | 2018-01-27 | Indeterminate | Drawing | Basic | Media Distribution System | Piping & Utility | TAM | 2018-02-03 14:43 | IFC | AC |  | 95%
132795 | I491TR07-0MBPP91-006-003 | Standard Pipe Support Drawings | 01 | 2018-01-27 | Indeterminate | Drawing | Basic | Media Distribution System | Piping & Utility | TAM | 2018-02-03 14:43 | IFC | AC |  | 95%
132796 | I491TR07-0MBPP91-006-004 | Standard Pipe Support Drawings | 01 | 2018-01-27 | Indeterminate | Drawing | Basic | Media Distribution System | Piping & Utility | TAM | 2018-02-03 14:43 | IFC | AC |  | 95%
132797 | I491TR07-0MBPP91-006-005 | Standard Pipe Support Drawings | 01 | 2018-01-27 | Indeterminate | Drawing | Basic | Media Distribution System | Piping & Utility | TAM | 2018-02-03 14:43 | IFC | AC |  | 95%
132798 | I491TR07-0MBPP91-006-006 | Standard Pipe Support Drawings | 01 | 2018-01-27 | Indeterminate | Drawing | Basic | Media Distribution System | Piping & Utility | TAM | 2018-02-03 14:43 | IFC | AC |  | 95%
132799 | I491TR07-0MBPP91-006-007 | Standard Pipe Support Drawings | 01 | 2018-01-27 | Indeterminate | Drawing | Basic | Media Distribution System | Piping & Utility | TAM | 2018-02-03 14:43 | IFC | AC |  | 95%
132800 | I491TR07-0MBPP91-006-008 | Standard Pipe Support Drawings | 01 | 2018-01-27 | Indeterminate | Drawing | Basic | Media Distribution System | Piping & Utility | TAM | 2018-02-03 14:43 | IFC | AC |  | 95%
132801 | I491TR07-0MBPP91-006-009 | Standard Pipe Support Drawings | 01 | 2018-01-27 | Indeterminate | Drawing | Basic | Media Distribution System | Piping & Utility | TAM | 2018-02-03 14:43 | IFC | AC |  | 95%
132783 | I491TR07-0MBPP91-006-010 | Standard Pipe Support Drawings | 01 | 2018-01-27 | Indeterminate | Drawing | Basic | Media Distribution System | Piping & Utility | TAM | 2018-02-03 14:43 | IFC | AC |  | 95%
132784 | I491TR07-0MBPP91-006-011 | Standard Pipe Support Drawings | 01 | 2018-01-27 | Indeterminate | Drawing | Basic | Media Distribution System | Piping & Utility | TAM | 2018-02-03 14:43 | IFC | AC |  | 95%
132785 | I491TR07-0MBPP91-006-012 | Standard Pipe Support Drawings | 01 | 2018-01-27 | Indeterminate | Drawing | Basic | Media Distribution System | Piping & Utility | TAM | 2018-02-03 14:43 | IFC | AC |  | 95%
132786 | I491TR07-0MBPP91-006-013 | Standard Pipe Support Drawings | 01 | 2018-01-27 | Indeterminate | Drawing | Basic | Media Distribution System | Piping & Utility | TAM | 2018-02-03 14:43 | IFC | AC |  | 95%
132787 | I491TR07-0MBPP91-006-014 | Standard Pipe Support Drawings | 01 | 2018-01-27 | Indeterminate | Drawing | Basic | Media Distribution System | Piping & Utility | TAM | 2018-02-03 14:43 | IFC | AC |  | 95%
132788 | I491TR07-0MBPP91-006-015 | Standard Pipe Support Drawings | 01 | 2018-01-27 | Indeterminate | Drawing | Basic | Media Distribution System | Piping & Utility | TAM | 2018-02-03 14:43 | IFC | AC |  | 95%
132789 | I491TR07-0MBPP91-006-016 | Standard Pipe Support Drawings | 01 | 2018-01-27 | Indeterminate | Drawing | Basic | Media Distribution System | Piping & Utility | TAM | 2018-02-03 14:43 | IFC | AC |  | 95%
132790 | I491TR07-0MBPP91-006-017 | Standard Pipe Support Drawings | 01 | 2018-01-27 | Indeterminate | Drawing | Basic | Media Distribution System | Piping & Utility | TAM | 2018-02-03 14:43 | IFC | AC |  | 95%
132791 | I491TR07-0MBPP91-006-018 | Standard Pipe Support Drawings | 01 | 2018-01-27 | Indeterminate | Drawing | Basic | Media Distribution System | Piping & Utility | TAM | 2018-02-03 14:43 | IFC | AC |  | 95%
132792 | I491TR07-0MBPP91-006-019 | Standard Pipe Support Drawings | 01 | 2018-01-27 | Indeterminate | Drawing | Basic | Media Distribution System | Piping & Utility | TAM | 2018-02-03 14:43 | IFC | AC |  | 95%
132794 | I491TR07-0MBPP91-006-020 | Standard Pipe Support Drawings | 01 | 2018-01-27 | Indeterminate | Drawing | Basic | Media Distribution System | Piping & Utility | TAM | 2018-02-03 14:43 | IFC | AC |  | 95%
16465 | I491TR07-0MBSS91-003-001 | Pipe Rack Structural And Foundation Calculation Sheet | 00 | 2013-03-03 | Indeterminate | Miscellaneous(MISC) | Detail | Media Distribution System | Civil and Steel Structure | TAM |  | IFA | AC |  | 95%
16466 | I491TR07-0MBSS91-004-001 | Pipe-Rack Structural Drawing3D-View(Pr001) | 00 | 2013-03-03 | Indeterminate | Drawing | Detail | Media Distribution System | Civil and Steel Structure | TAM |  | IFA | AC |  | 95%
16477 | I491TR07-0MBSS91-004-002 | Pipe-Rack Structural Drawing Column & Base-Plates(Pr001) | 00 | 2013-03-03 | Indeterminate | Drawing | Detail | Media Distribution System | Civil and Steel Structure | TAM |  | IFA | AC |  | 95%
16486 | I491TR07-0MBSS91-004-003 | Pipe-Rack Structural Drawing Framing Elev. & Plan(Pr001) | 00 | 2013-03-03 | Indeterminate | Drawing | Detail | Media Distribution System | Civil and Steel Structure | TAM |  | IFA | AC |  | 95%
16487 | I491TR07-0MBSS91-004-004 | Pipe-Rack Structural Drawing Framing Details(Pr001) | 00 | 2013-03-03 | Indeterminate | Drawing | Detail | Media Distribution System | Civil and Steel Structure | TAM |  | IFA | AC |  | 95%
16488 | I491TR07-0MBSS91-004-005 | Pipe-Rack Structural Drawing Framing & Connection Details(Pr001) | 00 | 2013-03-03 | Indeterminate | Drawing | Detail | Media Distribution System | Civil and Steel Structure | TAM |  | IFA | AC |  | 95%
16489 | I491TR07-0MBSS91-004-006 | Pipe-Rack Structural Drawing Typical Connection Details(Pr001) | 00 | 2013-03-03 | Indeterminate | Drawing | Detail | Media Distribution System | Civil and Steel Structure | TAM |  | IFA | AC |  | 95%
16490 | I491TR07-0MBSS91-004-007 | Pipe-Rack Structural Drawing 3D-View(Pr002) | 00 | 2013-03-03 | Indeterminate | Drawing | Detail | Media Distribution System | Civil and Steel Structure | TAM |  | IFA | AC |  | 95%
16491 | I491TR07-0MBSS91-004-008 | Pipe-Rack Structural Drawing Column & Base-Plates(Pr002) | 00 | 2013-03-03 | Indeterminate | Drawing | Detail | Media Distribution System | Civil and Steel Structure | TAM |  | IFA | AC |  | 95%
16492 | I491TR07-0MBSS91-004-009 | Pipe-Rack Structural Drawing Framing Plan(Pr002) | 00 | 2013-03-03 | Indeterminate | Drawing | Detail | Media Distribution System | Civil and Steel Structure | TAM |  | IFA | AC |  | 95%
16467 | I491TR07-0MBSS91-004-010 | Pipe-Rack Structural Drawing Framing Elev. & Details(Pr002) | 00 | 2013-03-03 | Indeterminate | Drawing | Detail | Media Distribution System | Civil and Steel Structure | TAM |  | IFA | AC |  | 95%
16468 | I491TR07-0MBSS91-004-011 | Pipe-Rack Structural Drawing Typical Connection Details(Pr002) | 00 | 2013-03-03 | Indeterminate | Drawing | Detail | Media Distribution System | Civil and Steel Structure | TAM |  | IFA | AC |  | 95%
16469 | I491TR07-0MBSS91-004-012 | Pipe-Rack Structural Drawing Framing Plan(Pr003) | 00 | 2013-03-03 | Indeterminate | Drawing | Detail | Media Distribution System | Civil and Steel Structure | TAM |  | IFA | AC |  | 95%
16470 | I491TR07-0MBSS91-004-013 | Pipe-Rack Structural Drawingcolumn & Base Plates(Pr003) | 00 | 2013-03-03 | Indeterminate | Drawing | Detail | Media Distribution System | Civil and Steel Structure | TAM |  | IFA | AC |  | 95%
16471 | I491TR07-0MBSS91-004-014 | Pipe-Rack Structural Drawing Column Elev. & Bracing(Pr003) | 00 | 2013-03-03 | Indeterminate | Drawing | Detail | Media Distribution System | Civil and Steel Structure | TAM |  | IFA | AC |  | 95%
16472 | I491TR07-0MBSS91-004-015 | Pipe-Rack Structural Drawing Typical Connections(Pr003) | 00 | 2013-03-03 | Indeterminate | Drawing | Detail | Media Distribution System | Civil and Steel Structure | TAM |  | IFA | AC |  | 95%
16473 | I491TR07-0MBSS91-004-016 | Pipe-Rack Structural Drawing Framing Plan(Pr004) | 00 | 2013-03-03 | Indeterminate | Drawing | Detail | Media Distribution System | Civil and Steel Structure | TAM |  | IFA | AC |  | 95%
16474 | I491TR07-0MBSS91-004-017 | Pipe-Rack Structural Drawing Column & Base Plates(Pr004) | 00 | 2013-03-03 | Indeterminate | Drawing | Detail | Media Distribution System | Civil and Steel Structure | TAM |  | IFA | AC |  | 95%
16475 | I491TR07-0MBSS91-004-018 | Pipe-Rack Structural Drawing Column Elev. & Bracing(Pr004) | 00 | 2013-03-03 | Indeterminate | Drawing | Detail | Media Distribution System | Civil and Steel Structure | TAM |  | IFA | AC |  | 95%
16476 | I491TR07-0MBSS91-004-019 | Pipe-Rack Structural Drawing Typical Connections(Pr004) | 00 | 2013-03-03 | Indeterminate | Drawing | Detail | Media Distribution System | Civil and Steel Structure | TAM |  | IFA | AC |  | 95%
16478 | I491TR07-0MBSS91-004-020 | Pipe-Rack Structural Drawing Framing Plan(Pr005) | 00 | 2013-03-03 | Indeterminate | Drawing | Detail | Media Distribution System | Civil and Steel Structure | TAM |  | IFA | AC |  | 95%
16479 | I491TR07-0MBSS91-004-021 | Pipe-Rack Structural Drawing Column & Base Plates(Pr005) | 00 | 2013-03-03 | Indeterminate | Drawing | Detail | Media Distribution System | Civil and Steel Structure | TAM |  | IFA | AC |  | 95%
16480 | I491TR07-0MBSS91-004-022 | Pipe-Rack Structural Drawing Column Elev. & Bracing(Pr005) | 00 | 2013-03-03 | Indeterminate | Drawing | Detail | Media Distribution System | Civil and Steel Structure | TAM |  | IFA | AC |  | 95%
16481 | I491TR07-0MBSS91-004-023 | Pipe-Rack Structural Drawing Typical Connections(Pr005) | 00 | 2013-03-03 | Indeterminate | Drawing | Detail | Media Distribution System | Civil and Steel Structure | TAM |  | IFA | AC |  | 95%
16482 | I491TR07-0MBSS91-004-024 | Pipe-Rack Structural Drawing Framing Plan(Pr006) | 00 | 2013-03-03 | Indeterminate | Drawing | Detail | Media Distribution System | Civil and Steel Structure | TAM |  | IFA | AC |  | 95%
16483 | I491TR07-0MBSS91-004-025 | Pipe-Rack Structural Drawing Column & Base Plates(Pr006) | 00 | 2013-03-03 | Indeterminate | Drawing | Detail | Media Distribution System | Civil and Steel Structure | TAM |  | IFA | AC |  | 95%
16484 | I491TR07-0MBSS91-004-026 | Pipe-Rack Structural Drawing Column Elev. & Bracing(Pr006) | 00 | 2013-03-03 | Indeterminate | Drawing | Detail | Media Distribution System | Civil and Steel Structure | TAM |  | IFA | AC |  | 95%
16485 | I491TR07-0MBSS91-004-027 | Pipe-Rack Structural Drawing Typical Connections(Pr006) | 00 | 2013-03-03 | Indeterminate | Drawing | Detail | Media Distribution System | Civil and Steel Structure | TAM |  | IFA | AC |  | 95%
16493 | I491TR07-0MBSS91-005-001 | Pipe-Rack Foundation Drawing Pr001 | 00 | 2013-03-03 | Indeterminate | Drawing | Detail | Media Distribution System | Civil and Steel Structure | TAM |  | IFA | AC |  | 95%
16494 | I491TR07-0MBSS91-005-002 | Pipe-Rack Foundation Drawing Pr002 | 00 | 2013-03-03 | Indeterminate | Drawing | Detail | Media Distribution System | Civil and Steel Structure | TAM |  | IFA | AC |  | 95%
16495 | I491TR07-0MBSS91-005-003 | Pipe-Rack Foundation Drawing Pr003 | 00 | 2013-03-03 | Indeterminate | Drawing | Detail | Media Distribution System | Civil and Steel Structure | TAM |  | IFA | AC |  | 95%
16496 | I491TR07-0MBSS91-005-004 | Pipe-Rack Foundation Drawing Pr004 | 00 | 2013-03-03 | Indeterminate | Drawing | Detail | Media Distribution System | Civil and Steel Structure | TAM |  | IFA | AC |  | 95%
16497 | I491TR07-0MBSS91-005-005 | Pipe-Rack Foundation Drawing Pr005 | 00 | 2013-03-03 | Indeterminate | Drawing | Detail | Media Distribution System | Civil and Steel Structure | TAM |  | IFA | AC |  | 95%
16498 | I491TR07-0MBSS91-005-006 | Pipe-Rack Foundation Drawing Pr006 | 00 | 2013-03-03 | Indeterminate | Drawing | Detail | Media Distribution System | Civil and Steel Structure | TAM |  | IFA | AC |  | 95%
114103 | I491TR07-0MMCT01-001-001 | Sleeper Newjersey Piping Support for WTP Outside of Pump Station | 00 | 2015-06-21 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Piping & Utility | TAM | 2015-06-22 09:55 | IFI | OB | 100%
114104 | I491TR07-0MMCT01-001-002 | Sleeper Newjersey Piping Support for WTP Outside of Pump Station | 00 | 2015-06-21 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Piping & Utility | TAM | 2015-06-22 09:55 | IFI | OB | 100%
114105 | I491TR07-0MMCT01-001-003 | Sleeper Newjersey Piping Support for WTP Outside of Pump Station | 00 | 2015-06-21 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Piping & Utility | TAM | 2015-06-22 09:55 | IFI | OB | 100%
115142 | I491TR07-0MMCT01-002-001 | Sleeper Newjersy Piping Support for WTP Outside of Pump Station | 01 | 2016-04-17 | Indeterminate | Drawing | Detail | Water Treatment & Cooling System | Piping & Utility | TAM | 2016-04-20 11:02 | IFC | AFC | 100%
16499 | I491TR07-0NGAA91-001-001 | Natural Gas Pressure Reducing Station Piping Plan Metering And Regulating Station | 00 | 2012-12-16 | Indeterminate | Drawing | Detail | Natural Gas Reducing Station | Piping & Utility | TAM |  | IFA | AC |  | 95%
114819 | I491TR08-0ASVA92-001-001 | Valve List For Air Separation Plant | 00 | 2016-01-23 | Indeterminate | Miscellaneous(MISC) | Detail | Air Separation Plant | Piping & Utility | TAM | 2016-01-24 09:46 | IFI | OB | 100%
16500 | I491TR08-0CPVA92-001-001 | Valve List For Compressed Air Plant | 00 | 2013-03-11 | Indeterminate | Miscellaneous(MISC) | Detail | Compressed Air Production Plant | Piping & Utility | HAVAYAR |  | IFA | A | 100%
132826 | I491TR09-0CCAM91-001-001 | CCM CONTROL CABIN AIR CONDITIONING UNITS LAYOUTPLAN AT LEVEL +0.00 | 02 | 2018-02-03 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | APEC | 2018-02-04 09:49 | IFC | AFC | 100%
132827 | I491TR09-0CCAM91-002-001 | CCM CONTROL CABIN AIR CONDITIONING UNITS LAYOUT PLAN AT LEVEL +4.90 | 02 | 2018-02-03 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | APEC | 2018-02-04 09:49 | IFC | AFC | 100%
132828 | I491TR09-0CCAM91-003-001 | CCM CONTROL CABIN AIR CONDITIONING UNITS LAYOUT PLAN AT LEVEL +9.87 | 02 | 2018-02-03 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | APEC | 2018-02-04 09:49 | IFC | AFC | 100%
132829 | I491TR09-0CCAM91-004-001 | CCM CONTROL CABIN AIR CONDITIONING UNITS LAYOUT PLAN AT LEVEL +13.37 | 02 | 2018-02-03 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | APEC | 2018-02-04 09:49 | IFC | AFC | 100%
132830 | I491TR09-0CCAM91-005-001 | CCM CONTROL CABIN AIR CONDITIONING UNITS SCHEDULE | 02 | 2018-02-03 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | APEC | 2018-02-04 09:49 | IFC | AFC | 100%
132843 | I491TR09-0CCAM91-006-001 | CCM CONTROL CABIN AIR CONDITIONING UNITS DRAIN LAYOUT PLAN AT LEVEL +0.00 | 02 | 2018-02-03 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | APEC | 2018-02-04 09:50 | IFC | AFC | 100%
132831 | I491TR09-0CCAM91-007-001 | CCM CONTROL CABIN AIR CONDITIONING UNITS DRAIN LAYOUT PLAN AT LEVEL +4.90 | 02 | 2018-02-03 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | APEC | 2018-02-04 09:49 | IFC | AFC | 100%
132832 | I491TR09-0CCAM91-008-001 | CCM CONTROL CABIN AIR CONDITIONING UNITS DRAIN LAYOUT PLAN AT LEVEL +9.87 | 02 | 2018-02-03 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | APEC | 2018-02-04 09:49 | IFC | AFC | 100%
132833 | I491TR09-0CCAM91-009-001 | CCM CONTROL CABIN DUCTING LAYOUT PLAN AT LEVEL +0.00 | 02 | 2018-02-03 | Indeterminate | Drawing | Basic | Continuous Casting Machine (CCM) | Mechanical | APEC | 2018-02-04 09:49 | IFC | AFC | 100%
132834 | I491TR09-0CCAM91-010-001 | CCM CONTROL CABIN DUCTING LAYOUT PLAN AT LEVEL +4.90 | 02 | 2018-02-03 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | APEC | 2018-02-04 09:49 | IFC | AFC | 100%
132835 | I491TR09-0CCAM91-011-001 | CCM CONTROL CABIN DUCTING LAYOUT PLAN AT LEVEL +0.00 | 02 | 2018-02-03 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | APEC | 2018-02-04 09:50 | IFC | AFC | 100%
132836 | I491TR09-0CCAM91-012-001 | CCM CONTROL CABIN DUCTING LAYOUT PLAN AT LEVEL +4.90 | 02 | 2018-02-03 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | APEC | 2018-02-04 09:50 | IFC | AFC | 100%
132837 | I491TR09-0CCAM91-013-001 | CCM CONTROL CABIN DUCTING LAYOUT PLAN AT LEVEL +9.87 | 02 | 2018-02-03 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | APEC | 2018-02-04 09:50 | IFC | AFC | 100%
132838 | I491TR09-0CCAM91-014-001 | CCM CONTROL CABIN DUCTING LAYOUT PLAN AT LEVEL +13.37 | 02 | 2018-02-03 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | APEC | 2018-02-04 09:50 | IFC | AFC | 100%
132844 | I491TR09-0CCAM91-015-001 | CCM CONTROL CABIN EQUIPMENT SCHEDULE & CONTROL DIAGRAM | 02 | 2018-02-03 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | APEC | 2018-02-04 09:50 | IFC | AFC | 100%
132839 | I491TR09-0CCAM91-016-001 | CCM CONTROL CABIN PLUMBING LAYOUT PLAN AT LEVEL +0.00 | 02 | 2018-02-03 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | APEC | 2018-02-04 09:50 | IFC | AFC | 100%
132840 | I491TR09-0CCAM91-017-001 | CCM CONTROL CABIN PLUMBING LAYOUT PLAN AT LEVEL +4.90 | 02 | 2018-02-03 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | APEC | 2018-02-04 09:50 | IFC | AFC | 100%
132841 | I491TR09-0CCAM91-018-001 | CCM CONTROL CABIN PLUMBING LAYOUT PLAN AT LEVEL +9.87 | 02 | 2018-02-03 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | APEC | 2018-02-04 09:50 | IFC | AFC | 100%
132842 | I491TR09-0CCAM91-019-001 | CCM CONTROL CABIN LEGENDS,GENERAL NOTES & DETAILS | 02 | 2018-02-03 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | APEC | 2018-02-04 09:50 | IFC | AFC | 100%
132845 | I491TR09-0CCAM91-020-001 | CCM RUN OUT CABIN AIR CONDITIONING UNITS LAYOUT PLAN AT LEVEL +0.20 | 02 | 2018-02-03 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | APEC | 2018-02-04 09:50 | IFC | AFC | 100%
132846 | I491TR09-0CCAM91-021-001 | CCM RUN OUT CABIN AIR CONDITIONING UNITS LAYOUT PLAN AT LEVEL +4.50 | 02 | 2018-02-03 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | APEC | 2018-02-04 09:50 | IFC | AFC | 100%
132847 | I491TR09-0CCAM91-022-001 | CCM RUN OUT CABIN AIR CONDITIONING UNITS DRAIN LAYOUT PLAN AT LEVEL +0.20 | 02 | 2018-02-03 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | APEC | 2018-02-04 09:50 | IFC | AFC | 100%
132848 | I491TR09-0CCAM91-023-001 | CCM RUN OUT CABIN AIR CONDITIONING UNITS DRAIN LAYOUT PLAN AT LEVEL +4.50 | 02 | 2018-02-03 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | APEC | 2018-02-04 09:50 | IFC | AFC | 100%
132849 | I491TR09-0CCAM91-024-001 | CCM RUN OUT CABIN AIR CONDITIONING UNITS LAYOUT ROOF PLAN AT LEVEL +8.50 | 02 | 2018-02-03 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | APEC | 2018-02-04 09:50 | IFC | AFC | 100%
132850 | I491TR09-0CCAM91-025-001 | CCM RUN OUT CABIN EXH. FANS LAYOUT PLAN AT LEVEL +0.20 | 02 | 2018-02-03 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | APEC | 2018-02-04 09:50 | IFC | AFC | 100%
135080 | I491TR09-0CCAM91-026-001 | CCM FNC MAINTENANCE ROOM HVAC | 04 | 2019-02-26 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | APEC | 2019-03-09 12:34 | IFC | AC |  | 95%
132852 | I491TR09-0CCAM91-027-001 | CCM LADLE TURRET AIR CONDITIONING UNITS LAYOUT PLAN AT LEVEL +0.00 1-2 | 02 | 2018-02-03 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | APEC | 2018-02-04 09:50 | IFC | AFC | 100%
132853 | I491TR09-0CCAM91-028-001 | CCM LADLE TURRET AIR CONDITIONING UNITS LAYOUT PLAN AT LEVEL +0.00 2-2 | 02 | 2018-02-03 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | APEC | 2018-02-04 09:50 | IFC | AFC | 100%
132854 | I491TR09-0CCAM91-029-001 | CCM LADLE TURRET EXH. FANS LAYOUT PLAN AT LEVEL + 0.00 | 02 | 2018-02-03 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | APEC | 2018-02-04 09:50 | IFC | AFC | 100%
16575 | I491TR09-0MEAM91-001-003 | SMP SUBSTATION BUILDING Domestic Hot and Cold Water and Sewage Layout | 01 | 2013-12-01 | Indeterminate | Drawing | Basic | General Civil | Civil and Steel Structure | TAM | 2014-02-18 09:36 | IFC | AFC | 100%
111280 | I491TR09-0MEAM91-001-004 | Installation Details Domestic Hot And Cold Water And Sewage Layout | 01 | 2013-12-01 | Indeterminate | Drawing | Detail | General Civil | Civil and Steel Structure | TAM | 2014-04-15 10:09 | IFC | AFC | 100%
134152 | I491TR09-0MRAC91-002-001 | HVAC Detail Drawing For EAF Building KEY PLAN & LIST OF DRAWING 1-14 | 02 | 2018-09-12 09:32 | Indeterminate | Drawing | Detail | Air Conditioning and Ventilation | Mechanical | TAM | 2018-09-12 09:32 | IFC | AC |  | 95%
134153 | I491TR09-0MRAC91-002-002 | HVAC Detail Drawing For EAF Building LEVEL -3.3 2-14 | 04 | 2018-09-12 09:32 | Indeterminate | Drawing | Detail | Air Conditioning and Ventilation | Mechanical | TAM | 2018-09-12 09:32 | IFC | AC |  | 95%
134154 | I491TR09-0MRAC91-002-003 | HVAC Detail Drawing For EAF Building LEVEL 0.0 3-14 | 04 | 2018-09-12 09:32 | Indeterminate | Drawing | Detail | Air Conditioning and Ventilation | Mechanical | TAM | 2018-09-12 09:32 | IFC | AC |  | 95%
134155 | I491TR09-0MRAC91-002-004 | HVAC Detail Drawing For EAF Building LEVEL 4.75 4-14 | 04 | 2018-09-12 09:32 | Indeterminate | Drawing | Detail | Air Conditioning and Ventilation | Mechanical | TAM | 2018-09-12 09:32 | IFC | AC |  | 95%
134156 | I491TR09-0MRAC91-002-005 | HVAC Detail Drawing For EAF Building LEVEL 8.5 5-14 | 04 | 2018-09-12 09:32 | Indeterminate | Drawing | Detail | Air Conditioning and Ventilation | Mechanical | TAM | 2018-09-12 09:32 | IFC | AC |  | 95%
134157 | I491TR09-0MRAC91-002-006 | HVAC Detail Drawing For EAF Building LEVEL 14.0 6-14 | 04 | 2018-09-12 09:32 | Indeterminate | Drawing | Detail | Air Conditioning and Ventilation | Mechanical | TAM | 2018-09-12 09:32 | IFC | AC |  | 95%
134158 | I491TR09-0MRAC91-002-007 | HVAC Detail Drawing For EAF Building ROOF PLAN 7-14 | 02 | 2018-09-12 09:32 | Indeterminate | Drawing | Detail | Air Conditioning and Ventilation | Mechanical | TAM | 2018-09-12 09:32 | IFC | AC |  | 95%
134159 | I491TR09-0MRAC91-002-008 | HVAC Detail Drawing For EAF Building VIEW A 8-14 | 02 | 2018-09-12 09:32 | Indeterminate | Drawing | Detail | Air Conditioning and Ventilation | Mechanical | TAM | 2018-09-12 09:32 | IFC | AC |  | 95%
134160 | I491TR09-0MRAC91-002-009 | HVAC Detail Drawing For EAF Building VIEW B 9-14 | 02 | 2018-09-12 09:32 | Indeterminate | Drawing | Detail | Air Conditioning and Ventilation | Mechanical | TAM | 2018-09-12 09:32 | IFC | AC |  | 95%
134161 | I491TR09-0MRAC91-002-010 | HVAC Detail Drawing For EAF Building VIEW C 10-14 | 02 | 2018-09-12 09:32 | Indeterminate | Drawing | Detail | Air Conditioning and Ventilation | Mechanical | TAM | 2018-09-12 09:32 | IFC | AC |  | 95%
134162 | I491TR09-0MRAC91-002-011 | HVAC Detail Drawing For EAF Building VIEW D 11-14 | 02 | 2018-09-12 09:32 | Indeterminate | Drawing | Detail | Air Conditioning and Ventilation | Mechanical | TAM | 2018-09-12 09:32 | IFC | AC |  | 95%
134163 | I491TR09-0MRAC91-002-012 | HVAC Detail Drawing For EAF Building SECTION A 12-14 | 02 | 2018-09-12 09:32 | Indeterminate | Drawing | Detail | Air Conditioning and Ventilation | Mechanical | TAM | 2018-09-12 09:32 | IFC | AC |  | 95%
134164 | I491TR09-0MRAC91-002-013 | HVAC Detail Drawing For EAF Building SECTION B 13-14 | 02 | 2018-09-12 09:32 | Indeterminate | Drawing | Detail | Air Conditioning and Ventilation | Mechanical | TAM | 2018-09-12 09:32 | IFC | AC |  | 95%
134165 | I491TR09-0MRAC91-002-014 | HVAC Detail Drawing For EAF Building 14-14 | 03 | 2018-09-12 09:32 | Indeterminate | Drawing | Detail | Air Conditioning and Ventilation | Mechanical | TAM | 2018-09-12 09:32 | IFC | AC |  | 95%
134166 | I491TR09-0MRAC91-003-001 | HVAC Detail Drawing For LF Building KEY PLAN 1-8 | 01 | 2018-09-12 09:33 | Indeterminate | Drawing | Detail | Air Conditioning and Ventilation | Mechanical | TAM | 2018-09-12 09:33 | IFC | AC |  | 95%
134167 | I491TR09-0MRAC91-003-002 | HVAC Detail Drawing For LF Building LEVEL -3.3 , 0.0 2-8 | 03 | 2018-09-12 09:33 | Indeterminate | Drawing | Detail | Air Conditioning and Ventilation | Mechanical | TAM | 2018-09-12 09:33 | IFC | AC |  | 95%
134168 | I491TR09-0MRAC91-003-003 | HVAC Detail Drawing For LF Building LEVEL -3.3 , 0.0 3-8 | 03 | 2018-09-12 09:33 | Indeterminate | Drawing | Detail | Air Conditioning and Ventilation | Mechanical | TAM | 2018-09-12 09:33 | IFC | AC |  | 95%
134169 | I491TR09-0MRAC91-003-004 | HVAC Detail Drawing For LF Building ROOF PLAN 4-8 | 02 | 2018-09-12 09:33 | Indeterminate | Drawing | Detail | Air Conditioning and Ventilation | Mechanical | TAM | 2018-09-12 09:33 | IFC | AC |  | 95%
134170 | I491TR09-0MRAC91-003-005 | HVAC Detail Drawing For LF Building SECTION A & DETAILS 5-8 | 01 | 2018-09-12 09:33 | Indeterminate | Drawing | Detail | Air Conditioning and Ventilation | Mechanical | TAM | 2018-09-12 09:33 | IFC | AC |  | 95%
134171 | I491TR09-0MRAC91-003-006 | HVAC Detail Drawing For LF Building SECTION B & VEIW A 6-8 | 01 | 2018-09-12 09:33 | Indeterminate | Drawing | Detail | Air Conditioning and Ventilation | Mechanical | TAM | 2018-09-12 09:33 | IFC | AC |  | 95%
134172 | I491TR09-0MRAC91-003-007 | HVAC Detail Drawing For LF Building VEIW B & VEIW C 7-8 | 01 | 2018-09-12 09:33 | Indeterminate | Drawing | Detail | Air Conditioning and Ventilation | Mechanical | TAM | 2018-09-12 09:33 | IFC | AC |  | 95%
134173 | I491TR09-0MRAC91-003-008 | HVAC Detail Drawing For LF Building 8-8 | 02 | 2018-09-12 09:33 | Indeterminate | Drawing | Detail | Air Conditioning and Ventilation | Mechanical | TAM | 2018-09-12 09:33 | IFC | AC |  | 95%
133224 | I491TR09-0MRAC91-005-001 | ASP-CAP SUBSTATION BUILDING HVAC DETAIL DRAWING 1-2 | 02 | 2018-05-30 | Indeterminate | Drawing | Detail | Air Conditioning and Ventilation | Mechanical | TAM | 2018-06-11 10:33 | IFC | AFC | 100%
133225 | I491TR09-0MRAC91-005-002 | ASP-CAP SUBSTATION BUILDING HVAC DETAIL DRAWING 2-2 | 02 | 2018-05-30 | Indeterminate | Drawing | Detail | Air Conditioning and Ventilation | Mechanical | TAM | 2018-06-11 10:33 | IFC | AFC | 100%
16502 | I491TR09-0MRAC91-007-002 | Hvac Detail Drawing For Scrap Yard | 00 | 2013-07-23 | Indeterminate | Miscellaneous(MISC) | Detail | Melt Shop Scrap Yard | Piping & Utility | TAM |  | IFC | AFC | 100%
16503 | I491TR09-0MRAC91-008-001 | Hvac Detail Drawing For Work Shop | 00 | 2013-01-02 | Indeterminate | Miscellaneous(MISC) | Detail | Maintenance Workshop | Piping & Utility | TAM |  | IFA | AC |  | 95%
16504 | I491TR09-0MRAC91-008-002 | Hvac Detail Drawing For Ware House | 00 | 2013-01-02 | Indeterminate | Drawing | Detail | Warehouse | Piping & Utility | TAM |  | IFA | AC |  | 95%
133227 | I491TR09-0MRAC91-009-001 | SMP SUBSTATION BUILDING HVAC DETAIL DRAWING 1-2 | 02 | 2018-05-30 | Indeterminate | Drawing | Detail | Air Conditioning and Ventilation | Mechanical | TAM | 2018-06-11 10:33 | IFC | AFC | 100%
133226 | I491TR09-0MRAC91-009-002 | SMP SUBSTATION BUILDING HVAC DETAIL DRAWING 2-2 | 02 | 2018-05-30 | Indeterminate | Drawing | Detail | Air Conditioning and Ventilation | Mechanical | TAM | 2018-06-11 10:33 | IFC | AFC | 100%
133228 | I491TR09-0MRAC91-010-001 | WTP SUBSTATION BUILDING HVAC DETAIL DRAWING | 02 | 2018-05-30 | Indeterminate | Drawing | Detail | Air Conditioning and Ventilation | Mechanical | DATIS | 2018-06-11 10:33 | IFC | AFC | 100%
133229 | I491TR09-0MRAC91-011-001 | FTP-MHS SUBSTATION BUILDING HVAC DETAIL DRAWING | 02 | 2018-05-30 | Indeterminate | Drawing | Detail | Air Conditioning and Ventilation | Mechanical | TAM | 2018-06-11 10:33 | IFC | AFC | 100%
16506 | I491TR09-0MRAC91-014-002 | Cable Tunnel Ventilation Plan | 01 | 2012-09-11 | Indeterminate | Miscellaneous(MISC) | Detail | Main Electrical Substation And Distribution Network | Piping & Utility | TAM |  | IFI | OB | 100%
113447 | I491TR09-0MRAC91-015-001 | HVAC FLOW DIAGRAM FOR MELT SHOP | 01 | 2015-04-04 10:18 | Indeterminate | Drawing | Detail | Air Conditioning and Ventilation | Mechanical | TAM | 2015-04-04 10:18 | IFC | AC |  | 95%
130693 | I491TR09-0MRAC91-017-001 | HVAC FOR LABORATORY BUILDING | 00 | 2017-06-13 | Indeterminate | Drawing | Detail | Laboratory | Mechanical | TAM | 2017-06-14 15:28 | IFA | AC |  | 95%
135329 | I491TR09-0MRAC91-018-001 | OFFICE "1" HVAC DRAWING | 02 | 2019-05-08 | Indeterminate | Drawing | Detail | Melt Shop | Mechanical | TAM | 2019-05-11 09:18 | IFC | AC |  | 95%
135334 | I491TR09-0MRAC91-019-001 | OFFICE "2" HVAC DRAWING | 02 | 2019-05-08 | Indeterminate | Drawing | Detail | Melt Shop | Mechanical | TAM | 2019-05-11 09:23 | IFC | AFC | 100%
135335 | I491TR09-0MRAC91-020-001 | W.C. HVAC DRAWING | 02 | 2019-05-08 | Indeterminate | Drawing | Detail | Melt Shop | Mechanical | TAM | 2019-05-11 09:24 | IFC | AFC | 100%
133450 | I491TR09-0MRAC91-021-001 | WORKSHOP HVAC DRAWING SECOND FLOOR PLAN / SECTIONS | 00 | 2018-07-07 | Indeterminate | Drawing | Detail | Air Conditioning and Ventilation | Mechanical | TAM | 2018-07-10 09:34 | IFA | A | 100%
134328 | I491TR09-0MRAC91-022-001 | ASP- Control Room HVAC Drawing PLAN 1-5 | 01 | 2018-10-29 14:19 | Indeterminate | Drawing | Detail | Air Separation Plant | Mechanical | TAM | 2018-10-29 14:19 | IFC | AFC | 100%
134329 | I491TR09-0MRAC91-022-002 | ASP- Control Room HVAC Drawing View A 2-5 | 01 | 2018-10-29 14:19 | Indeterminate | Drawing | Detail | Air Separation Plant | Mechanical | TAM | 2018-10-29 14:19 | IFC | AFC | 100%
134330 | I491TR09-0MRAC91-022-003 | ASP- Control Room HVAC Drawing View B and Section C-C 3-5 | 01 | 2018-10-29 14:19 | Indeterminate | Drawing | Detail | Air Separation Plant | Mechanical | TAM | 2018-10-29 14:19 | IFC | AFC | 100%
134331 | I491TR09-0MRAC91-022-004 | ASP- Control Room HVAC Drawing Sec. D-D 4-5 | 01 | 2018-10-29 14:19 | Indeterminate | Drawing | Detail | Air Separation Plant | Mechanical | TAM | 2018-10-29 14:19 | IFC | AFC | 100%
134332 | I491TR09-0MRAC91-022-005 | ASP- Control Room HVAC Drawing M.D-1 & ALW-1 5-5 | 01 | 2018-10-29 14:19 | Indeterminate | Drawing | Detail | Air Separation Plant | Mechanical | TAM | 2018-10-29 14:19 | IFC | AFC | 100%
111281 | I491TR09-0MYAM91-001-001 | Workshop Mechanical Drawing Sewage Layout | 01 | 2013-12-01 | Indeterminate | Drawing | Basic | General Civil | Civil and Steel Structure | IKS | 2014-04-15 10:14 | IFC | AFC | 100%
111282 | I491TR09-0MYAM91-001-002 | Workshop Mechanical Drawing Hot And Cold Water Layout | 01 | 2013-12-01 | Indeterminate | Drawing | Basic | General Civil | Civil and Steel Structure | IKS | 2014-04-15 10:17 | IFC | AFC | 100%
111283 | I491TR09-0MYAM91-001-003 | Installation Details Domestic Hot And Cold Water And Sewage Layout | 01 | 2013-12-01 | Indeterminate | Drawing | Basic | General Civil | Civil and Steel Structure | IKS | 2014-04-15 10:30 | IFC | AFC | 100%
113104 | I491TR09-0OFAC91-001-001 | NON INDUSTRIAL BUILDINGS (MECHANICAL DRAWINGS) List Of Drawings, General Notes and Legends | 02 | 2014-12-10 | Indeterminate | Drawing | Detail | Office - Canteen - Locker & Shower For Melt Shop | Mechanical | TAM | 2014-12-15 08:51 | IFC | AFC | 100%
113105 | I491TR09-0OFAC91-001-002 | NON INDUSTRIAL BUILDINGS (MECHANICAL DRAWINGS) Ground Floor Air Conditioning Piping | 02 | 2014-12-10 | Indeterminate | Drawing | Detail | Office - Canteen - Locker & Shower For Melt Shop | Mechanical | TAM | 2014-12-15 08:51 | IFC | AC |  | 95%
113106 | I491TR09-0OFAC91-001-003 | NON INDUSTRIAL BUILDINGS (MECHANICAL DRAWINGS) First Floor Air Conditioning Piping | 02 | 2014-12-10 | Indeterminate | Drawing | Detail | Office - Canteen - Locker & Shower For Melt Shop | Mechanical | TAM | 2014-12-15 08:51 | IFC | AC |  | 95%
113107 | I491TR09-0OFAC91-001-004 | NON INDUSTRIAL BUILDINGS (MECHANICAL DRAWINGS) Air Conditionongn Piping Of Roof | 02 | 2014-12-10 | Indeterminate | Drawing | Detail | Office - Canteen - Locker & Shower For Melt Shop | Mechanical | TAM | 2014-12-15 08:51 | IFC | AC |  | 95%
113108 | I491TR09-0OFAC91-002-001 | NON INDUSTRIAL BUILDINGS (MECHANICAL DRAWINGS) List Of Drawings, General Notes and Legends | 02 | 2014-12-10 | Indeterminate | Drawing | Detail | Office - Canteen - Locker & Shower For Melt Shop | Mechanical | TAM | 2014-12-15 08:52 | IFC | AFC | 100%
113109 | I491TR09-0OFAC91-002-002 | NON INDUSTRIAL BUILDINGS (MECHANICAL DRAWINGS) Ground Floor Air Exhust Ducting | 02 | 2014-12-10 | Indeterminate | Drawing | Detail | Office - Canteen - Locker & Shower For Melt Shop | Mechanical | TAM | 2014-12-15 08:52 | IFC | AC |  | 95%
113110 | I491TR09-0OFAC91-002-003 | NON INDUSTRIAL BUILDINGS (MECHANICAL DRAWINGS) First Floor Air Exhust Ducting | 02 | 2014-12-10 | Indeterminate | Drawing | Detail | Office - Canteen - Locker & Shower For Melt Shop | Mechanical | TAM | 2014-12-15 08:52 | IFC | AC |  | 95%
113111 | I491TR09-0OFAC91-002-004 | NON INDUSTRIAL BUILDINGS (MECHANICAL DRAWINGS) Air Exhust Ducting Of Roof | 02 | 2014-12-10 | Indeterminate | Drawing | Detail | Office - Canteen - Locker & Shower For Melt Shop | Mechanical | TAM | 2014-12-15 08:52 | IFC | AFC | 100%
113112 | I491TR09-0OFAC91-002-005 | NON INDUSTRIAL BUILDINGS (MECHANICAL DRAWINGS) Executive Details | 02 | 2014-12-10 | Indeterminate | Drawing | Detail | Office - Canteen - Locker & Shower For Melt Shop | Mechanical | TAM | 2014-12-15 08:52 | IFC | AC |  | 95%
113113 | I491TR09-0OFAM91-001-001 | NON INDUSTRIAL BUILDINGS (MECHANICAL DRAWINGS)List Of Drawings, General Notes and Legends | 02 | 2014-12-10 | Indeterminate | Drawing | Detail | Office - Canteen - Locker & Shower For Melt Shop | Mechanical | TAM | 2014-12-15 08:52 | IFC | AFC | 100%
113116 | I491TR09-0OFAM91-001-004 | NON INDUSTRIAL BUILDINGS (MECHANICAL DRAWINGS) Sewage Piping Of Roof | 02 | 2014-12-10 | Indeterminate | Drawing | Detail | Office - Canteen - Locker & Shower For Melt Shop | Mechanical | TAM | 2014-12-15 08:52 | IFC | AFC | 100%
113118 | I491TR09-0OFAM91-002-001 | NON INDUSTRIAL BUILDINGS (MECHANICAL DRAWINGS) List Of Drawings, General Notes and Legends | 02 | 2014-12-10 | Indeterminate | Drawing | Detail | Office - Canteen - Locker & Shower For Melt Shop | Mechanical | TAM | 2014-12-15 08:52 | IFC | AFC | 100%
113123 | I491TR09-0OFAM91-002-006 | NON INDUSTRIAL BUILDINGS (MECHANICAL DRAWINGS) Flow Diagram | 02 | 2014-12-10 | Indeterminate | Drawing | Detail | Office - Canteen - Locker & Shower For Melt Shop | Mechanical | TAM | 2014-12-15 08:52 | IFC | AC |  | 95%
113124 | I491TR09-0OFAM91-002-007 | NON INDUSTRIAL BUILDINGS (MECHANICAL DRAWINGS) Executive Details | 02 | 2014-12-10 | Indeterminate | Drawing | Detail | Office - Canteen - Locker & Shower For Melt Shop | Mechanical | TAM | 2014-12-15 08:52 | IFC | AC |  | 95%
113125 | I491TR09-0OFMS91-001-001 | NON INDUSTRIAL BUILDINGS (MECHANICAL DRAWINGS) List Of Drawings, General Notes and Legends | 02 | 2014-12-10 | Indeterminate | Drawing | Detail | Office - Canteen - Locker & Shower For Melt Shop | Mechanical | TAM | 2014-12-15 08:52 | IFC | AFC | 100%
113126 | I491TR09-0OFMS91-001-002 | NON INDUSTRIAL BUILDINGS (MECHANICAL DRAWINGS) Ground Floor Fire Fighting | 02 | 2014-12-10 | Indeterminate | Drawing | Detail | Office - Canteen - Locker & Shower For Melt Shop | Mechanical | TAM | 2014-12-15 08:52 | IFC | AC |  | 95%
113127 | I491TR09-0OFMS91-001-003 | NON INDUSTRIAL BUILDINGS (MECHANICAL DRAWINGS) First Floor Fire Fighting | 02 | 2014-12-10 | Indeterminate | Drawing | Detail | Office - Canteen - Locker & Shower For Melt Shop | Mechanical | TAM | 2014-12-15 08:52 | IFC | AFC | 100%
16510 | I491TR09-0TBAM91-001-001 | Melt Shop Main Building Lf Building Potable Water Plumbing Layout Plan At Level -3.20 & Plan At Level ±0.00 | 00 | 2013-03-16 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFA | A | 100%
16511 | I491TR09-0TBAM91-001-002 | Melt Shop Main Building Lf Building Potable Water Plumbing Layout Plan At Level +5.970 | 00 | 2013-03-16 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFA | A | 100%
16512 | I491TR09-0TBAM91-001-003 | Melt Shop Main Building Lf Building Potable Water Plumbing Layout Roof Plan | 00 | 2013-03-16 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFA | A | 100%
16513 | I491TR09-0TBAM91-002-001 | Melt Shop Main Building Lf Building Potable Water Plumbing Layout Plan At Level ±0.00 | 00 | 2013-03-16 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFA | A | 100%
16514 | I491TR09-0TBAM91-002-002 | Melt Shop Main Building Lf Building Potable Water Plumbing Layout Plan At Level +5.970 | 00 | 2013-03-16 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFA | A | 100%
16515 | I491TR09-0TBAM91-003-001 | Melt Shop Main Building Eaf Building Sever Drainage Plumbing Layout Plan At Level -3.200 | 00 | 2013-03-16 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFA | A | 100%
16516 | I491TR09-0TBAM91-003-002 | Melt Shop Main Building Eaf Building Sever Drainage Plumbing Layout Plan At Level ±0.00 | 00 | 2013-03-16 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFA | A | 100%
16517 | I491TR09-0TBAM91-003-003 | Melt Shop Main Building Eaf Building Sever Drainage Plumbing Layout Plan At Level +4.750 | 00 | 2013-03-16 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFA | A | 100%
16518 | I491TR09-0TBAM91-003-004 | Melt Shop Main Building Eaf Building Sever Drainage Plumbing Layout Plan At Level +8.200 | 00 | 2013-03-16 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFA | A | 100%
16519 | I491TR09-0TBAM91-003-005 | Melt Shop Main Building Eaf Building Sever Drainage Plumbing Layout Plan At Level +14.000 | 00 | 2013-03-16 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFA | A | 100%
16520 | I491TR09-0TBAM91-003-006 | Melt Shop Main Building Eaf Building Sever Drainage Plumbing Layout Roof Plan | 00 | 2013-03-16 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFA | A | 100%
16521 | I491TR09-0TBAM91-004-001 | Melt Shop Main Building Eaf Building Potable Water Plumbing Layout Plan At Level ±0.00 | 00 | 2013-03-16 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFA | A | 100%
16522 | I491TR09-0TBAM91-004-002 | Melt Shop Main Building Eaf Building Potable Water Plumbing Layout Plan At Level +4.750 | 00 | 2013-03-16 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFA | A | 100%
16523 | I491TR09-0TBAM91-004-003 | Melt Shop Main Building Eaf Building Potable Water Plumbing Layout Plan At Level +8.500 | 00 | 2013-03-16 | Indeterminate | Drawing | Detail | Melt Shop Main Building | Civil and Steel Structure | APEC |  | IFA | A | 100%
111285 | I491TR09-0WAAM91-001-001 | Installation Details Domestic Hot And Cold Water And Sewage Layout | 01 | 2013-12-01 | Indeterminate | Drawing | Basic | General Civil | Civil and Steel Structure | IKS | 2014-04-15 10:31 | IFC | AFC | 100%
111284 | I491TR09-0WAAM91-001-002 | Warehouse Mechanical Drawing Domestic Hot And Cold Water And Sewage Layout | 01 | 2013-12-01 | Indeterminate | Drawing | Basic | General Civil | Civil and Steel Structure | IKS | 2014-04-15 10:31 | IFC | AFC | 100%
16528 | I491TR99-0LFIH01-001-002 | Piping Electrode Arms Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Piping & Utility | FUCHS |  | IFI | OB | 100%
113593 | I491TR99-0LFLB92-001-001 | LUBRICATION SYSTEM - PIPING GANTRY LF | 00 | 2015-05-06 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | TAM | 2015-05-27 16:11 | IFI | OB | 100%
16529 | I491TR99-0LFLE01-001-001 | Pneumatic Piping Roof Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Piping & Utility | TAM |  | IFI | OB | 100%
16532 | I491TR99-0LFLE02-001-003 | Pneumatic Piping Roof Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Piping & Utility | FUCHS |  | IFI | OB | 100%
16535 | I491TR99-0LFLE03-001-003 | Pneumatic Piping Roof Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Piping & Utility | FUCHS |  | IFI | OB | 100%
16537 | I491TR99-0LFLE04-001-002 | Pneumatic Piping Roof Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Piping & Utility | FUCHS |  | IFI | OB | 100%
16538 | I491TR99-0LFLE10-001-001 | Water Piping Roof Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16539 | I491TR99-0LFLE11-001-001 | Water Piping Roof Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16540 | I491TR99-0LFLE12-001-001 | Water Piping Roof Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16541 | I491TR99-0LFLE13-001-001 | Water Piping Roof Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16542 | I491TR99-0LFLE14-001-001 | Water Piping Roof Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16543 | I491TR99-0LFLE15-001-001 | Water Piping Roof Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16544 | I491TR99-0LFLE16-001-001 | Water Piping Roof Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16545 | I491TR99-0LFLE17-001-001 | Piping Roof Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16546 | I491TR99-0LFLE18-001-001 | Piping Roof Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16547 | I491TR99-0LFLE19-001-001 | Piping Roof Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16548 | I491TR99-0LFLE20-001-001 | Water Piping Roof Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16549 | I491TR99-0LFLE21-001-001 | Water Piping Roof Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16550 | I491TR99-0LFLE22-001-001 | Hydraulic Piping Roof Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16551 | I491TR99-0LFLE23-001-001 | Hydraulic Piping Roof Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Mechanical | FUCHS |  | IFI | OB | 100%
16552 | I491TR99-0LFTF01-001-001 | Piping Tarnsformer Wall Water Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Piping & Utility | FUCHS |  | IFI | OB | 100%
16553 | I491TR99-0LFTF02-001-001 | Piping Tarnsformer Wall Flexibles Hss Lf | 00 | 2012-03-10 | Indeterminate | Drawing | Detail | Ladle Furnace | Piping & Utility | FUCHS |  | IFI | OB | 100%
16554 | I491TR99-0LFTF03-001-001 | Piping Tarnsformer Wall Water Lf | 00 | 2012-03-14 | Indeterminate | Drawing | Detail | Ladle Furnace | Piping & Utility | FUCHS |  | IFI | OB | 100%
16555 | I491TR99-0LFTF04-001-001 | Piping Tarnsformer Wall Water Lf | 00 | 2012-03-14 | Indeterminate | Drawing | Detail | Ladle Furnace | Piping & Utility | FUCHS |  | IFI | OB | 100%
16556 | I491TR99-0LFTF05-001-001 | Piping Tarnsformer Wall Water Lf | 00 | 2012-03-14 | Indeterminate | Drawing | Detail | Ladle Furnace | Piping & Utility | FUCHS |  | IFI | OB | 100%
16557 | I491TR99-0LFTF06-001-001 | Piping Tarnsformer Wall Water Lf | 00 | 2012-03-14 | Indeterminate | Drawing | Detail | Ladle Furnace | Piping & Utility | FUCHS |  | IFI | OB | 100%
16558 | I491TR99-0LFTF07-001-001 | Piping Tarnsformer Wall Water Lf | 00 | 2012-03-14 | Indeterminate | Drawing | Detail | Ladle Furnace | Piping & Utility | FUCHS |  | IFI | OB | 100%
135010 | I491TR99-0MBAA91-001-001 | Heat Tracing for Water Distribution Piping Lines | 00 | 2019-01-27 | Indeterminate | Miscellaneous(MISC) | Detail | Media Distribution System | Automation and Instrumentation | TAM | 2019-02-03 09:12 | IFI | OB | 100%
133035 | I491TR99-0MRAC91-001-001 | HVAC Design Report For EAF Building Transformer Room | 00 | 2018-04-08 08:56 | Indeterminate | Miscellaneous(MISC) | Detail | Air Conditioning and Ventilation | Mechanical | TAM | 2018-04-08 08:56 | IFA | A | 100%
114331 | I491TR99-0MRAC91-002-001 | Hvac Design Report For EAF Building | 01 | 2015-09-07 09:17 | Indeterminate | Miscellaneous(MISC) | Detail | Air Conditioning and Ventilation | Mechanical | TAM | 2015-09-07 09:17 | IFC | AFC | 100%
114332 | I491TR99-0MRAC91-003-001 | Hvac Design Report For LF Building | 01 | 2015-09-07 09:17 | Indeterminate | Miscellaneous(MISC) | Detail | Air Conditioning and Ventilation | Mechanical | TAM | 2015-09-07 09:17 | IFC | AFC | 100%
114629 | I491TT02-0CCHY91-003-001 | CCM Tundish Car Valve Stand 6.374965.A_001_01 | 00 | 2015-10-26 10:51 | Indeterminate | Drawing | Detail | Continuous Casting Machine (CCM) | Mechanical | DANIELI | 2015-10-26 10:51 | IFI | OB | 100%
135249 | I491TT03-0MXAA91-001-001 | Instruction For Performance Guarantee Tests | 00 | 2019-04-24 | Indeterminate | Miscellaneous(MISC) | Detail | General | Mechanical | TAM | 2019-04-29 10:23 | IFA | AC |  | 95%
[7 empty] | تعداد مدارك | [6 empty] | 4513 | 1099 | 2 | 0
[7 empty] | JOB PHASE | [6 empty] | 100% | 95% | 85% | 0%
[7 empty] | تعداد مدارك ارسال شده بر اساس Job Phase | [6 empty] | 5558.75
[7 empty] | تعداد كل مدارك فاز مهندسي | [6 empty] | 5614
[7 empty] | درصد پيشرفت مهندسي پايه و تفصيلي | [6 empty] | 99.02%
[7 empty] | درصد پيشرفت مدارك As Built | [6 empty] | 60%
[7 empty] | درصد پيشرفت كل فاز مهندسي | [6 empty] | 97.07%

## Sheet2 (hidden)
Immediate | عمومی | Started | N/A | Changed | General
Normal | NA | Finished To Comment | Started | No Changed | Interface
Urgent | فاز 0 | Started And Finished To Comment | Defined | Vendor Dependence
| فاز 1 | Finished To Both | Finished | Vendor Independence
| فاز 2 | Finished To Transmittal | In Progress
| Basic | Commented
| Detail | Started And Commented
| As Build | Finished To Both And Commented
Started And Finished To Transmit
Transmitted
Started And Transmitted
Finished To Both And Transmitted
Transmitted And Commented
Defined
Hold
Void