## Sheet1
1 | Well Drilling Operation | Remaining Dur. | Pred. | Risk Assignment
2 | Start | 0
3 | Movement | 15 | 2
4 | Spud Day | 0 | 2 | R02 | R03 | R04 | R05 | R06
5 | Drilling & Petrolium Eng Operation
6 | Start Drilling | 0 | 4
7 | 26" Phase
8 | Drilling 26" Hole | 13 | 6 | R03 | R04 | R05 | R06 | R07
9 | Running 20" Casing+Cementing 26" Hole | 1 | 7 | R05 | R06 | R07 | R08 | R09
10 | N.Up (Well Head) B.O.P 26" | 1 | 8 | R06
11 | 17 1/2" Phase
12 | Drilling 17 1/2" Hole | 82 | 10 | R06 | R07 | R08 | R09 | R10
13 | Logging in 17 1/2" Hole | 1 | 12 | R10 | R11 | R12 | R13 | R14
14 | Running 13 3/8" Casing+Cementing 17 1/2" Hole | 7 | 13 | R09 | R10 | R11 | R12 | R13
15 | N.Up (Well Head) B.O.P 17 1/2" | 1 | 14 | R10
16 | 12 1/4" Phase
17 | Drilling 12 1/4" Hole | 17 | 15 | R01 | R02 | R03 | R04 | R05
18 | Logging in 12 1/4" Hole | 2 | 16 | R04 | R05 | R06 | R07 | R08
19 | Running 9 5/8" Casing+Cementing 12 1/4" Hole | 5 | 17 | R03 | R04 | R05 | R06 | R07
20 | N.Up (Well Head) B.O.P 12 1/4" | 1 | 18 | R14
21 | 8 3/4" Phase
22 | Drilling 8 1/2" Hole | 47 | 20 | R15 | R16 | R17 | R18
23 | Logging in 8 1/2" Hole | 11 | 22 | R09 | R10 | R11 | R12
24 | Running 7" Liner+Cementing | 5 | 23 | R01 | R13 | R15 | R16
25 | Dry/Pressure Test | 2 | 24 | R01 | R14
26 | Finish Drilling | 0 | 25
توضیحات:
1- برنامه زمانبندی روبه رو را در نرم افزار پرت مستر وارد نمایید.
2- با تعریف ریسکها و تخصیص آن به هر فعالیت مطابق اطلاعات درج شده در هر شیت مربوط به هر فعالیت اقدام نمایید.
3- گزارش P80 و P50 و اختلاف P80 با P50 برای تاریخ پایان و مدت زمان و هزینه را تهیه نمایید.
4- با فرمول نویسی در ستون Calculation شاخص SSI را محاسبه نمایید.
5- در انتها با روش ریسک درایور تاثیر هر ریسک را در برنامه زمانبندی با انجام فرآیند کامل آن گزارش نمایید.
6- با تحلیل ریسکها و اولویت بندی آنها از لحاظ اهمیت، مشخص نمایید Risk Mitigate بهتر است روی کدام ریسکها انجام شود.
7- کلیه گراف ها و نمودارهای خروجی از برنامه ارایه گردد.
موفق باشید.

## 4
Impact for Task 4 |  |  | Schedule |  |  |  | Cost
Risk ID | T/O | Title | Shape | Min | Likely | Max | Shape | Min | Likely | Max
R02 | T | R22 | Triangle | 1 | 2 | 3 | Triangle | 0 | 0 | 0
R03 | T | R23 | Triangle | 3 | 6 | 10 | Triangle | 28800 | 62400 | 96000
R04 | T | R24 | Triangle | 10 | 20 | 30 | Triangle | 94860 | 189720 | 284580
R05 | T | R25 | Triangle | 10 | 20 | 30 | Triangle | 0 | 0 | 0
R06 | T | R26 | Triangle | 10 | 20 | 30 | Triangle | 0 | 0 | 0

## 8
Impact for Task 8 |  |  | Schedule |  |  |  | Cost
Risk ID | T/O | Title | Shape | Min | Likely | Max | Shape | Min | Likely | Max
R03 | T | R35 | Triangle | 0 | 0 | 1 | Triangle | 870 | 4785 | 8700
R04 | T | R36 | Single Value |  | 0 |  | Triangle |  | 9000
R05 | T | R37 | Triangle | 0 | 1 | 1 | Triangle | 17700 | 23790 | 37880
R06 | T | R38 | Triangle | 2 | 4 | 7 | Triangle | 41742 | 93920 | 146097
R07 | T | R39 | Triangle | 2 | 6 | 10 | Triangle | 8742 | 26226 | 43710

## 9
Impact for Task 9 |  |  | Schedule |  |  |  | Cost
Risk ID | T/O | Title | Shape | Min | Likely | Max | Shape | Min | Likely | Max
R05 | T | R55 | Triangle | 1 | 1 | 2 | Triangle | 14800 | 22200 | 29600
R06 | T | R56 | Single Value |  | 0 |  | Triangle | 8200 | 16400 | 24600
R07 | T | R57 | Triangle | 0 | 1 | 1 | Triangle | 444003 | 592004 | 740050
R08 | T | R59 | Triangle | 2 | 6 | 10 | Single Value |  | 44400
R09 | T | R60 | Triangle | 0 | 0 | 1 | Single Value |  | 22529

## 10
Impact for Task 10 |  |  | Schedule |  |  |  | Cost
Risk ID | T/O | Title | Shape | Min | Likely | Max | Shape | Min | Likely | Max
R06 | T | R60 | Triangle | 1 | 2 | 3 | Triangle | 29600 | 148001 | 444003

## 12
Impact for Task 12 |  |  | Schedule |  |  |  | Cost
Risk ID | T/O | Title | Shape | Min | Likely | Max | Shape | Min | Likely | Max
R06 | T | R65 | Triangle | 5 | 12 | 20 | Triangle | 84335 | 307420 | 1770887
R07 | T | R66 | Triangle | 2 | 3 | 5 | Triangle | 67048 | 89355 | 296742
R08 | T | R67 | Triangle | 3 | 7 | 10 | Triangle | 54613 | 106661 | 158710
R09 | T | R68 | Triangle | 0 | 1 | 1 | Triangle | 8700 | 14790 | 20871
R10 | T | R69 | Triangle | 2 | 6 | 10 | Triangle | 8742 | 26226 | 43710

## 13
Impact for Task 13 |  |  | Schedule |  |  |  | Cost
Risk ID | T/O | Title | Shape | Min | Likely | Max | Shape | Min | Likely | Max
R10 | T | R105 | Single Value |  | 1 |  | Single Value |  | 14800
R11 | T | R106 | Single Value |  | 1 |  | Triangle | 23653 | 26262 | 28871
R12 | T | R107 | Single Value |  | 4 |  | Single Value |  | 87200
R13 | T | R108 | Triangle | 5 | 12 | 20 | Triangle | 502000 | 613000 | 724000
R14 | T | R109 | Single Value |  | 0 |  | Single Value |  | 6887

## 14
Impact for Task 14 |  |  | Schedule |  |  |  | Cost
Risk ID | T/O | Title | Shape | Min | Likely | Max | Shape | Min | Likely | Max
R09 | T | R96 | Triangle | 0 | 0 | 1 | Triangle | 1739 | 7392 | 13044
R10 | T | R97 | Triangle | 0 | 0 | 1 | Triangle | 4348 | 8696 | 13044
R11 | T | R98 | Triangle | 0 | 0 | 1 | Single Value | 870 | 4783 | 8696
R12 | T | R99 | Triangle | 1 | 1 | 2 | Triangle | 14800 | 22200 | 29600
R13 | T | R100 | Single Value |  | 0 |  | Single Value | 3973 | 21852 | 39730

## 15
Impact for Task 15 |  |  | Schedule |  |  |  | Cost
Risk ID | T/O | Title | Shape | Min | Likely | Max | Shape | Min | Likely | Max
R10 | T | R101 | Single Value |  | 1 |  | Single Value |  | 29600

## 17
Impact for Task 17 |  |  | Schedule |  |  |  | Cost
Risk ID | T/O | Title | Shape | Min | Likely | Max | Shape | Min | Likely | Max
R01 | T | R111 | Triangle | 2 | 10 | 15 | Triangle | 29600 | 44400 | 59200
R02 | T | R112 | Triangle | 5 | 10 | 15 | Triangle | 29600 | 44400 | 59200
R03 | T | R113 | Triangle | 5 | 7 | 10 | Triangle | 14800 | 22200 | 29600
R04 | T | R114 | Triangle | 0 | 1 | 1 | Triangle | 4348 | 12610 | 20871
R05 | T | R115 | Triangle | 5 | 14 | 24 | Triangle | 14800 | 44400 | 74000

## 18
Impact for Task 18 |  |  | Schedule |  |  |  | Cost
Risk ID | T/O | Title | Shape | Min | Likely | Max | Shape | Min | Likely | Max
R04 | T | R65 | Triangle | 5 | 12 | 20 | Triangle | 84335 | 307420 | 1770887
R05 | T | R66 | Triangle | 2 | 3 | 5 | Triangle | 67048 | 89355 | 296742
R06 | T | R67 | Triangle | 3 | 7 | 10 | Triangle | 54613 | 106661 | 158710
R07 | T | R68 | Triangle | 0 | 1 | 1 | Triangle | 8700 | 14790 | 20871
R08 | T | R69 | Triangle | 2 | 6 | 10 | Triangle | 8742 | 26226 | 43710

## 19
Impact for Task 19 |  |  | Schedule |  |  |  | Cost
Risk ID | T/O | Title | Shape | Min | Likely | Max | Shape | Min | Likely | Max
R03 | T | R22 | Triangle | 1 | 2 | 3 | Triangle | 0 | 0 | 0
R04 | T | R23 | Triangle | 3 | 6 | 10 | Triangle | 28800 | 62400 | 96000
R05 | T | R24 | Triangle | 10 | 20 | 30 | Triangle | 94860 | 189720 | 284580
R06 | T | R25 | Triangle | 10 | 20 | 30 | Triangle | 0 | 0 | 0
R07 | T | R26 | Triangle | 10 | 20 | 30 | Triangle | 0 | 0 | 0

## 20
Impact for Task 20 |  |  | Schedule |  |  |  | Cost
Risk ID | T/O | Title | Shape | Min | Likely | Max | Shape | Min | Likely | Max
R14 | T | R101 | Single Value |  | 1 |  | Single Value |  | 29600

## 22
Impact for Task 22 |  |  | Schedule |  |  |  | Cost
Risk ID | T/O | Title | Shape | Min | Likely | Max | Shape | Min | Likely | Max
R15 | T | R22 | Triangle | 1 | 2 | 3 | Triangle | 0 | 0 | 0
R16 | T | R23 | Triangle | 3 | 6 | 10 | Triangle | 28800 | 62400 | 96000
R17 | T | R24 | Triangle | 10 | 20 | 30 | Triangle | 94860 | 189720 | 284580
R18 | T | R25 | Triangle | 10 | 20 | 30 | Triangle | 0 | 0 | 0

## 23
Impact for Task 23 |  |  | Schedule |  |  |  | Cost
Risk ID | T/O | Title | Shape | Min | Likely | Max | Shape | Min | Likely | Max
R09 | T | R65 | Triangle | 5 | 12 | 20 | Triangle | 84335 | 307420 | 1770887
R10 | T | R66 | Triangle | 2 | 3 | 5 | Triangle | 67048 | 89355 | 296742
R11 | T | R67 | Triangle | 3 | 7 | 10 | Triangle | 54613 | 106661 | 158710
R12 | T | R68 | Triangle | 0 | 1 | 1 | Triangle | 8700 | 14790 | 20871

## 24
Impact for Task 24 |  |  | Schedule |  |  |  | Cost
Risk ID | T/O | Title | Shape | Min | Likely | Max | Shape | Min | Likely | Max
R01 | T | R22 | Triangle | 1 | 2 | 3 | Triangle | 0 | 0 | 0
R13 | T | R23 | Triangle | 3 | 6 | 10 | Triangle | 28800 | 62400 | 96000
R15 | T | R24 | Triangle | 10 | 20 | 30 | Triangle | 94860 | 189720 | 284580
R16 | T | R25 | Triangle | 10 | 20 | 30 | Triangle | 0 | 0 | 0

## 25
Impact for Task 25 |  |  | Schedule |  |  |  | Cost
Risk ID | T/O | Title | Shape | Min | Likely | Max | Shape | Min | Likely | Max
R01 | T | R22 | Triangle | 1 | 2 | 3 | Triangle | 0 | 0 | 0
R14 | T | R101 | Single Value |  | 1 |  | Single Value |  | 29600

## Sheet2 (hidden)
Risk |  |  | Pre-Mitigation
ID | T/O | Title | Probability | Schedule | Cost | Performance | Score
20 | T | R22 | L (15%) | VL (2) | N | VH
21 | T | R23 | VL (10%) | L (6) | L ($62,400) | VH
22 | T | R24 | VL (10%) | H (20) | H ($189,720) | VH
23 | T | R25 | VL (10%) | H (20) | N | VH